## PI
VART
Infracon Pvt Ltd
229, Neha Ind. Est., Off Duttapada Road,
Opp. Oberoi Sky, Borivali (E), Mumbai - 400066
Contact No :- 022-40233596 / 28700110 Email : info@vartinfra.com
Proforma Invoice for Securty Alarm system for Warehouse LKO
To, | Simolina Kitchen Pvt. Ltd. |  |  | 2024-03-20
Ext-01 Ra-2nd
Kindly Attn.:- Mr. Irfaan ji
Sr. No. | Description | Unit | Previous | Up To Date | This Bill
1 | The Irish House Extra Item -01 Ra-2nd Bill | Job | 628554.2654 | 648423.3403 | 19869.0749
| Basic Total |  | 628554.2654 | 648423.3403 | 19869.0749
| Add GST @ 18% |  | 113139.7678 | 116716.2013 | 3576.4335
| Grand Total |  | 741694.0332 | 765139.5416 | 23445.5084
| This Bill Amount |  |  |  | 23445.5084
Work Completion Time Period
Material Delivery 1o days from the Date of PO with advance
Payment terms :
100% Advance with Work order
No Retention
For VART Infracon Pvt. Ltd.
Authorised Signatory

## Abstract
PRICE COMPARATIVE RA-3rd
PROJECT: IRISH HOUSE, LUCKNOW AIRPORT - TERMINAL-T3 | [5 empty] | Qty. |  |  | Amount (RS) |  |  | Variation | Remarks
SR. NO. | ITEM DESCRIPTION | UOM | QTY. | UNIT RATE | PO AMOUNT | Previous bill | This bill | Up To Date | Previous bill | This bill | Up To Date |  | Remarks
EXTRA ITEM
1 | Providing & fixing paneling made of 50x50mm MS framework @ 600mm c/c bothways fixed to the floor and soffit of slab/beam with MS cleats bolted as required, followed with 12mm thk. Bison board as base to receive tile cladding and different finishes over it as per design & details given in drawing/Architect instruction. Rate is inclusive of all necessary hardware & fixtures. | Sft. | 218.88 | 375 | 82080 | [6 empty] | 82080
2 | Providing and laying cast in situ RCC in Vertical Jamb and Horizontal Bands Grade equivalent to design mix M-25 including curing complete to achieve smooth finish, size 150mm/250mm having required length as per site requirement.(Ultratech) .Steel, shuttering and deshuttering will be include item | Rft | 164.5284 | 377.1961 | 62059.4712 | 164.5284 | 0 | 164.5284 | 62059.4712 | 0 | 62059.4712 | 0
3 | Exiting Ply Panelling Dismental with ms frame | Sft. | 352.7901 | 33 | 11642.0733 | 352.7901 | 0 | 352.7901 | 11642.0733 | 0 | 11642.0733 | 0
4 | Providing ,Laying & fixing of Bricks Tile Dado/Cladding of specified size as per drawings, shade and pattern to true level, alignment on wall laid over Bison board panelling and fixed with kerakoll chemical OR LATICRETE'S adhesive (as per manufacturer’s specification)or equivalent, inclusive of cleaning of site , curing of surface , wetting of tiles, cutting of edges, cutting holes for CP Fittings & Electrical points , fixing true to proper line , level, and slope as per approved design including making groove . The joints to be cleaned filled and flushed with white cement using pigment to match the shade of tiles as required as per instructions and to the complete satisfaction of the Project Manager. Bison board panelling shall be paid in separate item. Base rate of Bricks Tiles 150\ Sft. | Sft. | 453 | 414 | 187542 | 366 | 0 | 366 | 151524 | 0 | 151524 | 36018
5 | Providing and applying fire raidaint paint on ply surface whichever as per desire and as per project -in - charge.(Quantity will be change after measurment,so far taken a close approximate) | Sft. | 2150 | 34 | 73100 | 1482 | 554 | 2036 | 50388 | 18836 | 69224 | 3876
6 | P/fixing Veneer on exesting plyboard base or as per drawing and project in-charge . (Basic rate of Decorative plywood Veneer) - veneer as per approved sample ( The veneer company ,viyo) (Base rate of Veneer Rs. 125/- per Sq. ft.)(Quantity will be change after measurment,so far taken a close approximate) | Sft. | 410 | 411 | 168510 | 337 | 0 | 337 | 138507 | 0 | 138507 | 30003
7 | Removing and Redoing Bision Board paneling and achive the level fixing of ms display and level toward 40 mm. | Sft. | 218.8773 | 169 | 36990.2686 | 218.8773 | 0 | 218.8773 | 36990.2686 | 0 | 36990.2686 | 0
8 | Providing and fixing Electric metre as per approved make and specification or as per project in-charge MAKE- secure | nos | 1 | 16000 | 16000 | 1 | 0 | 1 | 16000 | 0 | 16000 | 0
9 | Providing and fixing PRV ( Pressure Release Valve) as per approved make and specification or as per project in-charge MAKE- Kranti | nos | 1 | 3800 | 3800 | 1 | 0 | 1 | 3800 | 0 | 3800 | 0
10 | Providing and fixing Water Metre as per approved make and specification or as per project in-charge MAKE- Kranti | nos | 1 | 7000 | 7000 | 1 | 0 | 1 | 7000 | 0 | 7000 | 0
11 | Providing and fixing 12 mm Bwr ply with fire rated paint on ceiling for track light and chaidliar support or hanging or as per directed by project in-charge . | Sft. | 65 | 110 | 7150 | 55.5422 | 9.3916 | 64.9338 | 6109.6464 | 1033.0749 | 7142.7213 | 7.2787
12 | P & f of MS framing for Screening of fixed glass wall, with 50mm X 50mm box section framing (14 swg gauge) with 3 nos of horizontal and 1000mm C/C of vertical frames as shown on details drawing, with base plate fixing with necessary fastener and to be finished in approve black powder coating. | Rft | 350 | 330 | 115500 | 320.8304 | 0 | 320.8304 | 105874.0254 | 0 | 105874.0254 | 9625.9746
13 | Providing and applying 4mm epoxy based grout in flooring as approved make and speacetion make- Laticrete and roff | Sft. | 1800 | 25 | 45000 | 1546.3912 | 0 | 1546.3912 | 38659.7806 | 0 | 38659.7806 | 6340.2194
| GRAND TOTAL |  |  |  | 816373.8131 |  |  |  | 628554.2654 | 19869.0749 | 648423.3403 | 167950.4727
| Add GST |  |  |  | 146947.2864 |  |  |  | 113139.7678 | 3576.4335 | 116716.2013 | 30231.0851
| TOTAL AFTER GST |  |  |  | 963321.0994 |  |  |  | 741694.0332 | 23445.5084 | 765139.5416 | 198181.5578

## MB Extra item
MB Sheet Extra Item
PROJECT: IRISH HOUSE, LUCKNOW AIRPORT - TERMINAL-T3 Extra item-01
SR. NO. | ITEM DESCRIPTION | Unit | No. | Length | Width | Height | Total | Remarks
Extra Item
1 | Providing & fixing paneling made of 50x50mm MS framework @ 600mm c/c bothways fixed to the floor and soffit of slab/beam with MS cleats bolted as required, followed with 12mm thk. Bison board as base to receive tile cladding and different finishes over it as per design & details given in drawing/Architect instruction. Rate is inclusive of all necessary hardware & fixtures.
| Irish House | Sqm | 1 | 18.7 |  | 0.96 | 17.952
| Vertical column | Sqm | 2 | 0.43 |  | 2.77 | 2.3822
| Total Qty in Sqm | Sqm |  |  |  |  | 20.3342
| Total Qty in Sft | Sft |  |  |  | 10.764 | 218.8773
| Previous Qty | Sft |  |  |  |  | 218.8773
| This Bill Qty. | Sft |  |  |  |  | 0
2 | Providing and laying cast in situ RCC in Vertical Jamb and Horizontal Bands Grade equivalent to design mix M-25 including curing complete to achieve smooth finish, size 150mm/250mm having required length as per site requirement.(Ultratech) .Steel, shuttering and deshuttering will be include item
| Wall -2 Vertical Jamb (150x250mm) | Rmt. | 3 | 3.71 |  |  | 11.13
| Wall -2 Horizontal (150x250mm) | Rmt. | 1 | 10.02 |  |  | 10.02
| Wall -3 Vertical Jamb (150x250mm) | Rmt. | 3 | 3.71 |  |  | 11.13
| Wall -3 Horizontal (150x250mm) | Rmt. | 1 | 7.82 |  |  | 7.82
| Door Lintel (150x250mm) | Rmt. | 1 | 1.7 |  |  | 1.7
| Jeep wall jamb | Rmt. | 2 | 2.4 |  |  | 4.8
| Jeep wall Horizontal Band | Rmt. | 2 | 1.75 |  |  | 3.5
| Total Qty in Sqm | Rmt. |  |  |  |  | 50.1
| Total Qty in Sft | Rft |  |  |  | 3.284 | 164.5284
| Previous qty | Rft |  |  |  |  | 164.5284
| This bill qty | Rft |  |  |  |  | 0
3 | Exiting Ply Panelling Dismental with ms frame
| Irish House | Sqm | 1 | 4.34 |  | 3.75 | 16.275
|  | Sqm | 1 | 4.4 |  | 3.75 | 16.5
| Total Qty in Sqm | Sqm |  |  |  |  | 32.775
| Total Qty in Sft | Sft |  |  |  | 10.764 | 352.7901
| Previous qty | [5 empty] | 352.7901
| This Bill qty | [5 empty] | 0
4 | Providing ,Laying & fixing of Bricks Tile Dado/Cladding of specified size as per drawings, shade and pattern to true level, alignment on wall laid over Bison board panelling and fixed with kerakoll chemical OR LATICRETE'S adhesive (as per manufacturer’s specification)or equivalent, inclusive of cleaning of site , curing of surface , wetting of tiles, cutting of edges, cutting holes for CP Fittings & Electrical points , fixing true to proper line , level, and slope as per approved design including making groove . The joints to be cleaned filled and flushed with white cement using pigment to match the shade of tiles as required as per instructions and to the complete satisfaction of the Project Manager. Bison board panelling shall be paid in separate item. Base rate of Bricks Tiles 150\ Sft. | Sft
| Glass fasade above area | Sqm | 1 | 18.7 |  | 0.85 | 15.895
| Column Panelling | Sqm | 2 | 2.77 |  | 0.43 | 2.3822
| Airport coridor side panelling | Sqm | 1 | 17.5 |  | 0.9 | 15.75
| Glass side Boxing | Sqm | 1 | 0.2 |  | 2.9
| Total Qty in Sqm | Sqm |  |  |  |  | 34.0272
| Total Qty in Sft | Sft |  |  |  | 10.76 | 366
| Previous Qty | Sft |  |  |  |  | 366
| This Bill qty | Sft |  |  |  |  | 0
5 | Providing and applying fire raidaint paint on ply surface whichever as per desire and as per project -in - charge.(Quantity will be change after measurment,so far taken a close approximate) | Sft
| Outer section rafter | Sqm | 2 | 9.21 | 0.8 |  | 14.736
| Center section Rafter | Sqm | 2 | 8.87 | 0.8 |  | 14.192
| Horizontal rafter | Sqm | 5 | 2.79 | 0.8 |  | 11.16
| Horizontal rafter side 2 | Sqm | 5 | 2.71 | 0.8 |  | 10.84
| Tapper Horizontal Rafter | Sqm | 5 | 3.08 | 0.8 |  | 12.32
| Tapper Horizontal Rafter side 2 | Sqm | 5 | 2.99 | 0.8 |  | 11.96
| Inner small rafter | Sqm | 5 | 1.185 | 0.8 |  | 4.74
| Inner small rafter side 2 | Sqm | 5 | 1.16 | 0.8 |  | 4.64
| Bar counter behind veneer Front side | Sqm | 2 | 3.83 |  | 1.15 | 8.809
| LHS | Sqm | 2 | 3.16 |  | 1.15 | 7.268
| RHS | Sqm | 2 | 2.68 |  | 1.15 | 6.164
| Bar counter top Front side | Rmt | 1 | 4.3 | 0.45 |  | 1.935
| LHS | Rmt | 1 | 2.9 | 0.45 |  | 1.305
| RHS | Rmt | 1 | 2.51 | 0.45 |  | 1.1295
| Bar counter Bottam Front side | Rmt | 1 | 4.3 | 0.35 |  | 1.505
| LHS | Rmt | 1 | 2.9 | 0.35 |  | 1.015
| RHS | Rmt | 1 | 2.51 | 0.35 |  | 0.8785
| near sofa ms column center | sqm | 4 | 0.2 |  | 3.6 | 2.88
|  | sqm | 4 | 0.235 |  | 3.6 | 3.384
| bar area side ms column center | sqm | 4 | 0.2 |  | 3.6 | 2.88
|  | sqm | 4 | 0.235 |  | 3.6 | 3.384
| Coridor side column near sofa front | sqm | 2 | 0.225 |  | 3.6 | 1.62
| Sides | sqm | 4 | 0.27 |  | 3.6 | 3.888
| Coridor side column near bar front | sqm | 2 | 0.225 |  | 3.6 | 1.62
| sides | sqm | 4 | 0.24 |  | 3.6 | 3.456
| service counter-1 small RHS And LHS | sqm | 2 | 0.6 |  | 1.13 | 1.356
| Back side | Sqm | 1 | 1 |  | 1.13 | 1.13
| Service counter-2 side | sqm | 2 | 0.6 |  | 1.8 | 2.16
| Back side | Sqm | 1 | 1 |  | 1.8 | 1.8
| Service counter-2 side | sqm | 2 | 0.6 |  | 1.8 | 2.16
| Back side | Sqm | 1 | 1.2 |  | 1.8 | 2.16
| Electrical DB sides inner and outer side | Sqm | 4 | 0.41 |  | 2.29 | 3.7556
| Top | Sqm | 2 | 1.7 |  | 0.41 | 1.394
| Inner partation | Sqm | 2 | 0.41 |  | 2.3 | 1.886
| Front and back | Sqm | 2 | 1.68 |  | 2.28 | 7.6608
| Sofa Back side | Sqm | 1 | 5.02 |  | 1.2 | 6.024
| Sofa sides | Sqm | 2 | 1.2 | 1.68 |  | 4.032
| Sitting area bottam | Sqm | 4 | 1.4 | 0.5 |  | 2.8
|  | Sqm | 2 | 0.95 | 0.5 |  | 0.95
| Sitting area Back | Sqm | 4 | 1.4 |  | 0.8 | 4.48
| Front Area Back | Sqm | 2 | 2.3 |  | 0.8 | 3.68
| Bottam area Lapet | Sqm | 2 | 4.11 |  | 0.375 | 3.0825
| Top | Sqm | 1 | 8.31 | 0.1 |  | 0.831
| Centre top | Sqm | 1 | 1.58 | 0.1 |  | 0.158
| Total Qty in Sqm | Sqm |  |  |  |  | 189.2089
| Total Qty in Sft | Sft |  |  |  | 10.76 | 2036
| Previous qty | Sft |  |  |  |  | 1482
| This Bill qty | Sft |  |  |  |  | 554
6 | P/fixing Veneer on exesting plyboard base or as per drawing and project in-charge . (Basic rate of Decorative plywood Veneer) - veneer as per approved sample ( The veneer company ,viyo) (Base rate of Veneer Rs. 125/- per Sq. ft.)(Quantity will be change after measurment,so far taken a close approximate) | Sft
| Service counter back side | Sqm | 1 | 1 |  | 1.8 | 1.8
|  | Sqm | 1 | 1 |  | 1.1 | 1.1
|  | Sqm | 1 | 1.2 |  | 1.8 | 2.16
| Bar counter veneer Front side | Sqm | 2 | 3.83 |  | 1.15 | 8.809
| LHS | Sqm | 2 | 3.16 |  | 1.15 | 7.268
| RHS | Sqm | 1 | 2.68 |  | 1.15 | 3.082
| Sofa RHS | Sqm | 1 | 1.685 |  | 1.185 | 1.9967
| Sofa LHS | Sqm | 1 | 1.685 |  | 1.185 | 1.9967
| Bar counter door veneer | Sqm | 1 | 0.7 |  | 0.9 | 0.63
| Electrical DB veneer sides | Sqm | 2 | 0.4 |  | 2.28 | 1.824
| Top | Sqm | 1 | 0.4 |  | 1.67 | 0.668
| Total Qty in Sqm | Sqm |  |  |  |  | 31.3345
| Total Qty in Sft | Sft |  |  |  | 10.76 | 337
| Previous qty | Sft |  |  |  |  | 337
| This bill qty | Sft |  |  |  |  | 0
7 | Removing and Redoing Bision Board paneling and achive the level fixing of ms display and level toward 40 mm.
| Irish House | Sqm | 1 | 18.7 |  | 0.96 | 17.952
| Column Panelling | Sqm | 2 | 2.77 |  | 0.43 | 2.3822
| Total Qty in Sqm | Sqm |  |  |  |  | 20.3342
| Total Qty in Sft | Sft |  |  |  | 10.764 | 218.8773
| Previous bill qty | Sft |  |  |  |  | 218.8773
| This Bill qty | Sft |  |  |  |  | 0
8 | Providing and fixing Electric metre as per approved make and specification or as per project in-charge MAKE- secure
| Electric metre | Nos | 1 |  |  |  | 1
| Total Qty in nos | Nos |  |  |  |  | 1
| Previous bill qty | Nos |  |  |  |  | 1
| This Bill qty | Nos |  |  |  |  | 0
9 | Providing and fixing PRV ( Pressure Release Valve) as per approved make and specification or as per project in-charge MAKE- Kranti
| PRV Valve | Nos | 1 |  |  |  | 1
| Total Qty in nos | Nos |  |  |  |  | 1
| Previous bill qty | Nos |  |  |  |  | 1
| This Bill qty | Nos |  |  |  |  | 0
10 | Providing and fixing Water Metre as per approved make and specification or as per project in-charge MAKE- Kranti
| Water metre | Nos | 1 |  |  |  | 1
| Total Qty in nos | Nos |  |  |  |  | 1
| Previous bill qty | Nos |  |  |  |  | 1
| This Bill qty | Nos |  |  |  |  | 0
11 | Providing and fixing 12 mm Bwr ply with fire rated paint on ceiling for track light and chaidliar support or hanging or as per directed by project in-charge .
| Ply for track light | Sqm | 14 | 1.2 | 0.2 |  | 3.36
| Chandlair | Sqm | 5 | 0.5 | 0.5 |  | 1.25
| KEG light | Sqm | 1 | 0.5 | 0.5 |  | 0.25
| Decorative light | Sqm | 1 | 0.5 | 0.5 |  | 0.25
| FILAMENT BULB | Sqm | 41 | 0.15 | 0.15 |  | 0.9225
| Total Qty in Sqm | Sqm |  |  |  |  | 6.0325
| Total Qty in Sft | Sqft |  |  |  | 10.764 | 64.9338
| Previous bill qty | Sft |  |  |  |  | 55.5422
| This Bill qty | Sft |  |  |  |  | 9.3916
12 | P & f of MS framing for Screening of fixed glass wall, with 50mm X 50mm box section framing (14 swg gauge) with 3 nos of horizontal and 1000mm C/C of vertical frames as shown on details drawing, with base plate fixing with necessary fastener and to be finished in approve black powder coating.
| Frame-1 Bar counter side Horizontal section | Rmt | 3 | 4.895 |  |  | 14.685
| Vertical member | Rmt | 6 | 2.73 |  |  | 16.38
| Frame-2 Horizontal section | Rmt | 3 | 4.525 |  |  | 13.575
| Vertical member | Rmt | 5 | 2.73 |  |  | 13.65
| Frame-3 Horizontal section | Rmt | 3 | 1.78 |  |  | 5.34
| Vertical member | Rmt | 3 | 2.73 |  |  | 8.19
| Frame-4 Horizontal section | Rmt | 3 | 4.075 |  |  | 12.225
| Vertical member | Rmt | 5 | 2.73 |  |  | 13.65
| Total Qty in Rmt | Rmt |  |  |  |  | 97.695
| Total Qty in Rft | Rft |  |  |  | 3.284 | 320.8304
| Previous bill Rft | Rft |  |  |  |  | 320.8304
| This Bill qty | Rft |  |  |  |  | 0
13 | Providing and applying 4mm epoxy based grout in flooring as approved make and speacetion make- Laticrete and roff
| 1200x600 grey tiles | Sqm | 1 | 7.4 | 13.5 |  | 99.9
| wooden tiles arount bar counter | Sqm | 1 | 12.51 | 1.175 |  | 14.6992
|  | Sqm | 1 | 18.165 | 1.6 |  | 29.064
| Total Qty in Sqm | Sqm |  |  |  |  | 143.6633
| Total Qty in Sft | Sft |  |  |  | 10.764 | 1546.3912
| Previous Qty | Sft |  |  |  |  | 1546.3912
| This Bill Qty. | Sft |  |  |  |  | 0