## Summary Sheet
Summary Sheet Mumbai Third Wave Coffee T2
Semolina Project Pvt Ltd. | [5 empty] | Date :- 08-11-2024
Vendor Name : Intercare Enterprise
PO No: Semolina/PO/24-25/000691
Sr no | Description | PO value | Previous Bill Amount | Present RA Bill-1 Amount | Cumulative Amount | Variance Amount
1 | Carpentry Work | 1420573.1176 | 0 | 1184662.4349 | 1184662.4349 | 235910.6827
2 | Plumbing Work | 50379.13 | 0 | 20295.49 | 20295.49 | 30083.64
3 | Electrical Work | 215647.54 | 0 | 205354.8675 | 205354.8675 | 10292.6725
| Total Amount (Without GST) | 1686599.7876 |  | 1410312.7924 | 1410312.7924 | 276286.9952
| GST 18 % | 303587.9618 |  | 253856.3026 | 253856.3026 | 49731.6591
Gross total Amount |  | 1990187.7494 |  | 1664169.095 | 1664169.095 | 326018.6543

## Measurement Sheet
Sr. No. | 1 |  | Name of site In charge : | [5 empty] | Ashish Nagar
PO No.: | Semolina/PO/24-25/000691 |  | Agency Name : | [5 empty] | TFS / Semolina Kitchen Pvt.Ltd
PO Date : | 31/07/2024 |  | Date : 08-11-2024
PO Validity : |  |  | Name of Work: MUMBAI THIRD WAVE COFFEE T2
Measurement Sheet No. of this PO: | 1 |  | Period of work Executed :
THIRD WAVE COFFEE |  |  | Measurement Sheet | [5 empty] | Total Qty | Claimable % | Claimable Qty
SR. NO. | MATERIAL | DESCRIPTION | UNIT | PO QTY | Nos | Length | Breadth | Height |  | RA-1
CARPENTRY WORK :
1 |  | P F of Low Height Wooden Partition to one of the side of the Cake Display Counter, 100mm thick 950mm height wooden partition, with 19mm thick plywood framing and 12mm thick plywood (fire retardant plywood, Archid or Kenwood make with pesticide treatment) to be fixed on the both surfaces of the framing. Partitions all the surfaces to be finished with 4mm thick selected and approved make veneer (Basic rate INR. 1614.00or SM) in 2 Hrs. fire rated PU polish, 50mm height top edge to be finished with 12mm thick Corian (Glacier White - DuPont make, basic rate INR. 10760.00or SM) with complete buffing or polishing up to the mark ,and 200mm ht. 2mm thick 304 grade SS (with selected and approved black coating finished) skirting on all the four sides. Rate including all necessary hardware fittings. Complete as per architectural detail drawing site engineer s instruction. Size 1000mm L x 950mm H x 100mm thick. | Sq.Mtr | 0.95 | 1 | 990 |  | 950 | 0.9405 | 99% | 0.9405
2 |  | P F of Low Height Wooden Partition in front of the Cake Display Counter, 50mm thick 200mm height wooden partition, with 19mm thick plywood framing and 12mm thick plywood (fire retardant plywood, Archid or Kenwood make with pesticide treatment) to be fixed on the both surfaces of the framing. Partition s all the surfaces and top to be finished with 200mm ht. 2mm thick 304 grade SS (with selected and approved black coating finished) skirting on all the four sides. Rate including all necessary hardware fittings. Complete as per architectural detail drawing site engineer sinstruction. Size 1335mm L x 200mm H x 50mm thick. | Sq.Mtr | 0.27 |  |  |  |  | 0 | 0% | 0
3 |  | P F of Cash Counter with 19mm thick plywood structure (fire retardant plywood, Archid or Kenwood make with pesticide treatment). Counter having with two different level tops, tops and fascia of 50mm thick edges to be finished with 12mm thick Corian (Glacier White - DuPont make, basic rate INR. 10760.00or SM) with complete buffing or polish up to the mark, counter s all the surfaces to be finished with 4mm thick selected and approved make veneer as per the detailed patterns (Basic rate INR. 1614.00or SM) in 2 Hrs. fire rated PU polish. Inside of the unit to be finished 1mm thick laminate (Formica make, basic rate INR. 1325.00 or Sheet). Counter will be having one no. of open space for cash machine provision, one no. of drawer with necessary draw compartment, one no. of open able shutter on working side of the unit. Counter front fascia will having cove light provision as per details shown. Front section of the counter having solid wooden stand for menu holder and 8mm dia ss rod s railing of 100mm height as shown on the detailed drawings. Includes 200mm ht. 2mm thick 304 grade SS (with selected and approved black coating finished) skirting on all the three sides. Rate inclusive of all the necessary hardware fittings as required (like - hinges, lock, handle, SS wire managers, etc. branded make) necessary cut out for the services requirement. Complete as per architectural detail drawing site engineer s instruction. Size 600mm L x 850mm D x 950mm H | Sq.Mtr | 0.57 | 1 | 600 |  | 950 | 0.57 | 100% | 0.57
4 |  | P F of Coffee Counter along with Pick-Up Counter with 19mm thick plywood structure (fire retardant plywood, Archid or Kenwood make with pesticide treatment). Counter s working top and fascia with 50mm edges, front and both the sides band with 100mm H x 60mm thick to be finished with 12mm thick Corian (Glacier White - DuPont make, basic rate INR. 10760.00or SM) with complete buffing or polishing up to the mark. Counter top will be having 350mm ht. x 12mm thick toughened glass partition on the 100mm thick band as shown on the details. Counter front fascia will having cove light provision as per details shown. Counter s all the rest surfaces to be finished with 4mm thick selected and approved make veneer as per the detailed patterns (Basic rate INR. 1614.00or SM) in 2 Hrs. fire rated PU polish. Inside of the unit to be finished with 1mm thick laminate (Formica make, basic rate INR. 1315.00 or Sheet). Counter s working side having two nos of open able shutter in 19mm said plywood. Includes 200mm ht. 2mm thick 304 grade SS (with selected and approved black coating finished) skirting on all the two sides. Rate including all necessary hardware fittings as required (like - hinges, locks, handles, wire mangers etc. - branded make) necessary 2 nos of cut out of 150mm dia for dipper well knock box and provision and fixing of SS Sink (Sink cost to be considered separately) on the working counter s top. Complete as per architectural detail drawing site engineer s instruction. Size (2150+625)mm L x 1000mm D x(950+100+350)mm H. | Sq.Mtr | 3.89 | 1 | 2760 |  | 1400 | 3.864 | 99.33% | 3.864
5 |  | P F of Condiment Counter with 19mm thick plywood structure (fire retardant plywood, Archid or Kenwood make with pesticide treatment). Counter s top and fascia of 50mm thick edges to be finished with 12mm thick Corian (Glacier White - DuPont make, basic rate INR. 10760.00or SM) with complete buffing or polish up to the mark, counter s all the surfaces to be finished with 4mm thick selected and approved make veneer as per the detailed patterns (Basic rate INR. 1614.00or SM) in 2 Hrs. fire rated PU polish. Inside of the unit to be finished 1mm thick laminate (Formica make, basic rate INR. 1325.00 or Sheet). Counter will be having two nos. of open able shutter on working side of the unit. Counter front fascia will having cove light provision as per details shown. Includes 200mm ht. 2mm thick 304 grade SS (with selected and approved black coating finished) skirting on all the two sides. Rate inclusive of all the necessary hardware fittings as required (like - hinges, lock, handle, SS wire managers, etc. branded make) necessary cut out for the services requirement. Complete as per architectural detail drawing site engineer s instruction. Size 900mm L x 500mm D x 950mm H. | Sq.Mtr | 0.86 | 0 |  |  |  | 0 | 0% | 0
6 |  | P F of Dispenser box with 12mm thick plywood structure (fire retardant plywood, Archid or Kenwood make with pesticide treatment), all surfaces of the dispenser box with 12mm thick Corian (Glacier White - DuPont make, basic rate INR. 10760.00or SM) with complete buffing or polish up to the mark, having provision of 100mm dia 4 nos. of SS containers, provisions for the mug container in said Corian finished. Rate including all necessary hardware fittings (branded make) SS containers. Complete as per architectural detail drawing site engineer s instruction. Size 500mm L x 350mm H x 200mm D. | Sq.Mtr | 0.18 | 0 |  |  |  | 0 | 0% | 0
7 |  | P F of Back Working Counter, with 19mm thick plywood structure 12mm plywood back (bwr fire retardant bwr grade plywood - Archid or Kenwood make with pesticide treatment). Counter having four nos. of compartments with both the sides of 100mm thick verticals, includes 1000mm L x 1150mm Ht. x 100mm thick back at LHS.. Two of the compartments (1436mm L + 925mm L) having five nos. of open able shutters (in 19mm thick plywood) on front side with one no. of open provisions (560mm L x 360mm H x 800mm D) for the Micro Oven, other two compartments (1375mm L x 918mm H x 800mm D and 875mm L x 918mm H x 800D) will be having open spaces to place the kitchen equipment s. Counter top, 32mm fascia and 200mm flush band of 50mm thick to be finished with 12mm thick Corian (Glacier White - DuPont make, basic rate INR. 10760.00or SM) with complete buffing or polishing up to the mark .. Counter s all the rest surfaces to be finished with 4mm thick selected and approved make veneer as per the detailed patterns (Basic rate INR. 1614.00or SM) in 2 Hrs. fire rated PU polish. Inside of the unit to be finished with 1mm thick laminate (Formica make, basic rate INR. 1315.00 or Sheet). Counter s working side having two nos of open able shutter in 19mm said plywood. Includes 200mm ht. 2mm thick 304 grade SS (with selected and approved black coating finished) skirting on all the two sides. Rate inclusive of all necessary hardware fittings - like hinges, cup board lock, handles, wire managers, etc. (approved branded make) necessary cut out for services requirements, installation of sink, etc.. Complete as per architectural detail drawing site engineer s instruction. Size 4800mm L x 800mm W x (950+200)mm H. | Sq.Mtr | 5.52 | 1 | 4750 |  | 1150 | 5.4625 | 98.96% | 5.4625
8 |  | P F of Back Storage Cabinet, with 19mm thick plywood structure 12mm plywood back (bwr fire retardant bwr grade plywood - Archid or Kenwood make with pesticide treatment). Counter having two nos. of compartments with having four nos. of open able shutters (in 19mm thick plywood). Counter top, 50mm fascia of 50mm thick to be finished with 12mm thick Corian (Glacier White - DuPont make, basic rate INR. 10760.00or SM) with complete buffing or polishing up to the mark. Counter s front and one of the side surfaces to be finished with 4mm thick selected and approved make veneer as per the detailed patterns (Basic rate INR. 1614.00or SM) in 2 Hrs. fire rated PU polish. Inside of the unit to be finished with 1mm thick laminate (Formica make, basic rate INR. 1315.00 or Sheet). Includes 200mm ht. 2mm thick 304 grade SS (with selected and approved black coating finished) skirting on all the visible sides. Rate inclusive of all necessary hardware fittings - like hinges, cup board lock, handles, wire managers, etc. (approved branded make) necessary cut out for services requirements. Complete as per architectural detail drawing site engineer sinstruction. Size 3800mm L x (One side 500 other side 10)mm W x1150mm H. | Sq.Mtr | 4.37 | 1 | 3780 |  | 1150 | 4.347 | 99.47% | 4.347
9 |  | P F of Flap door with 19mm thick plywood (bwr fire retardant bwr grade plywood - Archid or Kenwood make with pesticide treatment). Flap door s both of the surfaces to be finished with 4mm thick selected and approved make veneer as per the detailed patterns (Basic rate INR. 1614.00or SM) in 2 Hrs. fire rated PU polish. Top of the flap door with fascia of 50mm thick to be finished with 12mm thick Corian (Glacier White - DuPont make, basic rate INR. 10760.00or SM) with complete buffing or polishing up to the mark. Includes 200mm ht. 2mm thick 304 grade SS (with selected and approved black coating finished) skirting on all the visible sides. Rate including all necessary hardware fittings, heavy duty hinges, tower bolt, etc. Complete as per architectural detail drawing site engineer s instruction. Size 800mm L x 950mm H x 50mmthick. | Sq.Mtr | 0.76 | 1 | 800 |  | 950 | 0.76 | 100% | 0.76
10 |  | P F Parametric Baffle Ceiling Structure, with 25mm thick Birch Plywood (fire retardant plywood - standard make with pesticide treatment) with 300mm Peak depth clear distance of 125mm as per the drawing made of High Performance havea brasiliensis withan Organic base and a trimmer of cyanamide with 1-3-5 Triazine with machine metal coat white finish as approved to be installed using special clip system as per the manufacture specification. Includes 6 nos of vertical wooden supports with 60mm x 60mm MS Tube pole cladding with 12mm thick plywood (bwr fire retardant bwr grade plywood - Archid or Kenwood make with pesticide treatment))to hold the structure, has to be finished with 4mm thick selected and approved make veneer as per the detailed patterns (Basic rate INR. 1614.00or SM) in 2 Hrs. fire rated PU polish.. All material should be of approved make complete as per the drawing, specification and approval of architect. Rate including all necessary support, hardware fittings, heavy duty hinges, tower bolt, etc. Complete as per architectural detail drawing site engineer sinstruction. Size 5400mm L x 3680mm W x 900mm H. | Sq.Mtr | 19.87 | 1 | 5300 |  | 3680 | 19.504 | 98.16% | 19.504
11 |  | P F of MS Railing, with 50mm x 25mm x 2mm thick MS tube outer framing and crisscross framing with 25mm x 25mm x 2mm thick MS tube. Making the ms structure in proper line level, and fixing at the locations necessary anchor-bolting system. MS framing to be treated with antirust red oxide metal primer, to be finished with selected and approved fire rated black PU metal paint ( ICA make). Rate including ms welding works with necessary fire protection, all necessary hardware fittings to install the framing, including all necessary supports from the columns or walls or etc. as per site conditions, cut out for services requirements. Complete as per architectural detail drawing site engineer s instruction. Size (6450+4250)mm L x 950mm H. x 50mm thick. | Sq.Mtr | 10.17 | 1 | 10250 | 950 |  | 9.7375 | 95.75% | 9.7375
12 |  | P F of Self standing movable barricading, 25mm x 25mm x 2mm thick MS tube framing out of vertical members at 600 mm cor c with horizontal members at 600 mm cor c, after assembling the framework on the existing slabs or floors in proper line level, flex board (art work of the flex to be provided by client) to be installed on the front surface of the framing. The barricading will be made as per site engineer s instruction onsite and it would be reusable. It is considered up to 2400mm height for all four sides of the Kiosk having 900mm working space. Size (7500 + 5000 + 7500 +5000)mm L x 2400mm ht. | Sq.Mtr | 60 | 0 |  |  |  | 0 | 0% | 0
Plumbing Work :
13 |  | P F of CPVC pipes confirming to ASTM standard including all CPVC fittings like tees, elbows, bends, unions, coupling, reducer, collars etc. The work shall include cutting jointing with solvent cement pressure testing the joints pipeline for 10 kg sq.cm hydraulic pressure, for 2 hours etc. making holes, including chasing in solid block masonry walls with groove cutting machine to required width and depth, making bores in walls, foundations and RCC slabs, making good the walls and bores in CC or CM 1 3 as applicable, cleaning the debris, grouting of concealed pipes, MS hooks for fixing pipes and making good the walls and floors. Note Strictly use SDR-13.5 grade Astral UPVC pipe and fittings for internal cold water supply and SDR- 11 for hot water supply. 19mm dia | R.Mtr | 6 | 1 | 6 |  |  | 6 | 100% | 6
14 |  | P F of ball valves of brass body nickel plated with stainless steel ball, lever operated (RB TBS Cimbrio make) and tested to 20kg sq.cm. using Astral make UPVC fittings. 19mm dia | Nos | 1 | 1 |  |  |  | 1 | 100% | 1
15 |  | P F of UPVC PVC drain pipe (Supreme Prince B type make) including soil, waste and vent pipes including all fittings like bends, tees, elbows, collars, junctions, inspections doors, cowls, offsets, access pipes, jointing with solvent cement including cutting holes in walls and floors and making good. 50mm dia | R.Mtr | 3 | 1 | 3 |  |  | 3 | 100% | 3
16 |  | Section B Sanitary Fittings |  | 0
17 |  | P F of 15mm dia CP sink cock with swinging spout (floor mounted) for sink including necessary accessories like- flanges etc. (Jaquar- Cat. No. 359, make) | Nos | 2 | 2 |  |  |  | 2 | 100% | 2
18 |  | P F of 15mm dia CP angular stop cock (wall mounted) for water services including necessary accessories like- flanges etc. (Jaquar - Cat. No. 053, make) | Nos | 2 | 1 |  |  |  | 1 | 50% | 1
19 |  | P F of GI connectors 3 ft. length to water inlet, drainage, water cooler, coffee machine, Pepsi machine, Ice machine, etc. ( Approved make) | Nos | 4 | 2 |  |  |  | 2 | 50% | 2
20 |  | P F of CP waste coupling full thread 40mm dia, including all necessary accessories (branded make). | Nos | 2 | 1 |  |  |  | 1 | 50% | 1
21 |  | P F of PVC flexi waste pipe 38mm, including all necessary accessories (branded). | Nos | 3 | 1 |  |  |  | 1 | 33.33% | 1
22 |  | P F of pressure pump, Crompton make of .5HP, including fixing with all necessary accessories. | Nos | 1 | 0 |  |  |  | 0 | 0% | 0
23 |  | P F of SS Sink, Grace Plain, Nirali make - 355mm x305mm x150mm , including fixing with all necessary accessories. | Nos | 1 | 0 |  |  |  | 0 | 0% | 0
Electrical Work :
24 |  | DISTRIBUTION SWITCHGEAR Supply, installation, testing commissioning of Distribution Boards surface or flush mounted with Double door containing MCB or ELMCB as incomer and SPMCB as outgoing. All MCBs are of 10KA breaking capacity and ELMCBs or RCCB should be of 30mA or 100 or 300 mA sensivity. The DB shall have appropriate no. of top and bottom knock outs for outgoing circuits and shall be complete with necessary busbars, interconnection terminals and earth studs. All terminations in DB shall be complete with ferulling, dressing and all circuits shall be properly labeled with PVC strip (sticker type) having identification as per the final approval of Consultant. For UPS DB MCB shall be D type and other MCBs shall be C category for lighting and raw power DB. Lighting power DB - VTPN DB 12 way VTPN DB I or C- 63A FP RCBO, 100mA -1 No. O or G -2 # 16 or 20 or 32A TP MCB O or G -30 # 10 or 16 or 20A SP MCB | Nos | 1 | 1 |  |  |  | 1 | 100% | 1
25 |  | Supply, installation, testing commissioning of Switchgears. (Standard Product) | 0 | 0
26 |  | 32 amps 4P MCB with 32A 5 Pin Ray Roll Socket complete with all mounting accessories – for Kitchen Legrand make | Nos | 2 | 2 |  |  |  | 2 | 100% | 2
27 |  | 63 amps 4P MCB with 63A 5 Pin Ray Roll Socket complete with all mounting accessories – for Kitchen Legrand make | Nos | 1 | 1 |  |  |  | 1 | 100% | 1
28 |  | 32A Rey roll socket complete with 32 amps SPMCB with 3 pinmetal clad socket - Legrand make Model No. 6078 41 - kitchen power | Nos | 4 | 4 |  |  |  | 4 | 100% | 4
29 |  | 16A Rey roll socket complete with 16 amps SPMCB with 3 pin metal clad socket. | Nos | 15 | 15 |  |  |  | 15 | 100% | 15
30 |  | CABLES ACCESSORIES Supply installation of following LT XLPE FRLS cables rated for 600 or 1100 volts AC as per IS standard 1554 Part 1 with necessary M.S. clamps. All cables shall be properly clamped or tied when run on cable trays. All such cables shall be provided with temporary labelling at every 10 mtrs and ten finally with metal identification tags showing the size and the location from or to the specific Panel or DB at both ends. 4C x 6 Sq. mm 2XFY Cable ( Cu ) (Kitchen 3Ph equipments | Mtr | 15 | 1 | 14.25 |  |  | 14.25 | 95% | 14.25
31 |  | Termination of following sizes of cables with Single compression cable gland.(COMET or BRAKO) 4C x 6 Sq. mm 2XFY Cable ( Cu ) (Kitchen 3Ph equipments) | Nos | 2 | 2 |  |  |  | 2 | 100% | 2
32 |  | WIRING ACCESSORIES Notes 1) Rates for point wiring shall include supply installation of Wires wiring acccessories such as angle holders or ceiling roses as required. conduits, conduit accessories such as junction boxes, Ts, elbows etc,Switches, sockets fixtures shall not be included in the point wiring rates. These will be counted paid separately. 2) Unless otherwise specified, all wires in point wiring shall be 2.5 sq.mm Stranded copper conductor 1.1 KV grade, I.S.I. marked (P+N+E), Fire Retardant (FRLS) PVC insulated . Wires shall be colour coded (Red, Yellow and Blue for Phases, Black for Neutral Green for earth). 3) Looping of wires shall be in fittings and switch boxes only 4) Location of switches or sockets or DBs shown on the drawings shall be confirmed with the Architect or Consultant or Project Manager before installation. 5) All Surface and concealed Conduits shall be rigid GI conduits of size not less than 20 mm dia as per applicable IS. 6)The Contractor can take more than one circuit in the same conduitprovided they are of the same phase. The size of conduit shall be decided according to the number of wires in it as per applicable IS as specified. 7) Payments for light fixtures fans will be made separately as per the items given in Light Fixtures Accessories . 8) Type location of light fixtures shown in the drawings are tentative and subject to revision as per the recommendation of Architect or Consultant. The quantities (number of points and accessories) of point wiring will be revised as actual installed on account of such revisions in the layouts. 9) Circuit wiring from DBs to the switch boards or first light point shall Be included as primary points remaining points of the same looping shall be considered as Secondary points and shall be counted in nos. 10) Circuit Wiring from DB to Kitchen Power points shall be measured in running meters | 0 | 0
33 |  | Supply, installation, testing commissioning of point wiring for light points, power points. Point wiring for primary point shall include wiring from Distribution Board upto First point of the circuit and shall be measured in nos. Secondary points shall also be measured in nos and shall include the remaining light points of the circuit controlled from same distribution board where primary points are controlling. The Power points shall be measured in Nos. Cost of GI conduits and accessories shall be included. (Normal Light) Average length Primary point - 6 mtr Secondary point - 3 mtr | 0 | 0
34 |  | Primary Light points controlled by MCB (3R x 1.5 sqmm wire) | Nos | 4 | 4 |  |  |  | 4 | 100% | 4
35 |  | Secondary Light points looped in the same circuit. (3R x 1.5 sqmm wire) | Nos | 9 | 9 |  |  |  | 9 | 100% | 9
36 |  | Providing point wiring for a cluster of 3 nos., 13 amps socket outlets and 1 no. 16A switch or pop up box for Computer Points or POS using 2 x 2.5 sq. mm PVC insulated copper conductor wires and minimum 2.5 Sq. mm copper conductor PVC insulated green colour earth wire for continuous earthing from NPDB to plug point in GI Conduits as specified. (maximum 4 nos. clusters shall be connected on one circuit) switch and sockets to be mounted on front plate on partitions of furniture on hot dipped GI boxes concealed in wall 16A single pole plate switch with interconnections complete as per final approval of Architect or Consultant . (Cost of FRLS PVC Conduits or Floor Raceway and switch sockets are considered elsewhere). ( Wires shall be FRLS type ) |  | 0
37 |  | Primary Point | Nos | 1 | 1 |  |  |  | 1 | 100% | 1
38 |  | Secondary points | Nos | 1 | 1 |  |  |  | 1 | 100% | 1
39 |  | Providing point wiring for Raw Power points 1no. 6 or 16A switch socket outlet on Skirting level to be looped from the nearest point using 2 x 2.5 sq. mm copper conductor wires and minimum 2.5 sq. mm copper conductor PVC insulated green colour earth wire as per approval of Architect or Consultant. (Cost of GI Conduit is included and switch sockets are considered elsewhere). (Wires shall be FRLS type) Note Average primary or secondary point length to be derived by Contractor, from the drawing or site provided AND + or - 1 Mtr Measured Radially. |  | 0
40 |  | Primary Point | Nos | 4 | 4 |  |  |  | 4 | 100% | 4
41 |  | Secondary points | Nos | 8 | 8 |  |  |  | 8 | 100% | 8
42 |  | Supply and laying of following PVC insulated copper conductor 1100 volt grade stranded flexible FRLS wire in already laid GI conduit concealed or surface mounted making connections where ever required to complete the installation.(For Kitchen Power Points) |  | 0
43 |  | 2R x 2.5Sqmm + 1R x 2.5Sqmm Cu. Wires | Mtr | 100 | 1 | 97 |  |  | 97 | 97% | 97
44 |  | 2R x 4Sqmm + 1R x 2.5Sqmm Cu. Wires | Mtr | 50 | 1 | 48 |  |  | 48 | 96% | 48
45 |  | Supply installation of 25 mm dia. GI conduit with pull box or junction box all accessories for Kitchen Bar Power wiring as per the requirement
46 |  | do - but conduit pipe shall be Rigid type. | Mtr | 100 | 1 | 94 |  |  | 94 | 94% | 94
47 |  | do - but flexible conduit pipe | Mtr | 20 | 1 | 18.5 |  |  | 18.5 | 92.5% | 18.5
48 |  | Supply and installation of Perforated Cable Tray (ASIAN)out of 14 gauge GI sheet complete with necessary fixing arrangement with Anchor Fastener and all other accessories as per the final approval of the Consultant or Architect 150 x 50 x 2mm | Mtr | 20 | 0 |  |  |  | 0 | 0% | 0
49 |  | Supply, installation, testing commissioning of flush mounted plate type switch and switch + sockets with hot dipped GI box complete as per the final approval of Architect or Consultant |  | 0
50 |  | 6A 5 pin Socket outlet | Nos | 2 | 1 |  |  |  | 1 | 50% | 1
51 |  | 6 or 16A 5pin switch socket outlet | Nos | 12 | 11 |  |  |  | 11 | 91.67% | 11
52 |  | 3nos 6 or 13A 5pin switch socket outlet | Nos | 2 | 2 |  |  |  | 2 | 100% | 2
53 |  | Data Socket | Nos | 4 | 3 |  |  |  | 3 | 75% | 3
54 |  | Telephone Socket | Nos | 1 | 1 |  |  |  | 1 | 100% | 1
55 |  | Supply, installation of temporary lighting power arrangement for construction purpose of with industrial type switch sockets or MCB s or ELCB s lighting fittings as required to finish the work for interior contractor necessary electrical protections throughout the site for construction work till the handover of site. Contractor shall maintain the saftey rules regulations as per Airport Security Department. The material shall be taken back by the contractor. | Job | 1 | 1 |  |  |  | 1 | 100% | 1
56 |  | EARTHING - Supplying erecting bare GI conductor of 8 swg forearthing purpose | Mtr | 50 | 1 | 45 |  |  | 45 | 90% | 45

## Sheet1 (hidden)
15nos nhani trap
15nos 75*110 reducer
40ft 160mm pvc pipe
4nos 110mm Y
4nos 110mm shoe bend
70ft. 110mm pvc pipe
4nos 110mm bend
4nos 250gm solution pvc
6nos 110 coupling
1/2“ cpvc 60 ft
3/4” cpvc 50ft
1/2” cpvc elbow 25nos
3/4” cpvc elbow 25nos
1/2” cpvc T 6nos
3/4” cpvc T 6nos
1/2” cpvc 8nos
3/4” cpvc 8nos
3/4*1/2 bushing 5nos
1”*3/4” bushing 5nos
Ro ka ek motar

## Abstract Sheet
RA-01 - Abstract
WO No :-Semolina/PO/24-25/000691 | [6 empty] | Date:- 08-11-2024
Third Wave Coffee Revamp
RA1 BILL OF INTERIOR WORK PROJECT : THIRD WAVE COFFEE @ MUMBAI AIRPORT T2 | [6 empty] | RA - 1 (Current Bill) |  | Variation |  | Remarks
SR. NO. | MATERIAL | DESCRIPTION | UNIT | PO QTY. | PO RATE | PO AMOUNT | QTY | AMOUNT (Rs) | QTY | AMOUNT (Rs)
CARPENTRY WORK :
1 |  | P F of Low Height Wooden Partition to one of the side of the Cake Display Counter, 100mm thick 950mm height wooden partition, with 19mm thick plywood framing and 12mm thick plywood (fire retardant plywood, Archid or Kenwood make with pesticide treatment) to be fixed on the both surfaces of the framing. Partitions all the surfaces to be finished with 4mm thick selected and approved make veneer (Basic rate INR. 1614.00or SM) in 2 Hrs. fire rated PU polish, 50mm height top edge to be finished with 12mm thick Corian (Glacier White - DuPont make, basic rate INR. 10760.00or SM) with complete buffing or polishing up to the mark ,and 200mm ht. 2mm thick 304 grade SS (with selected and approved black coating finished) skirting on all the four sides. Rate including all necessary hardware fittings. Complete as per architectural detail drawing site engineer s instruction. Size 1000mm L x 950mm H x 100mm thick. | Sq.Mtr | 0.95 | 6329.1 | 6012.645 | 0.9405 | 5952.5186 | -0.0095 | -60.1264 | 99% Claimed in RA Bill 1
2 |  | P F of Low Height Wooden Partition in front of the Cake Display Counter, 50mm thick 200mm height wooden partition, with 19mm thick plywood framing and 12mm thick plywood (fire retardant plywood, Archid or Kenwood make with pesticide treatment) to be fixed on the both surfaces of the framing. Partition s all the surfaces and top to be finished with 200mm ht. 2mm thick 304 grade SS (with selected and approved black coating finished) skirting on all the four sides. Rate including all necessary hardware fittings. Complete as per architectural detail drawing site engineer sinstruction. Size 1335mm L x 200mm H x 50mm thick. | Sq.Mtr | 0.27 | 10367.94 | 2799.3438 | 0 | 0 | -0.27 | -2799.3438 | 0% Claimed in RA Bill 1
3 |  | P F of Cash Counter with 19mm thick plywood structure (fire retardant plywood, Archid or Kenwood make with pesticide treatment). Counter having with two different level tops, tops and fascia of 50mm thick edges to be finished with 12mm thick Corian (Glacier White - DuPont make, basic rate INR. 10760.00or SM) with complete buffing or polish up to the mark, counter s all the surfaces to be finished with 4mm thick selected and approved make veneer as per the detailed patterns (Basic rate INR. 1614.00or SM) in 2 Hrs. fire rated PU polish. Inside of the unit to be finished 1mm thick laminate (Formica make, basic rate INR. 1325.00 or Sheet). Counter will be having one no. of open space for cash machine provision, one no. of drawer with necessary draw compartment, one no. of open able shutter on working side of the unit. Counter front fascia will having cove light provision as per details shown. Front section of the counter having solid wooden stand for menu holder and 8mm dia ss rod s railing of 100mm height as shown on the detailed drawings. Includes 200mm ht. 2mm thick 304 grade SS (with selected and approved black coating finished) skirting on all the three sides. Rate inclusive of all the necessary hardware fittings as required (like - hinges, lock, handle, SS wire managers, etc. branded make) necessary cut out for the services requirement. Complete as per architectural detail drawing site engineer s instruction. Size 600mm L x 850mm D x 950mm H | Sq.Mtr | 0.57 | 57410.54 | 32724.0078 | 0 | 0 | -0.57 | -32724.0078 | 100% Claimed in RA Bill 1
4 |  | P F of Coffee Counter along with Pick-Up Counter with 19mm thick plywood structure (fire retardant plywood, Archid or Kenwood make with pesticide treatment). Counter s working top and fascia with 50mm edges, front and both the sides band with 100mm H x 60mm thick to be finished with 12mm thick Corian (Glacier White - DuPont make, basic rate INR. 10760.00or SM) with complete buffing or polishing up to the mark. Counter top will be having 350mm ht. x 12mm thick toughened glass partition on the 100mm thick band as shown on the details. Counter front fascia will having cove light provision as per details shown. Counter s all the rest surfaces to be finished with 4mm thick selected and approved make veneer as per the detailed patterns (Basic rate INR. 1614.00or SM) in 2 Hrs. fire rated PU polish. Inside of the unit to be finished with 1mm thick laminate (Formica make, basic rate INR. 1315.00 or Sheet). Counter s working side having two nos of open able shutter in 19mm said plywood. Includes 200mm ht. 2mm thick 304 grade SS (with selected and approved black coating finished) skirting on all the two sides. Rate including all necessary hardware fittings as required (like - hinges, locks, handles, wire mangers etc. - branded make) necessary 2 nos of cut out of 150mm dia for dipper well knock box and provision and fixing of SS Sink (Sink cost to be considered separately) on the working counter s top. Complete as per architectural detail drawing site engineer s instruction. Size (2150+625)mm L x 1000mm D x (950+100+350)mm H. | Sq.Mtr | 3.89 | 57410.54 | 223327.0006 | 3.864 | 221834.3266 | -0.026 | -1492.674 | 99% Claimed in RA Bill 1
5 |  | P F of Condiment Counter with 19mm thick plywood structure (fire retardant plywood, Archid or Kenwood make with pesticide treatment). Counter s top and fascia of 50mm thick edges to be finished with 12mm thick Corian (Glacier White - DuPont make, basic rate INR. 10760.00or SM) with complete buffing or polish up to the mark, counter s all the surfaces to be finished with 4mm thick selected and approved make veneer as per the detailed patterns (Basic rate INR. 1614.00or SM) in 2 Hrs. fire rated PU polish. Inside of the unit to be finished 1mm thick laminate (Formica make, basic rate INR. 1325.00 or Sheet). Counter will be having two nos. of open able shutter on working side of the unit. Counter front fascia will having cove light provision as per details shown. Includes 200mm ht. 2mm thick 304 grade SS (with selected and approved black coating finished) skirting on all the two sides. Rate inclusive of all the necessary hardware fittings as required (like - hinges, lock, handle, SS wire managers, etc. branded make) necessary cut out for the services requirement. Complete as per architectural detail drawing site engineer s instruction. Size 900mm L x 500mm D x 950mm H. | Sq.Mtr | 0.86 | 56172.57 | 48308.4102 | 0 | 0 | -0.86 | -48308.4102 | 0% Claimed in RA Bill 1
6 |  | P F of Dispenser box with 12mm thick plywood structure (fire retardant plywood, Archid or Kenwood make with pesticide treatment), all surfaces of the dispenser box with 12mm thick Corian (Glacier White - DuPont make, basic rate INR. 10760.00or SM) with complete buffing or polish up to the mark, having provision of 100mm dia 4 nos. of SS containers, provisions for the mug container in said Corian finished. Rate including all necessary hardware fittings (branded make) SS containers. Complete as per architectural detail drawing site engineer s instruction. Size 500mm L x 350mm H x 200mm D. | Sq.Mtr | 0.18 | 77372.69 | 13927.0842 | 0 | 0 | -0.18 | -13927.0842 | 0% Claimed in RA Bill 1
7 |  | P F of Back Working Counter, with 19mm thick plywood structure 12mm plywood back (bwr fire retardant bwr grade plywood - Archid or Kenwood make with pesticide treatment). Counter having four nos. of compartments with both the sides of 100mm thick verticals, includes 1000mm L x 1150mm Ht. x 100mm thick back at LHS.. Two of the compartments (1436mm L + 925mm L) having five nos. of open able shutters (in 19mm thick plywood) on front side with one no. of open provisions (560mm L x 360mm H x 800mm D) for the Micro Oven, other two compartments (1375mm L x 918mm H x 800mm D and 875mm L x 918mm H x 800D) will be having open spaces to place the kitchen equipment s. Counter top, 32mm fascia and 200mm flush band of 50mm thick to be finished with 12mm thick Corian (Glacier White - DuPont make, basic rate INR. 10760.00or SM) with complete buffing or polishing up to the mark .. Counter s all the rest surfaces to be finished with 4mm thick selected and approved make veneer as per the detailed patterns (Basic rate INR. 1614.00or SM) in 2 Hrs. fire rated PU polish. Inside of the unit to be finished with 1mm thick laminate (Formica make, basic rate INR. 1315.00 or Sheet). Counter s working side having two nos of open able shutter in 19mm said plywood. Includes 200mm ht. 2mm thick 304 grade SS (with selected and approved black coating finished) skirting on all the two sides. Rate inclusive of all necessary hardware fittings - like hinges, cup board lock, handles, wire managers, etc. (approved branded make) necessary cut out for services requirements, installation of sink, etc.. Complete as per architectural detail drawing site engineer s instruction. Size 4800mm L x 800mm W x (950+200)mm H. | Sq.Mtr | 5.52 | 51220.72 | 282738.3744 | 5.4625 | 279793.183 | -0.0575 | -2945.1914 | 99% Claimed in RA Bill 1
8 |  | P F of Back Storage Cabinet, with 19mm thick plywood structure 12mm plywood back (bwr fire retardant bwr grade plywood - Archid or Kenwood make with pesticide treatment). Counter having two nos. of compartments with having four nos. of open able shutters (in 19mm thick plywood). Counter top, 50mm fascia of 50mm thick to be finished with 12mm thick Corian (Glacier White - DuPont make, basic rate INR. 10760.00or SM) with complete buffing or polishing up to the mark. Counter s front and one of the side surfaces to be finished with 4mm thick selected and approved make veneer as per the detailed patterns (Basic rate INR. 1614.00or SM) in 2 Hrs. fire rated PU polish. Inside of the unit to be finished with 1mm thick laminate (Formica make, basic rate INR. 1315.00 or Sheet). Includes 200mm ht. 2mm thick 304 grade SS (with selected and approved black coating finished) skirting on all the visible sides. Rate inclusive of all necessary hardware fittings - like hinges, cup board lock, handles, wire managers, etc. (approved branded make) necessary cut out for services requirements. Complete as per architectural detail drawing site engineer sinstruction. Size 3800mm L x (One side 500 other side 10)mm W x1150mm H. | Sq.Mtr | 4.37 | 30175.35 | 131866.2795 | 4.347 | 131172.2465 | -0.023 | -694.033 | 99% Claimed in RA Bill 1
9 |  | P F of Flap door with 19mm thick plywood (bwr fire retardant bwr grade plywood - Archid or Kenwood make with pesticide treatment). Flap door s both of the surfaces to be finished with 4mm thick selected and approved make veneer as per the detailed patterns (Basic rate INR. 1614.00or SM) in 2 Hrs. fire rated PU polish. Top of the flap door with fascia of 50mm thick to be finished with 12mm thick Corian (Glacier White - DuPont make, basic rate INR. 10760.00or SM) with complete buffing or polishing up to the mark. Includes 200mm ht. 2mm thick 304 grade SS (with selected and approved black coating finished) skirting on all the visible sides. Rate including all necessary hardware fittings, heavy duty hinges, tower bolt, etc. Complete as per architectural detail drawing site engineer s instruction. Size 800mm L x 950mm H x 50mmthick. | Sq.Mtr | 0.76 | 18724.19 | 14230.3844 | 0.76 | 14230.3844 | 0 | 0 | 100% Claimed in RA Bill 1
10 |  | P F Parametric Baffle Ceiling Structure, with 25mm thick Birch Plywood (fire retardant plywood - standard make with pesticide treatment) with 300mm Peak depth clear distance of 125mm as per the drawing made of High Performance havea brasiliensis withan Organic base and a trimmer of cyanamide with 1-3-5 Triazine with machine metal coat white finish as approved to be installed using special clip system as per the manufacture specification. Includes 6 nos of vertical wooden supports with 60mm x 60mm MS Tube pole cladding with 12mm thick plywood (bwr fire retardant bwr grade plywood - Archid or Kenwood make with pesticide treatment))to hold the structure, has to be finished with 4mm thick selected and approved make veneer as per the detailed patterns (Basic rate INR. 1614.00or SM) in 2 Hrs. fire rated PU polish.. All material should be of approved make complete as per the drawing, specification and approval of architect. Rate including all necessary support, hardware fittings, heavy duty hinges, tower bolt, etc. Complete as per architectural detail drawing site engineer sinstruction. Size 5400mm L x 3680mm W x 900mm H. | Sq.Mtr | 19.87 | 24555.52 | 487918.1824 | 19.504 | 478930.8621 | -0.366 | -8987.3203 | 98% Claimed in RA Bill 1
11 |  | P F of MS Railing, with 50mm x 25mm x 2mm thick MS tube outer framing and crisscross framing with 25mm x 25mm x 2mm thick MS tube. Making the ms structure in proper line level, and fixing at the locations necessary anchor-bolting system. MS framing to be treated with antirust red oxide metal primer, to be finished with selected and approved fire rated black PU metal paint ( ICA make). Rate including ms welding works with necessary fire protection, all necessary hardware fittings to install the framing, including all necessary supports from the columns or walls or etc. as per site conditions, cut out for services requirements. Complete as per architectural detail drawing site engineer s instruction. Size (6450+4250)mm L x 950mm H. x 50mm thick. | Sq.Mtr | 10.17 | 5417.09 | 55091.8053 | 9.7375 | 52748.9139 | -0.4325 | -2342.8914 | 96% Claimed in RA Bill 1
12 |  | P F of Self standing movable barricading, 25mm x 25mm x 2mm thick MS tube framing out of vertical members at 600 mm cor c with horizontal members at 600 mm cor c, after assembling the framework on the existing slabs or floors in proper line level, flex board (art work of the flex to be provided by client) to be installed on the front surface of the framing. The barricading will be made as per site engineer s instruction onsite and it would be reusable. It is considered up to 2400mm height for all four sides of the Kiosk having 900mm working space. Size (7500 + 5000 + 7500 +5000)mm L x 2400mm ht. | Sq.Mtr | 60 | 2027.16 | 121629.6 | 0 | 0 | -60 | -121629.6 | 0% Claimed in RA Bill 1
|  |  | Grand total amount |  |  | 1420573.1176 |  | 1184662.4349 |  | -235910.6827
Plumbing Work :
13 |  | P F of CPVC pipes confirming to ASTM standard including all CPVC fittings like tees, elbows, bends, unions, coupling, reducer, collars etc. The work shall include cutting jointing with solvent cement pressure testing the joints pipeline for 10 kg sq.cm hydraulic pressure, for 2 hours etc. making holes, including chasing in solid block masonry walls with groove cutting machine to required width and depth, making bores in walls, foundations and RCC slabs, making good the walls and bores in CC or CM 1 3 as applicable, cleaning the debris, grouting of concealed pipes, MS hooks for fixing pipes and making good the walls and floors. Note Strictly use SDR-13.5 grade Astral UPVC pipe and fittings for internal cold water supply and SDR- 11 for hot water supply. 19mm dia | R.Mtr | 6 | 707.85 | 4247.1 | 6 | 4247.1 | 0 | 0 | 100% Claimed in RA Bill 1
14 |  | P F of ball valves of brass body nickel plated with stainless steel ball, lever operated (RB TBS Cimbrio make) and tested to 20kg sq.cm. using Astral make UPVC fittings. 19mm dia | Nos | 1 | 2784.21 | 2784.21 | 1 | 2784.21 | 0 | 0 | 100% Claimed in RA Bill 1
15 |  | P F of UPVC PVC drain pipe (Supreme Prince B type make) including soil, waste and vent pipes including all fittings like bends, tees, elbows, collars, junctions, inspections doors, cowls, offsets, access pipes, jointing with solvent cement including cutting holes in walls and floors and making good. 50mm dia | R.Mtr | 3 | 866.41 | 2599.23 | 3 | 2599.23 | 0 | 0 | 100% Claimed in RA Bill 1
16 |  | Section B Sanitary Fittings |  | 0 |  | 0 | 0 | 0 | 0 | 0
17 |  | P F of 15mm dia CP sink cock with swinging spout (floor mounted) for sink including necessary accessories like- flanges etc. (Jaquar- Cat. No. 359, make) | Nos | 2 | 2595.45 | 5190.9 | 2 | 5190.9 | 0 | 0 | 100% Claimed in RA Bill 1
18 |  | P F of 15mm dia CP angular stop cock (wall mounted) for water services including necessary accessories like- flanges etc. (Jaquar - Cat. No. 053, make) | Nos | 2 | 1769.63 | 3539.26 | 1 | 1769.63 | -1 | -1769.63 | 50% Claimed in RA Bill 1
19 |  | P F of GI connectors 3 ft. length to water inlet, drainage, water cooler, coffee machine, Pepsi machine, Ice machine, etc. ( Approved make) | Nos | 4 | 896.61 | 3586.44 | 2 | 1793.22 | -2 | -1793.22 | 50% Claimed in RA Bill 1
20 |  | P F of CP waste coupling full thread 40mm dia, including all necessary accessories (branded make). | Nos | 2 | 1368.51 | 2737.02 | 1 | 1368.51 | -1 | -1368.51 | 50% Claimed in RA Bill 1
21 |  | P F of PVC flexi waste pipe 38mm, including all necessary accessories (branded). | Nos | 3 | 542.69 | 1628.07 | 1 | 542.69 | -2 | -1085.38 | 33% Claimed in RA Bill 1
22 |  | P F of pressure pump, Crompton make of .5HP, including fixing with all necessary accessories. | Nos | 1 | 13921.05 | 13921.05 | 0 | 0 | -1 | -13921.05 | 0% Claimed in RA Bill 1
23 |  | P F of SS Sink, Grace Plain, Nirali make - 355mm x305mm x150mm , including fixing with all necessary accessories. | Nos | 1 | 10145.85 | 10145.85 | 0 | 0 | -1 | -10145.85 | 0% Claimed in RA Bill 1
|  |  | Grand total amount |  |  | 50379.13 |  | 20295.49 |  | -30083.64
Electrical Work :
24 |  | DISTRIBUTION SWITCHGEAR Supply, installation, testing commissioning of Distribution Boards surface or flush mounted with Double door containing MCB or ELMCB as incomer and SPMCB as outgoing. All MCBs are of 10KA breaking capacity and ELMCBs or RCCB should be of 30mA or 100 or 300 mA sensivity. The DB shall have appropriate no. of top and bottom knock outs for outgoing circuits and shall be complete with necessary busbars, interconnection terminals and earth studs. All terminations in DB shall be complete with ferulling, dressing and all circuits shall be properly labeled with PVC strip (sticker type) having identification as per the final approval of Consultant. For UPS DB MCB shall be D type and other MCBs shall be C category for lighting and raw power DB. Lighting power DB - VTPN DB 12 way VTPN DB I or C- 63A FP RCBO, 100mA -1 No. O or G -2 # 16 or 20 or 32A TP MCB O or G -30 # 10 or 16 or 20A SP MCB | Nos | 1 | 35863 | 35863 | 1 | 35863 | 0 | 0 | 100% Claimed in RA Bill 1
25 |  | Supply, installation, testing commissioning of Switchgears. (Standard Product) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
26 |  | 32 amps 4P MCB with 32A 5 Pin Ray Roll Socket complete with all mounting accessories – for Kitchen Legrand make | Nos | 2 | 3368.96 | 6737.92 | 2 | 6737.92 | 0 | 0 | 100% Claimed in RA Bill 1
27 |  | 63 amps 4P MCB with 63A 5 Pin Ray Roll Socket complete with all mounting accessories – for Kitchen Legrand make | Nos | 1 | 3441.41 | 3441.41 | 1 | 3441.41 | 0 | 0 | 100% Claimed in RA Bill 1
28 |  | 32A Rey roll socket complete with 32 amps SPMCB with 3 pinmetal clad socket - Legrand make Model No. 6078 41 - kitchen power | Nos | 4 | 2354.65 | 9418.6 | 4 | 9418.6 | 0 | 0 | 100% Claimed in RA Bill 1
29 |  | 16A Rey roll socket complete with 16 amps SPMCB with 3 pin metal clad socket. | Nos | 15 | 2209.75 | 33146.25 | 15 | 33146.25 | 0 | 0 | 100% Claimed in RA Bill 1
30 |  | CABLES ACCESSORIES Supply installation of following LT XLPE FRLS cables rated for 600 or 1100 volts AC as per IS standard 1554 Part 1 with necessary M.S. clamps. All cables shall be properly clamped or tied when run on cable trays. All such cables shall be provided with temporary labelling at every 10 mtrs and ten finally with metal identification tags showing the size and the location from or to the specific Panel or DB at both ends. 4C x 6 Sq. mm 2XFY Cable ( Cu ) (Kitchen 3Ph equipments | Mtr | 15 | 370.95 | 5564.25 | 14.25 | 5286.0375 | -0.75 | -278.2125 | 95% Claimed in RA Bill 1
31 |  | Termination of following sizes of cables with Single compression cable gland.(COMET or BRAKO) 4C x 6 Sq. mm 2XFY Cable ( Cu ) (Kitchen 3Ph equipments) | Nos | 2 | 297.05 | 594.1 | 2 | 594.1 | 0 | 0 | 100% Claimed in RA Bill 1
32 |  | WIRING ACCESSORIES Notes 1) Rates for point wiring shall include supply installation of Wires wiring acccessories such as angle holders or ceiling roses as required. conduits, conduit accessories such as junction boxes, Ts, elbows etc,Switches, sockets fixtures shall not be included in the point wiring rates. These will be counted paid separately. 2) Unless otherwise specified, all wires in point wiring shall be 2.5 sq.mm Stranded copper conductor 1.1 KV grade, I.S.I. marked (P+N+E), Fire Retardant (FRLS) PVC insulated . Wires shall be colour coded (Red, Yellow and Blue for Phases, Black for Neutral Green for earth). 3) Looping of wires shall be in fittings and switch boxes only 4) Location of switches or sockets or DBs shown on the drawings shall be confirmed with the Architect or Consultant or Project Manager before installation. 5) All Surface and concealed Conduits shall be rigid GI conduits of size not less than 20 mm dia as per applicable IS. 6)The Contractor can take more than one circuit in the same conduitprovided they are of the same phase. The size of conduit shall be decided according to the number of wires in it as per applicable IS as specified. 7) Payments for light fixtures fans will be made separately as per the items given in Light Fixtures Accessories . 8) Type location of light fixtures shown in the drawings are tentative and subject to revision as per the recommendation of Architect or Consultant. The quantities (number of points and accessories) of point wiring will be revised as actual installed on account of such revisions in the layouts. 9) Circuit wiring from DBs to the switch boards or first light point shall Be included as primary points remaining points of the same looping shall be considered as Secondary points and shall be counted in nos. 10) Circuit Wiring from DB to Kitchen Power points shall be measured in running meters | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 |  | Supply, installation, testing commissioning of point wiring for light points, power points. Point wiring for primary point shall include wiring from Distribution Board upto First point of the circuit and shall be measured in nos. Secondary points shall also be measured in nos and shall include the remaining light points of the circuit controlled from same distribution board where primary points are controlling. The Power points shall be measured in Nos. Cost of GI conduits and accessories shall be included. (Normal Light) Average length Primary point - 6 mtr Secondary point - 3 mtr | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
34 |  | Primary Light points controlled by MCB (3R x 1.5 sqmm wire) | Nos | 4 | 1430.9 | 5723.6 | 4 | 5723.6 | 0 | 0 | 100% Claimed in RA Bill 1
35 |  | Secondary Light points looped in the same circuit. (3R x 1.5 sqmm wire) | Nos | 9 | 978.08 | 8802.72 | 9 | 8802.72 | 0 | 0 | 100% Claimed in RA Bill 1
36 |  | Providing point wiring for a cluster of 3 nos., 13 amps socket outlets and 1 no. 16A switch or pop up box for Computer Points or POS using 2 x 2.5 sq. mm PVC insulated copper conductor wires and minimum 2.5 Sq. mm copper conductor PVC insulated green colour earth wire for continuous earthing from NPDB to plug point in GI Conduits as specified. (maximum 4 nos. clusters shall be connected on one circuit) switch and sockets to be mounted on front plate on partitions of furniture on hot dipped GI boxes concealed in wall 16A single pole plate switch with interconnections complete as per final approval of Architect or Consultant . (Cost of FRLS PVC Conduits or Floor Raceway and switch sockets are considered elsewhere). ( Wires shall be FRLS type ) |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
37 |  | Primary Point | Nos | 1 | 2318.42 | 2318.42 | 1 | 2318.42 | 0 | 0 | 100% Claimed in RA Bill 1
38 |  | Secondary points | Nos | 1 | 1956.17 | 1956.17 | 1 | 1956.17 | 0 | 0 | 100% Claimed in RA Bill 1
39 |  | Providing point wiring for Raw Power points 1no. 6 or 16A switch socket outlet on Skirting level to be looped from the nearest point using 2 x 2.5 sq. mm copper conductor wires and minimum 2.5 sq. mm copper conductor PVC insulated green colour earth wire as per approval of Architect or Consultant. (Cost of GI Conduit is included and switch sockets are considered elsewhere). (Wires shall be FRLS type) Note Average primary or secondary point length to be derived by Contractor, from the drawing or site provided AND + or - 1 Mtr Measured Radially. |  | 0 |  |  | 0 | 0 | 0 | 0
40 |  | Primary Point | Nos | 4 | 1521.46 | 6085.84 | 4 | 6085.84 | 0 | 0 | 100% Claimed in RA Bill 1
41 |  | Secondary points | Nos | 8 | 1014.31 | 8114.48 | 8 | 8114.48 | 0 | 0 | 100% Claimed in RA Bill 1
42 |  | Supply and laying of following PVC insulated copper conductor 1100 volt grade stranded flexible FRLS wire in already laid GI conduit concealed or surface mounted making connections where ever required to complete the installation.(For Kitchen Power Points) |  | 0 |  |  | 0 | 0 | 0 | 0
43 |  | 2R x 2.5Sqmm + 1R x 2.5Sqmm Cu. Wires | Mtr | 100 | 215.18 | 21518 | 97 | 20872.46 | -3 | -645.54 | 97% Claimed in RA Bill 1
44 |  | 2R x 4Sqmm + 1R x 2.5Sqmm Cu. Wires | Mtr | 50 | 163.01 | 8150.5 | 48 | 7824.48 | -2 | -326.02 | 96% Claimed in RA Bill 1
45 |  | Supply installation of 25 mm dia. GI conduit with pull box or junction box all accessories for Kitchen Bar Power wiring as per the requirement |  |  |  | 0 | 0 | 0 | 0 | 0
46 |  | do - but conduit pipe shall be Rigid type. | Mtr | 100 | 215.18 | 21518 | 94 | 20226.92 | -6 | -1291.08 | 94% Claimed in RA Bill 1
47 |  | do - but flexible conduit pipe | Mtr | 20 | 163.1 | 3262 | 18.5 | 3017.35 | -1.5 | -244.65 | 93% Claimed in RA Bill 1
48 |  | Supply and installation of Perforated Cable Tray (ASIAN)out of 14 gauge GI sheet complete with necessary fixing arrangement with Anchor Fastener and all other accessories as per the final approval of the Consultant or Architect 150 x 50 x 2mm | Mtr | 20 | 298.5 | 5970 | 0 | 0 | -20 | -5970 | 0% Claimed in RA Bill 1
49 |  | Supply, installation, testing commissioning of flush mounted plate type switch and switch + sockets with hot dipped GI box complete as per the final approval of Architect or Consultant |  | 0 | 0 | 0 |  | 0 | 0 | 0
50 |  | 6A 5 pin Socket outlet | Nos | 2 | 489.04 | 978.08 | 1 | 489.04 | -1 | -489.04 | 50% Claimed in RA Bill 1
51 |  | 6 or 16A 5pin switch socket outlet | Nos | 12 | 543.38 | 6520.56 | 11 | 5977.18 | -1 | -543.38 | 92% Claimed in RA Bill 1
52 |  | 3nos 6 or 13A 5pin switch socket outlet | Nos | 2 | 996.2 | 1992.4 | 2 | 1992.4 | 0 | 0 | 100% Claimed in RA Bill 1
53 |  | Data Socket | Nos | 4 | 298.5 | 1194 | 3 | 895.5 | -1 | -298.5 | 75% Claimed in RA Bill 1
54 |  | Telephone Socket | Nos | 1 | 224.6 | 224.6 | 1 | 224.6 | 0 | 0 | 100% Claimed in RA Bill 1
55 |  | Supply, installation of temporary lighting power arrangement for construction purpose of with industrial type switch sockets or MCB s or ELCB s lighting fittings as required to finish the work for interior contractor necessary electrical protections throughout the site for construction work till the handover of site. Contractor shall maintain the saftey rules regulations as per Airport Security Department. The material shall be taken back by the contractor. | Job | 1 | 14490.14 | 14490.14 | 1 | 14490.14 | 0 | 0 | 100% Claimed in RA Bill 1
56 |  | EARTHING - Supplying erecting bare GI conductor of 8 swg forearthing purpose | Mtr | 50 | 41.25 | 2062.5 | 45 | 1856.25 | -5 | -206.25 | 90% Claimed in RA Bill 1
|  |  | Grand total amount |  |  | 215647.54 |  | 205354.8675 |  | -10292.6725