## Summary
TRV_INT_THE LOUNGE_T2_ SHA
PO No | Semolina /PO/24-25/000268
PO Date | 13.05.2024
S.N | Item Description | PO Value | Final Bill
1 | ANTI TERMITE TREATMENT | 29340 | 0
2 | WATERPROOFING | 175500 | 60890.7847
3 | SIPORAX BLOCK BATS FILLING | 90000 | 0
4 | PCC LAYER | 202500 | 0
5 | BLOCK WORK | 210000 | 291198.04
6 | PLASTER | 253500 | 275116.5872
7 | RCC LINTEL BEAM | 159360 | 131621.4
| SUB .TOTAL | 1120200 | 758826.812
| GST 18 % | 201636 | 136588.8262
| GRAND . TOTAL | 1321836 | 895415.6381

## Abtract
BOQ-CIVIL WORKS |  |  | PO |  |  |  | Final Bill
SN. | AREA | ITEM | UNIT | QTY. | RATE | AMOUNT | QTY. | AMOUNT
[6 empty] | 1120200 |  | 758826.812
1 |  | ANTI TERMITE TREATMENT
1.1 | ALL BOH & FOH | Providing & doing anti termite treatment with IMIDACLOPRID (OZIER) for entire area (Pest control) Diluting and injecting chemical emulsion 3" in floor for pre constructional Anti Termite treatment and creating a continuous chemical @ 4' center to center barrier all over as per manufacturer specification and ISI standards. (OR AS APPVD.) including a 1 year guarantee under suitable undertaking on stamp paper etc, complete as directed by Architect.(Mode of measurement is to be carpet area of floor and not the area of surface treated). | Sq.m. | 180 | 163 | 29340
2 |  | CIVIL WORK
2.1 |  | WATERPROOFING
|  | Providing and Applying Fosroc RFX Brush Bond Coating waterproofing to RCC slabs comprising of the following operations. | Sq.m. | 130 | 1350 | 175500 | 45.1043 | 60890.7847
1. Removal of Top Screed from the Mother Slab. 2. Cleaning of the Mother Slab with Hard Brush & Removal of Dirt from the Surface with Air Blowers 3. Applying of the Fosroc RFX Brush Bond Coating on the mother slab with Brush in Clock wise directions & on all 2 Sides Walls till 450m.m Height . If the Floor has to be raised 150m.m 4. After drying of the 1st Coat of the Brush Bond Coating . 2nd Coat is applied in the Anticlockwise Directions 5. After drying of entire Surface say 24 Hours . we will fill Water to 3 Inch Levels for Ponding Testing. 6. Water will be kept for observations for 72 Hours . If Leakage is observed . Water is emptied 7. Above Procedure is Repeated . 8. If No Leakage is observed after 72 Hours . 9. Water will be drained out from the Floor Surface 10. Protective Screeding mixed with FOSROC NITOBOND SBR of Average 25m.m thickness is done on the Water Proofing Surface & Coving on Side Walls . 11. After Dryings of Protective Screed say 2 Days. Drain Lines are laid on the Floor with Slope & main Drain lines chambers are done . 12 . After this floor raising by Light Seaproax block is done followed by Kota Stone Flooring
2.2 |  | CINDER/ LIGHT WT. SIPORAX BLOCK BATS FILLING
a | BOH, TOILET RAISED AREA (up to 75 mm) | Providing & Filling light wt. Siporex block bats to conceal drainage & plumbing lines. The Top layer should be finished properly to receive P.C.C base flooring layer on it. The same shall be completed as per the details are provided in drawings or as directed by Architect. | Sq.m. | 50 | 1800 | 90000
2.3 |  | PCC LAYER
|  | Providing & Laying P.C.C 1:3:6 of average thickness of upto 50mm of M 10 grade of concrete ( 1 cement :3 coarse sand:6 graded stone aggregate 20 mm nominal size) as floor base. | Sq.m. | 180 | 1125 | 202500
2.4 |  | Block WORK
| 100 MM THICK BLOCK MASONARY | Providing & Laying of block masonry of thickness 150mm in super structure, bund wall, in raised MOH counter area using cement mortar 1:4 (1 cement :4 coarse sand) mix, joints finished, curing complete as per specification and drawing or as directed by Project Manager. | Sq.m. | 120 | 1750 | 210000 | 166.3989 | 291198.04
2.5 |  | PLASTER
|  | P/L12-15mm thick plaster in cement mortar 1:4 (1 cement : 4coarse sand) to ceiling, all typesof R.C.C. work, brick work surfaces at all levels in line,level and plumb including smooth cement finish and providing necessary grooves at junctions of walls.Rate shall be inclusive of scaffolding and complete with curing etc | Sq.m. | 300 | 845 | 253500 | 325.5818 | 275116.5872
2.6 | RCC LINTEL BEAM | P/L in place (cast in situ) RCC lintel beams in 100mm th. blockwork @ 1200 mm and at Door lintel lvtl approx. 2400mm from FFLvl. (1:4:8) 100mm high with 4 no.'s 8mm th. Steel bars as per general specifications, complete in all respects | Rm | 128 | 1245 | 159360 | 105.72 | 131621.4

## JMR
BOQ-CIVIL WORKS |  |  | PO |  | Joint Measurement Report
SN. | AREA | ITEM | UNIT | QTY. | Length | Width | Height | Nos | QTY.
1 |  | ANTI TERMITE TREATMENT
1.1 | ALL BOH & FOH | Providing & doing anti termite treatment with IMIDACLOPRID (OZIER) for entire area (Pest control) Diluting and injecting chemical emulsion 3" in floor for pre constructional Anti Termite treatment and creating a continuous chemical @ 4' center to center barrier all over as per manufacturer specification and ISI standards. (OR AS APPVD.) including a 1 year guarantee under suitable undertaking on stamp paper etc, complete as directed by Architect.(Mode of measurement is to be carpet area of floor and not the area of surface treated). | Sq.m. | 180
2 |  | CIVIL WORK
2.1 |  | WATERPROOFING
|  | Providing and Applying Fosroc RFX Brush Bond Coating waterproofing to RCC slabs comprising of the following operations. | Sq.m. | 130 |  |  |  |  | 45.1043
[5 empty] | 4120 | 1580 |  | 1 | 6.5096
[5 empty] | 8205 | 2315 |  | 1 | 18.9946
[5 empty] | 9510 | 2061 |  | 1 | 19.6001
2.2 |  | CINDER/ LIGHT WT. SIPORAX BLOCK BATS FILLING
a | BOH, TOILET RAISED AREA (up to 75 mm) | Providing & Filling light wt. Siporex block bats to conceal drainage & plumbing lines. The Top layer should be finished properly to receive P.C.C base flooring layer on it. The same shall be completed as per the details are provided in drawings or as directed by Architect. | Sq.m. | 50
2.3 |  | PCC LAYER
|  | Providing & Laying P.C.C 1:3:6 of average thickness of upto 50mm of M 10 grade of concrete ( 1 cement :3 coarse sand:6 graded stone aggregate 20 mm nominal size) as floor base. | Sq.m. | 180
2.4 |  | Block WORK
| 100 MM THICK BLOCK MASONARY | Providing & Laying of block masonry of thickness 150mm in super structure, bund wall, in raised MOH counter area using cement mortar 1:4 (1 cement :4 coarse sand) mix, joints finished, curing complete as per specification and drawing or as directed by Project Manager. | Sq.m. | 120 |  |  |  |  | 166.3989
|  | Wall -1 |  |  | 9400 |  | 3008 | 1 | 28.2752
|  | Wall -2 |  |  | 2160 |  | 3008 | 1 | 6.4973
|  | Wall -3 |  |  | 1620 |  | 3008 | 1 | 4.873
|  | Wall -4 |  |  | 8400 |  | 3008 | 2 | 50.5344
|  | Wall -5 |  |  | 1650 |  | 3008 | 1 | 4.9632
|  | Wall -6 |  |  | 1230 |  | 3008 | 1 | 3.6998
|  | Wall -7 |  |  | 6680 |  | 3008 | 1 | 20.0934
|  | Wall -8 |  |  | 5870 |  | 3008 | 1 | 17.657
|  | Wall -9 |  |  | 4050 |  | 3008 | 1 | 12.1824
|  | Wall -10 |  |  | 3400 |  | 3008 | 1 | 10.2272
|  | Additional Brick Wall |  |  | 790 |  | 400 | 1 | 0.316
|  | Additional Brick Wall |  |  | 8400 |  | 400 | 1 | 3.36
|  | Additional Brick Wall |  |  | 1040 |  | 400 | 1 | 0.416
|  | Additional Brick Wall |  |  | 1420 |  | 400 | 1 | 0.568
|  | Additional Brick Wall |  |  | 6840 |  | 400 | 1 | 2.736
2.5 |  | PLASTER
|  | P/L12-15mm thick plaster in cement mortar 1:4 (1 cement : 4coarse sand) to ceiling, all typesof R.C.C. work, brick work surfaces at all levels in line,level and plumb including smooth cement finish and providing necessary grooves at junctions of walls.Rate shall be inclusive of scaffolding and complete with curing etc | Sq.m. | 300 |  |  |  |  | 325.5818
|  | Wall -1 | Sq.m. |  | 9400 |  | 3008 | 2 | 56.5504
|  | Wall -2 | Sq.m. |  | 2160 |  | 3008 | 2 | 12.9946
|  | Wall -3 | Sq.m. |  | 1620 |  | 3008 | 2 | 9.7459
|  | Wall -4 | Sq.m. |  | 8400 |  | 3008 | 4 | 101.0688
|  | Wall -5 | Sq.m. |  | 1650 |  | 3008 | 2 | 9.9264
|  | Wall -6 | Sq.m. |  | 1230 |  | 3008 | 2 | 7.3997
|  | Wall -7 | Sq.m. |  | 6680 |  | 3008 | 2 | 40.1869
|  | Wall -8 | Sq.m. |  | 5870 |  | 3008 | 2 | 35.3139
|  | Wall -9 | Sq.m. |  | 4050 |  | 3008 | 2 | 24.3648
|  | Wall -10 | Sq.m. |  | 3400 |  | 3008 | 2 | 20.4544
|  | Additional Brick Wall | Sq.m. |  | 300 |  | 400 | 1 | 0.12
|  | Additional Brick Wall | Sq.m. |  | 8370 |  | 400 | 1 | 3.348
|  | Additional Brick Wall | Sq.m. |  | 1000 |  | 400 | 1 | 0.4
|  | Additional Brick Wall | Sq.m. |  | 2500 |  | 400 | 1 | 1
|  | Additional Brick Wall | Sq.m. |  | 6770 |  | 400 | 1 | 2.708
2.6 | RCC LINTEL BEAM | P/L in place (cast in situ) RCC lintel beams in 100mm th. blockwork @ 1200 mm and at Door lintel lvtl approx. 2400mm from FFLvl. (1:4:8) 100mm high with 4 no.'s 8mm th. Steel bars as per general specifications, complete in all respects | Rm | 128 |  |  |  |  | 105.72
|  | Wall -1 |  |  | 9400 |  |  | 2 | 18.8
|  | Wall -2 |  |  | 2160 |  |  | 2 | 4.32
|  | Wall -3 |  |  | 1620 |  |  | 2 | 3.24
|  | Wall -4 |  |  | 8400 |  |  | 4 | 33.6
|  | Wall -5 |  |  | 1650 |  |  | 2 | 3.3
|  | Wall -6 |  |  | 1230 |  |  | 2 | 2.46
|  | Wall -7 |  |  | 6680 |  |  | 2 | 13.36
|  | Wall -8 |  |  | 5870 |  |  | 2 | 11.74
|  | Wall -9 |  |  | 4050 |  |  | 2 | 8.1
|  | Wall -10 |  |  | 3400 |  |  | 2 | 6.8