## Summary
AHM_WOW China _Billing Summary
PO Date | 11.03.2024
PO No | Semolina/PO/23-24/000638 |  |  |  |  | Credit Note (RA_02)
S.N | Item | PO Value | RA-01 Value | RA-02 Invoice Value | RA-02 Revised 09.07.24 | Credit Note 09.07.2024 | Additional Value
1 | Civil & Interior | 973020 | 352687.3265 | 391145 | 387980.7527 | 3164.2473 | 66124.8479
2 | Electrical Work | 478060 | 0 | 294350 | 294350 | 0 | 0
3 | Plumbing Work | 145475 | 19919.5 | 60700 | 60700 | 0 | 0
4 | HVAC | 175120 | 115070 | 28950 | 28950 | 0 | 37919.9088
5 | Fire | 66650 | 0 | 15400 | 15400 | 0 | 0
6 | Total | 1838325 | 487676.8265 | 790545 | 787380.7527 | 3164.2473 | 104044.7567
7 | GST 18% | 330898.5 | 87781.8288 | 142298.1 | 141728.5355 | 569.5645 | 18728.0562
8 | Total Amount | 2169223.5 | 575458.6552 | 932843.1 | 929109.2882 | 3733.8118 | 122772.8129

## RA-02
WOW China_AHM_Bill Of Quantities_Civil&Interior_Plumbing _Electrical | [5 empty] | RA-01 |  | RA-02 |  | Total | Variation | Additional | Additional
Sr No. | Item Name | UOM | Qty | Unit Price | Amount | QTY | Amount | QTY | Amount | Qty | Qty | Qty | Amount
[5 empty] | 1838325 |  | 487676.8265 |  | 787380.7527 |  |  |  | 104044.7567
1 | Civil & Interior Work of AHM Wow China |  |  |  | 973020 |  | 352687.3265 |  | 387980.7527 |  |  |  | 66124.8479
1 | BOH MOH FOH - ANTI TERMITE TREATMENT - Providing doing anti termite treatment with IMIDACLOPRID (OZIER) for entire area (Pest control) Diluting and injecting chemical emulsion 3 in floor for pre constructional Anti Termite treatment and creating a continuous chemical @ 4 center to center barrier all over as per manufacturer specification and ISI standards. including a 1 year guarantee under suitable undertaking on stamp paper etc, complete as directed by Architect.(Mode of measurement is to be carpet area of floor and not the area of surface treated). | SFT | 216 | 15 | 3240 |  |  |  |  | 0 | -216
2 | BOH MOH FOH - CIVIL AND ALLIED WORKS - Providing And Laying of half brick partitions with well burnt 1st class good quality bricks in cement mortar 1 4 ( 1 cement 4 coarse sand ) including providing 2 NOS. of 6mm dia MS round bars at every 4th coarse in true line,level and plumb including racking the joints up to 20 mm depth, rubbing and cleaning the surface with necessary scaffolding, curing etc. Complete as directed.Note MS bar paid extra. Full height 4.5 Thick wall with 1 4 cement mortar Above raw slab Level. (Ref. to civil plan) Brick work Fly Ash Brick | SFT | 585 | 220 | 128700 | 466.7486 | 102684.685 | 4.1 | 902 | 470.8486 | -114.1514
3 | PLASTER WORK- Providing And Laying of 12 mm thick wall plaster 1 4. (Kitchen area Toilet area FOH MOH Etc. ) (Ref. to civil plan) Internal Plastering | SFT | 1030 | 75 | 77250 | 696.6676 | 52250.0706 | 4.1 | 307.5 | 700.7676 | -329.2324
4 | Water-Proffing Work | [7 empty] | 0
5 | Providing And Laying of 3 mm APP Waterproofing PU liquid Mebrance (3 Coat or as per mall specification) coating surface as per . manufacture specs, Included Racking hacking of Surface for Waterprofing, Finished smooth in line, level and plumb including curing, of R.C.C surfaces, racking of joints corner coving etc. Complete at all levels. (Ref. to waterproofing plan ) (Option-2) Dr. Fixit Asian Equivalent | SFT | 396 | 180 | 71280 |  | 0 | 184.7067 | 33247.1999 | 184.7067 | -211.2933
6 | Providing And Laying of 12 mm thick wall plaster 1 4. (Kitchen area toilet area FOH MOH Etc. ) (Ref. to civil plan) Protection Plastering. | SFT | 216 | 75 | 16200 | 197.782 | 14833.6531 |  | 0 | 197.782 | -18.218
7 | PCC WORK- 1 2 4 - Providing And Laying of Upto 50mm PPC above floor filling. (kitchen area ) Ratio 1 4 8 | SFT | 216 | 140 | 30240 | 188.0686 | 26329.6051 |  | 0 | 188.0686 | -27.9314
8 | FLOOR FILLING
9 | Providing and laying cinder filling of light weight of AAC blocks Brick coba (Auto Areated Concrete), placing the same in sunken area raised floor surrounded by 115 mm thick brick wall. All Complete As Per Detail Drawing, As Specified And As Directed By Architect Project - In - Charge. (Depth as per site)
10 | Depth upto 200 mm | SFT | 130 | 225 | 29250 | 130 | 29250 |  | 0 | 130 | 0 | 51.9378 | 11685.9942 | 181.9378 | RA-01 JMS
11 | Repairing of Wall Punctures size upto 2feetx2feet | NOS | 2 | 1500 | 3000 | 2 | 3000 |  | 0 | 2 | 0
12 | Core cutting or Demolotion of wall for the same (For Exhaust Fresh Air Duct Ac Pipe etc.) | NOS | 2 | 1500 | 3000 | 2 | 3000 |  | 0 | 2 | 0
13 | FLOORING | [7 empty] | 0
14 | VITRIFIED TILE KOTA STONE FLOORING -( INSIDE AREA ) Providing laying 2 -0 X2 -0 Vitrified Floor Tiles on a bed of 50mm thk. cement mortar (1 4) adhesive of approved make and design, complete with tile grout in white cement and pigment of latecrete balendura) matching color of tile. (Base rate -Rs 70) (Make-Nitco kajaria) (Ref. to Flooring plan) | [7 empty] | 0
15 | Tile-1 - Polished Kota Stone Flooring 550 X 550 MM (PREMIUM - FULL BODY, DRY MATTE, As per drawings Kajaria NITCO -2 -0 X2 -0 LATICRETE EPOXY GROUT | SFT | 130 | 190 | 24700 | 113.4256 | 21550.8735 |  | 0 | 113.4256 | -16.5744
16 | Tile-1 - ONTARIO GIRIS 600 X 600MM (PSTONE CREST - FULL BODY, MATTE FINISHing 600 X 600 MM (PREMIUM - FULL BODY, DRY MATTE, As per drawings Kajaria NITCO -2 -0 X2 -0 LATICRETE EPOXY GROUT | SFT | 86 | 210 | 18060 | 68.5796 | 14401.7153 | 11.9418 | 2507.783 | 80.5214 | -5.4786
17 | 8 wide black granite Kota stone band supply and installation using cement mortar paste in proper line and level with Half round chamfer and Half Nosing. | RFT | 3 | 1500 | 4500 | 3 | 4500 |  | 0 | 3 | 0 | 3 | 4500
18 | TILE CLADIING (FOR WALL) | [7 empty] | 0
19 | Tile wall cladding -Providing Fixing of WOW CHICKEN Multicolored Tile upto slab bottom OR 8 feet with 12mm thk cement slurry base1 4 and joined with white cement slurry mixed with pigment to match the shade of tile .All Complete As Per Detail Drawing, As Specified And As Directed By Architect Project - In - Charge. (size- 200x200mm) (Base rate-70)(make-Nitco Kajaria Jonshan) | SFT | 432 | 230 | 99360 | 351.6814 | 80886.7238 | 10.625 | 2443.75 | 362.3064 | -69.6936
20 | sales1@tirupatioffice.com | RFT | 8 | 450 | 3600 |  |  |  | 0 | 0 | -8
21 | COUNTER, PANELING WALL CLADDING | [7 empty] | 0
22 | WOW CHICKEN COUNTER Fixed Dispensing Counter- Providing and placing in position rectangular counter (POS counter or main counter) with under counter open shelf as per detail in drawing. Base shall be made by 19 mm thk. Ply with Drawers finished with solid laminate edge will be finished with edge binding tape. All Complete As Per Detail Drawing, As Specified And As Directed By Architect Project - In - Charge. Includs counter with GI corrugated sheet for Taglines. GI Corrugated sheet having deco finished fixed as per drawings having arrangements. Finish with laminet from inside.Length of counter varies as per drawings Height to be Considered 4feet. | RFT | 10 | 11000 | 110000 |  |  | 10 | 110000 | 10 | 0
23 | PANELLING WORK Providing and fixing 12mm thick commercial ply on seasoned 2 X 2 kailwood or MS framework with spacing 2 0 x 2 0 , Including two coats of anti - termite coat on all surfaces with necessary support as required including providing fixing of 1 mm laminate wherever indicated as per drawing, complete in all respects.Laminate shall be GREENLAM or as approved | SFT | 82 | 450 | 36900 |  |  | 82 | 36900 | 114.3639 | 32.3639 | 32.3639 | 14563.7747 | 114.36 | RA-02 JMS
24 | Corrugated Sheet with Duco Finish - Supply and Fixing of GI corrugated sheet Duco finish using PU filler and Primer base. Borders to have 2 *2 Pine wood insatlled with clear polished on all sides. | SFT | 36 | 650 | 23400 |  |  | 36 | 23400 | 39.2413 | 3.2413 | 3.2413 | 2106.8216 | 39.24 | RA-02 JMS
25 | 12 mm Ply without Laminate - | SFT | 20 | 200 | 4000 |  |  | 20 | 4000 | 23.4569 | 3.4569 | 3.4569 | 691.3774 | 3.46 | RA-02 JMS
26 | Providing and fixing wall huge storage cabinet 15 deep,dimensions as per drawing, made out of 19mm Commercial board in sides, shelves, partitions, shutters etc . 6mm thick commercial ply at the back ,shutters etc . 6mm thick commercial ply at the back ,shutters etc . 6mm thick commercial ply at the back,6 high pelmet, all exposed concealed surfaces to be laminated including concealed brass hinges, ball catchers,tower bolt inside, multipurpose lock, power coated aluminium handles, PVC stip or laminate lipping etc.Complete as per details. | [7 empty] | 0
27 | DB Cabinet | SFT | 10 | 1800 | 18000 |  |  | 10 | 18000 | 23.8191 | 13.8191 | 13.82 | 24876 | 13.82 | RA-02 JMS
28 | Storage Cabinet on left side of counter - 21 deep | SFT | 10 | 2400 | 24000 |  |  | 10 | 24000 | 10 | 0
29 | Yellow and Red CORIAN - Providing Fixing of 12mm thk. Corian fixed above counter top facia. All Complete As Per Detail Drawing, As Specified And As Directed By Architect Project - In - Charge. | SFT | 80 | 1500 | 120000 |  |  | 43.3295 | 64994.184 | 43.3295 | -36.6705
30 | Back Box-Providing and placing in position rectangular backlit box fixing in 12 mm thk. MR ply as detail finished with laminate outside white paint inside. box edge should be finihsed in pine wood frame surrounding .All Complete As Per Detail Drawing, As Specified And As Directed By Architect Project - In - Charge. Note- led module of back box will be chargeable extra. (back box size - 11 -0 x1 -2.5 ) | SFT | 15 | 1350 | 20250 |  |  | 15 | 20250 | 15 | 0
31 | Wooden Beading- Providing Fixing of poilished pine wood beading fixed at paneling top with cove light provision as specified in detail drawing. (for front counter top facia) | RFT | 18 | 150 | 2700 |  |  | 18 | 2700 | 69.3392 | 51.3392 | 51.3392 | 7700.88 | 69.34 | RA-02 JMS
32 | GLASS WORK - TOUGHENED GLASS IN WINDOW PARTITION 12 mm thick toughened glass partition | SFT | 9 | 850 | 7650 |  |  |  | 0 | 0 | -9
33 | POP OR PUTTY WORK - Providing and applying Putty or pop punning over plastered wall slab bottom up to 12 mm thick layer of super fine Plaster of Paris. [ Make Sakarni Super Fine] | SFT | 226 | 55 | 12430 |  |  | 137.3622 | 7554.9196 | 137.3622 | -88.6378
34 | PAINT WORK | [7 empty] | 0
35 | Providing and applying of 3 or more coats of Plastic emulsion paint of approved make (dulux ICI Asian or equivalent) on walls as specified. (for walls ceiling) | SFT | 120 | 55 | 6600 |  |  | 90.7084 | 4988.9606 | 90.7084 | -29.2916
36 | Perlina Texture Paint | SFT | 173 | 130 | 22490 |  |  | 46.6538 | 6064.9942 | 46.6538 | -126.3462
37 | Antique Linen Paint on perlina texture | SFT | 173 | 40 | 6920 |  |  | 46.6538 | 1866.1521 | 46.6538 | -126.3462
38 | CEILING WORK | [7 empty] | 0
39 | Providing and fixing of Metal Grid ceiling of approved make.All Complete As Per Detail Drawing, As Specified And As Directed By Architect Project - In - Charge. (Ref.ceiling plan) Providing and fixing suspended MS Grid ceiling, including Alminium Perameter of size 0.55 mm thick having one flange of 20mm and another flange of 30mm and a web of 27mm along with perimeter of ceiling, screw fixed to brick wall partition with the help of nylon sleeves and screw, at 610mm centers. The suspending Aluminium T channels of size 25mm 0.9mm thick with two flanges of 15mm each from the soffit at 600mm centers with ceiling angle of width 25X25 mm thick fixed to soffit with GI cleat and steel expansion fasteners. Ceiling section of 0.55mm thickness having knurled web of 51.5mm and two flanges of 26mm each with lips of 10.5mm are these fixed to the Main channel with the help of connecting clips and in direction perpendicular to the intermediate channel MS Grid Tile to IS-2095-1982) is then put at 600 mm centers. | SFT | 130 | 210 | 27300 |  |  | 113.5872 | 23853.3093 | 113.5872 | -16.4128
40 | ACP WORK - Housekeeping Providing services for Daily Site Cleaning proper House keeping on Handover day | LS | 5 | 3600 | 18000 |  |  |  | 0 | 0 | -5
2 | Electrical Work of AHM Wow China | no |  |  | 478060 |  | 0 |  | 294350 |  |  |  | 0
41 | ELECTRICAL WORKS
42 | Supply and installation Testing Commessioning of all electricalWork i.e Wiring (POLYCAB KEI OR Equevalent), in MS conduit for lighting, Power both RAW and by UPS , Power points for all sitting table kitchen, all switch sockets for power and lights to be a North West Anchor ROMA make. including TV wiring , Aircurtain Wiring, Speaker complete in all respect includeds Note- all wire should be FRLS. Light Circuit will be on 1.5 sqmm with 1mm earthing All industrial Socket wiring will be 4sqmm with 2.5 sqmm earthing Other Power will be 2.5 sqmm with 1.5 sqmm Earthing etc. | SFT | 230 | 450 | 103500 |  |  | 230 | 103500 | 230 | 0
43 | 12 WAY TPN DB as per Site Requirement with ELCB in each Phase. Commesioning with Proper Lugs, thimbling etc. 63-100A 4P MCB as incomer, 3 Nos ELCB 30mili Amp rating, 30 Poles of 6-32 A SP TP MCB as outgoings | NOS | 1 | 34500 | 34500 |  |  | 1 | 34500 | 1 | 0
44 | 12 WAY SPN DB as per Site Requirement with ELCB in each Phase. Commesioning with Proper Lux,thimbling etc 32 A, 2P, MCB as incomer - 10 n.o 6-32 A, SP, MCB as outgoings . | NOS | 1 | 14000 | 14000 |  |  | 1 | 14000 | 1 | 0
45 | SITC of 100-63A 4P MCCB MCB with box | NOS | 1 | 7500 | 7500 |  |  | 1 | 7500 | 1 | 0
46 | Surface Ceiling light (Make Philips Osram wipro- 18 watt. ) | NOS | 12 | 950 | 11400 |  |  | 12 | 11400 | 12 | 0
47 | 2X2Concealed Ceiling light (Make Philips Osram Wipro- 22 watt. ) | NOS | 8 | 2500 | 20000 |  |  | 6 | 15000 | 6 | -2
48 | Track light Cylinderical Light (Make Philips Osram Equvalent 18 watt. ) | NOS | 2 | 3250 | 6500 |  |  |  | 0 | 0 | -2
49 | Hanging Lights with Led Bulb | NOS | 2 | 2200 | 4400 |  |  | 2 | 4400 | 2 | 0
50 | Led strip light (make- Philips Havells or similar) | RFT | 15 | 280 | 4200 |  |  |  | 0 | 0 | -15
51 | Speaker as per Client Requirement Ahuja 10Watt AHUJA PS-300TM | NOS | 2 | 2400 | 4800 |  |  | 2 | 4800 | 2 | 0
52 | Ahuja Amplifire 350Watt AhujaDPA-370M | NOS | 1 | 8000 | 8000 |  |  | 1 | 8000 | 1 | 0
53 | Wall fans (make- Philips Havells or similar) | NOS | 1 | 3500 | 3500 |  |  |  | 0 | 0 | -1
54 | Digital meter Depend on electric Load | NOS | 1 | 8500 | 8500 |  |  |  | 0 | 0 | -1
55 | Providing Laying 4Core35 Sqmm Al Armoured Cable | RMT | 40 | 480 | 19200 |  |  | 8 | 3840 | 8 | -32
56 | Termination of Above cable Upto 35sqmm | NOS | 2 | 1500 | 3000 |  |  | 2 | 3000 | 2 | 0
57 | Termination of Above cable avove 35sqmm | NOS | 2 | 1500 | 3000 |  |  | 2 | 3000 | 2 | 0
58 | Supply fixing of Industrial type plug socket MCB in enclosure complete in all respects including MCB s and of following ratings | [7 empty] | 0
59 | 20A single phase 3 pin Ind socket with 20 A, MCB Metal Box | NOS | 2 | 1500 | 3000 |  |  | 2 | 3000 | 2 | 0
60 | 20A single phase 3 pin Ind socket with 20 A, MCB Neptune Box | NOS | 14 | 1550 | 21700 |  |  | 14 | 21700 | 14 | 0
61 | CAT6 Information outlet <FRLS wire Conduits | RMT | 70 | 75 | 5250 |  |  | 70 | 5250 | 70 | 0
62 | cctv wiring | RMT | 70 | 75 | 5250 |  |  | 70 | 5250 | 70 | 0
63 | Exhasut Freshair 5HP L T Motor Starter | NOS | 1 | 5500 | 5500 |  |  |  | 0 | 0 | -1
64 | Exhasut Freshair 7.5HP L T Motor Starter | NOS | 1 | 7500 | 7500 |  |  |  | 0 | 0 | -1
65 | MS Cable Tray of 150mmx50mm put in the kitchen area for the fixing of lights and wires to be painted in Grey color including all necessary fixing hardware like treadrod, nut bolt, fastner etc. | RMT | 21 | 210 | 4410 |  |  | 21 | 4410 | 21 | 0
66 | 2 KVA UPS | NOS | 1 | 35500 | 35500 |  |  |  | 0 | 0 | -1
67 | MS Stand | NOS | 1 | 2500 | 2500 |  |  | 1 | 2500 | 1 | 0
68 | Samsung led TV 32 - Supply and installation | Nos. | 4 | 19500 | 78000 |  |  |  | 0 | 0 | -4
69 | Supply and insatllation of all CCTV works - HD 2MP DOME CAMERA 8 | NOS | 8 | 3400 | 27200 |  |  | 5 | 17000 | 5 | -3
70 | DVR 8 CH | NOS | 1 | 9500 | 9500 |  |  | 1 | 9500 | 1 | 0
71 | 4CH SMPS | NOS | 1 | 1500 | 1500 |  |  | 1 | 1500 | 1 | 0
72 | 2TB SV | NOS | 1 | 6500 | 6500 |  |  | 1 | 6500 | 1 | 0
73 | RACK | NOS | 1 | 3500 | 3500 |  |  |  | 0 | 0 | -1
74 | Connector | NOS | 8 | 450 | 3600 |  |  | 8 | 3600 | 8 | 0
75 | PVC BOX | NOS | 2 | 450 | 900 |  |  | 1 | 450 | 1 | -1
76 | Electric Board | NOS | 1 | 750 | 750 |  |  | 1 | 750 | 1 | 0
3 | Plumbing Work of AHM Wow China | no | 1 |  | 145475 |  | 19919.5 |  | 60700 |  |  |  | 0
77 | PLUMBING
78 | Water supply
79 | Laying chasing new Water Supply lines to kitchen area sink, R.O., geyser ,toilet wc, health faucet wash basin connecting to existing lines, to make fully functional, incl.all tees, bends, junctions, elbows etc as also chasing making good with plastered surfaceas prescribed by the architect. Providing, laying and jointing PPR pipes ( PN-20 ) complete (PRINCE) with PPR fittings and clamps, including cutting and making good the walls and floors and excavation and back filling wherever necessary etc.complet (as per drawing)
80 | 20 mm nominal bore | RMT | 60 | 110 | 6600 | 17.7 | 1947 |  | 0 | 17.7 | -42.3
81 | 25 mm nominal bore | RMT | 40 | 145 | 5800 |  |  |  | 0 | 0 | -40
82 | 32 mm nominal bore | RMT | 12 | 165 | 1980 |  |  |  | 0 | 0 | -12
83 | Providing and fixing brass ball balve with SS 304 stem and ball, teflon seat complete. | [7 empty] | 0
84 | 25 mm nominal bore | NOS | 3 | 1450 | 4350 |  |  |  | 0 | 0 | -3
85 | 25 mm nominal bore | NOS | 2 | 1450 | 2900 |  |  |  | 0 | 0 | -2
86 | 32 mm nominal bore | NOS | 1 | 1745 | 1745 |  |  |  | 0 | 0 | -1
87 | Providing and installation of RO Water tank (o.h.w.t.) as site provisition.(For Kitchen @ cap.-200 ltr.) | NOS | 1 | 4500 | 4500 |  |  | 1 | 4500 | 1 | 0
88 | Water pressure Pump ( Make Crompton, 0.5HP ) | NOS | 1 | 11500 | 11500 |  |  | 1 | 11500 | 1 | 0
89 | Providing fixing bottle trap | NOS | 1 | 1750 | 1750 |  |  |  | 0 | 0 | -1
90 | Waste coupling | NOS | 1 | 950 | 950 |  |  |  | 0 | 0 | -1
91 | Providing and fixing 15mm C.P. brass Angle Valve (Jaguar-Continental) with C.P. copper connecting pipe 375mm long nuts, washer and C.P. brass flange complete, including cutting and making good the wall wherever required. | NOS | 10 | 2750 | 27500 |  |  | 10 | 27500 | 10 | 0
92 | C.P basin mixer with regular spout and pop-up waste system with 18 long copper connection | NOS | 2 | 9200 | 18400 |  |  |  | 0 | 0 | -2
93 | Drainage | [7 empty] | 0
94 | Laying chasing new drain discharge lines for kitchen area sink,new drain discharge lines for toilet wash basin connecting to existing lines, to make fully functional, incl all tees, bends, junctions, elbows etc as also chasing making good with plastered surface (avg.110 mm dia)6kg mtr as prescribed by the architect or connected to be existing waste water pipe line. 110mm | RMT | 5 | 1850 | 9250 |  |  |  | 0 | 0 | -5
95 | 110 mm | RFT | 5 | 1850 | 9250 | 4.85 | 8972.5 |  | 0 | 4.85 | -0.15
96 | SS Floor Trap 100 OR 150mm Jali Providing and fixing 100mm x 100mm Floor trap including making good of floor .(Cockroach Trap) | NOS | 3 | 1350 | 4050 |  |  |  | 0 | 0 | -3
97 | Providing and installation of Inspection chamber (size - 1 -3 x1 -3 ) | NOS | 2 | 4500 | 9000 | 2 | 9000 |  | 0 | 2 | 0
98 | Providing and fixing SS grating, 6mm thick with rim including setting in floor with cement mortar. | NOS | 2 | 1750 | 3500 |  |  |  | 0 | 0 | -2
99 | FIXTURES | [7 empty] | 0
100 | Health Faucet (hindware jacqar or similar) | NOS | 3 | 1750 | 5250 |  |  |  | 0 | 0 | -3
101 | 6 LTR (INSTANT GEYSER) | NOS | 1 | 7200 | 7200 |  |  | 1 | 7200 | 1 | 0
102 | Providing Fixing Hand dryer | NOS | 1 | 10000 | 10000 |  |  | 1 | 10000 | 1 | 0
4 | HVAC Work of AHM Wow China | no | 1 |  | 175120 |  | 115070 |  | 28950 |  |  |  | 37919.9088
103 | HVAC WORKS
104 | Providing and installation of 24G SWG GI duct complete in all respect. Note- Measurement of Ducting to be in sq.ft. | SFT | 650 | 150 | 97500 | 645 | 96750 | 5 | 750 | 650 | 0 | 195.1994 | 29279.9088
105 | Nitrile rubber insullation of Class O Grade | SFT | 234 | 80 | 18720 | 229 | 18320 | 5 | 400 | 234 | 0 | 13 | 1040
106 | VOLUME CONTROL DAMPERS | NOS | 6 | 4200 | 25200 |  |  | 3 | 12600 | 3 | -3
107 | SUPPLY AIR DIFFUSERS Size upto 600x600 | NOS | 4 | 3800 | 15200 |  |  | 4 | 15200 | 4 | 0 | 2 | 7600
108 | AIR CURTAIN | NOS | 1 | 18500 | 18500 |  |  |  | 0 | 0 | -1
[10 empty] | 0 | 0
5 | FIRE WORKS & FIRE ALARM SYSTEM for AHM Wow China | no | 1 |  | 66650 |  | 0 |  | 15400 |  |  |  | 0
109 | FIRE WORKS FIRE ALARM SYSTEM
110 | Providing and fixing of point of smoke detector | NOS | 2 | 2750 | 5500 |  |  |  | 0 | 0 | -2
111 | Providing and fixing of Fire Sprinkler line work | NOS | 6 | 3850 | 23100 |  |  | 4 | 15400 | 4 | -2
112 | Fire alarm pannel -2 Zone - Conventional type Commessioning with Mall Panel | NOS | 1 | 12500 | 12500 |  |  |  | 0 | 0 | -1
113 | Providing and fixing of 2c x 1.5 Sqmm FRLS cable | Mtr | 90 | 80 | 7200 |  |  |  | 0 | 0 | -90
114 | Supply, installation ,testing Commissioning of optical Photoelectric type R.I. of photo optic sensing chamber Make - Agni | NOS | 3 | 2350 | 7050 |  |  |  | 0 | 0 | -3
115 | Supply, installation ,testing Commissioning of Hooter Make - Agni | NOS | 1 | 2250 | 2250 |  |  |  | 0 | 0 | -1
116 | Supply, installation ,testing Commissioning of Mannual Call Point Make - Agni | NOS | 1 | 1850 | 1850 |  |  |  | 0 | 0 | -1
117 | Monitor Module for Intergration | NOS | 2 | 2350 | 4700 |  |  |  | 0 | 0 | -2
118 | ISI Mark Rubber Mat | NOS | 1 | 2500 | 2500 |  |  |  | 0 | 0 | -1
[9 empty] | 0 | 0 | 0

## RA-02 JMS
WOW China_AHM_Bill Of Quantities_Civil&Interior_Plumbing _Electrical |  |  |  | RA 02 Joint Measurement Sheet
Sr No. | Item Name | UOM | Qty | Length | Width | Height | Nos | Qty
1 | Civil & Interior Work of AHM Wow China | no | 1
2 | BOH MOH FOH - CIVIL AND ALLIED WORKS - Providing And Laying of half brick partitions with well burnt 1st class good quality bricks in cement mortar 1 4 ( 1 cement 4 coarse sand ) including providing 2 NOS. of 6mm dia MS round bars at every 4th coarse in true line,level and plumb including racking the joints up to 20 mm depth, rubbing and cleaning the surface with necessary scaffolding, curing etc. Complete as directed.Note MS bar paid extra. Full height 4.5 Thick wall with 1 4 cement mortar Above raw slab Level. (Ref. to civil plan) Brick work Fly Ash Brick | SFT | 585 |  |  |  |  | 4.1
| Extension of wall patta near LHS counter | SFT |  | 0.5 |  | 8.2 |  | 4.1
3 | PLASTER WORK- Providing And Laying of 12 mm thick wall plaster 1 4. (Kitchen area Toilet area FOH MOH Etc. ) (Ref. to civil plan) Internal Plastering | SFT | 1030 |  |  |  |  | 4.1
| Extension of wall patta near LHS counter | SFT |  | 0.5 |  | 8.2 |  | 4.1
4 | Water-Proffing Work
5 | Providing And Laying of 3 mm APP Waterproofing PU liquid Mebrance (3 Coat or as per mall specification) coating surface as per . manufacture specs, Included Racking hacking of Surface for Waterprofing, Finished smooth in line, level and plumb including curing, of R.C.C surfaces, racking of joints corner coving etc. Complete at all levels. (Ref. to waterproofing plan ) (Option-2) Dr. Fixit Asian Equivalent | SFT | 396 |  |  |  |  | 184.7067
| Floor wateproofing | SFT |  | 16.2688 | 11.3488 |  |  | 184.6314
| Less Pillar | SFT |  | 3.116 | -3.0832 |  |  | -9.6073
| Chamber waterproofing | SFT |  | 4.92 | 0.984 |  | 2 | 9.6826
13 | FLOORING
16 | Tile-1 - ONTARIO GIRIS 600 X 600MM (PSTONE CREST - FULL BODY, MATTE FINISHing 600 X 600 MM (PREMIUM - FULL BODY, DRY MATTE, As per drawings Kajaria NITCO -2 -0 X2 -0 LATICRETE EPOXY GROUT | SFT | 86 |  |  |  |  | 11.9418
| Floor tile extension till façade | SFT |  | 12.136 | 0.656 |  |  | 7.9612
| Skirting | SFT |  | 12.136 | 0.328 |  |  | 3.9806
17 | 8 wide black granite Kota stone band supply and installation using cement mortar paste in proper line and level with Half round chamfer and Half Nosing. | RFT | 3 |  |  |  |  | 3
18 | TILE CLADIING (FOR WALL)
19 | Tile wall cladding -Providing Fixing of WOW CHICKEN Multicolored Tile upto slab bottom OR 8 feet with 12mm thk cement slurry base1 4 and joined with white cement slurry mixed with pigment to match the shade of tile .All Complete As Per Detail Drawing, As Specified And As Directed By Architect Project - In - Charge. (size- 200x200mm) (Base rate-70)(make-Nitco Kajaria Jonshan) | SFT | 432 |  |  |  |  | 10.625
| Black tile installation on gas line wall | SFT |  | 8.5 | 1.25 |  |  | 10.625
21 | COUNTER, PANELING WALL CLADDING
22 | WOW CHICKEN COUNTER Fixed Dispensing Counter- Providing and placing in position rectangular counter (POS counter or main counter) with under counter open shelf as per detail in drawing. Base shall be made by 19 mm thk. Ply with Drawers finished with solid laminate edge will be finished with edge binding tape. All Complete As Per Detail Drawing, As Specified And As Directed By Architect Project - In - Charge. Includs counter with GI corrugated sheet for Taglines. GI Corrugated sheet having deco finished fixed as per drawings having arrangements. Finish with laminet from inside.Length of counter varies as per drawings Height to be Considered 4feet. | RFT | 10 |  |  |  |  | 10
23 | PANELLING WORK Providing and fixing 12mm thick commercial ply on seasoned 2 X 2 kailwood or MS framework with spacing 2 0 x 2 0 , Including two coats of anti - termite coat on all surfaces with necessary support as required including providing fixing of 1 mm laminate wherever indicated as per drawing, complete in all respects.Laminate shall be GREENLAM or as approved | SFT | 82 |  |  |  |  | 114.3639
| Ply panelling above bulkhead ceiling | SFT |  | 8.4624 | 2.6568 |  |  | 22.4829
| RHS L Shape cladding | SFT |  | 6.1992 | 8.856 |  |  | 54.9001
| LHS wall L shape | SFT |  | 2.9848 | 8.856 |  |  | 26.4334
| Inside bulkhead vertical | SFT |  | 1.2464 | 8.4624 |  |  | 10.5475
24 | Corrugated Sheet with Duco Finish - Supply and Fixing of GI corrugated sheet Duco finish using PU filler and Primer base. Borders to have 2 *2 Pine wood insatlled with clear polished on all sides. | SFT | 36 |  |  |  |  | 39.2413
| LHS Vertical | SFT |  | 1.476 | 2.296 |  | 2 | 6.7778
| RHS Vertical | SFT |  | 1.4924 | 2.296 |  | 2 | 6.8531
| RHS Vertical bottom | SFT |  | 0.82 | 2.296 |  | 2 | 3.7654
| Door | SFT |  | 2.952 | 1.7876 |  | 1 | 5.277
| Ceiling top | SFT |  | 1.804 | 2.296 |  | 4 | 16.5679
25 | 12 mm Ply without Laminate - | SFT | 20 |  |  |  |  | 23.4569
| RHS wall base | SFT |  | 2.6487 | 8.856 |  |  | 23.4569
26 | Providing and fixing wall huge storage cabinet 15 deep,dimensions as per drawing, made out of 19mm Commercial board in sides, shelves, partitions, shutters etc . 6mm thick commercial ply at the back ,shutters etc . 6mm thick commercial ply at the back ,shutters etc . 6mm thick commercial ply at the back,6 high pelmet, all exposed concealed surfaces to be laminated including concealed brass hinges, ball catchers,tower bolt inside, multipurpose lock, power coated aluminium handles, PVC stip or laminate lipping etc.Complete as per details.
27 | DB Cabinet | SFT | 10 | 2.6896 |  | 8.856 |  | 23.8191
28 | Storage Cabinet on left side of counter - 21 deep | SFT | 10 |  |  |  |  | 10
29 | Yellow and Red CORIAN - Providing Fixing of 12mm thk. Corian fixed above counter top facia. All Complete As Per Detail Drawing, As Specified And As Directed By Architect Project - In - Charge. | SFT | 80 |  |  |  |  | 43.3295
| Counter top corian | SFT |  | 6.6584 | 1.64 |  |  | 10.9198
| Front Counter | SFT |  | 1.3776 | 6.6584 |  |  | 9.1726
| Vertical counter | SFT |  | 1.312 | 2.952 |  |  | 3.873
| Door | SFT |  | 0.492 | 1.804 |  |  | 0.88757
| Grey Patta | SFT |  | 0.5248 | 10.2664 |  |  | 5.3878
| Grey pillar patta | SFT |  | 0.5248 | 8.2328 |  |  | 4.3206
| Counter billing position | SFT |  | 2.7224 | 1.64 |  |  | 4.4647
| Beading | SFT |  | 0.82 | 5.248 |  |  | 4.3034
30 | Back Box-Providing and placing in position rectangular backlit box fixing in 12 mm thk. MR ply as detail finished with laminate outside white paint inside. box edge should be finihsed in pine wood frame surrounding .All Complete As Per Detail Drawing, As Specified And As Directed By Architect Project - In - Charge. Note- led module of back box will be chargeable extra. (back box size - 11 -0 x1 -2.5 ) | SFT | 15 |  |  |  |  | 15
31 | Wooden Beading- Providing Fixing of poilished pine wood beading fixed at paneling top with cove light provision as specified in detail drawing. (for front counter top facia) | RFT | 18 |  |  |  |  | 69.3392
| RHS wall | RFT |  | 18.04 |  |  |  | 18.04
| LHS wall | RFT |  | 13.776 |  |  |  | 13.776
| Top ceiling | RFT |  | 28.3392 |  |  |  | 28.3392
| Low height top | RFT |  | 9.184 |  |  |  | 9.184
33 | POP OR PUTTY WORK - Providing and applying Putty or pop punning over plastered wall slab bottom up to 12 mm thick layer of super fine Plaster of Paris. [ Make Sakarni Super Fine] | SFT | 226 |  |  |  |  | 137.3622
| Gyspum ceiling area | SFT |  | 5.6416 | 11.48 |  |  | 64.7656
| Wall Patta paint | SFT |  | 33.7512 | 0.5248 |  |  | 17.7126
| Vertical wall inside | SFT |  | 1.6728 | 4.92 |  |  | 8.2302
| RHS wall | SFT |  | 5.412 | 4.8216 |  |  | 26.0945
| LHS Wall | SFT |  | 4.264 | 4.8216 |  |  | 20.5593
34 | PAINT WORK
35 | Providing and applying of 3 or more coats of Plastic emulsion paint of approved make (dulux ICI Asian or equivalent) on walls as specified. (for walls ceiling) | SFT | 120 |  |  |  |  | 90.7084
| Gyspum ceiling area | SFT |  | 5.6416 | 11.48 |  |  | 64.7656
| Wall Patta paint | SFT |  | 33.7512 | 0.5248 |  |  | 17.7126
| Vertical wall inside | SFT |  | 1.6728 | 4.92 |  |  | 8.2302
36 | Perlina Texture Paint | SFT | 173 |  |  |  |  | 46.6538
| LHS Wall | SFT |  | 5.412 | 4.8216 |  |  | 26.0945
| RHS Wall | SFT |  | 4.264 | 4.8216 |  |  | 20.5593
37 | Antique Linen Paint on perlina texture | SFT | 173 |  |  |  |  | 46.6538
| LHS Wall | SFT |  | 5.412 | 4.8216 |  |  | 26.0945
| RHS Wall | SFT |  | 4.264 | 4.8216 |  |  | 20.5593
38 | CEILING WORK
39 | Providing and fixing of Metal Grid ceiling of approved make.All Complete As Per Detail Drawing, As Specified And As Directed By Architect Project - In - Charge. (Ref.ceiling plan) Providing and fixing suspended MS Grid ceiling, including Alminium Perameter of size 0.55 mm thick having one flange of 20mm and another flange of 30mm and a web of 27mm along with perimeter of ceiling, screw fixed to brick wall partition with the help of nylon sleeves and screw, at 610mm centers. The suspending Aluminium T channels of size 25mm 0.9mm thick with two flanges of 15mm each from the soffit at 600mm centers with ceiling angle of width 25X25 mm thick fixed to soffit with GI cleat and steel expansion fasteners. Ceiling section of 0.55mm thickness having knurled web of 51.5mm and two flanges of 26mm each with lips of 10.5mm are these fixed to the Main channel with the help of connecting clips and in direction perpendicular to the intermediate channel MS Grid Tile to IS-2095-1982) is then put at 600 mm centers. | SFT | 130 |  |  |  |  | 113.5872
| BOH area | SFT |  | 10.824 | 11.3816 |  |  | 123.1944
| Less Pillar | SFT |  | -3.116 | 3.0832 |  |  | -9.6073
2 | Electrical Work of AHM Wow China | no | 1
41 | ELECTRICAL WORKS
42 | Supply and installation Testing Commessioning of all electricalWork i.e Wiring (POLYCAB KEI OR Equevalent), in MS conduit for lighting, Power both RAW and by UPS , Power points for all sitting table kitchen, all switch sockets for power and lights to be a North West Anchor ROMA make. including TV wiring , Aircurtain Wiring, Speaker complete in all respect includeds Note- all wire should be FRLS. Light Circuit will be on 1.5 sqmm with 1mm earthing All industrial Socket wiring will be 4sqmm with 2.5 sqmm earthing Other Power will be 2.5 sqmm with 1.5 sqmm Earthing etc. | SFT | 230 |  |  |  |  | 230
43 | 12 WAY TPN DB as per Site Requirement with ELCB in each Phase. Commesioning with Proper Lugs, thimbling etc. 63-100A 4P MCB as incomer, 3 Nos ELCB 30mili Amp rating, 30 Poles of 6-32 A SP TP MCB as outgoings | NOS | 1 |  |  |  |  | 1
44 | 12 WAY SPN DB as per Site Requirement with ELCB in each Phase. Commesioning with Proper Lux,thimbling etc 32 A, 2P, MCB as incomer - 10 n.o 6-32 A, SP, MCB as outgoings . | NOS | 1 |  |  |  |  | 1
45 | SITC of 100-63A 4P MCCB MCB with box | NOS | 1 |  |  |  |  | 1
46 | Surface Ceiling light (Make Philips Osram wipro- 18 watt. ) | NOS | 12 |  |  |  |  | 12
47 | 2X2Concealed Ceiling light (Make Philips Osram Wipro- 22 watt. ) | NOS | 8 |  |  |  |  | 6
49 | Hanging Lights with Led Bulb | NOS | 2 |  |  |  |  | 2
51 | Speaker as per Client Requirement Ahuja 10Watt AHUJA PS-300TM | NOS | 2 |  |  |  |  | 2
52 | Ahuja Amplifire 350Watt AhujaDPA-370M | NOS | 1 |  |  |  |  | 1
55 | Providing Laying 4Core35 Sqmm Al Armoured Cable | RMT | 40 |  |  |  |  | 8
56 | Termination of Above cable Upto 35sqmm | NOS | 2 |  |  |  |  | 2
57 | Termination of Above cable avove 35sqmm | NOS | 2 |  |  |  |  | 2
58 | Supply fixing of Industrial type plug socket MCB in enclosure complete in all respects including MCB s and of following ratings
59 | 20A single phase 3 pin Ind socket with 20 A, MCB Metal Box | NOS | 2 |  |  |  |  | 2
60 | 20A single phase 3 pin Ind socket with 20 A, MCB Neptune Box | NOS | 14 |  |  |  |  | 14
61 | CAT6 Information outlet <FRLS wire Conduits | RMT | 70 |  |  |  |  | 70
62 | cctv wiring | RMT | 70 |  |  |  |  | 70
65 | MS Cable Tray of 150mmx50mm put in the kitchen area for the fixing of lights and wires to be painted in Grey color including all necessary fixing hardware like treadrod, nut bolt, fastner etc. | RMT | 21 |  |  |  |  | 21
67 | MS Stand | NOS | 1 |  |  |  |  | 1
69 | Supply and insatllation of all CCTV works - HD 2MP DOME CAMERA 8 | NOS | 8 |  |  |  |  | 5
70 | DVR 8 CH | NOS | 1 |  |  |  |  | 1
71 | 4CH SMPS | NOS | 1 |  |  |  |  | 1
72 | 2TB SV | NOS | 1 |  |  |  |  | 1
73 | RACK | NOS | 1
74 | Connector | NOS | 8 |  |  |  |  | 8
75 | PVC BOX | NOS | 2 |  |  |  |  | 1
76 | Electric Board | NOS | 1 |  |  |  |  | 1
3 | Plumbing Work of AHM Wow China | no | 1
77 | PLUMBING
87 | Providing and installation of RO Water tank (o.h.w.t.) as site provisition.(For Kitchen @ cap.-200 ltr.) | NOS | 1 |  |  |  |  | 1
88 | Water pressure Pump ( Make Crompton, 0.5HP ) | NOS | 1 |  |  |  |  | 1
91 | Providing and fixing 15mm C.P. brass Angle Valve (Jaguar-Continental) with C.P. copper connecting pipe 375mm long nuts, washer and C.P. brass flange complete, including cutting and making good the wall wherever required. | NOS | 10 |  |  |  |  | 10
101 | 6 LTR (INSTANT GEYSER) | NOS | 1 |  |  |  |  | 1
102 | Providing Fixing Hand dryer | NOS | 1 |  |  |  |  | 1
4 | HVAC Work of AHM Wow China | no | 1
103 | HVAC WORKS
104 | Providing and installation of 24G SWG GI duct complete in all respect. Note- Measurement of Ducting to be in sq.ft. | SFT | 650 |  |  |  |  | 200.1994
| FAD | SFT |  | 3.936 | 3.936 |  | 3 | 46.4763
| SAD | SFT |  | 5.904 | 2.624 |  | 4 | 61.9684
| FAD | SFT |  | 3.94 | 6.232 |  | 1 | 24.5541
| RAD | SFT |  | 3.94 | 3.936 |  | 3 | 46.5235
| RAD | SFT |  | 3.94 | 1.312 |  | 1 | 5.1693
| RAD | SFT |  | 3.94 | 1.968 |  | 2 | 15.5078
105 | Nitrile rubber insullation of Class O Grade | SFT | 234 |  |  |  |  | 18
106 | VOLUME CONTROL DAMPERS | NOS | 6 |  |  |  |  | 3
107 | SUPPLY AIR DIFFUSERS Size upto 600x600 | NOS | 4 |  |  |  |  | 6
5 | FIRE WORKS & FIRE ALARM SYSTEM for AHM Wow China | no | 1
111 | Providing and fixing of Fire Sprinkler line work | NOS | 6 |  |  |  |  | 4

## RA-01 JMS
WOW China_AHM_Bill Of Quantities_Civil&Interior_Plumbing _Electrical |  |  |  | Revised RA 01 Measurement Sheet
Sr No. | Item Name | UOM | Qty | Length | Width | Height | Nos | QTY
1 | Civil & Interior Work of AHM Wow China | no | 1
1 | BOH MOH FOH - ANTI TERMITE TREATMENT - Providing doing anti termite treatment with IMIDACLOPRID (OZIER) for entire area (Pest control) Diluting and injecting chemical emulsion 3 in floor for pre constructional Anti Termite treatment and creating a continuous chemical @ 4 center to center barrier all over as per manufacturer specification and ISI standards. including a 1 year guarantee under suitable undertaking on stamp paper etc, complete as directed by Architect.(Mode of measurement is to be carpet area of floor and not the area of surface treated). | SFT | 216
2 | BOH MOH FOH - CIVIL AND ALLIED WORKS - Providing And Laying of half brick partitions with well burnt 1st class good quality bricks in cement mortar 1 4 ( 1 cement 4 coarse sand ) including providing 2 NOS. of 6mm dia MS round bars at every 4th coarse in true line,level and plumb including racking the joints up to 20 mm depth, rubbing and cleaning the surface with necessary scaffolding, curing etc. Complete as directed.Note MS bar paid extra. Full height 4.5 Thick wall with 1 4 cement mortar Above raw slab Level. (Ref. to civil plan) Brick work Fly Ash Brick | SFT | 585 |  |  |  |  | 466.7486
| Left Wall |  |  | 5.22 |  | 2.85 | 1 | 160.136
| Front Wall |  |  | 4.38 |  | 2.85 | 1 | 134.367
| RHS WALL |  |  | 4.62 |  | 2.85 | 1 | 141.7296
| Low Height Wall |  |  | 2.1 |  | 1.35 | 1 | 30.5159
3 | PLASTER WORK- Providing And Laying of 12 mm thick wall plaster 1 4. (Kitchen area Toilet area FOH MOH Etc. ) (Ref. to civil plan) Internal Plastering | SFT | 1030 |  |  |  |  | 696.6676
| Left Wall |  |  | 5.22 |  | 2.85 | 1 | 160.136
| Front Wall |  |  | 4.38 |  | 2.85 | 1 | 134.367
| RHS WALL |  |  | 4.62 |  | 2.85 | 1 | 141.7296
| Low Height Wall |  |  | 2.1 |  | 1.35 | 2 | 61.0319
| Front Wall Full Height |  |  | 6.5 |  | 2.85 | 1 | 199.4031
4 | Water-Proffing Work
5 | Providing And Laying of 3 mm APP Waterproofing PU liquid Mebrance (3 Coat or as per mall specification) coating surface as per . manufacture specs, Included Racking hacking of Surface for Waterprofing, Finished smooth in line, level and plumb including curing, of R.C.C surfaces, racking of joints corner coving etc. Complete at all levels. (Ref. to waterproofing plan ) (Option-2) Dr. Fixit Asian Equivalent | SFT | 396
6 | Providing And Laying of 12 mm thick wall plaster 1 4. (Kitchen area toilet area FOH MOH Etc. ) (Ref. to civil plan) Protection Plastering. | SFT | 216 | 3.52 | 5.22 |  | 1 | 197.782
7 | PCC WORK- 1 2 4 - Providing And Laying of Upto 50mm PPC above floor filling. (kitchen area ) Ratio 1 4 8 | SFT | 216 |  |  |  |  | 188.0686
|  |  |  | 5.22 | 3.52 |  | 1 | 197.782
| Less Pillar |  |  | 0.96 | -0.94 |  | 1 | -9.7134
8 | FLOOR FILLING
9 | Providing and laying cinder filling of light weight of AAC blocks Brick coba (Auto Areated Concrete), placing the same in sunken area raised floor surrounded by 115 mm thick brick wall. All Complete As Per Detail Drawing, As Specified And As Directed By Architect Project - In - Charge. (Depth as per site)
10 | Depth upto 200 mm | SFT | 130 |  |  |  |  | 181.9378
| BOH area |  |  | 3.25 | 3.52 |  |  | 11.44
| Less Pillar |  |  | 0.96 | -0.945 |  |  | -0.9072
| FOD area |  |  | 3.52 | 1.81 |  |  | 6.3712
11 | Repairing of Wall Punctures size upto 2feetx2feet | NOS | 2 |  |  |  |  | 2
12 | Core cutting or Demolotion of wall for the same (For Exhaust Fresh Air Duct Ac Pipe etc.) | NOS | 2 |  |  |  |  | 2
13 | FLOORING
14 | VITRIFIED TILE KOTA STONE FLOORING -( INSIDE AREA ) Providing laying 2 -0 X2 -0 Vitrified Floor Tiles on a bed of 50mm thk. cement mortar (1 4) adhesive of approved make and design, complete with tile grout in white cement and pigment of latecrete balendura) matching color of tile. (Base rate -Rs 70) (Make-Nitco kajaria) (Ref. to Flooring plan)
15 | Tile-1 - Polished Kota Stone Flooring 550 X 550 MM (PREMIUM - FULL BODY, DRY MATTE, As per drawings Kajaria NITCO -2 -0 X2 -0 LATICRETE EPOXY GROUT | SFT | 130 |  |  |  |  | 113.4256
|  |  |  | 3.25 | 3.52 |  | 1 | 123.1402
| Less Pillar |  |  | 0.95 | 0.95 |  | 1 | 9.7145
16 | Tile-1 - ONTARIO GIRIS 600 X 600MM (PSTONE CREST - FULL BODY, MATTE FINISHing 600 X 600 MM (PREMIUM - FULL BODY, DRY MATTE, As per drawings Kajaria NITCO -2 -0 X2 -0 LATICRETE EPOXY GROUT | SFT | 86 | 3.52 | 1.81 |  | 1 | 68.5796
17 | 8 wide black granite Kota stone band supply and installation using cement mortar paste in proper line and level with Half round chamfer and Half Nosing. | RFT | 3 | 3 |  |  |  | 3
18 | TILE CLADIING (FOR WALL)
19 | Tile wall cladding -Providing Fixing of WOW CHICKEN Multicolored Tile upto slab bottom OR 8 feet with 12mm thk cement slurry base1 4 and joined with white cement slurry mixed with pigment to match the shade of tile .All Complete As Per Detail Drawing, As Specified And As Directed By Architect Project - In - Charge. (size- 200x200mm) (Base rate-70)(make-Nitco Kajaria Jonshan) | SFT | 432 |  |  |  |  | 351.6814
| LHS Wall |  |  |  | 3.3 | 2.4 | 1 | 85.2509
| Front Wall |  |  |  | 4.38 | 2.4 | 1 | 113.1512
| RHS |  |  |  | 2.35 | 2.4 | 1 | 60.709
| Low height |  |  |  | 0.521 | 1 | 1 | 5.608
| Low height |  |  |  | 1 | 2.085 | 1 | 22.4429
| Front Side |  |  |  | 1.2 | 1.73 | 1 | 22.3461
| Wall |  |  |  | 3.265 | 1.2 | 1 | 42.1734
20 | sales1@tirupatioffice.com | RFT | 8
21 | COUNTER, PANELING WALL CLADDING
22 | WOW CHICKEN COUNTER Fixed Dispensing Counter- Providing and placing in position rectangular counter (POS counter or main counter) with under counter open shelf as per detail in drawing. Base shall be made by 19 mm thk. Ply with Drawers finished with solid laminate edge will be finished with edge binding tape. All Complete As Per Detail Drawing, As Specified And As Directed By Architect Project - In - Charge. Includs counter with GI corrugated sheet for Taglines. GI Corrugated sheet having deco finished fixed as per drawings having arrangements. Finish with laminet from inside.Length of counter varies as per drawings Height to be Considered 4feet. | RFT | 10
23 | PANELLING WORK Providing and fixing 12mm thick commercial ply on seasoned 2 X 2 kailwood or MS framework with spacing 2 0 x 2 0 , Including two coats of anti - termite coat on all surfaces with necessary support as required including providing fixing of 1 mm laminate wherever indicated as per drawing, complete in all respects.Laminate shall be GREENLAM or as approved | SFT | 82
24 | Corrugated Sheet with Duco Finish - Supply and Fixing of GI corrugated sheet Duco finish using PU filler and Primer base. Borders to have 2 *2 Pine wood insatlled with clear polished on all sides. | SFT | 36
25 | 12 mm Ply without Laminate - | SFT | 20
26 | Providing and fixing wall huge storage cabinet 15 deep,dimensions as per drawing, made out of 19mm Commercial board in sides, shelves, partitions, shutters etc . 6mm thick commercial ply at the back ,shutters etc . 6mm thick commercial ply at the back ,shutters etc . 6mm thick commercial ply at the back,6 high pelmet, all exposed concealed surfaces to be laminated including concealed brass hinges, ball catchers,tower bolt inside, multipurpose lock, power coated aluminium handles, PVC stip or laminate lipping etc.Complete as per details.
27 | DB Cabinet | SFT | 10
28 | Storage Cabinet on left side of counter - 21 deep | SFT | 10
29 | Yellow and Red CORIAN - Providing Fixing of 12mm thk. Corian fixed above counter top facia. All Complete As Per Detail Drawing, As Specified And As Directed By Architect Project - In - Charge. | SFT | 80
30 | Back Box-Providing and placing in position rectangular backlit box fixing in 12 mm thk. MR ply as detail finished with laminate outside white paint inside. box edge should be finihsed in pine wood frame surrounding .All Complete As Per Detail Drawing, As Specified And As Directed By Architect Project - In - Charge. Note- led module of back box will be chargeable extra. (back box size - 11 -0 x1 -2.5 ) | SFT | 15
31 | Wooden Beading- Providing Fixing of poilished pine wood beading fixed at paneling top with cove light provision as specified in detail drawing. (for front counter top facia) | RFT | 18
32 | GLASS WORK - TOUGHENED GLASS IN WINDOW PARTITION 12 mm thick toughened glass partition | SFT | 9
33 | POP OR PUTTY WORK - Providing and applying Putty or pop punning over plastered wall slab bottom up to 12 mm thick layer of super fine Plaster of Paris. [ Make Sakarni Super Fine] | SFT | 226
34 | PAINT WORK
35 | Providing and applying of 3 or more coats of Plastic emulsion paint of approved make (dulux ICI Asian or equivalent) on walls as specified. (for walls ceiling) | SFT | 120
36 | Perlina Texture Paint | SFT | 173
37 | Antique Linen Paint on perlina texture | SFT | 173
38 | CEILING WORK
39 | Providing and fixing of Metal Grid ceiling of approved make.All Complete As Per Detail Drawing, As Specified And As Directed By Architect Project - In - Charge. (Ref.ceiling plan) Providing and fixing suspended MS Grid ceiling, including Alminium Perameter of size 0.55 mm thick having one flange of 20mm and another flange of 30mm and a web of 27mm along with perimeter of ceiling, screw fixed to brick wall partition with the help of nylon sleeves and screw, at 610mm centers. The suspending Aluminium T channels of size 25mm 0.9mm thick with two flanges of 15mm each from the soffit at 600mm centers with ceiling angle of width 25X25 mm thick fixed to soffit with GI cleat and steel expansion fasteners. Ceiling section of 0.55mm thickness having knurled web of 51.5mm and two flanges of 26mm each with lips of 10.5mm are these fixed to the Main channel with the help of connecting clips and in direction perpendicular to the intermediate channel MS Grid Tile to IS-2095-1982) is then put at 600 mm centers. | SFT | 130
40 | ACP WORK - Housekeeping Providing services for Daily Site Cleaning proper House keeping on Handover day | LS | 5
2 | Electrical Work of AHM Wow China | no | 1
41 | ELECTRICAL WORKS
42 | Supply and installation Testing Commessioning of all electricalWork i.e Wiring (POLYCAB KEI OR Equevalent), in MS conduit for lighting, Power both RAW and by UPS , Power points for all sitting table kitchen, all switch sockets for power and lights to be a North West Anchor ROMA make. including TV wiring , Aircurtain Wiring, Speaker complete in all respect includeds Note- all wire should be FRLS. Light Circuit will be on 1.5 sqmm with 1mm earthing All industrial Socket wiring will be 4sqmm with 2.5 sqmm earthing Other Power will be 2.5 sqmm with 1.5 sqmm Earthing etc. | SFT | 230
43 | 12 WAY TPN DB as per Site Requirement with ELCB in each Phase. Commesioning with Proper Lugs, thimbling etc. 63-100A 4P MCB as incomer, 3 Nos ELCB 30mili Amp rating, 30 Poles of 6-32 A SP TP MCB as outgoings | NOS | 1
44 | 12 WAY SPN DB as per Site Requirement with ELCB in each Phase. Commesioning with Proper Lux,thimbling etc 32 A, 2P, MCB as incomer - 10 n.o 6-32 A, SP, MCB as outgoings . | NOS | 1
45 | SITC of 100-63A 4P MCCB MCB with box | NOS | 1
46 | Surface Ceiling light (Make Philips Osram wipro- 18 watt. ) | NOS | 12
47 | 2X2Concealed Ceiling light (Make Philips Osram Wipro- 22 watt. ) | NOS | 8
48 | Track light Cylinderical Light (Make Philips Osram Equvalent 18 watt. ) | NOS | 2
49 | Hanging Lights with Led Bulb | NOS | 2
50 | Led strip light (make- Philips Havells or similar) | RFT | 15
51 | Speaker as per Client Requirement Ahuja 10Watt AHUJA PS-300TM | NOS | 2
52 | Ahuja Amplifire 350Watt AhujaDPA-370M | NOS | 1
53 | Wall fans (make- Philips Havells or similar) | NOS | 1
54 | Digital meter Depend on electric Load | NOS | 1
55 | Providing Laying 4Core35 Sqmm Al Armoured Cable | RMT | 40
56 | Termination of Above cable Upto 35sqmm | NOS | 2
57 | Termination of Above cable avove 35sqmm | NOS | 2
58 | Supply fixing of Industrial type plug socket MCB in enclosure complete in all respects including MCB s and of following ratings
59 | 20A single phase 3 pin Ind socket with 20 A, MCB Metal Box | NOS | 2
60 | 20A single phase 3 pin Ind socket with 20 A, MCB Neptune Box | NOS | 14
61 | CAT6 Information outlet <FRLS wire Conduits | RMT | 70
62 | cctv wiring | RMT | 70
63 | Exhasut Freshair 5HP L T Motor Starter | NOS | 1
64 | Exhasut Freshair 7.5HP L T Motor Starter | NOS | 1
65 | MS Cable Tray of 150mmx50mm put in the kitchen area for the fixing of lights and wires to be painted in Grey color including all necessary fixing hardware like treadrod, nut bolt, fastner etc. | RMT | 21
66 | 2 KVA UPS | NOS | 1
67 | MS Stand | NOS | 1
68 | Samsung led TV 32 - Supply and installation | Nos. | 4
69 | Supply and insatllation of all CCTV works - HD 2MP DOME CAMERA 8 | NOS | 8
70 | DVR 8 CH | NOS | 1
71 | 4CH SMPS | NOS | 1
72 | 2TB SV | NOS | 1
73 | RACK | NOS | 1
74 | Connector | NOS | 8
75 | PVC BOX | NOS | 2
76 | Electric Board | NOS | 1
3 | Plumbing Work of AHM Wow China | no | 1
77 | PLUMBING
78 | Water supply
79 | Laying chasing new Water Supply lines to kitchen area sink, R.O., geyser ,toilet wc, health faucet wash basin connecting to existing lines, to make fully functional, incl.all tees, bends, junctions, elbows etc as also chasing making good with plastered surfaceas prescribed by the architect. Providing, laying and jointing PPR pipes ( PN-20 ) complete (PRINCE) with PPR fittings and clamps, including cutting and making good the walls and floors and excavation and back filling wherever necessary etc.complet (as per drawing)
80 | 20 mm nominal bore | RMT | 60 |  |  |  |  | 17.7
81 | 25 mm nominal bore | RMT | 40
82 | 32 mm nominal bore | RMT | 12
83 | Providing and fixing brass ball balve with SS 304 stem and ball, teflon seat complete.
84 | 25 mm nominal bore | NOS | 3
85 | 25 mm nominal bore | NOS | 2
86 | 32 mm nominal bore | NOS | 1
87 | Providing and installation of RO Water tank (o.h.w.t.) as site provisition.(For Kitchen @ cap.-200 ltr.) | NOS | 1
88 | Water pressure Pump ( Make Crompton, 0.5HP ) | NOS | 1
89 | Providing fixing bottle trap | NOS | 1
90 | Waste coupling | NOS | 1
91 | Providing and fixing 15mm C.P. brass Angle Valve (Jaguar-Continental) with C.P. copper connecting pipe 375mm long nuts, washer and C.P. brass flange complete, including cutting and making good the wall wherever required. | NOS | 10
92 | C.P basin mixer with regular spout and pop-up waste system with 18 long copper connection | NOS | 2
93 | Drainage
94 | Laying chasing new drain discharge lines for kitchen area sink,new drain discharge lines for toilet wash basin connecting to existing lines, to make fully functional, incl all tees, bends, junctions, elbows etc as also chasing making good with plastered surface (avg.110 mm dia)6kg mtr as prescribed by the architect or connected to be existing waste water pipe line. 110mm
95 | 110 mm | RFT | 5 | 4.85 |  |  |  | 4.85
96 | SS Floor Trap 100 OR 150mm Jali Providing and fixing 100mm x 100mm Floor trap including making good of floor .(Cockroach Trap) | NOS | 3
97 | Providing and installation of Inspection chamber (size - 1 -3 x1 -3 ) | NOS | 2 | 2 |  |  |  | 2
98 | Providing and fixing SS grating, 6mm thick with rim including setting in floor with cement mortar. | NOS | 2
99 | FIXTURES
100 | Health Faucet (hindware jacqar or similar) | NOS | 3
101 | 6 LTR (INSTANT GEYSER) | NOS | 1
102 | Providing Fixing Hand dryer | NOS | 1
4 | HVAC Work of AHM Wow China | no | 1
103 | HVAC WORKS
104 | Providing and installation of 24G SWG GI duct complete in all respect. Note- Measurement of Ducting to be in sq.ft. | SFT | 650 |  |  |  |  | 645
105 | Nitrile rubber insullation of Class O Grade | SFT | 234 |  |  |  |  | 229
106 | VOLUME CONTROL DAMPERS | NOS | 6
107 | SUPPLY AIR DIFFUSERS Size upto 600x600 | NOS | 4
108 | AIR CURTAIN | NOS | 1
5 | FIRE WORKS & FIRE ALARM SYSTEM for AHM Wow China | no | 1
109 | FIRE WORKS FIRE ALARM SYSTEM
110 | Providing and fixing of point of smoke detector | NOS | 2
111 | Providing and fixing of Fire Sprinkler line work | NOS | 6
112 | Fire alarm pannel -2 Zone - Conventional type Commessioning with Mall Panel | NOS | 1
113 | Providing and fixing of 2c x 1.5 Sqmm FRLS cable | Mtr | 90
114 | Supply, installation ,testing Commissioning of optical Photoelectric type R.I. of photo optic sensing chamber Make - Agni | NOS | 3
115 | Supply, installation ,testing Commissioning of Hooter Make - Agni | NOS | 1
116 | Supply, installation ,testing Commissioning of Mannual Call Point Make - Agni | NOS | 1
117 | Monitor Module for Intergration | NOS | 2
118 | ISI Mark Rubber Mat | NOS | 1