## BOQ Wrap it up
| WRAP IT UP | INDOOR AREA _2550x2575x2700H(mm) | LOCATION |  | PO TFSPL/PO/24-25/000520 |  |  | RA Bill
S.No | Head | Description | Make | UOM | QTY | Rate | Amount (INR) | QTY | Amount (INR) | Variation
1 | MS Work | Providing & fixing of MS work in single section fixed with or without connecting plate including cutting, hoisting, fixing in position and applying a priming coat of approved red oxide steel primer and powder coated paint of approved shared at the top all complete. Item includes all MS steel items including sections, MS plates of grade Yst- 250,cleats,stiffners, anchor fasteners/ bolts, sleeves for pipes and wire management etc, as required for fixing. | Jindal/Tata | Kgs | 256 | 165 | 42240 | 229.5 | 37867.5 | -26.5
2 | Base & Flooring | Providing and fixing of 18mm FR Ply with 1.5mm thick aluminium checker sheet finish mounted over MS pipe 50mm SHS , C/C 600x600mm grid, | Century Ply, Tata/ Jindal | Sqm | 6.57 | 2000 | 13140 | 6.57 | 13140 | 0.57
3 | Rubber Mat | Rubber Mat Rubber Mat Rolls, Thickness: 5 Mm ₹ 45/ Square Feet Thickness: 3 mm |  | Sqm | 8.44 | 850 | 7174 | 7.14 | 6069 | -1.3
4 | Plywood Panelling | Providing , installing and fixing in position FR Plywood for linear as well as curvilinear portions of the building , for all heights and all levels & one side laminate finish etc. (MS Frame work charged seperatly) Includes all the performance characteristics all complete with 12mm PR Ply. | Century or equivalent | Sqm | 28.93 | 2800 | 81004 | 28.93 | 81004 | 10.8497
5 | Paint | Apply of 2 coat white enamel emulsion paint on pillar & side partition left&right | Asian Berger, Indgo | Sqm | 4.71 | 650 | 3061.5 | 3.28 | 2132 | -1.43
6 | Flap Door | Providing & Fixing of Slab & Flap door made of 18mm FR Ply with laminate finish , hinges, SS knob, tower bolt etch. | Century, Merino, Ebco | No | 1 | 6500 | 6500 | 1 | 6500 | 0
7 | Kitchen Door With Vision Panel | Providing & Fixing of Kitchen door made of 32mm FR Ply with Flush door with both side laminate, with vision panel, 300x150mm, with hardware accessories & MS 50x50mm Frame work iwith paint finish | Century, Merino, Ebco, Jindal | No | 1 | 28000 | 28000 | 1 | 28000 | 0
7 | POS Counter | Providing and fixing of POS counter made of 18mm FR Ply with Laminate finish, Step & inside laminate finish, two drawer, key board tray, storage, wire manager etc. (As per approved GFC) | Century/Merino/ FGV | No. | 0 | 30000 | 0 | 0 | 0 | 0
8 | Side Storages | Providing and installation of make of 18mm & 12mm Fr Plywood with approved laminate finish with hinges soft closed shutter. | Century/Merino/ FGV | Nos. | 0 | 18000 | 0 | 0 | 0 | 0
9 | Pendant Light | LED Light fixtures-Supply, installation, testing & commissioning of lighting fittings/ fixtures complete with LED driver, complete as required:- (Hanging Lamp) | Havells, Syska or equivalent | No. | 3 | 2500 | 7500 | 3 | 7500 | 0
10 | Linear Profile Light T5 | Providing & fixing linear profile light consealed in Rafter | Custom Make | No. | 3 | 650 | 1950 | 3 | 1950 | 0
11 | Electrical | Supply and Laying of 1.5mm, 2.5mm & 4sqmm wiring with PVC conduit , 5amp & 15amp switch socket with box & plate, as per requirement or as approved electrical drawing | Polycab, Finolex, Roma, Crompton | No. | 1 | 35000 | 35000 | 1 | 35000 | 0
12 | Industrial Socket | Industrial Socket & Panel Box (32amp ) |  | No. | 2 | 3500 | 7000 | 1 | 3500 | -1
13 | DB Panel | Supply & Fixing of 12mm Way DB Panel wit 1 No. RCB & MCB 12 No's. | L&T | No | 0 | 12500 | 0 | 0 | 0 | 0
14 | Main Cable | Supply & Fixing of 4 core 10 Sqm Coppe Cable for main DB to Meter | Polycab, Finolex, Roma, Crompton | Mtr. | 0 | 750 | 0 | 0 | 0 | 0
14 | Branding | Supply and pasting of HP latex printed artwork on grey back LG/Ivory/Pioneer media as per approved design artwork | HP Latex, 3M , LG Vinyl or equivalent | Sqft. | 215.76 | 150 | 32364 | 215.76 | 32364 | 86.1415
15 | WRAP IT UP | Front logo signaged fixed front façade , UV Printed 3mm raised acrylic . | A cast , NGX , Osram | No. | 0 | 18000 | 0 | 0 | 0 | 0
16 | Menu Board | Providing and fixing of Auto snap channel 32x32 powder coated with acrylic 040 & Clear Acrylic, edge lit LED, Changeable Translite Print. | A cast , NGX , Osram | No. | 0 | 4500 | 0 | 0 | 0 | 0
17 | CCTV Camera (4 Channel DVR) | DVR 5MP, 1 TB, 3 nos. 5MP Camera with Audio, 16" Display Monitor, 90mtr. D Link Wire | Hikvision | Set | 0 | 38000 | 0 | 0 | 0 | 0
18 | Installation | T-1 Delhi Airport |  | EA | 1 | 38000 | 38000 | 1 | 38000 | 0
19 | Transportation | T-1 Delhi Airport |  | EA | 1 | 12500 | 12500 | 1 | 12500 | 0
19 |  | Equipment Shifting Cost Extra |  |  |  |  | 0
TOTAL | [6 empty] | 315433.5 |  | 305526.5
Discount 3.51 | [6 empty] | 11071.7159 |  | 10723.9801
TOTAL | [6 empty] | 304361.7842 |  | 294802.5198

## JMS
| WRAP IT UP | INDOOR AREA _2550x2575x2700H(mm) | LOCATION | T-1 IGI DELHI | Measurement sheet
S.No | Head | Description | Make | Size | UOM | Length | Width | Height | Nos/Wt | Qty | Final to billing BOQ
1 | MS Work | Providing & fixing of MS work in single section fixed with or without connecting plate including cutting, hoisting, fixing in position and applying a priming coat of approved red oxide steel primer and powder coated paint of approved shared at the top all complete. Item includes all MS steel items including sections, MS plates of grade Yst- 250,cleats,stiffners, anchor fasteners/ bolts, sleeves for pipes and wire management etc, as required for fixing. | Jindal/Tata |  | Kgs |  |  |  |  | 229.5 | 229.5
|  | Back Structure - 40x40x1.5mm | [6 empty] | 60
|  | Bottom Structure -50x50x1.5mm | [6 empty] | 60
|  | Left Side-40x40x1.5 | [6 empty] | 7.5
|  | Front Side-40x40x1.5 | [6 empty] | 32
|  | Pillar (50x50x1.5)/right side | [6 empty] | 30
|  | Roof Horizontal Pipe (50mmx50mmx1.5) | [6 empty] | 40
2 | Base & Flooring | Providing and fixing of 18 bison board over MS pipe 50mm SHS , C/C 600x600mm grid, | NCL |  | Sqm | 2.8 | 2.55 |  | 1 | 7.14 | 7.14
|  | Passage Area |  |  | Sqm |  |  |  |  | 0
3 | Rubber Mat | Rubber Mat Rubber Mat Rolls, Thickness: 5 Mm ₹ 45/ Square Feet Thickness: 3 mm |  |  |  | 2.05 | 2.55 |  | 1 | 5.2275 | 7.14
|  | Passage Area |  |  |  | 0.75 | 2.55 |  | 1 | 1.9125
4 | Plywood Panelling | Providing , installing and fixing in position FR Plywood for linear as well as curvilinear portions of the building , for all heights and all levels & one side laminate finish etc. (MS Frame work charged seperatly) Includes all the performance characteristics all complete with 12mm PR Ply. | Century or equivalent |  | Sqm |  |  |  |  | 39.7797 | 39.7797
|  | Back Wall |  |  |  | 3.55 | 2.7 | 2 | 19.17
|  | Front |  |  |  | 1.8 | 0.938 | 2 | 3.3768
|  | Front 2 |  |  |  | 0.935 | 0.938 | 2 | 1.7541
|  | Left Wall |  |  |  | 2.55 | 0.938 | 2 | 4.7838
|  | Façade |  |  |  | 3.55 | 0.4 | 2 | 2.84
|  | Branding Side Wall(Righ front) |  |  |  | 2.7 | 1.45 | 1 | 3.915
|  | Left Wall 2 |  |  |  | 2.9 | 2.6 | 1 | 7.54
|  | Less Door Kitchen |  |  |  | 0.75 | 2.4 | -2 | -3.6
5 | Paint | Apply of 2 coat white enamel emulsion paint on pillar & side partition left&right | Duco Paint |  | Sqm |  |  |  |  | 3.28 | 3.28
|  | Roof Horizontal Pipe (50mmx50mm) |  |  |  | 2.8 | 0.2 | 2 | 1.12
|  | Pillar |  |  |  | 2.7 | 0.2 | 4 | 2.16
6 | Flap Door | Providing & Fixing of Slab & Flap door made of 18mm FR Ply with laminate finish , hinges, SS knob, tower bolt etch. |  |  | No | 0.75 | 0.07 | 0.9 |  | 1 | 1
7 | Kitchen Door With Vision Panel | Providing & Fixing of Kitchen door made of 32mm FR Ply with Flush door with both side laminate, with vision panel, 300x150mm, with hardware accessories & MS 50x50mm Frame work iwith paint finish |  |  | No | 0.75 | 0.05 | 2.4 |  | 1 | 1
8 | POS Counter | Providing and fixing of POS counter made of 18mm FR Ply with Laminate finish, Step & inside laminate finish, two drawer, key board tray, storage, wire manager etc. (As per approved GFC) | Century/Merino/ FGV | 825x750x900 | No. |  |  |  |  | 0 | 0
9 | Side Storages | Providing and installation of make of 18mm & 12mm Fr Plywood with approved laminate finish with hinges normal | Century/Merino/ FGV | 900x900x750 | Nos. |  |  |  |  | 0 | 0
10 | Pendant Light | LED Light fixtures-Supply, installation, testing & commissioning of lighting fittings/ fixtures complete with LED driver, complete as required:- (Hanging Lamp) | Havells, Syska or equivalent |  | No. |  |  |  |  | 3 | 3
11 | Linear Profile Light T5 | Providing & fixing linear profile light consealed in Rafter | Custom Make | 1200x1 | No. |  |  |  |  | 3 | 3
12 | Electrical | Supply and Laying of 1.5mm, 2.5mm & 4sqmm wiring with PVC conduit , 5amp & 15amp switch socket with box & plate, DB panel, MCB, ELCB, as per requirement or as approved electrical drawing | Polycab, Finolex, Roma, Crompton | 2550x2576 | No. |  |  |  |  | 1 | 1
13 | Industrial Socket | Industrial Socket & Panel Box (32amp ) |  |  | No. |  |  |  |  | 1 | 1
14 | DB Panel | Supply & Fixing of 12mm Way DB Panel wit 1 No. RCB & MCB 12 No's. | L&T |  | No |  |  |  |  | 0 | 0
15 | Main Cable | Supply & Fixing of 4 core 10 Sqm Coppe Cable for main DB to Meter | Polycab, Finolex, Roma, Crompton |  | Mtr. |  |  |  |  | 0 | 0
16 | Branding | Supply and pasting of HP latex printed artwork on grey back LG/Ivory/Pioneer media as per approved design artwork | HP Latex, 3M , LG Vinyl or equivalent |  | Sqft. |  |  |  |  | 301.9015 | 301.9015
|  | Back Wall |  |  |  | 3.55 | 2.7 | 1 | 9.585
|  | Front |  |  |  | 1.8 | 0.938 | 1 | 1.6884
|  | Front 2 |  |  |  | 0.935 | 0.938 | 1 | 0.87703
|  | Left Wall |  |  |  | 2.55 | 0.938 | 1 | 2.3919
|  | Façade |  |  |  | 3.55 | 0.4 | 1 | 1.42
|  | Branding Side Wall(Righ front) |  |  |  | 2.7 | 1.45 | 1 | 3.915
|  | Left Wall 2 |  |  |  | 2.9 | 2.6 | 1 | 7.54
|  | Flap Door |  |  |  | 0.7 | 0.9 | 1 | 0.63
17 | Wrap it Up | Front logo signaged fixed front façade , UV Printed 3mm raised acrylic . | A cast , NGX , Osram | 400x750 | No. |  |  |  |  | 0 | 0
18 | Menu Board | Providing and fixing of Auto snap channel 32x32 powder coated with acrylic 040 & Clear Acrylic, edge lit LED, Changeable Translite Print. | A cast , NGX , Osram | 2x 3 | No. |  |  |  |  | 0 | 0
19 | CCTV Camera (4 Channel DVR) | DVR 5MP, 1 TB, 3 nos. 5MP Camera with Audio, 16" Display Monitor, 90mtr. D Link Wire | Hikvision |  | Set |  |  |  |  | 0 | 0
20 | Installation | T-1 Delhi Airport |  |  | EA |  |  |  |  | 1 | 1
21 | Transportation | T-1 Delhi Airport |  |  | EA |  |  |  |  | 1 | 1
22 |  | Equipment Shifting Cost Extra
[6 empty] | Signature | [5 empty] | 2