## NON TENDERING
BUDWISER BAR ,DELHI T1
NON TENDERING ITEMS
NO | DETAILS | UNIT | QTY | RATE | AMOUNT | REMARK
1 | Extetsion 4'' Thick wall | SQFT | 765.02 | 245 | 187429.9
2 | Extetsion 4'' Thick wall 12mm to 18mm platser work. | SQFT | 794.02 | 110 | 87342.2
3 | 4'' Thick Drain Line Trench wall | RFT | 132.4 | 245 | 32438
4 | Drain Line Trench wall & Floor Plaster work. | SQFT | 207.01 | 110 | 22771.1
5 | Drain Line Trench wall & Floor waterproofing work. | SQFT | 207.01 | 210 | 43472.1
6 | P/F of Tile SS Profile Corner Guard | RFT | 80 | 761.5 | 60920
7 | P/F of Plumbing Water Supply Line SS Flat Patti work. | RFT | 32.58 | 695 | 22643.1
8 | P/F of SS ' L ' Patti | RFT | 32 | 610 | 19520
9 | P/F of Grease Trap SS Stand | No | 1 | 5500 | 5500
10 | Metal Door Frame Fixing work | No | 2 | 8400 | 16800
11 | Wall Painting Work | SQFT | 37.36 | 75 | 2802
Total for Civil work (A) |  |  |  |  | 501638.4
PLUMBING WORK'
1 | SS SINK (NIRALI MAKE) | No | 1 | 8500 | 8500
2 | Supply and installation of Pipe Connector | No | 9 | 850 | 7650
Total for Plumbing work (B) |  |  |  |  | 16150
TOTAL AMOUNT (A+B) |  |  |  |  | 517788.4
|  |  |  | GST (18%) | 93201.912
GRAND TOTAL |  |  |  |  | 610990.312

## MB NT
NON TENDERING MEASUREMENT ITEMS
NO | DETAILS | NO | L | B | H | TOTAL QTY
1 | FOOT RAIL | 1
2 | SNEEZE GUARD | 1 | 2 | 0.625 |  | 1.25
|  | 1 | 1.9 | 0.625 |  | 1.1875
2.4375
3 | Toughned Glass | 2 | 0.6 |  | 0.45 | 0.54
|  | 1 | 1.9 |  | 0.45 | 0.855
1.395
4 | Main Signage M.S Frame (50 x 50 mm ) | 1 | 5.285 |  |  | 5.285
|  | 4 |  |  | 2.575 | 10.3
15.585
5 | Drain Line Trench wall & Floor waterproofing work. | 1 | 39.48 |  |  | 39.48
6 | Kaling Stone Supply and Fixing
| Poss Counter & Printer Guard | 1 | 1.5 |  | 0.2 | 0.3
7 | water Meter Access Door ( 450 x 525 mm ) | 1 |  |  | 1 | 1
8 | Dry Wall made up of12 mm Ply wood | 1 | 7.7 |  | 1.9 | 14.63
|  | 1 | 0.65 |  | 1.9 | 1.235
|  | 1 | 0.6 |  | 1.175 | 0.705
16.57
9 | Supply and Fixing of Swing Door With Dorr Closer ( Near sink ) | 1 |  |  | 1 | 1
10 | SS Stand For Ice Machine with Wheel Base | 1 |  |  | 1 | 1
11 | Grease Trap SS Stand | 1 |  |  | 1 | 1
12 | Wall Putty Primer Work | 1 | 6.35 |  | 1.775 | 11.2712
13 | #REF! | 2 |  |  |  | 2
14 | #REF! | 4 |  |  |  | 4
PLUMBING NONTENDERING ITEM
1 | Supply, Installation, Testing Commissioning of chrome plated Angle Valve with wall flange / rosette for all plumbing equipments / fixtures with a pressure rating of 16 Bar of approved make and with all necessary fittings. Including making good the wall / partition as per Architectural / Interior Design and as per relevant standards. | NO | 8
2 | SS SINK (NIRALI MAKE) | NO | 1
3 | SUPPLY AND FIXING OF BIB COCK (JAGUAR MAKE) | NO | 1
4 | Kranti Water Meter | NO | 1
5 | mason + labour + plumber | No | 1
6 | Supply and installation of Pipe Connector | No | 6