## Summary
LOCATION - MOPA AIRPORT - GOA - Domio's International Arrival
S.No. | DESCRIPTION | PO Value | Executed Amount | NT Items | Deviation
1 | TOTAL OF CIVIL & INTERIOR | 2051038.4967 | 2096524.5397 |  | 45486.043
2 | TOTAL OF PLUMBING 1 | 226170 | 196990 |  | -29180
3 | Equipment Loading Unloading | 30000 | 30000 |  | 0
4 | Additional Items |  |  | 622709.045 | 622709.045
| Total Amount | 2307208.4967 | 2323514.5397 | 622709.045 | 639015.088
| GST | 415297.5294 | 418232.6171 | 112087.6281 | 115022.7158
| Total After Tax | 2722506.0261 | 2741747.1568 | 734796.6731 | 754037.8038

## Civil & Interior BOQ
Domino's International Arrival |  |  |  |  | Area | 915
1. Partition, Panelling - Sq. Ft area – one side only
2. Storage Units - Sq. Ft area – Front elevation length x Front Finished height
3. False Ceiling - Sq. Ft area – Flat surface area in reflected ceiling plan
4. Flooring - Sq. Ft. area – Internal area contained within skirting
5. Pls Note Only Bison , Marine Ply and Wpc Board to be used instead of Commercial Ply
6. Chiseling work included in the items or else specified
7. Scaffolding will be in contractor scope upto 4mtr & Above 4mtr rate will be chargeable. If required for installation of civil & MEP.
8. All Items Rates are inclusive of material lead & lift charges.
A. CIVIL & INTERIOR BOQ-Mopa Goa | [7 empty] | Pikture perfect
Task No. |  | Sub Task No. | Name of Item | Description of Item | Unit | Quantity |  | Rate | Amount | Nos. | L | W | Qty | Amount
A |  |  |  | Civil Head
| A.1.0 |  |  | Dismantling and Demolitions
|  | a | Dismantling | Dismantling the existing flooring, ceiling, walls, partition, fixed & loose furniture, toilets, pantry, etc.Cost to include carting away all debris from site, lead and lifts, material, labours, transportation and all other incidental charges etc. complete and as directed by Site Engineer
|  | a.1 |  | Brick Wall ,Wall tiles, Floor tiles, including base,Partitions,Existing Wall Plaster ,Electrical conduits ,wiring,DB,sockets and Punning removing including old plumbing and sanitary lines | Sq.ft | 35 | 0 | 30 | 1050
|  | a.2 |  | Removal PCC of thickness upto 5 inches | Sq.ft | 0 | 0
|  | a.3 |  | Removal PCC of thickness between 6 inches to 12 inches | Sq.ft | 0 | 0 |  | 0
|  | a.4 |  | False Ceiling removing inclusive wire & Light | Sq.ft | 0 | 0 |  | 0
|  | a.5 |  | Façade (Including Glass ,Signgage ,Window ,Frames and ACP boxing etc) | Sq.ft | 0 | 0 |  | 0
|  | a.6 |  | Existing Rolling shutter removing | Sq.ft | 0 | 0 |  | 0
|  | a.7 |  | Existing Cable Trays ,Duct Removing from the site and carting away from the site | Sq.ft | 0 | 0 |  | 0
|  | b | Making Core Cut | Making Core cut with Diamond cutter & clearing the debris and carting away the same from site. |  |  |  |  | 0
|  | b.1 |  | Making core cutting of 75 dia | Nos. | 0 | 0 |  | 0
|  | b.2 |  | Making core cutting of 100 dia | Nos. | 0 | 0 |  | 0
|  | b.3 |  | Making core cutting of 150 dia | Nos. | 1 | 0 | 3500 | 3500
|  | b.4 |  | Making core cutting of 200 dia | Nos. | 0 | 0 |  | 0
|  | c | Making Cut -out & Opening | Making cutouts and openings in existing walls for ducts etc. The cost to be inclusive of making good all affected areas with smooth plaster and disposal of debris at an indicated location off site. | Nos. | 2 | 0 | 500 | 1000
Sub Total of A.1.0 | [8 empty] | 5550 |  |  |  |  | 0
| A.2.0 |  |  | RCC and PCC
|  | a | PCC | Providing & Laying Plain cement concrete specified grade (M10) including the cost of centering and shuttering & required curing. Approved make cement is PPC (ACC, Ultra tech , Birla) | Sq.ft | 850 | 0 | 75 | 63750 |  | 35.167 | 14.08 | 495.1514
[11 empty] | 9.75 | 1.25 | -12.1875
[11 empty] | 24.5 | 12.25 | 300.125
[11 empty] | 12.5 | 0.75 | -9.375
[11 empty] | 19.5 | 6 | 117
[13 empty] | 890.7139 | 66803.5395
|  | b | RCC with reinforcement | Provinding & Laying in position Reinforced cement concrete of specified grade (M15) including the cost centering, shuttering , steel bending with binding wire (18 G annealed Steel wire) ,cutting & curing.Approved make cement is PPC (ACC, Ultra tech , Birla)
|  | b.1 |  | 1:2:4 (1 cement : 2 coarse sand :6 graded stone aggregate 20mm nominal size)- M15. In Shelves , counters, lintels, beams, waist slab etc. | cuft | 0 | 0 |  | 0
Sub Total of A.2.0 | [8 empty] | 63750 |  |  |  |  | 66803.5395
| A.3.0 |  |  | Brick Wall and Plaster
|  | a |  | Autoclaved Aerated Concrete Block
|  | a.1 | 4" thick AAC (Autoclaved Aerated Concrete) Block | Providing and laying autoclaved aerated cement blocks masonry with 100 mm thick AAC blocks in super structure above plinth level in cement mortar 1:4 (1 cement : 4 coarse sand ). The rate includes providing and placing in position 2 Nos 8 mm dia M.S. bars at every third course of masonry work. | Sq.Ft | 380 | 0 | 160 | 60800 |  | 6.25 | 11.25 | 70.3125
[11 empty] | 6.25 | 11.25 | 70.3125
[13 empty] | 140.625 | 22500
|  | a.2 | 6" thick AAC (Autoclaved Aerated Concrete) Block | Providing and laying autoclaved aerated cement blocks masonry with 150 mm thick AAC blocks in super structure above plinth level in cement mortar 1:4 (1 cement : 4 coarse sand ). The rate includes providing and placing in position 2 Nos 8 mm dia M.S. bars at every third course of masonry work. | Sq.Ft | 30 | 0 | 185 | 5550 |  | 1.3333 | 3.4167 | 4.5556
[11 empty] | 0.75 | 3.4167 | 2.5625
[11 empty] | 5.5 | 3.4167 | 18.7917
[11 empty] | 23.75 | 3.4167 | 81.1458
[11 empty] | 2.5 | 12.5 | 31.25
[11 empty] | 10 | 12.5 | 125
|  | b |  | Brick Work | [8 empty] | 263.3056 | 48711.5278
|  | b.1 | 115mm thick Brick Masonry | Providing & Constructing 115mm thick wall of class1 Brick with conventional IS type bricks in 1:4 cement mortar inclusive of RCC tie member at every one meter height interval in 1:3:6 Cement Concrete with 2no. of 6mm diameter mild steel reinforcement & 2 no. of hoop iron strips 25mm x 1.6mm, painted with anti-corrosive paint, properly bent and bonded at the end ,inclusive of shuttering, scaffolding, Raking of joints and proper curing etc. complete. | Sq.Ft | 79.7197 | 0 | 225 | 17936.9424
|  | b.2 | 230 mm thick Brick Masonry | Providing and laying 9" brick masonry work with well burnt 1st class table moulded, good quality approved bricks in 1:6 Cement Mortar (1 Cement : 6 Coarse Sand by volume) in true line, level and plumb for wall foundations, trenches, pedestals, columns, compound walls, steps, pillars etc., complete with necessary scaffolding, raking of joints, curing etc., complete as directed and specified upto plinth level. Rate to include soaking of bricks adequately before construction, complete as directed and specified. | cuft | 0 | 0 |  | 0
|  | c |  | Plaster
|  | c.1 | 12mm to 15mm Plastering | Plastering the Siporex / brick masonry walls with 12mm to 15mm thk. Single coat cement plaster in 1: 4 (cement : sand proportion) with chickenmesh jali wherever required, including scaffolding and curing complete as specified and as directed by Site Engineer. | Sq.Ft | 1550 | 0 | 56 | 86800 | 2 | 6.25 | 11.25 | 140.625
[10 empty] | 1 | 0.5 | 11.25 | 5.625
[10 empty] | 1 | 6.25 | 11.25 | 70.3125
[10 empty] | 1 | 6 | 12 | 72
[10 empty] | 2 | 1.33 | 3.42 | 9.0972
[10 empty] | 2 | 9 | 3.42 | 61.56
[10 empty] | 2 | 5.5 | 3.42 | 37.62
[10 empty] | 2 | 23.75 | 3.42 | 162.45
[10 empty] | 1 | 2.5 | 12.5 | 31.25
[10 empty] | 2 | 10 | 12.5 | 250
[10 empty] | 1 | 0.75 | 12.5 | 9.375
[10 empty] | 1 | 35.25 | 11.25 | 396.5625
[10 empty] | 1 | 1.33 | 12 | 15.96
[10 empty] | 1 | 4.33 | 11.25 | 48.7125
[13 empty] | 1311.1497 | 73424.3832
Sub Total of A.3.0 | [8 empty] | 171086.9424 |  |  |  |  | 144635.911
| A.4.0 |  |  | Brickbat Coba and Water proofing
|  | a | Raised Brickbat Coba (Toilets) | Providing and laying brick-bat coba system, cm 1:3 base coat, brick-bat coba filling as per site requirement & 1:4 top-finish coat. the mortar for the brick-bat koba filling shall be cm 1:4 and admixed with integral waterproofing compound and mortar plasticizer, properly compacted, curing, complete. The top-finish coat shall be broom-finished suitable for laying tiles. The cost should include sealing the annular space between the pipe and the masonary, making khurras, river sand screened and washed, at all leads, lifts, heights, with proper slope to drain-off water entirely, complete, etc. Curing shall be done for maximum for 7 days by ponding with water or after getting checked & satisfied by Site Engineer . | cuft | 0 | 0 |  | 0
|  |  |  | Providing and laying BBC 150mm thk Light weight raised floor (Siporex Block) Height -150mm | Sq. Ft | 447 | 0 | 175 | 78225 |  | 35.167 | 14.08 | 495.1514
[11 empty] | 9.75 | 1.25 | -12.1875
[13 empty] | 482.9639 | 84518.6755
|  | b | Cinder Filling | Filling motar Light weight cinder with cement salary - Providing and laying Cinder Coba,cm 1:3 base coat, cinder filling as per site requirement & 1:4 top-finish coat. the mortar for the cinder koba filling shall be cm 1:4 and admixed with integral waterproofing compound and mortar plasticizer, properly compacted, curing, complete. The top-finish coat shall be broom-finished suitable for laying tiles. The cost should include sealing the annular space between the pipe and the masonary, making khurras, river sand screened and washed, at all leads, lifts, heights, with proper slope to drain-off water entirely, complete, etc. Curing shall be done for maximum for 7 days by ponding with water or after getting checked & satisfied by Site Engineer . | cuft | 61.7148 | 0 | 225 | 13885.83 |  |  |  | 122.5 | 27562.5
|  | c | Water proofing (Toilet & Kitchen sink area) | Providing of water proofing - chemical Treatment – the slab to be cleaned and apply 3 coats of chemical (FOSROC or equivalent) on the floor and on the peripheral walls up to 0.30m. b) Base coat – Applying base coat of 1:6 mortar over chemical treatment on the floor and on the peripheral walls up to 0.60m. Note - Warrantee to be provided up to 5 years | Sq. Ft | 0 | 0 |  | 0
|  | d | Water proofing (Toilet & Kitchen sink area)with Membrane | P/f one layer of 3mm APP membrane waterproofing ( 1 layer of membrane & Two coat adhesive) of approved make in toilet & kitchen area or as directed by the Site Engineer minimum 2 coats with requisite adhesive / compounds as per the manufacturers specifications on floor, sunken slab and up to height of 24” on wall. Waterproofing works to be carried out by company authorised installers and guarantee/warrantee provided for 5 years. Including protection plaster Ponding test to be carried out for minimum 48 hours. Approved makes : Zydex, sika | Sq. Ft | 474 | 0 | 190 | 90060 | 1 | 35.17 | 14.08 | 495.1936
[10 empty] | 1 | 9.75 | 1.25 | -12.1875
[10 empty] | 2 | 35.17 | 2 | 140.68
[10 empty] | 2 | 14.08 | 2 | 56.32
[10 empty] | 2 | 6.25 | 2 | 25
[10 empty] | 1 | 1.8333 | 2 | 3.6667
[13 empty] | 708.6728 | 134647.8257
|  |  |  | Providing of water proofing - liquid membrane from Fosroc chemical Treatment – the slab to be cleaned and apply 3 coats of chemical (FOSROC ) | Sq. Ft | 620 | 0 | 190 | 117800 |  |  |  | 709 | 134710
|  | e | Water proofing (Toilet & Kitchen sink area)with Membrane | P/f 5mm to 6 mm membrane waterproofing ( 1 layer of membrane & Two coat adhesive) of approved make in toilet & kitchen area or as directed by the Site Engineer minimum 2 coats with requisite adhesive / compounds as per the manufacturers specifications on floor, sunken slab and up to height of 24” on wall. Waterproofing works to be carried out by company authorised installers and guarantee/warrantee provided for 5 years. Including protection plaster Ponding test to be carried out for minimum 48 hours. Approved makes : Zydex, sika | Sq. Ft | 0 | 0 |  | 0
Sub Total of A.4.0 | [8 empty] | 299970.83 |  |  |  |  | 381439.0012
| A.5.0 |  |  | Rolling Shutter , Awning & Mild Steel work
|  | a | Motorized Rolling Shutter for entrance | Providing & fixing Rolling Shutter including motarized mechanism to be operated with key/switch of min. 20 guage MS sheet, including floor locks, guide rail, first quality enamel paint ( 1 coat of primer & 2 or more coat of paint until achieved smooth finish ). Rate including cost of transportation, loading, unloading, scaffolding, wastage, taxes etc. as mentioned in drawings directed by Site Engineer. | Sq. Ft | 0 | 0 |  | 0
|  | b | Manual Rolling Shutter with gear Box for entrance | Providing & fixing manual Rolling Shutter including manual gear box of min. 20 guage MS sheet, including floor locks, guide rail, first quality enamel paint ( 1 coat of primer & 2 or more coat of paint until achieved smooth finish ). Rate including cost of transportation, loading, unloading, scaffolding, wastage, taxes etc. as mentioned in drawings directed by Site Engineer. | Sq. Ft | 0 | 0 |  | 0
|  | c | HEAVY M.S Work & Framework | Providing, fabricating & erection of Steel work in built up section/ framed work i/c cutting, welding, hoisting, fixing in position & applying a priming coat of approved steel primer using steel etc, as required. In structure slab (ISMB, ISMC etc.) or stringers, treads, landing of stair case i/c use of chequered plate wherever required, all complete. Including primer and 2 coat paints | KG | 139.4982 | 0 | 220 | 30689.604 |  |  |  | 127.5 | 28050
|  | d | M.s louvers with approved Paint | Providing and Fabricating M.S louvers as per detail drawing and site engineer for Gas Bank and AC Outdoor | KG | 0 | 0 |  | 0
|  | e | Aluminum louvers with approved Paint | Providing and Fabricating Aluminium louvers as per detail drawing and site engineer for Gas Bank and AC Outdoor / diffuser 2ft x 2ft in sqft. | KG | 0 | 0 |  | 0
|  | f | Motorized Poly Carbonate Shutter | Providing & fixing Motorized Poly carbonate (minimimum 3mm thickness) Rolling Shutter including motarized mechanism to be operated with key/switch of min. including floor locks, guide rail, Rate including cost of transportation, loading, unloading, scaffolding, wastage, taxes etc. as mentioned in drawings directed by Site Engineer. | Sq. Ft | 0 | 0 |  | 0
Sub Total of A.5.0 | [8 empty] | 30689.604 |  |  |  |  | 28050
| A.6.0 |  |  | Flooring and Cladding
|  | a | Tiles for Flooring (General seating area) FF 01 Kajaria -Fog Perla, cool cement, cool silver (Matt Finish) /Somany-Ethos grey (Details- Refer Material Spec. sheet) | Providing and fixing in position Glazed Vitrified Tile flooring as per detail in drawing. It shall be fixed with cement mortar of 1:4, (required mortar bed is 25mm to 50mm thk) with thick grey cement slurry, using cement grout. The job including cutting of tiles & making smooth edges wherever required for drain pipes. The work shall also include cost of materials, wastages, labour, all lead and lift at all levels, loading and unloading, transportation, curing etc. and all other incidental charges etc., complete and as directed by Engineer-in-charge. The cost should include PVC floor covering material. Including Corrugated sheet/Plastic sheet for tile Protection . (size - 600x600 mm) | Sq. Ft | 0 | 0 |  | 0
|  | b | Tiles for Flooring (Light) - (Booth seating) FF 04 - Kajaria Sheesham Rosewood/ RAK AMBER OAK or Somany Strio Verano wood Teak (Details- Refer Material Spec. sheet) | Providing and fixing in position Glazed Vitrified Tile flooring as per detail in drawing. It shall be fixed with cement mortar of 1 :4,(required mortar bed is 25mm to 50mm thk), with thick grey cement slurry, with hairline joints using cement grout. The job including cutting of tiles & making smooth edges wherever required for drain pipes. The work shall also include cost of materials, wastages, labour, all lead and lift at all levels, loading and unloading, transportation, curing etc. and all other incidental charges etc., complete and as directed by Engineer-in-charge. The cost should include PVC floor covering material. Including Corrugated Sheet /Plastic sheet for tile Tile Protection .(size - 130x800 mm)/ Option - RAK -AMBER OAK (SIZE-198X1200mm) | Sq. Ft | 0 | 0 |  | 0
|  | c | Tiles for Flooring (Dark) - (Booth seating) FF 05 - Kajaria Sheesham Nero /RAK CEDAR BROWN or Strio Benz wood Nero (Details- Refer Material Spec. sheet) | Providing and fixing in position Glazed Vitrified Tile flooring as per detail in drawing. It shall be fixed with cement mortar of 1 :4, (required mortar bed is 25mm to 50mm thk), with thick grey cement slurry, with hairline joints using cement grout. The job including cutting of tiles & making smooth edges wherever required for drain pipes. The work shall also include cost of materials, wastages, labour, all lead and lift at all levels, loading and unloading, transportation, curing etc. and all other incidental charges etc., complete and as directed by Engineer-in-charge. The cost should include PVC floor covering material. Including POP /Plastic sheet for Tile Protection ..(size - 130x800mm)/ Option 2 RAK -CEDAR BROWN (SIZE-198X1200mm) | Sq. Ft | 0 | 0 |  | 0
|  | d | Tiles for Flooring - FF02 Kajaria-Dessert grey, cool gris,cairo gris (Matt Finish) (Kitchen & BOH) or equivalent in somany (Details- Refer Material Spec. sheet) | Providing and fixing in position Glazed Vitrified Tile flooring as per detail in drawing. It shall be fixed with cement mortar of 1 :4, (required mortar bed is 25mm to 50mm thk),with thick grey cement slurry, with hairline joints using cement grout. The job including cutting of tiles & making smooth edges wherever required for drain pipes. The work shall also include cost of materials, wastages, labour, all lead and lift at all levels, loading and unloading, transportation, curing etc. and all other incidental charges etc., complete and as directed by Engineer-in-charge. The cost should include PVC floor covering material. Including Corrugated sheet /Plastic sheet for Tile Protection (Size - 600x600mm) | Sq. Ft | 832 | 498 | 235 | 195520 |  | 35.25 | 14.08 | 496.32
[11 empty] | 9.75 | 1.25 | 12.1875
[11 empty] | 24.5 | 12.25 | 300.125
[11 empty] | 20 | 8 | 160
[13 empty] | 968.6325 | 227628.6375
|  | d.1 (opt.) | Tiles for Flooring -(Details- Refer Material Spec. sheet) no.- A (2a), FF02 (Kitchen & BOH) | Providing and fixing in position Glazed Vitrified Tile flooring as per detail in drawing. It shall be fixed with cement mortar of 1 :4, (required mortar bed is 25mm to 50mm thk),with thick grey cement slurry, with hairline joints using cement grout. The job including cutting of tiles & making smooth edges wherever required for drain pipes. The work shall also include cost of materials, wastages, labour, all lead and lift at all levels, loading and unloading, transportation, curing etc. and all other incidental charges etc., complete and as directed by Engineer-in-charge. The cost should include PVC floor covering material. Including Corrugated sheet /Plastic sheet for tile Protection. | Sq. Ft | 0 | 0 |  | 0
|  | e | Tiles for Flooring (Toilet areas) Johson- Quartz grey/Somany -EC sapphire matt (Details- Refer Material Spec. sheet) | Providing and fixing in position Tile flooring as per detail in drawing. It shall be fixed with cement mortar of 1 :4,(required mortar bed is 25mm to 50mm thk),with thick grey cement slurry, with hairline joints using cement grout. The job including cutting of tiles & making smooth edges wherever required for drain pipes. The work shall also include cost of materials, wastages, labour, all lead and lift at all levels, loading and unloading, transportation, curing etc. and all other incidental charges etc., complete and as directed by Engineer-in-charge. The cost should include PVC floor covering material. Including corrugated sheet /Plastic sheet for Tile Protection . | Sq. Ft | 0 | 0 |  | 0
|  | f | Tiles for Flooring FF 03 - Johnson Endura Stepping Stone - Dona Paula Plain (Outdoor Area) or Somany - Largo Stepon Verde (Details- Refer Material Spec. sheet) | Providing and fixing in position Glazed Vitrified Tile flooring as per detail in drawing. It shall be fixed with cement mortar of 1 :4,(required mortar bed is 25mm to 50mm thk),with thick grey cement slurry, with hairline joints using cement grout. The job including cutting of tiles & making smooth edges wherever required for drain pipes. The work shall also include cost of materials, wastages, labour, all lead and lift at all levels, loading and unloading, transportation, curing etc. and all other incidental charges etc., complete and as directed by Engineer-in-charge. The cost should include PVC floor covering material. Including Corrugated sheet /Plastic sheet for Tile Protection | Sq. Ft | 0 | 0 |  | 0
|  | g | Tread & Riser in Johnson Endura Stepping Stone - Dona Paula Plain (Outdoor area) | Providing and fixing in position Glazed Vitrified Tile flooring as per detail in drawing. It shall be fixed with cement mortar of 1 :4,(required mortar bed is 25mm thk) with thick grey cement slurry,with hairline joints using cement grout. The job including cutting of tiles & making smooth edges wherever required for drain pipes. The work shall also include cost of materials, wastages, labour, all lead and lift at all levels, loading and unloading, transportation, curing etc. and all other incidental charges etc., complete and as directed by Engineer-in-charge. The cost should include PVC floor covering material. | Sq. Ft | 0 | 0 |  | 0
|  | h | Tiles in Johnson Endura Stepping Stone - Dona Paula Tread (Outdoor area) or Largo Riser Verde | Providing and fixing in position Glazed Vitrified Tile flooring as per detail in drawing. It shall be fixed with cement mortar of 1 :4 ,(required mortar bed is 25mm to 50mm thkk) with thick grey cement slurrywith hairline joints using cement grout. The job including cutting of tiles & making smooth edges wherever required . The work shall also include cost of materials, wastages, labour, all lead and lift at all levels, loading and unloading, transportation, curing etc. and all other incidental charges etc., complete and as directed by Engineer-in-charge. | Rft | 0 | 0 |  | 0
|  | i | Skirting (General seating area) FF 01 - Kajaria - Fog Perla, cool cement, cool silver (Matt Finish) /Somany-Ethos grey. (Details- Refer Material Spec. sheet) | Providing and fixing in position 100 mm ht. Skirting as per detail in drawing. Over 20 mm thk bed of cement mortar 1:4 (cement : fine sand ) with thick grey cement slurry ,with hairline joints using cement grout. The job including cutting of tiles & making smooth edges wherever required for drain pipes. The work shall also include cost of materials, wastages, labour, all lead and lift at all levels, loading and unloading, transportation, curing etc. and all other incidental charges etc., complete and as directed by Engineer-in-charge. Finish of skirting to match with individual areas as per flooring plan. | Rft | 0 | 0 |  | 0
|  | j | Skirting FF02 - Kajaria-Dessert grey, cool gris,cairo gris (Matt Finish) (Kitchen & BOH) or equivalent in somany. (Details- Refer Material Spec. sheet) | Providing and fixing in position 100 mm ht. Skirting as per detail in drawing. Over 20 mm thk bed of cement mortar 1:4 (cement : fine sand ) with thick grey cement slurry, with hairline joints using cement grout. The job including cutting of tiles & making smooth edges wherever required for drain pipes. The work shall also include cost of materials, wastages, labour, all lead and lift at all levels, loading and unloading, transportation, curing etc. and all other incidental charges etc., complete and as directed by Engineer-in-charge. Finish of skirting to match with individual areas as per flooring plan. | Rft | 135 | 78 | 140 | 18900 |  | 165.74 |  | 165.74 | 23203.6
|  | j.1 op 1 | Skirting -(Details- Refer Material Spec. sheet) no.- 2a, FF02 (Kitchen & BOH) | Providing and fixing in position 100 mm ht. Skirting as per detail in drawing. Over 20 mm thk bed of cement mortar 1:4 (cement : fine sand ) with thick grey cement slurry, with hairline joints using cement grout. The job including cutting of tiles & making smooth edges wherever required for drain pipes. The work shall also include cost of materials, wastages, labour, all lead and lift at all levels, loading and unloading, transportation, curing etc. and all other incidental charges etc., complete and as directed by Engineer-in-charge. Finish of skirting to match with individual areas as per flooring plan. | Rft | 0 | 0 |  | 0
|  | k | Skirting (Booth seating) FF 04 - Kajaria Sheesham Rosewood or Somany Strio Verano wood Teak . (Details- Refer Material Spec. sheet) | Providing and fixing in position 100 mm ht. Skirting as per detail in drawing.Over 20 mm thk bed of cement mortar 1:4 (cement : fine sand ) with thick grey cement slurry, with hairline joints using cement grout. The job including cutting of tiles & making smooth edges wherever required for drain pipes. The work shall also include cost of materials, wastages, labour, all lead and lift at all levels, loading and unloading, transportation, curing etc. and all other incidental charges etc., complete and as directed by Engineer-in-charge. Finish of skirting to match with individual areas as per flooring plan. | Rft | 0 | 0 |  | 0
|  | l | Wall Tile Cladding - 2 (Kitchen & BOH area). (Details- Refer Material Spec. sheet) no.B(3) | Providing and fixing in position dado tile of approved make & shade on any surface as per details in drawing and Over 12 mm thk bed of cement mortar 1:3 (cement : fine sand ) with thick grey cement slurry, with hairline joints using cement grout. The job including cutting of tiles & making smooth edges wherever required . The work shall also include cost of materials, wastages, labour, all lead and lift at all levels, loading and unloading, transportation, curing etc. and all other incidental charges etc. Complete as specified in the drawing & to the satisfaction of the Site Engineer. Ceramic wall tile (Printed) With customize line work | Sq. Ft | 540 | 227 | 175 | 94500 |  | 35.25 | 8 | 282
[11 empty] | 0.75 | 8 | 6
[11 empty] | 6.25 | 8 | 50
[11 empty] | 6.25 | 8 | 50
[11 empty] | 0.583 | 8 | 4.664
[11 empty] | 6.25 | 8 | 50
[11 empty] | 3.583 | 8 | 28.664
[11 empty] | 5.5 | 3 | 16.5
[11 empty] | 24 | 3 | 72
[11 empty] | 2.5 | 8 | 20
[11 empty] | 1 | 8 | 8
[11 empty] | 0.75 | 8 | 6
[11 empty] | 1.3333 | 3 | 4
[11 empty] | 1.25 | 3 | 3.75
[13 empty] | 601.578 | 105276.15
|  | m | Wall Cladding - plain Tile (BOH & Staff changing room area). (Details- Refer Material Spec. sheet) no.B(4) | Providing and fixing in position dado tile of approved make & shade on any surface as per details in drawing and Over 12 mm thk bed of cement mortar 1:3 (cement : fine sand ) with thick grey cement slurry, with hairline joints using cement grout.The job including cutting of tiles & making smooth edges wherever required . The work shall also include cost of materials, wastages, labour, all lead and lift at all levels, loading and unloading, transportation, curing etc. and all other incidental charges etc. Complete as specified in the drawing & to the satisfaction of the Site Engineer. | Sq. Ft | 90 | 169 | 175 | 15750
|  | n | Dado Tile Cladding (Booth Seating)Sheesham Oak or Somany Strio Benz wood dune | Providing and fixing in position dado tile of approved make & shade on any surface as per details in drawing and Over 12 mm thk bed of cement mortar 1:3 (cement : fine sand ) with thick grey cement slurry, with hairline joints using cement grout. The job including cutting of tiles & making smooth edges wherever required . The work shall also include cost of materials, wastages, labour, all lead and lift at all levels, loading and unloading, transportation, curing etc. and all other incidental charges etc. Complete as specified in the drawing & to the satisfaction of the Site Engineer. | Sq. Ft |  | 0 |  | 0
|  | o | Dado in Johnson Endura Stepping Stone - Dona Paula Plain (Outdoor area) or Somany Largo Riser Verde | Providing and fixing in position Glazed Vitrified Tile flooring as per detail in drawing. It shall be fixed with cement mortar of 1:3, required mortar bed is 25mm to 50mm thk), with thick grey cement slurry, using cement grout The job including cutting of tiles & making smooth edges wherever required . The work shall also include cost of materials, wastages, labour, all lead and lift at all levels, loading and unloading, transportation, curing etc. and all other incidental charges etc. Complete as specified in the drawing & to the satisfaction of the Site Engineer. | Sq. Ft | 0 | 0 |  | 0
|  | p | Dado Tile Cladding - Johson- Plain grey/Somany -EC sapphire matt(Toilets). (Details- Refer Material Spec. sheet) | Providing and fixing in position dado tile of approved make & shade on any surface as per details in drawing and Over 12 mm thk bed of cement mortar 1:3 (cement : fine sand ) with thick grey cement slurry.The job including cutting of tiles & making smooth edges wherever required . The work shall also include cost of materials, wastages, labour, all lead and lift at all levels, loading and unloading, transportation, curing etc. and all other incidental charges etc. Complete as specified in the drawing & to the satisfaction of the Site Engineer. | Sq. Ft | 0 | 0 |  | 0
|  | q | Dado Tile Cladding - White Tile in Staff Toilet or changing room | Providing and fixing in position dado tile (White Tile ) as per details in drawing and Over 12 mm thk bed of cement mortar 1:3 (cement : fine sand ) with thick grey cement slurry, with hairline joints using cement grout. The job including cutting of tiles & making smooth edges wherever required . The work shall also include cost of materials, wastages, labour, all lead and lift at all levels, loading and unloading, transportation, curing etc. and all other incidental charges etc. Complete as specified in the drawing & to the satisfaction of the Site Engineer. (Size - 200x250mm) | Sq. Ft | 0 | 0 |  | 0
|  | r | Granite (Jet Black) Frame | Providing and Fixing 19mm thick, upto 6" wide granite door frames with 6mm champhered edges machine polished edges externally and internally. Rate to include cutting/moulding/polishing/Transport etc. Complete as specified in the drawing & to the satisfaction of the Architect & Site-in-charge. (required mortar bed is 25mm to 50mm thk) | RFt | 20 | 20 | 320 | 6400
|  | s | Granite (Jet Black/Steel grey) Band | Providing & Fixing 6" -8" wide band of granite of approved shade & sample. It shall be fixed along the doors. (it shall be flushed with finished edge of the wall) with 1:3 cement mortar as per detailed design & shall be flushed with adjoining flooring, etc. Minimum 15 mm | RFt | 0 | 0 |  | 0
|  | t | Jet Black Granite | Providing and Fixing 19mm thick black granite on floor. Rate to include cutting/moulding/polishing/Installation/Transport etc. Complete as specified in the drawing & to the satisfaction of the Architect & Site-in-charge.(required mortar bed is 25mm thk) | sq ft | 0 | 0 |  | 0
|  | u | Dado Tile Cladding on Counter- 130 x 800 mm - Kajaria - Mahogany, Sheesham Nero, Sheesham Rosewood, Sheesham Oak or equivalent in Somany as mentioned above | Providing and fixing in position Glazed Vitrified Tile Dado on Makeline & POS counter as per detail in drawing. Over 12 mm thk bed of cement mortar 1:4 (cement : fine sand ) with thick grey cement slurry, with hairline joints. The job including cutting of tiles & making smooth edges wherever required for drain pipes. The work shall also include cost of materials, wastages, labour, all lead and lift at all levels, loading and unloading, transportation, curing etc. and all other incidental charges etc., complete and as directed by Engineer-in-charge. The cost should include PVC floor covering material. | Sq. Ft | 90 | 80 | 280 | 25200 |  | 24 | 3.5 | 84
[11 empty] | 0.75 | 3.5 | 2.625
[11 empty] | 8.5 | 3.5 | 29.75
[13 empty] | 116.375 | 32585
Sub Total of A.6.0 | [8 empty] | 356270 |  |  |  |  | 388693.3875
B |  |  |  | Interior Head
| B.1.0 |  |  | False Ceiling
|  | a | Gypsum False Ceiling | Gypsum Board false Ceiling: Providing, fabrication and fixing in position of false ceiling ( height will be decided on the spot as per site conditions) by fixing 12 mm Th. Gypsum Board sheets on frame work of GI sheet section. The main runners of 22 gauge GI sheet and cross runners of 24 gauge GI sheet must be framed to form a mesh of 2’0”x2’0” c/c. The Gypsum Board must be fixed to the GI frame and joint to be properly filled in with POP paste and paper tape to get a leveled smooth ceiling. Recessing of the Gypsum Board for light fixtures must be done along with extra frame work of GI sheet section to hold the concealed light fixtures etc. directed by the site engineer | Sq. Ft | 937 | 0 | 145 | 135865 |  | 35.25 | 14.1 | 497.025
[11 empty] | 9.75 | 1.25 | -12.1875
[11 empty] | 26 | 13.75 | 357.5
[11 empty] | 21.5 | 9.5 | 204.25
[11 empty] | 24.5 | 3 | 73.5
[11 empty] | 12.25 | 3 | 36.75
[13 empty] | 1156.8375 | 167741.4375
|  | b | Bison False ceiling | Providing and Fixing in position suspended type 12 mm Bison Board False Ceiling with required M.S frame (50x50 mm ,18 gauge with 1 coat of primer & 2 or more coat of paint until achieved smooth finish as per drawing) work/ fixing arrangement of 2'x2' c/c and accessories, including groove joint filler, tapes, cut out for lights, & fixing for cove/ pelmet / box of approved size with necessary M.S. brackets / supports for light fittings / A.C. grills / Blinds, cleaning etc. complete as per detail drawing, as specified and as directed by Site Engineer. | sqft | 0 | 0 |  | 0
|  | c | ACP Fale Ceiling. (Details- Refer Material Spec. sheet) | Providing and Fixing in position suspended type 4mm thk ACP False Ceiling with required M.S frame 50x50 mm ,18 Gauge and work/ fixing arrangement of 2'x2' c/c and accessories, including groove joint filler, tapes, cut out for lights, & fixing for cove/ pelmet / box of approved size with necessary M.S. brackets / supports for light fittings / Blinds, cleaning etc. complete as per detail drawing, as specified and as directed by Site Engineer. | sqft | 0 | 0 |  | 0
Sub Total of B.1.0 | [8 empty] | 135865 |  |  |  |  | 167741.4375
| B.2.0 |  |  | Ceiling Elements
|  | a | Ceiling Suspended metal framing (Community Seating Ceiling ) | Providing and Fixing in position Ceiling Suspended Metal Grid frame (1500 x 900 ) made out of 25x25mm m.s. hollow box pipe finished with approved shade of .5 micron powder coat . Also to have 10 mm dia m.s. rods placed on every 110 mm c/c horizontaly & verticaly, finish with approved shade of powder coat. Necessary suspension arrangement to be done with m.s. string to fix with m.s. plate & anchor fasteners to the RCC slab. Complete as per detail drawing, as specified and as directed by SIte Engineer. | Sq. Ft | 0 | 0 |  | 0
|  | b | Baffles Ceiling -Wooden rafter with rubber wood/Ash wood (Booth seating) | Providing and Fixing 125mmX25mm thick wood finish with natural clear polish make suspended from ceiling. Complete as specified in the drawing & to the satisfaction of the Architect & Site-in-charge. | R.ft | 0 | 0 |  | 0
Sub Total of B.2.0 | [8 empty] | 0
| B.3.0 |  |  | Wall Claddings / Wall Partitions /Claddings
|  | a | Bison Partition - P1 | Providing and fixing in position Bison Board Partition made out of 12mm thk. Bison Board both sides with necessary aluminum/M.S sections ( 40 mm x 40 mm x 1.5 mm ) framework at 600mm c/c both ways in partition included bolted or welded in built up section to recieve bison pallening . The rate should include applying of two or more coats of primer , putty , complete as per standard technical specification, instructions of site engineer and as per decoration plan. | Sq. Ft |  | 0 |  | 0
|  | a.(i) |  | Framing-Cutting of section & Providing and fixing M.S frame work in built up tubular section (square hollow tubes 40 mm x 40 mm x 1.5 mm ) framework at 600mm c/c both ways in partition included bolted or welded in built up section to recieve bison pallening . The rate should include applying of two or more coats of primer , putty , complete as per standard technical specification, instructions of site engineer and as per decoration plan. |  |  | 0
|  | a.1 |  | Providing & Fixing 8 mm thk Bison board with above mentioned framing details - a.(i) (Rate will be include the cost of framing) | Sq. Ft | 0 | 0 |  | 0
|  | a.2 |  | Providing & Fixing 10 mm thk Bison board with above mention framing deatails - a.(i) (Rate will be include the cost of framing) | Sq. Ft | 0 | 0 |  | 0
|  | b | Ply Partition - P2 | Providing and fixing in position full height ply Partition as mentioned in drawing made out of 12mm thk. Marine ply to be fixed on both sides with necessary aluminum /M.S sections, framing details as mentioned above - a.(i). Items include making, cut-out for electrical swtich plates , swtich boxes and 4" ht skirting as per drawing and direction .Plyboard make should be GREEN, CENTURY 0R EQUIVALENT. (Surface area of single side will be consider for billing) | Sq. Ft | 32 | 0 | 575 | 18400 |  | 35.25 | 4.5 | 158.625
[11 empty] | 14.5 | 4.5 | 65.25
[11 empty] | 1.5 | 4.5 | 6.75
[13 empty] | 230.625 | 132609.375
|  | c | Bison Panelling - PN1 | Providing and fixing in position Panelling made out of 12 mm thk. Bison Board of approved make on one side with necessary aluminum/M.S sections, framing details as mentioned below - c.(i). (Surface area of single side will be consider for billing) | Sq. Ft | 0 | 0 |  | 0
|  | c.(i) |  | Framing-Cutting of section & Providing and fixing M.S frame work in built up tubular section (square hollow tubes 25 mm x 35 mm x 1.5 mm ) framework at 600mm c/c both ways in partition included bolted or welded in built up section to recieve bison pallening . The rate should include applying of two or more coats of primer , putty , complete as per standard technical specification, instructions of site engineer and as per decoration plan. |  |  | 0
|  | d | Marine Ply | Providing & Fixing 12 mm Marine Ply on Existing Provided Surface. Rate will exclude cost of framing | Sqft | 10 | 0 | 218 | 2180 |  | 9.58 | 11.33 | 108.5414 | 23662.0252 | MDF paneling
|  | d.1 | Marine Ply | Providing & Fixing 19 mm Marine Ply on Existing Provided Surface. Rate will exclude cost of framing | Sq.ft | 10 | 0 | 266 | 2660 |  | 9.58 | 11.33 | 108.5414 | 28872.0124 | play paneling
|  | d.2 | Marine Ply | Providing & Fixing 19 mm marine ply to be fixed with wooden gitty and the wall undulation to be covered by cement plaster | Sqft | 0 | 0 |  | 0
|  | e | Bison Boxing - PN5 For Façade | Providing and fixing in position Panelling made out of 6 mm thk. Bison Board of approved make on one side with necessary aluminum /M.S sections ( 25 mm x 35 mm x 1.5 mm ) framework at 600mm c/c both ways bison joints to have 6x6mm groove . Complete as per decoration plan and as specified & directed by Site Engineer. (Surface Area of the partition shall be measured for billing) | Sq. Ft | 0 | 0 |  | 0
|  | f | Prelam Panelling (Base for Vinyl pasting) - PN2 Upto 2500mm level from FFL | Providing and fixing in position Panelling made out of 12mm thk. Prelam Board on one side with necessary aluminum /M.S sections ( 25 mm x 35 mm x 1.5 mm ) framework at 600mm c/c both ways. Wood work to be treated with anti termite treatment.and edges to be finish with matching PVC Tape . Complete as per decoration plan and as specified & directed by Site Engineer. (Surface Area of the partition shall be measured for billing) | Sq. Ft | 0 | 0 |  | 0
|  | g | Prelam on Existing Surface | Providing and fixing in position Panelling made out of 12mm thk. Prelam Board on Existing Provided Surface. edges to be finish with matching PVC Tape . Complete as per decoration plan and as specified & directed by Site Engineer. (Surface Area of the partition shall be measured for billing) & (Rate will exclude the cost of framing) | Sq. Ft | 0 | 0 |  | 0
|  | h | WPC board (Base for Vinyl Pasting)PN2.2 | Providing and fixing in position Panelling made out of 8mm thk. WPC on one side with necessary Aluminium /M.S sections ( 25 mm x 35 mm x 1.5 mm ) framework at 600mm c/c both ways. Complete as per decoration plan and as specified & directed by Site Engineer. (Surface Area of the partition shall be measured for billing) | Sft | 0 | 0 |  | 0
|  | h.1 | WPC board on Existing Surface | Providing and fixing in position Panelling made out of 8mm thk. WPC on Existing Surface. Complete as per decoration plan and as specified & directed by Site Engineer. (Surface Area of the partition shall be measured for billing).Rate will exclude cost of framing | Sft | 0 | 0 |  | 0
|  | i | Ply Panelling - PN3 | Providing and fixing in position Panelling made out of 12mm thk. Marine ply on one side with necessary aluminum /M.S sections ( 25 mm x 35 mm x 1.5 mm )framework at 600mm c/c both ways. Wood work to be treated with anti termite treatment. Complete as per decoration plan and as specified & directed by Site Engineer. (Surface Area of the partition shall be measured for billing) | Sq. Ft | 0 | 0 |  | 0
|  | j | Laminate on panelling | Providing and fixing in position 1mm Thk. Laminate (14554 RH Hooked Holz Acasia) of merinolam make. Complete as per details in drawing and as specified & directed by Site Engineer. (surface area shall be measured for billing) on Columns upto 2500 mm & Booth seating cladding upto 900 mm of customer area | Sq. Ft | 0 | 0 |  | 0
|  | k | Laminate (in Staff changing room) | Providing and fixing in position 1mm Thk. Laminate (21141 Snow White) of Merinolam make. Complete as per details in drawing and as specified & directed by Site Engineer. (surface area shall be measured for billing) | Sq. Ft | 0 | 0 |  | 0
|  | l | Wall Corner Guard | Providing & fixing 15mmX15mm anodized Aluminium finish corner guard in approved shade powder coat matching to tile color above skirting level upto 2500 mm. | R. Ft | 60 | 58 | 310 | 18600 | 6 | 8.33 |  | 49.98
[10 empty] | 1 | 3 |  | 3
[13 empty] | 52.98 | 16423.8
|  | m | MS Tube Wall guards for articlad | Providing & fixing MS Tube 25mmX25mm finish in black Powder coat (0.5 micron) for Booth area articlad wall till skirting level as/drawing. | R. Ft | 37.9674 | 38 | 275 | 10441.035
|  | n | Floor Transition strip | Providing & fixing 15mm wide 'T' shape anodized Aluminium Transition strip | R. Ft | 25 | 19 | 225 | 5625 |  | 36 |  | 36 | 8100
|  | o op1 | Dado Brick / Tile Cladding - 3 (Booth seating area)-(ACG 795 Articlad-Aggregate Material-German Handmade) | Providing and fixing in position Brick / Brick finish dado tile as per drawing . Its shall be fixed with chemical (Laticrete L335) & grout -Roff Rainbow -khaki of approved make & shade directly on wall. Complete as specified in the drawing & to the satisfaction of the Architect & Site-in-charge.(Cost will include of Articlad directly on wall, Moratar Mixture Average thich 12-15mm , 1:4) | Sq. Ft | 110 | 0 | 355 | 39050 |  | 9.58 | 11.33 | 108.5414
[11 empty] | 23.67 | 1.08 | 25.5636
[11 empty] | 2.25 | 11.33 | 25.4925
[11 empty] | 9.83 | 1 | 9.83
[13 empty] | 169.4275 | 60146.7625
|  | o op2 | Dado Brick / Tile Cladding - 3 (Booth seating area)-(ACG 795 Articlad- Aggregate Material-German Handmade) | Providing and fixing in position Brick / Brick finish dado tile with grout -Roff Rainbow -khaki of approved make of approved make & shade on Existing provided surface as per details in drawing and as specified & directed by Site Engineer. (Cost will include of Articlad & Moratar Mixture Average thich 12-15mm , 1:4) | Sq. Ft | 0 | 0 |  | 0
|  | o op3 | Dado Brick / Tile Cladding - 3 (Booth seating area)-Unistone (Zara cotswold) | Providing and fixing in Unistone Wall Cladding Tile as per drawing . Its shall be fixed with chemical (Laticrete L335) & matching grout of approved make & shade on brick wall surface and as specified & directed by Site Engineer.( Moratar Mixture Average thich 12-15mm , 1:4) | Sq. Ft | 0 | 0 |  | 0
|  | o op4 | Dado Brick / Tile Cladding - 3 (Booth seating area)-MCM(Code -A Series Brick 54058) | Providing and fixing in position Brick / Brick finish dado Clay tile as per drawings . Its shall be fixed with chemical (Laticrete L335) & matching grout of approved make & shade on brick Wall Surface details as mentioned above on any surface as per details in drawing and as specified & directed by Site Engineer.((Cost will include of tiles cladding, Mortar Mixture Thick 12-15 mm, 1:4) | Sq. Ft | 0 | 0 |  | 0
|  | p op1 | Dado Brick / Tile Cladding - White Brick at Entrance area-Articlad ACG 555 Exterior Grade-Aggregate Material-German Handmade | Providing and fixing in position Brick / Brick finish dado tile coated with exterior grade sealer with 8mmX4mm . Its shall be fixed with chemical (Laticrete L335) & grout- Roff Snow White on brick wall surface. Complete as specified in the drawing & to the satisfaction of the Architect & Site-in-charge.(Cost will include of Articlad. Mortar Mixture Thick 12-15 mm, 1:4) | Sq. Ft | 0 | 0 |  | 0
|  | p op2 | Dado Brick / Tile Cladding - White Brick at Entrance area-MCM Clay Tile(Code -K series ,facing brick /052) | Providing and fixing in position Brick / Brick finish dado clay tile on brick wall surface Complete as specified in the drawing & to the satisfaction of the Architect & Site-in-charge.(Cost will include Mortar Mixture Thick 12-15 mm, 1:4) | Sq. Ft | 0 | 0 |  | 0
|  | p op3 | Dado Brick / Tile Cladding - White Brick at Entrance area- Unistone (Dholpur) | Providing and fixing in position Brick / Brick finish dado clay tile on direcet brick wall surface Complete as specified in the drawing & to the satisfaction of the Architect & Site-in-charge. (Cost will include Mortar Mixture Thick 12-15 mm, 1:4) | Sq. Ft | 0 | 0 |  | 0
|  | q | Framing for articlad | Providing and fixing 10 mm shera board with MS section of 25 mm * 25mm *1.5 mm(18 guage) as per drawings . | sq.ft | 0 | 0 |  | 0
|  | r | Exterior Textured Paint (Spectrum/Equivalent -Graniplast stone dust finish) on facade portal- Refer material specification sheet | Providing and applying textured Paint on wall including 10-12 mm groove (as per drawing) of two coats of approved make & shade . Filling the dents with approved Acrylic putty gypsum / or approved crack filler, binder, cleaning and making the surface dust free, preparing surfaces, applying a coat of sealer or primer as per the manufacturers specifications. Applying two under coats and one finished coat of paint to achieve the required finish including scrapping the existing paint, scaffolding, cleaning etc. Complete as per detail drawing and as directed by Engineer-in-charge. | Sq. Ft | 0 | 0 |  | 0
Sub Total of B.3.0 | [8 empty] | 96956.035 |  |  |  |  | 269813.9751
| B.4.0 |  |  | Doors & Windows
|  | a | Main Entry Glass Door with metal frame as per drawing- 6 ft wide | Providing and Fixing in position Main Entry Door as per details in drawings including outer MS sections 40 mm x 45 mm and 10 mm toughened glass to be sandwiched with pivot and hardware including S.S Brush Finish Handle 1500 mm ht (square one) with inbuilt locking & Floor Spring (Ozone FS-9400 STD ) provision in the floor as mentoned in the hyper linked drawing.and M.S Frame to be finish in Armada Blue Duco Paint or colour matching to Pantone shade PMS 2965 C (Cost will include all hardwares including Floor Spring ,Handle , Brush seal etc) | Sq.ft | 0 | 0 |  | 0
|  | b | Frameless toughened glass door with patch fittings and lock | Providing and fixing 12 mm toufghed glass door with patch fitting ,Pivot , lock and floor spring (Ozone FS-9400 STD), SS Handle H Type Ozone/Equivalent 12 Inches ,Collar seal. | Sq.ft | 21 | 0 | 1050 | 22050 |  | 4.1667 | 1.9167 | 7.9861
[11 empty] | 7 | 4.1667 | 29.1667
[11 empty] | 7 | 2.25 | 15.75
[11 empty] | 7 | 2.25 | 15.75
[11 empty] | 5.0833 | 4.1667 | 21.1806
[11 empty] | 5.0833 | 2.25 | 11.4375
[11 empty] | 2.6667 | 2.25 | 6
[11 empty] | 0.66667 | 4.1667 | 2.7778
[11 empty] | 0.67 | 2.25 | 1.5075
[11 empty] | 0.83333 | 4.1667 | 3.4722
[11 empty] | 0.83333 | 2.25 | 1.875
[11 empty] | 7 | 4.1667 | 29.1667
[11 empty] | 2.25 | 1.9167 | 4.3125
[13 empty] | 150.3825 | 157901.625
|  | c | Single Leaf Flush Door -With Vision Panel (SDP Entry) With Teak wood frame- 3ft wide | Providing and Fixing in position 35 mm Thk. wooden flush door including Vision Panel size of ( 300 x 500 mm ) & section on Teak Wood Door Frame of specified size, section well notched & screwed with cutting of grooves, edges, mouldings over rough ground including necessary hardware, fittings, fixtures, conch bolt, 150 mm high, 2mm thick s.s kick Plate, Door closure ,Handle,Lock as mentioned in drg,bitumen paint to non exposed surface, lacquer/melamine polish matching to Laminate on door frames & Horizontal grain Laminate on the panel from both sides of approved make & shade, etc. complete as per detail drawing, as specified and as directed by engineer-in-charge.(Cost will include all the hardwares mentioned above including brush seal) | Sq.ft | 0 | 0 |  | 0
|  | c.1 | Single Leaf Flush Door - With Vision Panel with Granite framing (SDP Entry) | Providing and Fixing in position 35 mm Thk. wooden flush door including Vision Panel size of ( 300 x 500 mm ) with Granite frame including necessary hardware, fittings,pivot hinges ,fixtures, conch bolt, 150 mm high ,2 mm thick s.s kick Plate, Door closure ,Handle,Lock as mentioned in drg,bitumen paint to non exposed surface, Lacquer/melamine polish matching to Laminate on door frames & Horizontal grain Laminate on the panel from both sides of approved make & shade, etc. complete as per detail drawing, as specified and as directed by engineer-in-charge. (Cost will include all the hardwares mentioned above and brush seal) | Sq.ft | 0 | 0 |  | 0
|  | c.2 | Single Leaf Fire Rated Flush Door -D2V With Vision Panel without door frame ( Back Exit) | Providing and Fixing in position 35 mm Thk. Fire Rated wooden flush door including vision panel (300*500 mm) including necessary hardware, fittings, fixtures, conch bolt, 150 mm high ,2 mm thick s.s kick Plate, Door closure ,Handle,Lock as mentioned in drg, bitumen paint to non exposed surface, melamine polish matching to Laminate on door frames & Horizontal grain Laminate on the panel from both sides of approved make & shade, etc. complete as per detail drawing, as specified and as directed by engineer-in-charge.(Cost will include all the hardwares mentioned above) size as per site | Sq.ft | 0 | 0 |  | 0
|  | d | Single Leaf Flush Door -D2(Back Exit Door ,Toilet ) | Providing and Fixing in position 35 mm Thk. wooden flush door & section on Teak Wood Door Frame of specified size, section well notched & screwed with cutting of grooves, edges, mouldings over rough ground including necessary hardware, fittings, fixtures, conch bolt, 150 mm high s.s kick Plate (1.5 thickness), Door closure ,Handle,Lock as mentioned in drg, bitumen paint to non exposed surface, matt melamine polish matching to Laminate on door frames & Horizontal grain Laminate on the panel from both sides of approved make & shade, etc. complete as per detail drawing, as specified and as directed by engineer-in-charge. (Cost will include all the hardwares mentioned above) | Sq.ft | 0 | 0 |  | 0
|  | d.1 | Single Leaf Flush Door -D2 without Door Frame (Back Exit Door ,Toilet ) | Providing and Fixing in position 35 mm Thk. wooden flush door including necessary hardware, fittings, fixtures, conch bolt, 150 mm high s.s kick Plate (1.5 thickness), Door closure ,Handle,Lock as mentioned in drg, bitumen paint to non exposed surface, matt Lacquer /melamine polish matching to Laminate on door frames & Horizontal grain Laminate on the panel from both sides of approved make & shade, etc. complete as per detail drawing, as specified and as directed by engineer-in-charge. (Cost will include all the hardwares mentioned above, including brush seal) | Sq.ft | 0 | 0 |  | 0
|  | e | Swing Single Leaf Flush Door -D2SV with Vision Panel (Kitchen to BOH) | Providing and Fixing Wooden Swing door in position 35 mm Thk. wooden flush door including Vision Panel size of (300 x 500 )& section on Teak Wood Door Frame of specified size, section well notched & screwed with cutting of grooves, edges, mouldings over rough ground wooden frame cutting of grooves, edges, mouldings including necessary hardware including floor spring ,150 mm high s.s kick Plate,Handle,Lock as mentioned in drg, bitumen paint to non exposed surface, melamine polish matching to Laminate on door frames & Horizontal grain Laminate on the panel from both sides of approved make & shade etc. complete as per detail drawing, as specified and as directed by engineer-in-charge. (Cost will include all the hardwares mentioned above) | Sq.ft | 0 | 0 |  | 0
|  | f | Fire Exit door | Metal fire door 2 hr fire rating with 35-40 mm thickness , vision panel (300*300) mm with push type panic bar, powder coated (Off white)As specified by project incharge(Navair/Shakti/Radiant)(FRG Glass- Saint Gobain/Asahi/Equivalent) | sqft | 0 | 0 |  | 0
|  | g | Swing Single Leaf Flush Door -D2SV without door Frame (Kitchen to BOH) | Providing and Fixing Wooden Swing door in position 35 mm Thk. wooden flush door including Vision Panel size of (300 x 500 ) including necessary hardware including floor spring ,150 mm high s.s kick Plate,Handle,Lock as mentioned in drg,bitumen paint to non exposed surface, lacquer/melamine polish matching to Laminate on door frames & Horizontal grain Laminate on the panel from both sides of approved make & shade etc. complete as per detail drawing, as specified and as directed by engineer-in-charge. (Cost will include all the hardwares mentioned above) | Sq.ft | 0 | 0 |  | 0
|  | h | Counter Swing Door | 19 MM Thk Solid Core Counter Swing Door with double side Piano S.S hinge 2 nos as mention in the detail drawing and as directed by Site Engineer .Door Front finish to be done with as / Approved Tile with 38 mm corian Profile in all the sides of tile and top of Swing Door and Door inside finish with Approved Laminate. 19 MM thick patti on all the edges on all three sides (Cost will include all the hardwares mentioned above) | Sq.ft | 7 | 11 | 2400 | 16800 |  | 2.4167 | 3 | 7.25 | 17400
Sub Total of B.4.0 | [8 empty] | 38850 |  |  |  |  | 175301.625
| B.5.0 |  |  | P.O.P/Painting
|  | a | POP Punning | Providing & applying wall punning up to 12mm to 15mm thick layer of super fine Plaster of Paris applied on specified area over existing plastered surface on walls and columns, to be finished smooth. Surface to be prepared by hacking, sand papering and applying coat of cement slurry if required including all incidentals, making grooves, patties, sills etc. complete and as directed by engineer in charge. The finish surface should be smooth, cover up all the patch work done by electrical agencies so as to avoid unevenness and ready to take on paint. Rate including cost of transportation, loading, unloading, scaffolding, wastage, taxes etc. as directed by Engineer-in-charge. | Sq. Ft | 30 | 341 | 40 | 1200 |  | 3.67 | 1.92 | 7.0464
[11 empty] | 35.167 | 1.92 | 67.5206
[10 empty] | 3 | 0.66667 | 1.92 | 3.84
[10 empty] | 2 | 6.25 | 1.92 | 24
[11 empty] | 0.67 | 1.92 | 1.2864
[11 empty] | 6 | 1.92 | 11.52
[11 empty] | 4.08 | 1.92 | 7.8336
[11 empty] | 10 | 11.5 | 115
[13 empty] | 238.047 | 9521.8816
|  | a.1 | POP Punning | Providing & applying wall punning up to 6 mm thick layer of super fine Plaster of Paris applied on specified area over existing plastered surface on walls and columns, to be finished smooth. Surface to be prepared by hacking, sand papering and applying coat of cement slurry if required including all incidentals, making grooves, patties, sills etc. complete and as directed by engineer in charge. The finish surface should be smooth, cover up all the patch work done by electrical agencies so as to avoid unevenness and ready to take on paint. Rate including cost of transportation, loading, unloading, scaffolding, wastage, taxes etc. as directed by Engineer-in-charge. | Sq. Ft | 0 | 0 |  | 0
|  | b | Painting - Lustre Paint (Vertical Exposed Surfaces) | Providing and applying Lustre Paint on wall of approved make & shade filling the dents with approved Acrylic putty gypsum / or approved crack filler, binder, cleaning and making the surface dust free, preparing surfaces, applying a coat of sealer or primer as per the manufacturers specifications, applying two under coats and one finished coat of paint to achieve the required finish including scrapping the existing paint, scaffolding, cleaning etc. complete as per detail drawing, as specified and as directed by Engineer-in-charge. | Sq. Ft | 250 | 177 | 38 | 9500
|  | c | Painting - Textured Paint -(Details- Refer Material Spec. sheet) (Vertical Exposed Surfaces) | Providing and applying textured Paint on wall of two coates of approved make & shade filling the dents with approved Acrylic putty gypsum / or approved crack filler, binder, cleaning and making the surface dust free, preparing surfaces, applying a coat of sealer or primer as per the manufacturers specifications, applying two under coats and one finished coat of paint to achieve the required finish including scrapping the existing paint, scaffolding, cleaning etc. complete as per detail drawing, as specified and as directed by Engineer-in-charge. | Sq. Ft | 0 | 0 |  | 0
|  | d | Painting - Plastic Emulsion Paint (Ceiling) | Providing and applying Plastic Emulsion Paint on Ceiling of approved make & shade filling the dents with approved Acrylic putty gypsum / or approved crack filler, binder, cleaning and making the surface dust free, preparing surfaces, applying a coat of sealer or primer as per the manufacturers specifications, applying two under coats and one finished coat of paint to achieve the required finish including scrapping the existing paint, scaffolding, cleaning etc. complete as per detail drawing, as specified and as directed by Engineer-in-charge. | Sq. Ft | 850 | 474 | 38 | 32300 |  | 35.25 | 14.08 | 496.32
[11 empty] | 9.75 | 1.25 | -12.1875
[11 empty] | 26 | 13.75 | 357.5
[11 empty] | 8 | 5 | -40
[11 empty] | 21.5 | 9.5 | 204.25
[11 empty] | 24.5 | 3 | 73.5
[11 empty] | 12.25 | 3 | 36.75
[11 empty] | 10 | 1 | 10
[10 empty] | 2 | 10.08 | 1.42 | 28.6272
[11 empty] | 24 | 1.42 | 34.08
[11 empty] | 2 | 44.25 | 88.5
[11 empty] | 1.25 | 10.08 | 12.6
[10 empty] | 2 | 1 | 10.08 | 20.16
[11 empty] | 1 | 10 | 10
[11 empty] | 1 | 11.08 | 11.08
[11 empty] | 1 | 6.75 | 6.75
[11 empty] | 3.67 | 1.5 | 5.505
[11 empty] | 35.25 | 1.5 | 52.875
[10 empty] | 3 | 1 | 1.5 | 4.5
[10 empty] | 2 | 6.25 | 1.5 | 18.75
[11 empty] | 1 | 1.5 | 1.5
[11 empty] | 6 | 1.5 | 9
[11 empty] | 4.08 | 1.5 | 6.12
[11 empty] | 7.83 | 2 | 15.66
[11 empty] | 5.67 | 2 | 11.34
[10 empty] | 2 | 6 | 2 | 24
[10 empty] | 2 | 8 | 2 | 32
[13 empty] | 1022.8597 | 38868.6686
|  | e | Enamel Paint | Providing and Applying synthetic enamel paint (Armada Blue) of approved make & Shade on Metal surfaces.to be prepared by rubbing with coarser sand paper suitable for painting by filling all dents and crack & two coat of primer .The rate includes scrapping ,Filling with Putty etc complete. - Colour and pattern to be specified at site by site supervisor.Approved make - Asain paint | sq.ft | 280 | 106 | 38 | 10640 |  | 14.25 | 6.75 | 96.1875
[11 empty] | 2.25 | 6.75 | 15.1875
[11 empty] | 8.75 | 6.75 | 59.0625
[11 empty] | 5.33 | 6.75 | 35.9775
[11 empty] | 4.33 | 6.75 | 29.2275
[11 empty] | 9.5 | 2.75 | 26.125
[11 empty] | 2.58 | 2.75 | 7.095
[11 empty] | 2 | 9.75 | 19.5
[11 empty] | 5.83 | 1 | 5.83
[11 empty] | 1.25 | 9.75 | 12.1875
[10 empty] | 4 | 11.33 | 2 | 90.64
[10 empty] | 4 | 4.67 | 1 | 18.68
[10 empty] | 4 | 10 | 2 | 80
[13 empty] | 495.7 | 18836.6
|  | f | Duco Paint | Providing and Applying Duco spray paint (Armada Blue) of approved make on Wooden /Expose metal frame. Surface to be prepared by rubbing wooden surface with coarser sand paper suitable duco paint putty to be applied and finish with priemer .The rate includes scrapping ,Filling with Putty etc completein spec. Approved make - Asain paint | sq.ft | 0 | 0 |  | 0
Sub Total of B.5.0 | [8 empty] | 53640 |  |  |  |  | 67227.1502
C |  |  |  | Exterior Head
| C.1.0 |  |  | Façade Work
|  | a | Shera board Panelling-1 (Signage front) | Providing and fixing in position panelling made out of 8x 150 x 3000 mm Shera board Teak planks (with application of 2 coat of primer on all side of shera plank & finished with Duco paint-Armada blue or colour matching to Pantone shade PMS 2965 C on shera Planks) to be fixed on 25x25x1.5 mm Alluminium/MS framework to be painted with anti -corrosion Paint on all sides and Duco Painted M S Border size of 25X25x1.5 to be fixed all around the signage. Complete as per store front Detail and as specified in Drawing.(Cost will include Shera board Teak Planks & ,Frame)Approved make - Asain paint. | Sq. Ft | 41.8068 | 42 | 515 | 21530.502 |  | 9.67 | 11.33 | 109.5611
[11 empty] | 23.67 | 1.08 | 25.5636
[11 empty] | 2.25 | 11.33 | 25.4925
[11 empty] | 9.83 | 1 | 9.83
[13 empty] | 170.4472 | 87780.308
|  | b | Shera board Paneling for Textured paint /White Paint at Façade | Providing and fixing in position Shera Board Panelling made out 8 mm thk. Shera board with 25mm x 50mm aluminum sections/M.S framework at 600mm x 1200 mm c/c with two coat of primer . Complete as per decoration plan and as specified & directed by Site Engineer. (Surface area of the partition shall be measured for billing) | Sq. Ft | 0 | 0 |  | 0
|  | c | Screen Module at Entrance | Providing and fixing in position screen module as per details in drawing . Provision for Glass panel shutter made up from 19 mm Marine PLY frame & 10 mm toughened Glass and Ply framing boxing to be made with necessary locking arrangement, Hinges,150x 150 mm ,fastener & Dorma Patch Fitting for Shutter .Complete as per detail drawing and as specified & directed by Site Engineer. (Length & width of the partition shall be measured for billing.) | Nos | 0 | 0
|  | d | Promo Panel | Proving & Fixing of heavy duty cable turnking box at the floor and ceiling/ beam with help of nessacary arrangement. Fixing of at digital display (LED TV) approved size at cable turnking box witg nessacary arrangement and powder coating to be done for cable trunking box in approved shade. All the necessary arrangements to be done for thinclient fixing, Also all the cables to be trunked in the cable trucking box. | Nos |  |  |  | 0
|  | e | Fixed Glass with Metal Frame at entrance | Providing and fixing in position fixed 10 mm Toughened glass partition with As/approved Duco Painted -(ARMADA BLUE) or colour matching to Pantone shade PMS 2965 C metal frame of 40 x 45 x1.5 mm section and intermediate sections of 25 x 25 x1.5 mm from outside and 25 x 12 x1.5 mm from inside with toughened glass. Complete as per details in drawing. (Surface area of the partition shall be measured for billing.) | Sq. Ft | 165 | 0 | 775 | 127875 |  | 14.25 | 6.67 | 95.0475
[11 empty] | 2.167 | 6.67 | 14.4539
[11 empty] | 5.33 | 6.67 | 35.5511
[11 empty] | 1.5 | 6.67 | 10.005
[11 empty] | 3 | 2.67 | 8.01
[13 empty] | 163.0675 | 126377.3047
|  | f | Fixed Glass with Aluminium Frame at entrance | Providing and fixing in position fixed 10 mm Toughened glass partition with As/approved poweder coated on Aluminium frame of 45 x 25 mm section with glazing rubber and intermediate sections of 45 x 25 from outside and 45 x 25 from inside with toughened glass. Complete as per details in drawing. (Surface area of the partition shall be measured for billing.) | Sq. Ft | 62 | 0 | 550 | 34100
|  | g | 25 x 25mm Duco Painted | Providing and fixing in position metal section of 25 x 25 x1.5 mm Duco Painted in matt finish blue Paint. | R. Ft | 148 | 0 | 415 | 61420
|  | h | Trap door for rolling shutter | Providing and fixing in position Trap door for rolling shutter made out of 8mm thk bison board finished with approved paint, shade to match white brick cladding. complete as per details in drawing and as specified & directed by Site Engineer. | Sq. Ft | 28 | 0 | 750 | 21000 |  | 3.75 | 2.58 | 9.675
[11 empty] | 3.75 | 2.58 | 9.675
[11 empty] | 3 | 2.25 | 6.75
[13 empty] | 26.1 | 19575
Sub Total of C.1.0 | [8 empty] | 265925.502 |  |  |  |  | 214157.6128
D |  |  |  | Wood Work
| D.1.0 |  |  | Furniture /WOOD Work
|  | a | Order Counter | Providing and fixing in position Order counter : Counter top finished in 6mm thick Acrylic Solid Surface LG Hausys-HI-MACS G109 Beige Island over 19 mm thick WPC/Marine Ply. 150mm height Drawers (2 nos )to be provided below each POS.Internal area to be finish with 1 mm thick approved laminate with necessary hardwares(Lock ,Telescopic channel etc). MS powder coated framework (40x40x1.5mm) as per detail drawing to be provided with necessay arrangement and Ledge having LED cove strip as per detail drawing Complete in all respect . Cost to include all materials, DMB Framing ,labours and necessary leads & lift etc. -Counter Height-3'6" | RFT | 9.5 | 8 | 16000 | 152000 |  | 9.33 |  | 9.33 | 149280
|  | a.1 | Order Counter with Glass Slider/Openable | Providing and fixing in position Order counter : Counter top finished in 6mm thick Acrylic Solid Surface LG Hausys-HI-MACS G109 Beige Island over 19 mm thick WPC/Marine Ply. 150mm height Drawers (2 nos)to be provided below each POS.Internal area to be finish with 1 mm thick approved laminate with necessary hardwares (Lock ,Telescopic channel etc). MS powder coated framework (40 x40 x 1.5 mm) with 10 mm toughened glass and having provision of sliding glass opening with necceaasy fittings and channels as per detail drawing and Ledge having LED cove strip as per detail drawing Complete in all respect . Cost to include all materials, DMB Framing ,labours and necessary leads & lift etc. Counter Height-3'6" | RFT | 0 | 0 |  | 0
|  | b | Make line | Providing and fixing in position Makeline : Counter top finished in 6mm thick Acrylic Solid Surface LG Hausys-HI-MACS G109 Beige Island over 19 mm thick Marine Ply / WPC and Ledge having LED cove strip as per detail drawing Complete in all respect. Duco Paint M.S framework with 10 mm toughened Glass as per detail drawing above counter Cost to include all materials, labours and necessary leads & lift etc. | RFT | 14 | 14 | 16000 | 224000
|  | c | MOP/Janitor storage | Providing and fixing in position MOP storage made of 18mm thk. Marine ply in appd. Laminate from outside and white laminate inside with necessary support framework. Cost to include shelves in 18 mm thk. marine ply finished in white laminate with all hardware, fasteners, and rubber / PVC leveller etc. complete in all respect as per detailed drawing and size to be considered in Width x Height for Billing Depth 500 mm | Sq.ft | 0 | 1 | 1850 | 0
|  | d | SoftBoard | Providing and Fixing in position softboard as specified size. complete in all respect as per detailed drawing. Panel Size : 1200 x 900 | Nos. | 0 | 0 |  | 0
|  | e | Staff Lunch Table | Providing and placing foldable staff table in position 40mm thk table top made out of 2 nos 19mm thk marine ply finished with 1mm thk laminate LAM01 on both side and edges to be finished with PVC edge bending to be sopported on L bracket with Table bracket (HAFFLE ) complete in all respect as per detailed drawing. Size- 4'x1'6", width can be adjusted as per site. Fixing of table to be kept 3' from thr floor. | Sq.ft | 0 | 6 | 1650 | 0
|  | f | M S railing | Providing and fixing in position M. S. Railing made out of 25 x 25 x1.5 MS hollow section for vertical sections and 12 x 12 x1.5 mm midrails finished in matt duco paint as per approved shade and wooden section Hardwood oak 50 x 25 mm (With Malamine Matt Polished) Handrail to be fixed on 6 mm x 50 mm M.S flat and End to End Main Balusters will be in size of 50 x 50 mm Cost to include all hardware and fasteners etc. complete in all respect as per detailed drawing. | R. Ft | 0 | 0 |  | 0
|  | g | S S railing | Providing and fixing in position S. S. Railing made out of ss grade 304 hollow section for vertical sections and midrails and S.S Hollow handrail . Cost to include all hardware and fasteners etc. complete in all respect as per detailed drawing. | R. Ft | 0 | 0 |  | 0
|  | h | Removing & Re-fixing existing M.s/ S. S. Railing | Removing and re-fixing in position existig S. S. Railing/M.S Railing with glass panels for installation of finishing material of tread & riser. Cost to include all hardware, fasteners, and rubber / PVC leveller etc. complete in all respect as per detailed drawing. | LS | 1 | 0 |  | 0
|  | i | Mirror | Providing and placing in position 6mm thk extra clear mirror of size 450mm x 1200 mm with 12mm thk marine ply at back to be fixed over ss stud on wall. Cost to include all hardware, fasteners, and rubber / PVC leveller etc. complete in all respect as per detailed drawing. | No. | 2 | 2 | 2700 | 5400
|  | j | Hood Graphic Panel | Providing and fixing in place Hood Graphic Panel made out of approved shade powder coated sheet metal Complete as per details in drawing Reference Drawing No. 960 | sq ft | 25.8917 | 26 | 1850 | 47899.5833
|  | k | Computer Holder above Dough Tray & Router | Providing and fixing ceiling mounted ,Metal fabricated Computer Holder for Thin clients above Dough Tray & Router. Complete in all respect as per detailed drawing. | Nos. | 0 | 1 | 3500 | 0
|  | l | Computer Holder Wall Mounted for SDP & Makeline | Providing and fixing Wall mounted ,Metal fabricated Computer Holder for Thin clients above Dough Tray & Router. Complete in all respect as per detailed drawing. | Nos. | 0 | 1 | 3500 | 0
|  | m | Corian -6 MM THK.LG HAUSYS G-109 Foldable Ledge- Take away (Samsung aspen glow - AG636/ Rehau frost white 180L) | Providing & fixing in position Corian foldable ledge to be made up of 6mm corian with necessary angle & bracket support required to fix on m.s frame. It shall be fixed with Chemical Adhesive . The job including cutting of corian & making smooth edges wherever required . The work shall also include cost of materials, wastages,bracket, labour, all lead and lift at all levels, loading and unloading, transportation, etc. and all other incidental charges etc., complete and as directed by Engineer-in-charge. Measurement to be calculated basis on Actual area in running feet. | rft | 0 | 0 |  | 0
|  | n | Take away counter | Providing and placing in position Take away table made out of 19mm thk. Marine ply finished with appd. Laminate (Outside Laminate- 1mm THK. 14554 RH HOOKED ACACIA LAMINATE, MERINO WITH 2mm THK. REHAU MAKE MATCHING EDGE BAND & Inisde laminate Merino Lam 21141 snow white ) and table top to be finish with 6 mm thk LG Hausys -109 Hi Macs over marine Ply with necessary support framework as approved, Cost to include all hardware, fasteners, and rubber / PVC leveller etc..Cost to inlude of making 1 drawer and shelve ,as per shared detailed drawing and Size 900 x 550 x 975 mm ht | rft | 0 | 0 |  | 0
|  |  |  | Providing & fixing DMB for TV' Backing Ply with paint as per requirment. | Sq.ft | 16 |  | 550 | 8800
|  |  |  | Providing & fixing Loft doors above cold room | Sq.ft | 20 |  | 1150 | 23000 |  | 5.583 | 2 | 11.166 | 12840.9
|  |  |  | Providing & fixing KDS Stand in MS as per Requirement | LS | 1 |  | 2500 | 2500 | 1 |  |  | 1 | 2500
|  |  |  | Providing & fixing of glass frosted film as per instruction | Sq.ft | 80 |  | 95 | 7600
|  |  |  | Providing and fixing of 150mm thk gypsum partition as per requirment | Sq.ft | 50 |  | 165 | 8250
|  |  |  | Providing and fixing 75mm thk x 200mm deep Gypsum PORTAL partition with both side 12mm thk gypsum. | Rft | 43 |  | 185 | 7955
|  |  |  | Dummy coalman Top and Bottom Fiber Molds | LS | 4 |  | 2500 | 10000
|  |  |  | Floor protection covering material (Protection PVC sheet) | Sq.ft | 832 |  | 15 | 12480
|  |  |  | Fixing of kitchne SS selves, kitchne accessories, Machine connections and fire extinguisher as per requirtment OPS tram and instructuction by Projects team. | LS | 1 |  | 5000 | 5000 | 1 |  |  | 1 | 5000
|  |  |  | Removing of existing barricade as per requirment. | Sq.ft | 280 |  | 20 | 5600 |  | 46 | 12 | 552 | 11040
|  |  |  | Debris ( Other Agencies ) | LS | 1 |  | 12000 | 12000 | 1 |  |  | 1 | 12000
Sub Total of D.1.0 | [8 empty] | 532484.5833 |  |  |  |  | 192660.9
|  |  |  | Grand Total |  |  |  |  | 2051038.4967 |  |  |  |  | 2096524.5397
|  |  |  | Contingency work (Tools and materia entry and material long distance) |  |  |  |  | 512759.6242 |  |  |  |  | 524131.1349
|  |  |  | Grand Total |  |  |  |  | 2563798.1209 |  |  |  |  | 2620655.6746

## Plumbing BOQ
Domino's International Arrival
Pikture Perfect
Sr. No | Name of Item | Description of Item | Unit | Rev Qty | Rate | Amount |  |  | Remarks
Plumbing
INTERNAL WATER SUPPLY SYSTEM
| CPVC Water Supply Pipes | Providing & fixing on walls / ceiling / floors, medium grade having embossed ISI Mark CPVC pipes of diameter as mentioned below with fittings i.e.connector, clamps, tees, elbows, reducers, male-female etc. necessary fittings. Make-(Supreme / Prince/Astral or as approved. )
|  | 15mm nominal bore | Rmt | RO
|  | 20mm nominal bore (Sink, Geyser, RO, Basin,+ Pepsi machine) | Rmt | 42 | 361 | 15162
|  | 25mm nominal bore | Rmt | 54 | 477 | 25758 | 62 | 29574
|  | 32mm nominal bore | Rmt | 10 | 708 | 7080 | 18.5 | 13098
|  | 40mm nominal bore | Rmt | 3 | 1050 | 3150
| GI C Class (Heavy) Pipes | Providing & fixing on walls / ceiling / floors, GI C class pipe ( Heavy) of diameter as mentioned below with screwed sockets, joints & necessary. Make-(Supreme / Prince/Astral or as approved)
|  | 25MM nominal bore | Rmt
|  | 50 MM nominal bore | Rmt
| Medium Class GI Pipes | Providing, fixing and testing GI pipes (medium class) of approved make conforming to IS 1239-1982 complete with G.I. fittings such as tees, crosses, plugs, sockets, elbows, reducers, unions, sleeve pieces, check nuts etc including jointing with C.I. pipes (wherever required), cutting & making good the walls, floors, R.C.C. work etc. including cutting chases & filling the same, painting the GI pipes with two coats of bitumastic paint, wrapping with one layer of polythene tape 400 micron thick and applying a final coat of bitumestic paint complete including surface preparation (for waste connection and fixtures venting).
|  | 32 mm dia | Rmt
|  | 40 mm dia | Rmt
|  | 50 mm dia | Rmt
|  | 65 mm dia | Rmt
| Gate Valves | Providing, Fixing, testing and commissioning of ISI marked Gun Metal Screwed pattern full way Gate valve with wheel tested to non shock cold working pressure upto 10 kg /sq cm(Stop Valve) conforming to IS 778 class 1 including jointing, supporting etc complete and as directed. Make-(Danfoss/Jayhiwa/Zoloto or equivalent)
|  | 20mm class 1.0 | Nos.
|  | 25mm class 1.0 | Nos.
|  | 32mm class 1.0 | Nos.
|  | 40mm class 1.0 | Nos.
|  | 50 mm class 1.0 | Nos.
| CPVC Ball Valves | Providing & Fixing forged CPVC ball valves with ball/stem, union/fange,washer, nuts & bolts, rated to temperature of 85 deg. C and tested to a pressure not less than 15 kg/sq.cm. Including coating against mechanical damage as per manufactures sepcification.
|  | 19 mm nominal bore | Nos.
|  | 25 mm nominal bore | Nos. | 3 | 680 | 2040
|  | 32 mm nominal bore | Nos. | 5 | 850 | 4250 | 4 | 3400
| Angle Valve | Providing and fixing of angle valves of following diameters
|  | 15mm | Nos. | 14 | 1650 | 23100 | 15 | 24750
|  | 25mm | Nos. |  | 2150
| SINGLE LEVER WALL MIXER | Providing and fixing 15mm C.P. Single lever wall mixer for 3 Bowl Sink. (Jaguar-Continental make.) | Each | 3 | 4000 | 12000
| BIB TAP LONG BODY | Providing and fixing 15mm C.P. brass bib tap (Jaguar-Continental) with C.P. brass threaded flange complete, including cutting and making good the walls wherever required. | Each | 2 | 2420 | 4840 | 1 | 2420
| SINGLE LEVER FLOOR MIXER | Providing and fixing 15mm C.P. Single lever wall mixer for 3 Bowl Sink. (Jaguar-Continental make.) | Each | 1 | 4000 | 4000 | 4 | 16000
|  | Fixing of kitchne SS selves, kitchne accessories, Machine connections and fire extinguisher as per requirtment OPS tram and instructuction by Projects team. | Lot | 1 | 5500 | 5500
|  | Holl cutting in SS 3 boll sink and fixing of Sink sprey tap as per requirment. | Each | 1 | 3800 | 3800 | 3 | 11400
| GREASE TRAP | Providing and fixing SS Grease Trap of NGT-8, complete with all necessary fittings. ( Only Installation ) | Nos | 1 | 3300 | 3300 | 1 | 3300
| 03 BOWL SINK CONNECTION | Providing and fixing 3-Bowl Sink Drain outlet connection with valve & Drain pipe complete with all necessary fittings. | No | 1 | 4000 | 4000 | 1 | 4000
| SINK CONNECTION | Fixing Hand Wash Sink Drain outlet connection with valve & Drain pipe complete with all necessary fittings. | No | 2 | 2750 | 5500 | 2 | 5500
| SINK CONNECTION | Providing and fixing Veg. Prep. Sink Drain outlet connection with valve & Drain pipe complete with all necessary fittings. | No | 2 | 1320 | 2640
| pvc connection pipe | Providing and Fixing uplasticised PVC connection pipe with unions : 45 cm length , 15 mm nominal bore. | Nos. | 18 | 350 | 6300 | 15 | 5250
| Insulation over hot water pipes | Providing and fixing nitrle rubber insulation on hot water supply / return pipes.
|  | 15 mm nominal Bore | Rmt |  | 180
|  | 20 mm nominal Bore | Rmt | 10 | 210 | 2100
| Water Meter | Providing and fixing of water meter for cold water supply for following diameters
|  | 25mm | Nos. |  | 8000
|  | 32mm | Nos. |  | 12500
| CPVC Union | Supply and Fixing of CPVC union under the kitchen equipments in the drain line of following diameters
|  | 25mm | Nos. | 0 | 800
|  | 32mm | Nos. | 5 | 900 | 4500 | 4 | 3600
INTERNAL DRAINAGE SYSTEM
| UPVC Waste Pipes | Providing and fixing of UPVC Pipes for Soil/Vent/Waste SWR pipe of required diameter conforming to I.S.-13592, and I.S.-4985 to withstand continous internal hydroulic pressure of 4 kg/cm2 including necessary fixtures and fittings, such as bends, tees, single junctions, double junctions and joining with rubber rings and lubricants, on wall by means of clips or in ground including necessary excavation, laying refilling, trench testing etc. complete. (Prior approval of sample and brand by Ex.Engineer is necessary before use.) Make-(Supreme / Prince/Astral or as approved. )
|  | 32 mm dia | Rmt
|  | 40 mm dia | Rmt
|  | 50 mm dia. | Rmt
|  | 65mm dia | Rmt
|  | 75 mm dia. | Rmt
|  | 110 mm dia. | Rmt
|  | 160mm dia | Rmt
| PVC Waste Pipes | Providing & fixing of PVC waste pipes and fittings with synthetic enamel paint of any colour as per pipe colour code over a coat of primer (of approved quality).
|  | 50 mm dia | Rmt | 10 | 450 | 4500 | 7 | 3150
|  | 65 mm dia | Rmt |  | 525
|  | 75 mm dia | Rmt | 15 | 640 | 9600 | 18 | 11520
|  | 100 mm dia | Rmt | 15 | 880 | 13200 | 10.6 | 9328
| P or S Trap | Providing and fixing of Cast Iron centrifuguly spun `P' or `S' trap of self cleansing design without vent arm conforming to IS: 3989-1984 complete in all respects including cutting and making good the walls, floors & RCC work.
|  | 100 mm inlet & 100 mm outlet. | Nos.
|  | 100 mm inlet & 75 mm outlet. | Nos. | 1 | 1200 | 1200
| Grtaing | Providing and fixing 125 mm dia, 3 mm thick Stainless steel grating with frame for floor traps or drains of required pattern including cutting and making good the floors complete.
|  | 125 mm x 125 mm | Nos. | 1 | 850 | 850
| Floor Trap/Nahani Trap | Providing ,laying, testing & commissioning of approved Cast Iron Multi floor trap / Nahani trap with cockroach jali of required sizes, including jointing etc. complete and as directed. (GMGR/Chilly or equivalent) | Nos. | 8 | 1800 | 14400 | 8 | 14400
| Chilly Trap | Providing ,laying, testing & commissioning of approved Chilly trap with Jali with required sizes, including jointing etc. complete and as directed. | Nos. | 8 | 1050 | 8400 | 6 | 6300
| Clean Out Plug | Providing laying, testing & commissioning of approved Cast Iron Clean out plugs (for the downtakes near bends).
|  | 75 mm dia | Nos.
|  | 100 mm dia | Nos.
|  | 150 mm dia | Nos.
| Floor Clean out | Providing and fixing of Floor Clean out of 100 mm diameter in basement area | Nos.
| Cement Concrete around buried pipes | Providing and laying cement concrete 1:2:4 mix (1 cement :2 coarse sand :4 graded stone aggregate, 20 mm down gauge) 75 mm thick in bed and all around UPVC Rain water pipes burried under floor, including shuttering and centering for complete in all respects (For Burried Rain Water Pipes/Connection to CB).
|  | 75 mm dia | Rmt
|  | 110 mm dia | Rmt
160mm dia
| Water Pump | Providing and fixing of following Motor water pumps of following capacities. (Make- Cromption Greaves or Equivalent)
|  | 0.5 HP | Set
|  | 1.0 HP | Set
|  | 1.5 HP | Set
| Flexible Pipes | Providing and fixing of GI flexible pipe of following diameters for waste pipe connection
|  | 25mm | Rmt
|  | 32mm | Rmt
|  | 40mm | Rmt
|  | 50mm | Rmt
| Sensor Pillar Cock | Providing and fixing of Sensor Pillar cock for basin of Jaguar make as per approval of Project Incharge | Nos.
| 0.01 | Constructing brick masonry chamber for C.I. inspection chamber and bends with bricks in cement mortar 1:4 (1 cement : 4 coarse sand) C.I. cover with frame (light duty) 455x610 mm internal dimensions, total weight of cover with frame to be not less than 38 kg (weight of cover 23 kg and weight of frame 15 kg), R.C.C. top slab with 1:1.5:3 mix (1 cement : 1.5 fine sand : 3 graded stone aggregate 20 mm nominal size), foundation concrete 1:5:10 (1 cement : 5 fine sand : 10 graded stone aggregate 40 mm nominal size), inside plastering 12 mm thick with cement mortar 1:3 (1 cement : 3 coarse sand), finished smooth with a floating coat of neat cement on walls and bed concrete etc. complete as per standard design: | nos.
Inside dimensions 900x300 mm and 30 cm deep for 100 mm dia double pipe line :
| 0.02 | Providing and fixing of SS Drain Channel of Required sizes along with all the required fittings complete cutting and making good to the Kitchen Equipment drainage floor where required as per instruction of Engineer in charge.
| a | Making chamber in brick work including internal tiling etc for S.S Grating size, 350mm x 350mm, in 16 swg 25mm x25mm Square Pipe around the Frame and 20mmX 20mm Square pipe in center of frame with SS perforated tray (304 SWR). Complete as per architectural detail drawing & Site Engineer's instruction. | Nos. | 2 | 3500 | 7000 | 2 | 7000 | Only Civil Work considered
| b | Making chamber in brick work including internal tiling etc for S.S Grating size, 900mm x 350mm, in 16 swg 25mm x25mm Square Pipe around the Frame and 20mmX 20mm Square pipe in center of frame with SS perforated tray (304 SWR). Complete as per architectural detail drawing & Site Engineer's instruction. | Nos. | 1 | 6500 | 6500 | 1 | 6500 | Only Civil Work considered
EXTERNAL SEWERAGE
| Masonary Manhole | Constructing brick masonry manhole with 1st class bricks in cement mortar 1:5(1 cement:5 fine sand) RCC top slab with 1:2:4 mix (1 cement :2coarse sand:4graded stone aggregate 20mm nominal size) foundation concrete 1:4:8 mix (1 cement:4 coarse sand :8 graded stone aggregate 40mm nominal size) inside and out side plastering 12mm thick with cement mortar 1:3(1 cement :3 coarse sand) finished with a floating coat of neat cement inside and rough plaster on outside and making channels in cement concrete 1:2:4 mix(1 cement:2 coarse sand:4 graded stone aggregate 20mm nominal size) neatly finished complete as per standard design including excavation refilling and disposal of surplus earth.Inside size 80X80 cms and 60 cms deep including C.I cover with frame (light duty) 455 x 610 mm internal dimensions total weight of cover and frame not less than 38 kg(wt. Of cover 23 kg and wt.of frame15kg). | Each
| Gully Trap (300x300) | Providing and fixing of gully trap complete with SS grating, brick masonsary chamber and water tight SS cover with pull out handle with frame of 300x300mm inside size complete and inside chamber base finish in PCC and brick surface to be finished with tile | Each
| Gully Trap (600x600) | Providing and fixing of gully trap complete with SS grating, brick masonsary chamber and water tight SS cover with pull out handle with frame of 600x600mm inside size complete and inside chamber base finish in PCC and brick surface finished with tile | Each
| Gully Trap (300x 750-1200) | Providing and fixing of Open gully trap complete with SS grating, brick masonsary chamber and 300mm width inside size and leghth to be vary 750-900-1200 from complete and inside chamber base finish in PCC and brick surface to be finished with tile (SS grating TO Be Provided By Kitchen Vendor) | Each
Sanitarywares & Fittings
| WC | Providing & Fixing following fixtures, the rate for the following shall be inclusive of all necessary fixtures, accessories & attachments to make then operational, etc. complete to the satisfaction of the Architect Cost excludes internal concealed plumbing with CPVC/PVC Pipes only-part of plumbing boq)
|  | Hindware - Pluto - P Coupled Closets - Catelogue No.20065 ,size 64 x 36 x 82 cm (Color : Starwhite) | No.
| Wash Basin | Fixing white glazed vitreous wash basin with 32 mm dia C.P brass waste of standard pattern, 32 mm dia C.P cast brass bottle trap and union, 32 mm dia C.P brass pipe to wall and CP wall flange, and rubber acceptors for waste connection, R.S. or C.I. painted brackets bolts, nuts etc. cutting & making good the wall and floor wherever required. Gap shall be filled with silicon sealant whereever required.
|  | Oval wash basin (Make : Cera Cloister 1046 Wash Basin) | No.
|  | Wash Basin without pedestal (New Cat No: S2040102 450 x 350 mm,color : Snow white) | No.
Toilet Accessories
| Toilet Paper Holder | Fixing recessed type stainless steel toilet paper holder of approved makes. Including cutting hole in the masonary/R.C.C wall and making good with cement mortar (Size 150 mm x 150 mm) | No.
| Soap Dispenser | Providing and fixing of 400ml Wall mounted Liquid soap dispenser | No.
| Brass Hooks | Fixing CP brass hooks (double) of approved make. Including providing & fixing C.P brass screws, washers, rawl plug etc. | No.
| Air Neutralizer system | Fixing kimcare Air Neutralizer system, windows micro mist economy dispenser (Kimberly Clark make) | No.
| Tissue Dispenser | Fixing of Stainless Steel Towel Paper Dispenser | No.
| Pillar Cock for Wash Basin FOH | Parryware G3164A1 Crust Tall Pillar Tap | No.
| Pillar Cock for Wash Basin Toilet | Cera Pillar Tap Garnet Quarter Turn Fitting (Chroma Finish) Cat no.F2002101 | No.
| Bib cock | Bib Cock 2 In 1 With Wall Flange (Make Perryware & Hindware) | No.
| Jet Spray (Health Faucet) | Hindware F160038CP Health Faucet ABS with 1.2 m long Flexible PVC Tube and Wall Hook (Chrome) | No.
| Bottle Trap | Hindware-Addons - Bottle Trap 32mm With 125mm & 175mm Long Wall Connection Pipe &Wall Flange (ECONOMY MODEL) | No.
| File Sorter | Infomate make wall File Sorter | No.
| Wall Mounted Sink Mixer | Providing and fixing C.P brass wall mounted sink mixer with swinging spout including cutting and constructing the walls where required.(Jaquar- make) | Each
| Floor Mounted Sink Mixer | Providing and fixing C.P brass Floor mounted sink mixer with swinging spout including cutting and finishing the floor surface where required.(Jaquar- make) | Each
| 40 mm Dia Pipe | 40 mm CPVC Dia Pipe for 3 way sink including all accessorie like 40 mm MS Pipe, 3 no's 40mm union and 3 no's elbow and other neccesarry parts including connections. | Set
| C.P Anglular Stop cock | Supply , Installation, testing and commissioning of Stop Cock / Angular cock for wash basin ,Gyser, as specified by site engineer including all accessories complete in all respect. | Each
| Waste Coupling | Waste Coupling for 3Way sink and Makeline sink | No.
| Waste Flexible Pipe | PVC Waste flexible Pipe of 1.0m length. | No.
| Conceal Cock | Conceal cock for makeline sink (Make Jaquar or equivalent) | No.
| Floor Trap Jali | Providing and fixing of 100 mm square floor trap jali | Each
| Central Hole Jali | Providing and fixing of central hole S.S. jali | Each
| Connector | Providing and fixing of connectors 3 ft. length to water inlet, drainage, RO,Beverage counter, Ice machine, etc. | Nos
| Wc Concealed Cistern | Providing & fixing of Wc concealed cistern of approved model & company. | NO
| Hand Dryer | Providing & fixing of Hand dryer of approved model & company. | NO
| Pvc Curtain | Providing and fixing in position of pvc curtain as per details in drawing or as specified & directed by Site Engineer. | Rn.ft
| MS Box for water motor | Supply, fabrication, Installation and erection of MS Box for water motor. The item also include providing & applying of approved make Primer and Enamel paint as per Site Engineer recommendations. | Kg.
| Fly catcher Installation | Installation of Fly catcher with all necessary fittings. | NO
| SS Pipe + SS plate for KDS stand | Providing and fixing in position SS Pipe + SS plate for KDS stand with necessary support, Cost to include all hardware, fasteners, and rubber / PVC leveller etc. | NO
| Kds Stand | Installation of Kds stand. | NO
| Mop Hanger | Supply & Installation of Mop Hanger with all necessary fittings. | NO
| Lock | Providing Lock for :- Water motor,bike chain,ladder chain,ro shade,odu,ro tank,raw water tank & shutter lock. | NO
| GI Chain | Providing GI Chain for :- Bike & Ladder. | NO
| MS Stand | Providing,fixing & fabricating of ms stand for cable tray & pipe support, with necessary fittings Cost to include all hardware etc. | Kg.
| Pre-Rinse | Providing & fixing of Pre-rinse spray on 3 sink of approved model & company. | NO
| Storage type Gyser | Providing and fixing storage type electric hot water heater made out of heavy gauge steel jacket finished with rust proof baked-on glossy white enamel paint, inside glass lined heavy gauge steel tank, 25 mm thick polyurethane foam insulation, thermostatically controlled immersion heater with pilot neon lamp, replaceable magnesium anode bar, suitable for 8.0 bar maximum working pressure, cold water inlet and hot water outlet pipe, suitable length of electrical cable and 15 amp 3 pin plug top, complete in all respect including testing etc. (Horizontal/Vertical)
|  | 25 Ltrs Capacity | No. | 1 | 16500 | 16500 | 1 | 16500
| Instant type gyser | Providing and fixing Instant type electric hot water heater made out of heavy gauge steel jacket finished with rust proof baked-on glossy white enamel paint, inside glass lined heavy gauge steel tank, 25 mm thick polyurethane foam insulation, thermostatically controlled immersion heater with pilot neon lamp, replaceable magnesium anode bar, suitable for 8.0 bar maximum working pressure, cold water inlet and hot water outlet pipe, suitable length of electrical cable and 15 amp 3 pin plug top, complete in all respect including testing etc. (Horizontal/Vertical)
|  | 3 Ltrs Capacity | No. | 1 | 5000 | 5000
|  | Total |  |  |  | 226170 |  | 196990
|  | Contingency work (Tools and materia entry and material long distance) |  |  |  | 56542.5 |  | 49247.5
|  | Sub Total |  |  |  | 282712.5 |  | 246237.5

## Additional
Sr. No. | Particulars | Unit | Nos. | L | W | Qty | Rate | Amount
1 | P&F of plywood ledge with corian finish | R.Ft. |  | 14.33 |  | 14.33
|  |  |  | 8.08 |  | 8.08
[6 empty] | 22.41 | 2625 | 58826.25
2 | P&F of ply box in laminate finish behind TV | Sq.Ft. |  | 7.08 | 1 | 7.08 | 450 | 3186
3 | P&F of storage above coldroom with MS framework | Sq.Ft. |  | 5.58 | 7.83 | 43.6914 | 2650 | 115782.21
4 | UPS Shelve | R.Ft. |  | 2 |  | 2 | 1250 | 2500
5 | 8" Bundwall for mopstick with tile finish | Sq.Ft. |  | 2.75 | 2 | 5.5 | 460 | 2530
6 | Corecut for coldroom AC piping | Nos. | 1 |  |  | 1 | 3500 | 3500
7 | P&F of ply boxing for DB box behind oven with tile finish and access door | Sq.Ft. |  | 3.25 | 9.75 | 31.6875 | 1550 | 49115.625
8 | Ramp for Coldroom in tilie finish | Job | 1 |  |  | 1 | 5500 | 5500
9 | HPL sheet rate difference | Sq.Ft. |  | 9.67 | 11.33 | 109.5611
|  |  |  | 23.67 | 1.08 | 25.5636
|  |  |  | 2.25 | 11.33 | 25.4925
|  |  |  | 9.83 | 1 | 9.83
[6 empty] | 170.4472 | 550 | 93745.96
10 | Covering above hood with MS sheet & framing finished in paint | Sq.Ft. | 2 | 8 | 2 | 32
|  |  | 2 | 6 | 2 | 24
[6 empty] | 56 | 450 | 25200
11 | Supplying of LED panel light (panasonic make) | Nos. | 12 |  |  | 12 | 550 | 6600
12 | Supplying of hanging light | Nos. | 9 |  |  | 9 | 942 | 8478
13 | Boxing of coloumn near order counter | Sq.Ft. | 4 | 1.5 | 16 | 96 | 1250 | 120000
14 | Ceiling Rework | Sq.Ft. |  | 3 | 3 | 9 | 185 | 1665
15 | Closing of drain line with tile and waterproofing work | Sq.Ft. | 2 | 2 | 2 | 8 | 410 | 3280
16 | Plumbing repairing | Job | 1 |  |  | 1 | 1500 | 1500
17 | P&F of SS grating chamber
| 450X350 | Nos. | 1 |  |  | 1 | 7500 | 7500
| 750X350 | Nos. | 1 |  |  | 1 | 10500 | 10500
| 350X350 | Nos. | 1 |  |  | 1 | 6500 | 6500
18 | Fabrication work for signage | Job | 1 |  |  | 1 | 27500 | 27500
19 | Hood Installation | Nos. | 1 |  |  | 1 | 20350 | 20350
20 | Additional Ducting Work of GMR scope | Job | 1 |  |  | 1 | 48950 | 48950
| Total | [6 empty] | 622709.045

## HVAC Summary Sheet
LOCATION - MOPA AIRPORT - GOA - Domio's International Arrival
S.No. | DESCRIPTION | PO Value | Executed Amount
1 | HVAC High Side | 292961 | 292961
2 | HVAC Low Side | 236287 | 237114
| Total Amount | 529248 | 530075
| GST | 124560.74 | 124709.6
| Total After Tax | 653808.74 | 654784.6

## Hvac High Side
NAME OF PROJECT: Domnios M&G AT GOA
HVAC WORK (HIGH SIDE)
S.NO. | ITEM DESCRIPTION | UNIT | QTY. | SUPPLY | INSTALLATION | SUPPLY | INSTALLATION
A | EQUIPMENTS |  |  | RATE |  | AMOUNT
1 | KITCHEN EXHAUST AIR SCRUBBER
Supply, Installation, Testing and Commissioning of Scrubber each comprising of extract air intake section, electrostatic precipitation technology, dry type air cleaner to remove oil, smoke and fumes from exhaust air, as per the Specifications.
Electrostatic section shall be made of 16 gauge galvanised sheet, high bake epoxy powder coated, washable type SS Filters with aluminium mesh filters, Tungsten wire type type ionizers to create high voltage DC field, aluminum collector plates which should be alternatively charged positive and negative with large collecting area, collection area should not be less than 6.0 sqmt, to work as magnet for charged smoke and oil particles. Average efficiency of 90-95% in single pass as per ASHRAE test method. Electrostatic Precipitator should be able to charge particles from 0.01 micron to 10 microns through solid state power supply. Collector cell should be of permanent type and incorporate slide out facility for easy removal for cleaning. Power supplies shall be 100% solid state and entier unit should be CE Certified. all units shall have shall be equipped with Pulse width modulating (PWM) The system should be fitted with interlock switch for safety. The units should be BMS compatible for Feedback information on Run,Wash and Fault,dry contact point. The system should allow connection to a fan section to achieve velocity between 2.5 - 3.8 m/s across the air cleaner and should units should meet MERV 15 requirements even at velocity of 3.81 m/s (750 FPM)
Operating Voltage : 220V, 50 Hz
Ionizing Voltage : 12 to 13 KVDC
Collector Cell Voltage : 6 to 6.5 KVDC
ESP Power Consumption : Not more than 50W per cell.
Air Moving Capacities are as follows:
| 3000 CFM | No. | 1 | 199000 | 22000 | 199000 | 22000
2 | Ceiling Suspended AHU
Supplying, installing, testing and commissioning of double skin construction draw thru type Ceiling Suspended AIR HANDLING UNITS as per specification, each complete with pre-filter section (90% down to 10 microns), min 4 Row Deep Chilled water coil of copper tube & aluminium fins construction, squirrel cage induction motor, airfoil centrifugal fan belt drive and vibration isolators, coil size shall be selected for a maximum face velocity of 500 feet/minute and static pressure shall be as indicated. The motor selected shall be energy efficient having efficiency (IE2) at full load ranging between 82.5% to 92% in accordance with motor rating as per specification. Motor shall be suitable for 415±10% volts, 50 cycles, 3 phase AC supply. Fan motor assembly (as whole) shall be statically and dynamically balanced to grade G 6.3 as per ISO-1940/AMCA 204-3.All units shall be complete with opposed blade volume control dampers at oulet. Duct flexible connector (fire proof) shall be provided at outlets of AHU. ( Temporary bypass arrangement in Chilled Water Line with related accessories to be considered to facilitate flushing during precommissioning and commissioning of the System).
AHU Tag. Description AHU CFM TR ESP Motor HP
| AHU-01 Domnios 1480 cfm 3.71 15 mm 1 | No. | 1 | 71880 | 15500 | 71880 | 15500
TOTAL | [5 empty] | 270880 | 37500
GRAND TOTAL (SUPPLY+INSTALLATION) | [6 empty] | 308380
Discount | Discount | [5 empty] | 15419
Total After Discount | [6 empty] | 292961
GST | GST |  |  |  |  | 28% | 82029.08
Total After Tax | Total After Tax | [5 empty] | 374990.08

## HVAC Low Side
NAME OF PROJECT: Domnios M&G AT GOA
HVAC WORK (LOW SIDE)
S.NO. | ITEM DESCRIPTION | UNIT | QTY. | RATE | AMOUNT | QTY. | AMOUNT
A | SHEET METAL WORKS:
1 | GI SHEET METAL DUCTING
Supply, Fabrication, Testing, and Commissioning of Factory Fabricated GI Sheet Metal 180GSM Rectangular boxed ducting, Plenums, Cowls, Elbows with turning vanes, Splitters, Reducers, Flanges, Collars etc as per IS standard and installation as per SMACNA standards, The complete ducting shall be provided with MS Supports, Rods, Angles, Flanges, Bracing, Rubber Gaskets, Wooden frames, Canvas Connections, etc. as per drawings and specifications.
GI Sheet Makes : Tata, Jindal, SAIL, Ispat
Make: Rola Star, Zeco & Ductofab
| 18 Gauge GI Sheet Metal Duct (Above 2251mm & Plenum) | Sq.mtr | RO
| 20 Gauge GI Sheet Metal Duct (1501-2250mm) | Sq.mtr | RO
| 22 Gauge GI Sheet Metal Duct (751-1500mm) | Sq.mtr | 10 | 1350 | 13500
| 24 Gauge GI Sheet Metal Duct (0-750mm) | Sq.mtr | 35 | 1150 | 40250 | 52.19 | 60018.5
2 | EXTRUDED ALUMINIUM CEILING GRILLES
Supply, Installation, Testing and Balancing of Powder coated aluminium linear supply air grilles complete with removable inner core as per approved shop drawing and specifications. The area of grille can be of any geometrical shape (Square/rectangular/Linear). The grilles shall be with 15/30/45° deflections as per requirement. The Colour shall be decided and approved by client and architect.
Make: Cosmos, Air Master & System Air
| 100mm Wide Grille | Rmt | 4 | 4518 | 18072 | 5 | 22590
3 | OPPOSED BLADE DAMPER
| SITC of Aluminium Opposed blade dampers black powder coated vertical blades type for supply air collar. The damper should be gear operated type. | Sq.mtr | 0.5 | 8392 | 4196 | 1 | 8392
Make: Cosmos, Air Master & System Air
4 | SS EXHAUST AND FRESH AIR GRILLES
| SITC of 18G S.S 304 Grills adjustable Double Deflector With S.S Volume Control Dampers. Grills to be of Double Deflection Type for ease of deflection on all sides and to have necessary built in Dampers for adjustable nature. | Sq.mtr | 2 | 9000 | 18000
Make: Carryaire / System Air / Dynacraft / Air Master
5 | DOOR TRANSFER GRILLES
SITC of Aluminium extruded powder coated Door transfer grills.
| Door transfer grille (Back to Back) | Sq.mtr | RO
Make: Cosmos, Air Master & System Air
6 | CANVAS CONNECTION
Supply & fixing of flexible Canvas connections between mouth piece and initial piece of ducting. Flexible connections shall be fire resistant made of closely woven, double layer canvass / neoprene coated fibre glass.
| Cabinet Exhaust Fan with Wet Scrubber | Nos. | 2 | 4950 | 9900 | 2 | 9900
| Cabinet Fresh Air Fan | Nos. | 2 | 4950 | 9900 | 2 | 9900
NOTES:
The ducting support should be as per tender specification and additional supports are to be provided by Contractor as decided by Consultant.
Muslin cloth cover for all air outlets during construction.
Pressure testing of complete duct work as per DW/ SMACNA standard.
Silicon sealant for longitudinal & transverse joints as per specification.
Diffusers & grilles shall be powder coated as per color approved by Architect.
B | THERMAL INSULATION
1 | THERMAL INSULATION
| Supply & fixing of Thermal insulation for supply air duct using 13mm thick class " O " Closed cell nitrile rubber with anti-microbial coating on it. Insulation shall have Thermal conductivity of 0.033 W/(m.K) and water vapor permeance of 0.10. Joints should be sealed with 50 mm wide 3 mm thick self adhesive tape. The duct shall be stick with recommended adhesive. | sq.m | 20 | 624 | 12480 | 20.5 | 12792
Make: Armaflex & K-flex
2 | ACOUSTIC INSULATION
| Supply & fixing acoustic insulation for ducting using Class "1" closed cell elastomeric insulation of 10mm thick Nitrile rubber insulation adhesive, longitudinal & transverse joints sealed with adhesive in neat & clean manner. Material shall be processed Nitrile Rubber foam with anti-microbial protection. Insulation shall have thermal conductivity of 0.047 W/(m.K) and density of 140 - 180 kg/m³. | sq.m | 15 | 755 | 11325 | 20.5 | 15477.5
Make: Armaflex & K-flex
3 | THERMAL INSULATION FOR KITCHEN DUCTS
| SITC of Glass Fibre Blanket Insulation material bonded with Thrmosetting Resin, with factory applied laminated aluminium foil of 22 micrns with fibre glass backing. Nominal density : 48 Kg/CuM. Thermal conductivity, < 0.033 W/m.K at 24 degreeC. All Insuation material and adhesives shall be as per Class I for surface spread and in accordance with BS 476, & Class O for non-combustible grade. | sq.m | 20 | 620 | 12400 | 19 | 11780
Makes : UP Twiga, Owens Corning, Supreme
| 50 mm Thick | sq.m | 15 |  | 0
14 | Supplying, installing and testing of UPVC pipe ( heavy duty) with 6 mm thick nitrile rubber insulation with protective coating on condensing water piping and fitting like bends, elbow, tee and union, etc. as per the approved shop drawings and specifications.
14.1 | 25 mm Dia | Rmt | 10 | 330 | 3300 | 10 | 3300
14.2 | 32 mm Dia | Rmt | 3 | 450 | 1350 | 3 | 1350
15 | Supply ,Installation ,Testing and commissioning of ERW heavy duty C Class MS pipes as per IS-1239 upto 6" dia. and as per IS-3589 above 6" dia. cut to required lengths and installed with all welded joints, complete with necessary pipe hot dip galvanized MS supports, GI hangers with rubber lined universal clamps and hangers , fittings like bends, elbows, tees, reducers, matching flanges, neoprene 6 mm thick gaskets, hot dipped galvanized nut & blots & washers ,PUF gutti with U clamp, socket and fittings for instruments and sensors connections etc. ERW pipes shall be with two coats of Zinc Chromate paint for anti-rust including all fittings like valves, flanges and unions, etc. Note : Pipe Measurement are in Pair (Supply + Return) . Quoted rates shall be inclusive of the cost of piping Insulation of Class O rated thermal insulations with one sided factory laminated glass clothed Nitrile Rubber insulation with density 45-60 kg/m3 with covered with two coats of UL Listed lag coating (Low VOC) Anti-fungal, Anti-microbial & vapour barrier for line item sealed with acrylic based food grade sealant.
15.1 | 25 mm dia MS Pipe with 25 mm thick Insulation | Rmt | 3 | 1850 | 5550 | 3 | 5550
15.2 | 40 mm dia MS Pipe with 25 mm thick Insulation | Rmt | 8 | 2150 | 17200 | 8 | 17200
16 | Providing and fixing in position following ball valves
16.1 | 40 mm dia valves | Nos. | 1 | 3300 | 3300 | 1 | 3300
16.2 | 25 mm dia valves | Nos. | RO
17 | Providing and fixing in position the following ‘Y’ Strainers :
17.1 | 40 mm dia strainers | Nos. | 1 | 4500 | 4500 | 1 | 4500
17.2 | 25 mm dia strainers | Nos. | RO
18 | Supplying, installation, testing and commissioning of Auto air vents.
18.1 | 25 mm dia pipes | Nos. | 1 | 1800 | 1800 | 1 | 1800
19 | Providing and fixing in position SS 304 the industrial dial type pressure gauges with gun metal valves. | Nos. | 2 | 3300 | 6600 | 2 | 6600
20 | Providing and fixing in position SS 304 the mercury-in- glass industrial dial type thermometers. | Nos. | 2 | 3300 | 6600 | 2 | 6600
21 | Supply, installation, testing and commissioning of THERMOSTAT for cooling. The thermostat shall be electronic room temperature controller with digital display & fan speed control, capable of providing individual space temperature control for cooling application. The controller shall produce a dual output to cooling coils in response to load change in rooms. The controller shall be designed to modulate two control devices such as 2 way motorized valves for chilled water duty . (minimum of 5 Deg F dead band ) | No. | 1 | 5400 | 5400 | 1 | 5400
22 | Supply, installation, testing and commissioning of Electronic Self Balancing Valve pressure independent with independent type dynamic balancing valve for AHUs with integrated 2 way modulating control valves in a single body. The actuator shall be capable of accepting 2-10 VDC / 4-20 mA electric signal and shall provide similar transduced feedback output signal to control system for flow measurement. The minimum close off pressure actuator must be 1.5 times shut off head of pump 5 bars whichever is maximum. The valves shall be suitable for following pipe sizes:
22.1 | 40 mm dia | No. | 1 | 18600 | 18600 | 1 | 18600
22.2 | 25 mm dia | No. | RO
23 | Supply, Installation, Testing and Commissioning of BMS compatible ultrasonic BTU Meter complete with flanged type water flow meter (pressure drop across water meter not exceeding 0.1 bar at the specified nominal flow rate), temperature sensors, LCD display panel, inbuilt Lithium battery backup with minimum six years life. The units shall be capable to calculate and store maximum values, display flow rates and temperature difference across supply and return. The quoted price shall be inclusive of necessary wiring, conduiting between the flow meter and the display panel. The unit shall be housed in a totally tamper proof box. The size of the BTU meter is as under:
23.1 | 40 mm dia BTU Meter | No. | 0
24 | CONTROL PANEL FOR AHU (WITH DOL / SD STARTER)
Design, manufacture, supply, installation, testing and commissioning of the following cubicle type, dead front, sheet steel, wall mounted control panels including anchoring into the wall, wiring, incoming, earthing & terminating into MCCB in each panel shall be provided by the electrical contractor.
All internal wiring power cabling and copper earthing of air handling unit motors from the panel shall be included.
All outgoing shall be provided with Stop / Manual /Auto selector switch to facilitate operation through BAS. All starters shall be provided with potential free Contact for Connections to Building Automation System.
The panel shall include the following components and accessories.
a. | MCCB as per the ratings given below, suitable for motor duty and able to withstand fault level of 20 KA.
b. | DOL / SD starter as per HP ratings
c. | Terminal block for power distribution.
d. | Contactor, over load relay with built in single phasing protection.
e. | Phase indicating lights and indicating light for ON status.
f. | Digital voltmeter and digital ammeter with selector switches.
g. | Time delay relay for delayed automatic restart of air handling unit motor.
h | For on/off/remote and local operation, 3 pole single throw switch shall be provided in each AHU panel to facilitate override of the automatic operation.
i | All starters shall be provided with suitable potential free contract for connections to the Building Automation System.
The number of AHU control panels shall be as follows.
| Up to 3 HP DOL Starter | No. | 1 | 24500 | 24500 | 1 | 24500
GRAND TOTAL |  |  |  |  | 248723 |  | 249550
Discount |  |  |  |  | 12436 |  | 12436
Total After Discount |  |  |  |  | 236287 |  | 237114
GST | GST |  |  | 18% | 42531.66 |  | 42680.52
Total After Tax | Total After Tax |  |  |  | 278818.66 |  | 279794.52