## Summary
Sr No | Particulars | TFS Amount
1 | Extra Items | 565756.91
Grand Total |  | 565756.91

## BIKANER EXTRA WORK
Sr No | Item Description | Unit | No | L | W | H | QTY | TFS Rates | TFS Amount
Add-1 | Providing and Fixing 20mm thick, 12" wide granite window frame with 6mm champhered edges machine polished edges externally and internally. Rate to include cutting moulding polishing Transport etc. Complete as specified in the drawing to the satisfaction of the Architect Site-in-charge. (required mortar bed is 25mm to 40mm thk) | Rft |  |  |  |  | 28 | 350 | 9800
| Moh area pass through window jamb |  | 4 | 5 |  |  | 20 |  | 0
|  |  | 4 | 2 |  |  | 8 |  | 0
0
| Wooden waffle MOH area |  | 5 | 7.6 |  |  | 38 |  | 0
| Wooden waffle MOH area |  | 5 | 5.16 |  |  | 25.8 |  | 0
| Wooden waffle MOH area |  | 1 | 31.5 |  |  | 31.5 |  | 0
| Wooden waffle MOH area |  | 1 | 16.7 |  |  | 16.7 |  | 0
0
Add-2 | Providing and fixing with wooden frame 4mm thick vineer over 12 mm thick commercial plyboard of approved shade and make by the architect designer and site engineer. | Rft |  |  |  |  | 112 | 715 | 80080
0
0
0
0
0
Add-3 | P/F 12mm toughned glass on patch fitting | Sqft |  |  |  |  | 46.5578 | 550 | 25606.79
| Counter above pc |  | 1 | 0.86 | 9.33 |  | 8.0238 |  | 0
| Back side pc |  | 1 | 0.9 | 9.5 |  | 8.55 |  | 0
| Top pc |  | 4 | 0.9 | 0.9 |  | 3.24 |  | 0
| Hood glass |  | 1 | 2.9 | 5.16 |  | 14.964 |  | 0
| Pass through window |  | 2 | 5.89 | 1 |  | 11.78 |  | 0
0
Add-4 | P/F 18mm HDMR board with m.s frame | Sqft |  |  |  |  | 66.5 | 285 | 18952.5
| Bulkhead back |  | 1 | 19 | 3.5 |  | 66.5 |  | 0
0
Add-5 | Providing & constructing Brick masonry of 230mm thk with CM 1:4 in proper line, level & plumb | Sqft |  |  |  |  | 292.64 | 220 | 64380.8
| Kicthen area |  | 1 | 26.35 | 12 |  | 316.2 |  | 0
| Less window |  | -2 | 5.89 | 2 |  | -23.56 |  | 0
0
| Counter Rhs |  | 1 | 8.1 | 7.86 |  | 63.666 | 0 | 0
0
Add-6 | Providing and fixing 4mm thick vineer over 12 mm thick commercial plyboard with 5mm groove of approved shade and make by the architect designer and site engineer. | Sqft |  |  |  |  | 63.666 | 295 | 18781.47
Add-7 | P/L 3CX2.5 sqmm FRLS wire | Rmtr |  |  |  |  | 585.63 | 165 | 96628.95
| DB to dishwash area geyser(2.5+2.5+2.75+1.5+1.5+.5) |  |  |  | 1 | 11.25 | 11.25 |  | 0
| DB to aircurtain (2.5+2.5+1.5+.7+1.5+2+1) |  |  |  | 1 | 11.7 | 11.7 |  | 0
| DB to freezer (2.5+2+1.5+.23+2.4+1+1.9+1.5) |  |  |  | 1 | 13.03 | 13.03 |  | 0
| DB to freezer (2.5+2+1.5+.23+2.4+1+1.9+1.5+1.4) |  |  |  | 1 | 14.43 | 14.43 |  | 0
| DB to freezer (2.5+2+1.5+.23+2.4+1+1.9+1.5+1.4) |  |  |  | 1 | 14.43 | 14.43 |  | 0
| DB to freezer (2.5+2+1.5+.23+2.4+1+1.9+1.5+1.4+1.4) |  |  |  | 1 | 15.83 | 15.83 |  | 0
| DB to freezer (2.5+2+1.5+.23+2.4+1+1.9+1.5+1.4+1.4+1.2) |  |  |  | 1 | 17.03 | 17.03 |  | 0
| DB to freezer (2.5+2+1.5+.23+2.4+1+1.9+1.5+1.4+1.4+1.2) |  |  |  | 1 | 17.03 | 17.03 |  | 0
| DB to Y4 (2.5+2.5+1.6+9.5+1.5+1.5+1.65+2.25+.3) |  |  |  | 1 | 23.3 | 23.3 |  | 0
| DB to B4 (2.5+2.5+1.6+9.5+1.5+1.5+1.65+2.25+.7+.3) |  |  |  | 1 | 24 | 24 |  | 0
| DB to R4 (2.5+2.5+1.6+9.5+1.5+1.5+1.65+2.25+1.3+.3) |  |  |  | 1 | 24.6 | 24.6 |  | 0
| DB to Y5 (2.5+2.5+1.6+9.5+1.5+1.5+1.65+2.25+1.3+.3) |  |  |  | 1 | 24.6 | 24.6 |  | 0
| DB to B5 (2.5+2.5+1.6+9.5+1.5+1.5+1.65+2.25+2.1+.3) |  |  |  | 1 | 25.4 | 25.4 |  | 0
| DB to B6 (2.5+2.5+1.6+9.5+1.5+1.5+1.65+2.25+2.1+.3) |  |  |  | 1 | 25.4 | 25.4 |  | 0
| DB to Y6 (2.5+2.5+1.6+9.5+1.5+1.5+1.65+2.25+2.6+.3) |  |  |  | 1 | 25.9 | 25.9 |  | 0
| DB to Y7 (2.5+2.5+1.6+9.5+1.5+1.5+1.65+2.25+3.1+.3) |  |  |  | 1 | 26.4 | 26.4 |  | 0
| DB to B7 (2.5+2.5+1.6+9.5+1.5+1.5+1.65+2.25+3.4+.3) |  |  |  | 1 | 26.7 | 26.7 |  | 0
| DB to R6 (2.5+2.5+1.6+9.5+1.5+1.5+1.65+2.25+3.6+.3) |  |  |  | 1 | 26.9 | 26.9 |  | 0
| DB to R5 (2.5+2.5+1.6+9.5+1.5+1.5+1.65+2.25+3.7+.3) |  |  |  | 1 | 27 | 27 |  | 0
| DB to B8 (2.5+2.5+1.6+9.5+1.5+1.5+1.65+2.25+3.89+.3) |  |  |  | 1 | 27.19 | 27.19 |  | 0
| DB to Y8 (2.5+2.5+1.6+9.5+1.5+1.5+1.65+2.25+5.25+.3) |  |  |  | 2 | 28.55 | 57.1 |  | 0
| DB to geyser (2.5+2.5+1.5+1.5+2+1.2+.3) |  |  |  | 1 | 11.5 | 11.5 |  | 0
| Loop |  |  |  | 1 | 2 | 2 |  | 0
| DB to sighnage (2.5+2.5+1.6+9.5+1.5+1.5+1.65+2.77+1.5+2) |  |  |  | 1 | 27.02 | 27.02 |  | 0
| DB to hood (2.5+2.5+4+1.5+1+.3) |  |  |  | 1 | 11.8 | 11.8 |  | 0
| Loop (1.5+2.3+1.5) |  |  |  | 1 | 5.3 | 5.3 |  | 0
| DB to counter back wall point | [7 empty] | 0
| (2.5+2.5+4.1+1.5+3.4+1+1.5+3+2.44+.3) |  |  |  | 1 | 22.24 | 22.24 |  | 0
| DB to pos counter(2.5+2.5+1.6+9.5+1.5+1.5+1.65+1.4+1.6+2.5+.3) |  |  |  | 1 | 26.55 | 26.55 |  | 0
0
Add-8 | P/L 6.0 sqmm FRLS wire | Rmtr |  |  |  |  | 17.75 | 135 | 2396.25
| DB to Fresh air (3.5+2.5+5+1+3.75+1.5+.5) |  |  |  | 1 | 17.75 | 17.75 |  | 0
0
0
Add-9 | P/F VTPN DB AS PER SITE DETAILS. | [7 empty] | 0
| 12 WAY VTPN - LPDB -AS PER SITE DETAILS. | No |  |  | 1 | 1 | 1 | 39000 | 39000
| Incomer : 63A, FP, MCCB, 25kA: 1 Nos- Okey As per site | [7 empty] | 0
| Outgoings : 10/16/20/25 A SP MCB "C" Type - 15 Nos.-All Blanker Needs to removed and MCB needs to installed for fucture. | [7 empty] | 0
| Outgoings : 40A TP MCCB "C" Type - 2 Nos. | [7 empty] | 0
| 8 WAY VTPN - LPDB -AS PER SITE DETAILS. | No |  |  | 1 | 1 | 1 | 39000 | 39000
| Incomer : 63A, FP, MCCB, 25kA: 1 Nos- Okey As per site | [7 empty] | 0
| Outgoings : 10/16/20/25 A SP MCB "C" Type -33 Nos. All Blanker Needs to removed and MCB needs to installed for fucture. | [7 empty] | 0
Add-10 | P/L Data cable | Rmtr |  |  |  |  | 234.8 | 52 | 12209.6
| (6+5+20.1+6.5+2+3.5+9.5+12.5+5.5+1.5+3.6+1+3) |  |  |  | 4 | 58.7 | 234.8 |  | 0
0
Add-11 | 5A point for GLDS | No | [6 empty] | 0
| 5A point for wall fan | No | [6 empty] | 0
| Wooden waffle MOH area |  | 5 | 7.6 |  |  | 38 | 0 | 0
| Wooden waffle MOH area |  | 5 | 5.16 |  |  | 25.8 |  | 0
| Wooden waffle MOH area |  | 1 | 31.5 |  |  | 31.5 |  | 0
| Wooden waffle MOH area |  | 1 | 16.7 |  |  | 16.7 |  | 0
| Counter Rhs |  | 1 | 8.1 | 7.86 |  | 63.666 |  | 0
Add-12 | Applying Polish on Vineer Surface (Front LHS Wall paneling ADD-6 + Rafters ADD-2) | sft |  |  |  |  | 175.666 |  | 0
0
Add-13 | P/F Soap Dispencer | No | [6 empty] | 0
Add-14 | Installation of spot lights | Nos | 18 |  |  | 1 | 18 | 200 | 3600
Add-15 | Installation of 2'x2' light | Nos | 6 |  |  | 1 | 6 | 250 | 1500
Add-16 | Cutouts in wall for ducting | Nos | 2 |  |  | 1 | 2 | 2500 | 5000
Add-17 | Providing & fixing of DMB Box | SFT | 8.8 |  |  | 1 | 8.8 | 1200 | 10560
Add-18 | Grease trap installation with material | Nos | 1 |  |  | 1 | 1 | 3000 | 3000
Add-19 | P&F Seekh Hanging Rod | Nos | 1 |  |  | 1 | 1 | 850 | 850
Add-20 | Strip Curtain hanging | Nos | 1 |  |  | 1 | 1 | 500 | 500
Add-21 | Wooden Partition (Laminated) behind Hood in front lane | L/S | 1 |  |  | 1 | 1 | 2500 | 2500
Add-22 | Wooden partition above Exhaust Hoods | L/s | 1 |  |  | 1 | 1 | 5000 | 5000
Add-23 | P/L 2Cx4sqmm+1Cx1.5sqmm | [7 empty] | 0
| Basement UPS DB to Bikaner DB | [7 empty] | 0
| (6+3.9+19.44+6.44+1+1+3.5+3.5+3.5+3.5+2+2) | Rmtr |  |  |  | 1 | 55.78 | 225 | 12550.5
0
ADD-24 | P/L 3Cx4sqmm | [5 empty] | 107.95 | 439 | 47390.05
| DB to outdoor 1 (.5+4+3.5+4+1) |  |  |  |  | 13 | 13 |  | 0
| DB to outdoor 2 (.5+3+2.5+4+1) |  |  |  |  | 11 | 11 |  | 0
| DB to outdoor 3 (.5+2+2.5+4+1) |  |  |  |  | 10 | 10 |  | 0
| DB to outdoor 4 (.5+3.5+4+1) |  |  |  |  | 9 | 9 |  | 0
| DB to outdoor 5 (.5+2.5+4+1) |  |  |  |  | 8 | 8 |  | 0
| DB to outdoor 6 (.5+2+3.5+1) |  |  |  |  | 7 | 7 |  | 0
| DB to outdoor 7 (1.5+3.5+1) |  |  |  |  | 6 | 6 |  | 0
| DB to outdoor 8 (1.5+2.5+2.2+1.5+1) |  |  |  |  | 8.7 | 8.7 |  | 0
| Db to cold ben merry(2.5+2.5+1.5+1.5+6.5+2+2.5+1) |  |  |  |  | 20 | 20 |  | 0
| DB to exhust (2.5+2.5+5+1+2.75+1.5) |  |  |  |  | 15.25 | 15.25 |  | 0
0
Add-25 | P/F 32A 4 ploe weather proof box with enclosure | No |  |  |  |  | 2 | 8000 | 16000
0
Add-26 | Supplying and erecting PVC armoured cable 2 core 1.5 sq. mm FRLS copper conductor complete erected on wall / celling as per specification | Rmtr |  |  |  |  | 148 | 140 | 20720
| MCP to Smoke 1 (3+2+2) |  |  |  |  | 1 | 7 |  | 0
| Smoke 2 (3+2+2) |  |  |  |  | 1 | 7 |  | 0
| Smoke 3 (3+2+2) |  |  |  |  | 1 | 7 |  | 0
| Smoke 4 (1+2+2+2.7) |  |  |  |  | 1 | 7.7 |  | 0
| Smoke 5 (2.9+2+2) |  |  |  |  | 1 | 6.9 |  | 0
| Smoke 6 (1.2+2+2) |  |  |  |  | 1 | 6.1 |  | 0
| Smoke 7 (2.5+2+2) |  |  |  |  | 1 | 6.5 |  | 0
| Main zone to Bikanerwala hooter | [7 empty] | 0
| (1.5+3+5+5++5+2+5+7+5+4+2+5.4) |  |  |  | 2 | 49.9 | 99.8 |  | 0
0
Add-27 | Supplying, installation, testing & commissioning of sprinkler flexible pipe (UL Listed) of stainless steel complete with 15 NPT on reducer thread with maximum working pressure of 175 PSI test pressure of 875 PSI (Burst) with branch line (Inlet) 25mm NPT male thread to sprinkler head (Outlet) 15mm NPT female thread with reducer, nipple, 2 side brackets, center bracket, stockbar of following sizes complete as required. | No |  |  |  |  | 8 | 1350 | 10800
| 1500 mm Long Sprinkler flexible pipe | [5 empty] | 8 |  | 0
0
Add-28 | Supply, installation, testing & commissioning of Conventional Type optical Smoke Detector with inbuilt scattered light measurement, rate of rise and fixed temperature based technology and LED indication should be on the centre of the detector with mounting base complete as required. | No |  |  |  |  | 7 | 2000 | 14000
0
Add-29 | Supply, installation, testing & commissioning of conventional Manual Call Point (break glass type)complete with push button,enclosed in box with provision of conduit/cable coupling.The unit to be painted fire red outside ,white inside and written "in case of fire break glass" or as required. | No |  |  |  |  | 1 | 1200 | 1200
0
Add-30 | Supply, installation, testing & commissioning of Conventional Hooter cum Strobe complete as required.110 cd light & 85 dB adjustable at different locations complete with all fixing accessories etc under false ceiling ,roof,wall etc complete as required. | No |  |  |  |  | 1 | 1200 | 1200
0
Add-31 | PVC pipe and chasing in wall | Rmtr |  |  |  |  | 2 | 75 | 150
0
Add=32 | Making core cuts of 125mm dia for main drain tap off | nos |  |  |  |  | 2 | 1200 | 2400
0
TOTAL AMOUNT | [8 empty] | 565756.91