## Summary-Basement's-1
Sr No | Particulars | TFS Amount
1 | Basement's Extra Work | 900355.5975
Grand Total of Basement's |  | 900355.5975

## Basement
SR.NO. | ITEM | DESCRIPTION | UNIT | BOQ QTY | No | L | W/H | SITE QTY | TFS Rates | Material Rate | TFS -Amount
1 | Kitchen equipments unloading/ shifting | Unloading/Shifitng/ fixing of kitchen equipments. | JOB | 1 | [6 empty] | 0
2 | Kota Skirting | Fixing & laying of 150mm high kota stone for skirting with bedding of appropriate approved make adhesive & colour joint filler inclusive of making all groove/chamfering/rounding/hole where ever required, in proper line and level in all direction, polishing/finishing/cleaning etc. Complete as per detail drawing, specification and as directed by PMC. | RFT | 280 |  |  |  | 274.9 | 100 |  | 27490
|  | Admin room |  |  | 2 | 15.85 |  | 31.7 |  |  | 0
[5 empty] | 2 | 12.75 |  | 25.5 |  |  | 0
|  | Less door |  |  | -1 | 3.5 |  | -3.5 |  |  | 0
|  | Admin room front gallery |  |  | 2 | 17.08 |  | 34.16 |  |  | 0
|  | Less door |  |  | -2 | 3.5 |  | -7 |  |  | 0
|  | DB wall |  |  | 1 | 2.75 |  | 2.75 |  |  | 0
|  | Column |  |  | 1 | 2.5 |  | 2.5 |  |  | 0
[5 empty] | 1 | 3.08 |  | 3.08 |  |  | 0
|  | Coldroom outdoor wall |  |  | 1 | 11.1 |  | 11.1 |  |  | 0
|  | Dry sotre outside wall |  |  | 1 | 17.58 |  | 17.58 |  |  | 0
[5 empty] | -1 | 3.5 |  | -3.5 |  |  | 0
[5 empty] | 1 | 19.6 |  | 19.6 |  |  | 0
|  | Column |  |  | 3 | 0.82 |  | 2.46 |  |  | 0
|  | Below stair |  |  | 1 | 9.5 |  | 9.5 |  |  | 0
[5 empty] | 1 | 11.3 |  | 11.3 |  |  | 0
[5 empty] | 1 | 1.08 |  | 1.08 |  |  | 0
|  | Stair case side |  |  | 1 | 5 |  | 5 |  |  | 0
|  | Lift wall |  |  | 1 | 10 |  | 10 |  |  | 0
|  | Less lift opening |  |  | -2 | 3.5 |  | -7 |  |  | 0
[5 empty] | 1 | 5.75 |  | 5.75 |  |  | 0
|  | Changing room outside walll |  |  | 1 | 10 |  | 10 |  |  | 0
|  | Less door |  |  | -1 | 3.5 |  | -3.5 |  |  | 0
|  | Changing room inside |  |  | 2 | 13.25 |  | 26.5 |  |  | 0
[5 empty] | 2 | 11.92 |  | 23.84 |  |  | 0
|  | Less door |  |  | -1 | 3.5 |  | -3.5 |  |  | 0
|  | Dry store inside |  |  | 2 | 16.5 |  | 33 |  |  | 0
[5 empty] | 2 | 10 |  | 20 |  |  | 0
|  | Less door |  |  | -1 | 3.5 |  | -3.5 |  |  | 0
[8 empty] | 274.9 |  |  | 0
3 | Kota Flooring (including basement & Dominos cold rooms) | Kota stone slab flooring over 20 mm (average) thick base laid over and jointed with grey cement slurry mixed with pigment to match the shade of the slab including rubbing and polishing complete with base of cement mortar 1 : 4 (1 cement : 4 coarse sand) : | SFT | 1200 |  |  |  | 1328.9939 | 145 |  | 192704.1155
|  | Bikanerwala coldroom inside |  |  | 1 | 11.15 | 14.5 | 161.675 |  |  | 0
|  | Less column |  |  | -2 | 2.5 | 2 | -10 |  |  | 0
|  | Dry store |  |  | 1 | 10 | 16.5 | 165 |  |  | 0
|  | Dominos coldroom |  |  | 1 | 10.25 | 11.75 | 120.4375 |  |  | 0
|  | Dry store front gallery |  |  | 1 | 11.77 | 33 | 388.41 |  |  | 0
|  | Less changing room area |  |  | -1 | 9.89 | 5.66 | -55.9774 |  |  | 0
|  | Less stair case |  |  | -1 | 1 | 5.5 | -5.5 |  |  | 0
|  | Less granite |  |  | -1 | 3.5 | 1 | -3.5 |  |  | 0
|  | Less column |  |  | -1 | 0.82 | 1.41 | -1.1562 |  |  | 0
|  | Stair case below |  |  | 1 | 6.75 | 9.4 | 63.45 |  |  | 0
|  | Changing room inside |  |  | 1 | 11.92 | 13.25 | 157.94 |  |  | 0
|  | Coldroom outdoor side area |  |  | 1 | 19.5 | 3.75 | 73.125 |  |  | 0
|  | Admin room front gallery |  |  | 1 | 4.25 | 17.08 | 72.59 |  |  | 0
|  | Admin room inside |  |  | 1 | 16 | 12.75 | 204 |  |  | 0
|  | Less column |  |  | -1 | 1 | 1.5 | -1.5 |  |  | 0
0
4 | PCC Work | Providing and laying up to 50-75 mm thick cement concrete flooring with 1:2:4 cement concrete laid to proper level and slope in alternate bays including compactions, filling joints, or as directed, finishing smooth with cement Mortar 1:1 of sufficient minimum thickness to give a smooth & even surface and curing etc. complete as per architects instructions. | Sq.Ft | 1200 |  |  |  | 1328.9939 | 60 |  | 79739.634
|  | Bikanerwala coldroom inside |  |  | 1 | 11.15 | 14.5 | 161.675 |  |  | 0
|  | Less column |  |  | -2 | 2.5 | 2 | -10 |  |  | 0
|  | Dry store |  |  | 1 | 10 | 16.5 | 165 |  |  | 0
|  | Dominos coldroom |  |  | 1 | 10.25 | 11.75 | 120.4375 |  |  | 0
|  | Dry store front gallery |  |  | 1 | 11.77 | 33 | 388.41 |  |  | 0
|  | Less changing room area |  |  | -1 | 9.89 | 5.66 | -55.9774 |  |  | 0
|  | Less stair case |  |  | -1 | 1 | 5.5 | -5.5 |  |  | 0
|  | Less granite |  |  | -1 | 3.5 | 1 | -3.5 |  |  | 0
|  | Less column |  |  | -1 | 0.82 | 1.41 | -1.1562 |  |  | 0
|  | Stair case below |  |  | 1 | 6.75 | 9.4 | 63.45 |  |  | 0
|  | Changing room inside |  |  | 1 | 11.92 | 13.25 | 157.94 |  |  | 0
|  | Coldroom outdoor side area |  |  | 1 | 19.5 | 3.75 | 73.125 |  |  | 0
|  | Admin room front gallery |  |  | 1 | 4.25 | 17.08 | 72.59 |  |  | 0
|  | Admin room inside |  |  | 1 | 16 | 12.75 | 204 |  |  | 0
|  | Less column |  |  | -1 | 1 | 1.5 | -1.5 |  |  | 0
0
4 | Flush Doors | Supply and installation of the 35mm thick flush door for the designated area and chaukhat of 150 x 75mm in solid wood. The door will be finished (standard thickness) with 1mm thick approved shade laminate by the architect or designer. The door will be equipped with, hinges, handles, vision panels and locks, as per project requirements. | Nos | 3 | 3 |  |  | 3 | 20000 | 17100 | 60000
5 | Work Station for Admin Room | P&F work station as per site engineers directions with approved laminate on all carcus ant top | SFT | 40 |  |  |  | 39.625 | 500 | 19828 | 19812.5
|  | Admin room |  |  | 1 | 2.5 | 15.85 | 39.625 |  |  | 0
0
6 | Over Head Cabinets for admin room | P&F work station as per site engineers directions with approved laminate on all carcus & with Doors anf complete with all necessary hardware | SFT | 48 |  |  |  | 39.625 | 650 | 29288 | 25756.25
|  | Admin room |  |  | 1 | 2.5 | 15.85 | 39.625 |  |  | 0
0
7 | Managers Table with Pedastels | P&F modular managers table with pedastal | Nos | 1 |  |  |  | 1 | 12149 |  | 12149
|  | Manager table |  |  | 1 |  |  | 1 |  |  | 0
0
8 | Lose pedastals | P&F modular lose pedastals | Nos | 3 | 1 |  |  | 3 | 5763 |  | 17289
9 | Changing room cubicles | P&F Cubicles for changing room | Nos | 2 | 1 |  |  | 2 | 20248 |  | 40496
10 | Light Fittings | P&F Light fittings of approved make & specifications in Changing Room, Store Room, Admin Room | Nos | 18 | 1 |  |  | 22 | 1100 |  | 24200
11 | Wall Fan | P&F Wall Fan | Nos | 2 | 1 |  |  | 3 | 1900 |  | 5700
|  | 2 No in basement and 1 no in bikaner store | [8 empty] | 0
12 | Exhaust Fan | P&F Exhaust Fan | Nos | 2 | 1 |  |  | 2 | 1900 |  | 3800
13 | Ceiling Fan | P&F Ceiling Fan | Nos | 1 | 1 |  |  | 1 | 2000 |  | 2000
15 | Cable | P&F Aluminium Armoured cable of 4C x 25 sqmm | RMT | 58.5 | 1 |  |  | 58.5 | 380 | 365 | 22230
|  | (3+3+5+18+6+19.5+2+2) | [5 empty] | 58.5 |  |  | 0
|  | Terminations |  |  | 1 |  |  | 2 | 400 |  | 800
16 | Conduiting | [9 empty] | 0
17 | TPN DB | 8 WAY TPN - LPDB( Normal DB )AS per site detials Material Used | nos | 1 | 1 |  |  | 1 | 39000 |  | 39000
|  | Incomer : 63A, FP, MCB, 10kA: 1 Nos-ok | [8 empty] | 0
|  | Sub Incomer : 40A, TP, MCCB, 100mA: 2 Nos | [8 empty] | 0
|  | Outgoings : 10/16/20/25 A SP MCB "C" Type - 15Nos. | [8 empty] | 0
18 | Cable Tray | P&F Cable tray of size 150 x 40 | RMT | 90 |  |  |  | 102.96 | 500 | 349 | 51480
|  | (6.21+1+23.2+3.05+3.95+15+1+1-2.93) |  |  | 2 |  | 51.48 | 102.96 |  |  | 0
0
0
19 | Wall Paint | Providing & applying two or more coats of approved make and shade over walls etc. after preparing the surface with a coat of primer and 4-6mm thick plaster of Paris punning to give a smooth and even surface etc. | SFT | 3100 |  |  |  | 4551.6272 | 40 | 21 | 182065.088
|  | Above coldroom |  |  | 1 | 12 | 2.66 | 31.92 |  |  | 0
|  | Dry store entry outside |  |  | 1 | 10.16 | 17.25 | 175.26 |  |  | 0
|  | Less door |  |  | -1 | 3 | 7 | -21 |  |  | 0
|  | Dry store front ceiling |  |  | 1 | 6.25 | 30 | 187.5 |  |  | 0
|  | Beam |  |  | 4 | 1.5 | 6.25 | 37.5 |  |  | 0
|  | Coldroom outdoor wall |  |  | 1 | 10.16 | 17.9 | 181.864 |  |  | 0
|  | Less gallery opening |  |  | 1 | 4 | 8.75 | 35 |  |  | 0
|  | Column |  |  | 1 | 1.5 | 10.16 | 15.24 |  |  | 0
|  | Admin room front gallery |  |  | 2 | 10.16 | 17.04 | 346.2528 |  |  | 0
|  | Less door |  |  | -2 | 3 | 7 | -42 |  |  | 0
[5 empty] | 1 | 4.54 | 10.16 | 46.1264 |  |  | 0
|  | Beam |  |  | 2 | 4.5 | 2 | 18 |  |  | 0
|  | Admin room lhs and rhs wall |  |  | 2 | 10.2 | 15.65 | 319.26 |  |  | 0
[5 empty] | 2 | 12.75 | 10.2 | 260.1 |  |  | 0
|  | Less door |  |  | -1 | 3 | 7 | -21 |  |  | 0
|  | Beam |  |  | 2 | 2.5 | 12.75 | 63.75 |  |  | 0
|  | Changing room inside wall |  |  | 2 | 13.25 | 10.16 | 269.24 |  |  | 0
[5 empty] | 2 | 11.9 | 10.16 | 241.808 |  |  | 0
|  | Less door |  |  | -1 | 3 | 7 | -21 |  |  | 0
|  | Beam |  |  | 2 | 1.5 | 12.25 | 36.75 |  |  | 0
|  | Dry store |  |  | 2 | 16.5 | 10.16 | 335.28 |  |  | 0
|  | Less door |  |  | -1 | 3.5 | 7 | -24.5 |  |  | 0
[5 empty] | 2 | 10 | 10.16 | 203.2 |  |  | 0
|  | Beam |  |  | 2 | 1 | 10 | 20 |  |  | 0
[5 empty] | 2 | 1 | 16 | 32 |  |  | 0
|  | Stair case bottom |  |  | 1 | 4 | 10.5 | 42 |  |  | 0
|  | Stair case ceiling |  |  | 1 | 4 | 3 | 12 |  |  | 0
|  | Stair case ceiling |  |  | 1 | 4 | 5.8 | 23.2 |  |  | 0
|  | Front wall |  |  | 1 | 9.4 | 5.25 | 49.35 |  |  | 0
|  | RHS wall |  |  | 1 | 4.25 | 5.25 | 22.3125 |  |  | 0
|  | RHS traingle wall |  |  | 1 | 7.5 | 7.9 | 59.25 |  |  | 0
|  | Staircase bottom ceiling |  |  | 1 | 4 | 8.62 | 34.48 |  |  | 0
|  | Column |  |  | 1 | 1 | 9.5 | 9.5 |  |  | 0
|  | Column |  |  | 1 | 1.5 | 8.5 | 12.75 |  |  | 0
|  | Column |  |  | 1 | 1 | 10.16 | 10.16 |  |  | 0
|  | Beam top side |  |  | 1 | 8.75 | 1.75 | 15.3125 |  |  | 0
|  | Beam bottom |  |  | 1 | 23.25 | 2.25 | 52.3125 |  |  | 0
|  | Column next coldroom side wall |  |  | 1 | 6.5 | 10.16 | 66.04 |  |  | 0
|  | Changing room entry outside |  |  | 1 | 13.75 | 10.2 | 140.25 |  |  | 0
|  | Less door |  |  | -1 | 3 | 7 | -21 |  |  | 0
|  | Lift front lhs wall |  |  | 1 | 5.75 | 10.2 | 58.65 |  |  | 0
|  | Lift wall |  |  | 1 | 13 | 10.2 | 132.6 |  |  | 0
|  | Less lift opening |  |  | -2 | 3 | 7 | -42 |  |  | 0
|  | Lift rhs wall |  |  | 1 | 5.5 | 10.2 | 56.1 |  |  | 0
|  | Stair case lhs wall |  |  | 1 | 13.5 | 8 | 108 |  |  | 0
|  | Next wall glass side |  |  | 1 | 5.5 | 11.16 | 61.38 |  |  | 0
|  | Window side column |  |  | 1 | 0.5 | 7.5 | 3.75 |  |  | 0
|  | Window side column |  |  | 1 | 1.16 | 3 | 3.48 |  |  | 0
|  | Stair case ceiling |  |  | 1 | 4 | 9.5 | 38 |  |  | 0
[5 empty] | 1 | 5.5 | 11.16 | 61.38 |  |  | 0
|  | Stair |  |  | 1 | 13.5 | 8.25 | 111.375 |  |  | 0
|  | Celing |  |  | 2 | 9.5 | 5 | 95 |  |  | 0
|  | Second floor celing |  |  | 1 | 10.51 | 7.85 | 82.5035 |  |  | 0
|  | Changing room ceiling |  |  | 1 | 11.92 | 13.25 | 157.94 |  |  | 0
|  | Dry store ceiling |  |  | 1 | 10 | 16.5 | 165 |  |  | 0
|  | Admin room ceiling |  |  | 1 | 12.75 | 16 | 204 |  |  | 0
0
| Basement electrical | [9 empty] | 0
20 |  | P/L 3Cx1.5sqmm | Rmtr |  |  |  | 39.06 | 39.06 | 130 |  | 5077.8
|  | Coldroom to DB (3+6.83+1+5.87+1.33+1.5) |  |  | 2 | 19.53 | 39.06 |  |  |  | 0
0
|  | P/L 3Cx2.5sqmm |  |  |  |  | 132 | 132 | 165 | 95 | 21780
|  | Store room to DB(1+4.5+1+4.24+1.33+1.5) |  |  | 2 | 13.57 | 27.14 |  |  |  | 0
|  | Changing room to DB(1.46+1+7.3+1.33+1.5) |  |  | 2 | 12.59 | 25.18 |  |  |  | 0
|  | Admin room entry door LHS(1.94+2.5+1.33+1.5) |  |  | 2 | 7.27 | 14.54 |  |  |  | 0
|  | Server rack to DB(2.84+3.2+.4+4.5+1.33+1.5) |  |  | 2 | 13.77 | 27.54 |  |  |  | 0
|  | Admin table to DB(1+1.5+3.5+4+4.8) |  |  | 2 | 14.8 | 29.6 |  |  |  | 0
|  | UPS to server rack |  |  | 2 | 4 | 8 |  |  |  | 0
0
21 |  | P/L 4Cx4sqmm |  |  |  |  | 16.16 | 16.16 | 546 |  | 8823.36
|  | DB to coldroom outdoor(2+1.33+2.9+1.5) |  |  | 1 | 7.73 | 7.73 |  |  |  | 0
|  | DB to coldroom outdoor(2+1.33+3.6+1.5) |  |  | 1 | 8.43 | 8.43 |  |  |  | 0
0
22 |  | Cat 6 Wire for camera |  |  |  |  | 68 | 68 | 0 |  | 0
|  | (2+2+5+2+5+3+5) |  |  | 1 | 24 | 24 |  |  |  | 0
|  | (3+6+2+5+3+5) |  |  | 1 | 24 | 24 |  |  |  | 0
|  | (5+2+5+3+5) |  |  | 1 | 20 | 20 |  |  |  | 0
0
0
23 |  | 10A Point UPS point | No |  | 1 | 10 | 10 | 10 | 350 |  | 3500
0
24 |  | 16A point Switch socket | No |  | 1 | 11 | 11 | 11 | 450 |  | 4950
0
25 |  | UPS input Box | No |  | 1 | 1 | 1 | 1 | 800 |  | 800
0
26 |  | 6A point in store room | No |  | 1 | 9 | 9 | 9 | 350 |  | 3150
0
27 |  | P/L 6sqmm earthing wire | Rmtr |  | 1 | 25 | 25 | 25 | 135 | 87 | 3375
0
28 |  | P/F Basement bus bar | No |  | 1 | 1 | 1 | 1 | 2000 |  | 2000
29 |  | Coldroom front 12" Width Granite ramp | SFT |  | 1 |  | 3 | 3 | 350 |  | 1050
30 |  | P/L 3cX2.5sqmm FRLS wire |  |  |  |  | 68.09 | 68.09 | 165 | 95 | 11234.85
|  | RO area basement DB to terrace (2+1+3+15.25+2.64+16+8+9.7+3+3+3+1.5) |  |  |  |  | 68.09 |  |  |  | 0
31 |  | P/F Basement UPS input output 32A enclosure box | No |  |  |  | 6 | 6 | 1000 |  | 6000
32 |  | Supplying and erecting PVC armoured cable 2 core 1.5 sq. mm FRLS copper conductor complete erected on wall / celling as per specification / Red fire cable | Rmtr |  |  |  | 19.9 | 19.9 | 140 |  | 2786
|  | Admin room smoke 1 (2.3) |  |  |  |  | 2.3 |  |  |  | 0
|  | Smoke 2 (2+.6+.6) |  |  |  |  | 3.2 |  |  |  | 0
|  | Smoke 3 (1.6+2.7) |  |  |  |  | 4.3 |  |  |  | 0
|  | Dry store+Common passage+Changing room Smoke 4 (2.7+.6) |  |  |  |  | 3.3 |  |  |  | 0
|  | Smoke 5 (2.2) |  |  |  |  | 2.2 |  |  |  | 0
|  | Smoke 6 (2+2.6) |  |  |  |  | 4.6 |  |  |  | 0
0
33 |  | Pendent Sprinler | No |  |  |  | 9 |  | 470 | 4230 | 4230 | 38070 | 33840 | OK
0
34 |  | Supply, laying, testing & Commissioning of 'C' class heavy duty MS pipe conforming to IS 3589 / 1239 for hydrent and sprinkler applications including fittings like elbows, tees, flanges, tapers, nuts bolts, gaskets etc. fixing the pipe on the wall/ceiling with suitable clamps, U bolt and including painting of two coats of Red Oxide , painting with two or more coats of synthetic enamel paint of Post office red shade complete as required.The installation includes all civil openings , breakages and making good the same. ( Final Quantity Measure as per site after working ) | Rmtr | [7 empty] | 0
|  | 65mm |  |  |  |  | 10.5 | 10.5 | 910 |  | 9555
|  | Fire Basement (4+5+1.5) |  |  |  |  | 10.5 |  |  |  | 0
0
|  | 25mm |  |  |  |  | 12.4 | 12.4 | 430 |  | 5332
|  | Fire basement (1.9+1.5+3+3+3) |  |  |  |  | 12.4 |  |  |  | 0
|  | TOTAL AMOUNT | [8 empty] | 900355.5975

## Sheet-1 (hidden)
| Description | Purchase | Installation | Amount | 20% O/H & profit | Total Amount
7 | Managers Table with Pedastels | 9204 | 920.4 | 10124.4 | 2024.88 | 12149.28
8 | Lose pedastals | 4366 | 436.6 | 4802.6 | 960.52 | 5763.12
9 | Changing room cubicles | 15340 | 1534 | 16874 | 3374.8 | 20248.8
| Description | Base Rate | Unit | 3% Wastage | Hardware/Fitting | Labour Charges | 2% Tools & Plants | 1% Transport Charges | Amount | 20% O/H & profit | Total Amount
20 | P/L 3Cx1.5sqmm | 21.6 | Mtr | 0.648 | 10 | 35 | 0.432 | 0.216 | 67.896 | 13.5792 | 81.4752
| 25 mm PVC Counduit | 22 | Mtr | 0.66 | 10 | 20 | 0.44 | 0.44 | 53.54 | 10.708 | 64.248
145.7232
21 | P/L 3CX2.5 sqmm FRLS wire | 105.21 | Mtr | 3.1563 | 10 | 35 | 2.1042 | 1.0521 | 156.5226 | 31.3045 | 187.8271
| 25 mm PVC Counduit | 22 | Mtr | 0.66 | 10 | 20 | 0.44 | 0.44 | 53.54 | 10.708 | 64.248
252.0751
22 | P/L 4Cx4sqmm | 336.72 | Mtr | 10.1016 | 10 | 35 | 6.7344 | 3.3672 | 401.9232 | 80.3846 | 482.3078
| 25 mm PVC Counduit | 22 | Mtr | 0.66 | 10 | 20 | 0.44 | 0.44 | 53.54 | 10.708 | 64.248
546.5558
28 | P/L 6.0 sqmm FRLS wire | 84.18 | Mtr | 2.5254 | 10 | 20 | 1.6836 | 1.6836 | 120.0726 | 24.0145 | 144.0871