## Summary
Sr No | Particulars | RRR Amount
1 | Extra Items | 193867.3869
Grand Total of Karim's Outlet's |  | 193867.3869

## KARIME EXTRA WORK JMS
Sr No | Item Description |  | No | L | W | QTY | TFS Rates | Material Rate | Labour Rate | Wastage | Rupess | Remark's | TFS Amount
Add-1 | Above door 18mm HDMR board partition with m.s frame. | Sqft |  |  |  | 10.8875 | 277.25 | 160 | 80 | 15 | 22.25 | 100HDHMR+50 CARPENTER +30 MS BOARD+MS 50+SCREWS 10 | 3018.5594
| Above Moh to Boh door |  | 1 | 3.35 | 3.25 | 10.8875 | [6 empty] | 0
0
Add-2 | P/F Service counter made out of 19mm marine ply for sides, 12MM THK corian top, bottom, shelves and shutters IN PLYWOOD. Back of cabinet to be made out of 6mm marine ply. All external surfaces to be finished with approved laminate of 1.0mm thickness. etc complete as per drawing and details. | Sqft |  |  |  | 9 | 1520 | 1000 | 400 | 0 | 120 | 1080 | 13680
| Karime store |  | 1 | 3 | 3 | 9 | [6 empty] | 0
0
Add-3 | P/F 35mm flush door with all hardware |  | 1 |  | 1 | 1 | 20000 | [5 empty] | 20000
0
Add-4 | P&F DMB base comprising of MS Frame & 12mm commercial ply & duely painted in approved shade | rft | 1 |  |  | 7.16 | 750 | 345 | 160 | 35 | 210 |  | 5370
0
Add-5 | Glass Sneeze Guard | Sqft | 1 |  |  | 18.6584 | 550 | 325 | 50 | 0 | 175 |  | 10262.12
|  |  | 1 | 0.83 | 7.58 | 6.2914 | [6 empty] | 0
|  |  | 1 | 0.83 | 7.58 | 6.2914 | [6 empty] | 0
|  |  | 4 | 0.83 | 0.83 | 2.7556 | [6 empty] | 0
| Pass through window |  | 1 | 4 | 0.83 | 3.32 | [6 empty] | 0
0
Add-6 | 3Cx4sqmm+1Cx1.5sqmm FRLS wire-(2Cx2.5 Sqmm Used ) | Rmtr |  |  |  | 69.72 | 165 | 95 | 25 | 16 | 29 |  | 11503.8
| DB to geyser (2+2+2+3.83+1+2) |  | 1 | 12.83 |  | 12.83 | [6 empty] | 0
| DB to visi cooler (2+2+4.1+1.68+2) |  | 1 | 11.78 |  | 11.78 | [6 empty] | 0
| DB to freezer (2+1.1+3.3+2.2+4.1+2.2) |  | 1 | 14.9 |  | 14.9 | [6 empty] | 0
| DB to freezer (2+1.1+3.3+2.2+4.1+2.2) |  | 1 | 14.9 |  | 14.9 | [6 empty] | 0
| DB to ice machine (2+2+2+3.83+1.48+1+3) |  | 1 | 15.31 |  | 15.31 | [6 empty] | 0
0
Add-7 | 2Cx2.5sqmm+1Cx1.5sqmm FRLS wire | Rmtr |  |  |  | 115.41 | 165 | 95 | 25 | 16 | 29 |  | 19042.65
| DB to hot ben marry (2+2+4.1+1.84+1.25+1.72) |  | 1 | 12.91 |  | 12.91 | [6 empty] | 0
| Loop |  | 1 | 1 |  | 1 | [6 empty] | 0
| DB to pos counter (2+2+4.1+1.84+1.25) |  | 1 | 11.19 |  | 11.19 | [6 empty] | 0
| DB to BOH entry door RHS (2+2+4.1+1.68+2+2.64) |  | 1 | 14.42 |  | 14.42 | [6 empty] | 0
| DB to Under counter (2+2+4.1+1.68+2+1.52) |  | 1 | 13.3 |  | 13.3 | [6 empty] | 0
| DB to UC chiller (2+1.5+3.25+2.5+4.1+2+2) |  | 1 | 17.35 |  | 17.35 | [6 empty] | 0
| DB to UC chiller (1.94+2+1.68+4.1+2+2) |  | 1 | 13.72 |  | 13.72 | [6 empty] | 0
| DB to DVR (1+5.74+1.68+4.1+2+2) |  | 1 | 16.52 |  | 16.52 | [6 empty] | 0
| DB to DMB (2+2+3+1) |  | 1 | 8 |  | 8 | [6 empty] | 0
| Loop |  | 1 | 1.5 |  | 1.5 | [6 empty] | 0
| DB to Pesto flash (2+2+.5+1) |  | 1 | 5.5 |  | 5.5 | [6 empty] | 0
0
Add-8 | 3cX2.5sqmm FRLS wire | Rmtr |  |  |  | 68.09 | 165 | 95 | 25 | 16 | 29 |  | 11234.85
| RO area eclectrical point basement DB to terrace | [11 empty] | 0
| (2+1+3+15.25+2.64+16+8+9.7+3+3+3+1.5) | [11 empty] | 0
0
Add-9 | P/L 1Cx6sqmm Earthing wire | Rmtr |  |  |  | 32.01 | 135 | 87 | 15 | 13.5 | 19.5 |  | 4321.35
| karime store to fresh air and exhust |  | 1 | 32.01 |  | 32.01 | [6 empty] | 0
| (2.5+2+4.1+7.5+1.5+1.5+6.9+5.71+.3) | [11 empty] | 0
0
Add-10 | P/L 4sqmm FRLS wire 4 core 4 sq.mm | Rmtr |  |  |  | 64.02 | 356 | [5 empty] | 22791.12
| karime store to fresh air and exhust |  | 2 | 32.01 |  | 64.02 | [6 empty] | 0
| (2.5+2+4.1+7.5+1.5+1.5+6.9+5.71+.3) | [11 empty] | 0
0
Add-11 | P/L 2Cx4sqmm+1Cx1.5sqmm sqmm FRLS wire | Rmtr |  |  |  | 43.98 | 225 | [5 empty] | 9895.5
| DB to UPS room (6+3.9+2.1+10.78+1.3+1+3.3+7.5+4.1+2+2) |  | 1 | 43.98 |  | 43.98 | [6 empty] | 0
0
Add-12 | Supplying and erecting PVC armoured cable 2 core 1.5 sq. mm FRLS copper conductor complete erected on wall / celling as per specification |  |  |  |  | 169.1 | 140 | [5 empty] | 23674
| MCP (3+3) |  |  |  |  | 6 | [6 empty] | 0
| Smoke1 (3+1.5+1.5) |  |  |  |  | 6 | [6 empty] | 0
| Smoke2 (5+1.5+1.5) |  |  |  |  | 8 | [6 empty] | 0
| Smoke3 (2.3+1.5+1.5) |  |  |  |  | 5.3 | [6 empty] | 0
| Smoke4 (5+1.5+1.5) |  |  |  |  | 8 | [6 empty] | 0
| Main zone to hooter (1.5+4.2+1.9+.7+.8+3.6+3+1.2+5+5+3.2+5+5+.7+5+2.5+5+5+4.9+2.5+.7+1.5) |  | 2 | 67.9 |  | 135.8 | [6 empty] | 0
0
Add-13 | Supply, installation, testing & commissioning of Conventional Type optical Smoke Detector with inbuilt scattered light measurement, rate of rise and fixed temperature based technology and LED indication should be on the centre of the detector with mounting base complete as required. |  |  |  |  | 5 | 2000 | [5 empty] | 10000
0
0
Add-14 | Supply, installation, testing & commissioning of conventional Manual Call Point (break glass type)complete with push button,enclosed in box with provision of conduit/cable coupling.The unit to be painted fire red outside ,white inside and written "in case of fire break glass" or as required. |  |  |  |  | 1 | 1200 | [5 empty] | 1200
0
0
Add-15 | Supply, installation, testing & commissioning of Conventional Hooter cum Strobe complete as required.110 cd light & 85 dB adjustable at different locations complete with all fixing accessories etc under false ceiling ,roof,wall etc complete as required. |  |  |  |  | 1 | 1200 | [5 empty] | 1200
0
Add-16 | Supplying, installation, testing & commissioning of sprinkler flexible pipe (UL Listed) of stainless steel complete with 15 NPT on reducer thread with maximum working pressure of 175 PSI test pressure of 875 PSI (Burst) with branch line (Inlet) 25mm NPT male thread to sprinkler head (Outlet) 15mm NPT female thread with reducer, nipple, 2 side brackets, center bracket, stockbar of following sizes complete as required. |  |  |  |  | 5 | 1230 | [5 empty] | 6150
0
Add-17 | Making core cuts of 125mm dia for main drain tap off | nos | 1 |  |  | 1 | 1000 | [5 empty] | 1000
0
Add-18 | Brick work Demolition of old Noodle wok | Sft |  |  |  | 780.9375 | 25 | [5 empty] | 19523.4375
|  |  | 1 | 18.75 | 12.25 | 229.6875 | [6 empty] | 0
|  |  | 2 | 15 | 12.25 | 367.5 | [6 empty] | 0
|  |  | 1 | 15 | 12.25 | 183.75 | [6 empty] | 0
0
0
|  | TOTAL AMOUNT | [10 empty] | 193867.3869