## NFA-SO (hidden)
Adani Airport Holdings Ltd
[8 empty] | Plant Code | 112A
Note for Approval
For Amendment of Service Order
Ref. No. |  | GAU/Soil Inv. Consultant |  |  |  | Date: |  | 2022-11-02
Project Name & Location: |  | Lokpriya Gopinath Bordoloi International Airport, Guwahati |  |  |  | Project WBS |  | D-2026-01-P1-AL-CM-PC-SY-
Work/Package |  | Appointment of Consultant for Soil Investigation Work for CSD land parcels (Land Areas: 18.53 Acre)
A. | Requisition | 1. | Name of Project Manager |  |  |  | to be appointed
|  | 2. | SO Requisition no. & date |  |  |  | 2022-08-16
|  | 3. | Date of Last release
|  | 4. | Target date for placement of SO |  |  |  | 2022-09-06
|  | 5. | Justify delay, if any |  |  |  | -
|  | 6. | Target date for Mobilization of Consultant
|  | 7. | Explain & justify if any delays are likely |  |  |  | -
|  | 8. | Any other significant information about PR |  |  |  | -
B. | Bidding | RFP issued on |  |  |  |  | 2022-08-16
|  | Proposals received on |  |  |  |  | 2022-08-23 | 2022-08-31
C. | Proposal Details | Parties to Whom Enquiry Issued. |  |  |  |  | R0 offer (Rs. Lakhs) | R1 offer (Rs. Lakhs) | Position
|  | 1 | Geotest Engineers |  |  |  | 16.5 | 8.232 | L1
|  | 2 | Gaveshana Geosciences |  |  |  | 11.07 | 8.76 | L2
|  | 3 | SS Solution |  |  |  | 11.44 | 11.04 | L3
|  | 4 | Bose Engineers |  |  |  | 14.25 | 12.516 | L4
D. | Basis & Justification | 1. Basis and justification for the recommendation:
|  | a. | Lowest offer |  |  |  | Yes
|  | b. | Repeat order |  |  |  | -
|  | c. | Prices as per pervious SO |  |  |  | -
|  | d. | Based on SO approved SOR |  |  |  | -
|  | e. | Based on the internal cost estimate
|  | f. | Others (specify in details) - (in case of other than lowest, indicate the financial impact)
2. Supporting enclosures (please specify):
|  | a. | Schedule of Approximate Quantities and Unit Rates |  |  |  | Yes
|  | b. | Comparatives statement of quoted & revised prices and internal estimates |  |  |  | Yes
|  | c. | Quotations of the parties |  |  |  | Yes
|  | d. | Last Order Price details
3. Emergency PR
|  | a. | Was it an Emergency PR? |  |  |  | No
|  | b. | If Yes, Was there any implication (Incase of implication specify amount and provide justification in the General Remarks). |  |  |  | -
E. | Consultant | Consultant ’s name (and place) |  |  |  |  | M/s. Geotest Engineers Pvt. Ltd
|  | Whether the Consultant is pre-qualified: |  |  |  |  | No
|  | If no, has the prequalification been carried out satisfactorily: |  |  |  |  | Yes
|  | Consultant’s PF Registration No. |  |  |  |  | -
|  | Any other details: |  |  |  |  | -
F. | Price | Part A : |  |  |  |  | Recommended Price Rs. |  | Budget
|  | Basic Order Value: |  |  |  |  | 823200 |  | 2800000
|  | Provision for travel expenses |  |  |  |  | 0 |  | 0
|  | GST : 18 % |  |  |  |  | 148176 |  | 504000
|  | Total Implication including Basic Order value, travel expenses , GST : |  |  |  |  | 971376 |  | 3304000
|  | Price Basis : |  |  |  |  | Firm Price till completion of services
|  | Provision for Quantity Variation: |  |  |  |  | Nil
G. | SEZ Benefit | Whether eligible for SEZ benefit. |  |  |  |  | No.
|  | If yes then LOP No. |  |  |  |  | -
| Other Major Terms & Conditions | Schedule of Completion: |  |  | SO Commencement Date. |  | From the date of the Service Order or Notice to proceed whichever is later
[5 empty] | SO Completion Date. |  | 30 days from effective date
|  | Payment Terms: |  |  | Mobilization Advance: |  | Nil
[5 empty] | R/A Bills: |  | 1.Max. 2 bills can be raised , one on completion of field work and other at completion and submission of final report. 2. Billing on item rate basis for actual work done. Quantities mentioned in the Price Schedule are tentative and may vary to any extent. 3. Payment shall be made within 30 days from submission of bill
|  | Securities applicable and their validity: |  |  | Advance BG: |  | Nil
[5 empty] | Contract Performance BG: |  | Nil
[5 empty] | Retention Money: |  | Nil
[5 empty] | Any other guarantees: |  | -
|  | Insurance: |  |  | CAR Policy |  | NA
Third party insurance
Workmen compensation
Contractor’s P&M
[5 empty] | Professional Indemnity |  | NA
[5 empty] | Any other |  | Staff of their company and of sub consultants engaged are fully covered under the insurance policy including COVID-19 epidemic
|  | Liquidated damages |  |  |  |  | One percent (1%) of the SO Price (along with applicable GST), for each completed week of delay or part thereof, subject to a maximum of Five percent (5 %) of the SO Price.
|  | Defect Liability Period |  |  |  |  | NA
|  | Any other significant terms and conditions: |  |  |  |  | a) Employer shall retain the right to close the assignment at any stage, as per the needs of the overall development Program. In such an event the breakup of Fees as agreed in Price Schedule shall form the basis for finalization of payment of consultancy fees, after successful completion of the work for respective stage. b) Consultant shall arrange water and electricity for the use in its work/services at its own cost. c) Safety and security of the equipment and personnel of the Consultant deployed at the site shall be its own responsibility. The Consultant shall indemnify the Employer of all the related liabilities.
|  | Mention and justify significant deviations, if any: |  |  |  |  | -
I. | General Remarks | 1. Scope of Works & Plot Layout document was received from Design team consisting of BOQ
J. | Approvers’ Notes, if any
K. | Post Approval Notes | 1. Service Order No. _________________________ dated ____________.
2. Unconditional acceptance of Service Order received on ______________.
| Proposed by |  |  | Recommended by |  | Recommended by |  | Verified by
| Manish Mulchandani |  |  | Avadhesh Kr Singh |  | Parag Thakurdesai |  | Dushyant Kumar
| Manager - Contracts & Procurement (CSD) |  |  | AGM- Contracts & Procurement (CSD) |  | Head- Contracts & Procurement (CSD) |  | GM- Finance Controller (CSD)
| Approved by |  |  |  |  | Approved by
| Vishal Mirchandani |  |  |  |  | Dr. Malay Mahadevia
| CEO (CSD) |  |  |  |  | CEO (AAHL)

## Variation Statement
VARIATION STATEMENT
Project: |  | IRISH HOUSE, LUCKNOW AIRPORT - TERMINAL-T3
Package Details:
Previous SO No.:
Document Date:
SR NO | SERVICE NO | ITEM DESCRIPTION | UNIT | Previous BOQ |  |  | Variation |  |  | Revised BOQ |  |  | % Variation | Remarks
|  |  |  | QTY | RATE | AMOUNT | QTY | RATE | AMOUNT | QTY | RATE | AMOUNT
CIVIL AND INTERIOR
EXTRA ITEM
1 |  | Providing & fixing paneling made of 50x50mm MS framework @ 600mm c/c bothways fixed to the floor and soffit of slab/beam with MS cleats bolted as required, followed with 12mm thk. Bison board as base to receive tile cladding and different finishes over it as per design & details given in drawing/Architect instruction. Rate is inclusive of all necessary hardware & fixtures. | Sft. |  |  |  | 218.8773 | 375 | 82078.9983 | 218.8773 | 375 | 82078.9983
2 |  | Providing and laying cast in situ RCC in Vertical Jamb and Horizontal Bands Grade equivalent to design mix M-25 including curing complete to achieve smooth finish, size 150mm/250mm having required length as per site requirement.(Ultratech) .Steel, shuttering and deshuttering will be include item | Sft. |  |  |  | 164.5284 | 377.1961 | 62059.4712 | 164.5284 | 377.1961 | 62059.4712 |  | New Items
3 |  | Exiting Ply Panelling Dismental with ms frame | Sft. |  |  |  | 352.7901 | 33 | 11642.0733 | 352.7901 | 33 | 11642.0733
4 |  | Providing ,Laying & fixing of Bricks Tile Dado/Cladding of specified size as per drawings, shade and pattern to true level, alignment on wall laid over Bison board panelling and fixed with kerakoll chemical OR LATICRETE'S adhesive (as per manufacturer’s specification)or equivalent, inclusive of cleaning of site , curing of surface , wetting of tiles, cutting of edges, cutting holes for CP Fittings & Electrical points , fixing true to proper line , level, and slope as per approved design including making groove . The joints to be cleaned filled and flushed with white cement using pigment to match the shade of tiles as required as per instructions and to the complete satisfaction of the Project Manager. Bison board panelling shall be paid in separate item. Base rate of Bricks Tiles 150\ Sft. | Sft. |  |  |  | 453 | 414 | 187542 | 453 | 414 | 187542
5 |  | Providing and applying fire raidaint paint on ply surface whichever as per desire and as per project -in - charge.(Quantity will be change after measurment,so far taken a close approximate) | Sft. |  |  |  | 2150 | 34 | 73100 | 2150 | 34 | 73100
6 |  | P/fixing Veneer on exesting plyboard base or as per drawing and project in-charge . (Basic rate of Decorative plywood Veneer) - veneer as per approved sample ( The veneer company ,viyo) (Base rate of Veneer Rs. 125/- per Sq. ft.)(Quantity will be change after measurment,so far taken a close approximate) | Sft. |  |  |  | 410 | 411 | 168510 | 410 | 411 | 168510
7 |  | Removing and Redoing Bision Board paneling and achive the level fixing of ms display and level toward 40 mm. | Sft. |  |  |  | 218.8773 | 169 | 36990.2686 | 218.8773 | 169 | 36990.2686
8 |  | Providing and fixing Electric metre as per approved make and specification or as per project in-charge MAKE- secure | nos |  |  |  | 1 | 16000 | 16000 | 1 | 16000 | 16000
9 |  | Providing and fixing PRV ( Pressure Release Valve) as per approved make and specification or as per project in-charge MAKE- Kranti | nos |  |  |  | 1 | 3800 | 3800 | 1 | 3800 | 3800
10 |  | Providing and fixing Water Metre as per approved make and specification or as per project in-charge MAKE- Kranti | nos |  |  |  | 1 | 7000 | 7000 | 1 | 7000 | 7000
11 |  | Providing and fixing 12 mm Bwr ply with fire rated paint on ceiling for track light and chaidliar support or hanging or as per directed by project in-charge . | Sft. |  |  |  | 65 | 110 | 7150 | 65 | 110 | 7150
12 |  | P & f of MS framing for Screening of fixed glass wall, with 50mm X 50mm box section framing (14 swg gauge) with 3 nos of horizontal and 1000mm C/C of vertical frames as shown on details drawing, with base plate fixing with necessary fastener and to be finished in approve black powder coating. | Rft |  |  |  | 350 | 330 | 115500 | 350 | 330 | 115500
13 |  | Providing and applying 4mm epoxy based grout in flooring as approved make and speacetion make- Laticrete and roff | Sft. |  |  |  | 1800 | 25 | 45000 | 1800 | 25 | 45000
|  | Sub total for Extra Work. Amt. Rs. |  |  |  | 0 |  |  | 816372.8114 |  |  | 816372.8114
0
|  | TOTAL AMOUNT |  |  |  | 4902753 |  |  | 857772.8114 |  |  | 5760525.8114
0.17496
| Sl. No. | Outlet | Previous amount as per existing contract | Amendment Amount | Revised PO value
| 1 | Irish House | 4902753 | 857772.8114 | 5760525.8114

## MB
MB Sheet
PROJECT: IRISH HOUSE, LUCKNOW AIRPORT - TERMINAL-T3
SR. NO. | ITEM DESCRIPTION | Unit | No. | Length | Width | Height | Total | Remarks
1 | Providing & fixing paneling made of 50x50mm MS framework @ 600mm c/c bothways fixed to the floor and soffit of slab/beam with MS cleats bolted as required, followed with 12mm thk. Bison board as base to receive tile cladding and different finishes over it as per design & details given in drawing/Architect instruction. Rate is inclusive of all necessary hardware & fixtures.
| Irish House | Sqm | 1 | 18.7 |  | 0.96 | 17.952
| Column Panelling | Sqm | 2 | 2.77 |  | 0.43 | 2.3822
| Total Qty in Sqm | Sqm |  |  |  |  | 20.3342
| Total Qty in Sft | Sft |  |  |  | 10.764 | 218.8773
2 | Providing and laying cast in situ RCC in Vertical Jamb and Horizontal Bands Grade equivalent to design mix M-25 including curing complete to achieve smooth finish, size 150mm/250mm having required length as per site requirement.(Ultratech) .Steel, shuttering and deshuttering will be include item
| Wall -2 Vertical Jamb (150x250mm) | Rmt. | 3 | 3.71 |  |  | 11.13
| Wall -2 Horizontal (150x250mm) | Rmt. | 1 | 10.02 |  |  | 10.02
| Wall -3 Vertical Jamb (150x250mm) | Rmt. | 3 | 3.71 |  |  | 11.13
| Wall -3 Horizontal (150x250mm) | Rmt. | 1 | 7.82 |  |  | 7.82
| Door Lintel (150x250mm) | Rmt. | 1 | 1.7 |  |  | 1.7
| Jeep wall jamb | Rmt. | 2 | 2.4 |  |  | 4.8
| Jeep wall Horizontal Band | Rmt. | 2 | 1.75 |  |  | 3.5
| Total Qty in Sqm | Rmt. |  |  |  |  | 50.1
| Total Qty in Sft | Rft |  |  |  | 3.284 | 164.5284
3 | Exiting Ply Panelling Dismental with ms frame
| Irish House | Sqm | 1 | 4.34 |  | 3.75 | 16.275
|  | Sqm | 1 | 4.4 |  | 3.75 | 16.5
| Total Qty in Sqm | Sqm |  |  |  |  | 32.775
| Total Qty in Sft | Sft |  |  |  | 10.764 | 352.7901
4 | Providing ,Laying & fixing of Bricks Tile Dado/Cladding of specified size as per drawings, shade and pattern to true level, alignment on wall laid over Bison board panelling and fixed with kerakoll chemical OR LATICRETE'S adhesive (as per manufacturer’s specification)or equivalent, inclusive of cleaning of site , curing of surface , wetting of tiles, cutting of edges, cutting holes for CP Fittings & Electrical points , fixing true to proper line , level, and slope as per approved design including making groove . The joints to be cleaned filled and flushed with white cement using pigment to match the shade of tiles as required as per instructions and to the complete satisfaction of the Project Manager. Bison board panelling shall be paid in separate item. Base rate of Bricks Tiles 150\ Sft. | Sft
| Glass fasade above area | Sqm | 1 | 18.7 |  | 0.96 | 17.952
| Column Panelling | Sqm | 2 | 2.77 |  | 0.43 | 2.3822
| Airport coridor side panelling | Sqm | 1 | 19.8 |  | 1.1 | 21.78
| Total Qty in Sqm | Sqm |  |  |  |  | 42.1142
| Total Qty in Sft | Sft |  |  |  | 10.76 | 453
5 | Providing and applying fire raidaint paint on ply surface whichever as per desire and as per project -in - charge.(Quantity will be change after measurment,so far taken a close approximate) | Sft
| Outer section rafter | Sqm | 2 | 9.21 | 0.8 |  | 14.736
| Center section Rafter | Sqm | 2 | 8.87 | 0.8 |  | 14.192
| Horizontal rafter | Sqm | 5 | 2.79 | 0.8 |  | 11.16
| Horizontal rafter side 2 | Sqm | 5 | 2.71 | 0.8 |  | 10.84
| Tapper Horizontal Rafter | Sqm | 5 | 3.08 | 0.8 |  | 12.32
| Tapper Horizontal Rafter side 2 | Sqm | 5 | 2.99 | 0.8 |  | 11.96
| Inner small rafter | Sqm | 5 | 1.185 | 0.8 |  | 4.74
| Inner small rafter side 2 | Sqm | 5 | 1.16 | 0.8 |  | 4.64
| Bar counter behind veneer Front side | Sqm | 1 | 3.83 |  | 1.15 | 4.4045
| LHS | Sqm | 1 | 3.16 |  | 1.15 | 3.634
| RHS | Sqm | 1 | 2.68 |  | 1.15 | 3.082
| Bar counter top Front side | Rmt | 1 | 4.3 | 0.45 |  | 1.935
| LHS | Rmt | 1 | 2.9 | 0.45 |  | 1.305
| RHS | Rmt | 1 | 2.51 | 0.45 |  | 1.1295
| Bar counter Bottam Front side | Rmt | 1 | 4.3 | 0.35 |  | 1.505
| LHS | Rmt | 1 | 2.9 | 0.35 |  | 1.015
| RHS | Rmt | 1 | 2.51 | 0.35 |  | 0.8785
| near sofa ms column center | sqm | 2 | 0.2 |  | 3.6 | 1.44
|  | sqm | 2 | 0.235 |  | 3.6 | 1.692
| bar area side ms column center | sqm | 2 | 0.2 |  | 3.6 | 1.44
|  | sqm | 2 | 0.235 |  | 3.6 | 1.692
| Coridor side column near sofa front | sqm | 1 | 0.225 |  | 3.6 | 0.81
| Sides | sqm | 2 | 0.27 |  | 3.6 | 1.944
| Coridor side column near bar front | sqm | 1 | 0.225 |  | 3.6 | 0.81
| sides | sqm | 2 | 0.24 |  | 3.6 | 1.728
| Total Qty in Sqm | Sqm |  |  |  |  | 115.0325
| Total Qty in Sft | Sft |  |  |  | 10.76 | 1238
6 | P/fixing Veneer on exesting plyboard base or as per drawing and project in-charge . (Basic rate of Decorative plywood Veneer) - veneer as per approved sample ( The veneer company ,viyo) (Base rate of Veneer Rs. 125/- per Sq. ft.)(Quantity will be change after measurment,so far taken a close approximate) | Sft
| Total Qty in Sqm | Sqm |  |  |  |  | 0
| Total Qty in Sft | Sft |  |  |  | 10.76 | 0
7 | Providing and fixing on fire rated board inseart of normal gypsum board on Boq exesting item no-20, devitation price
| ceiling flat area | Sqm | 1 | 18.89 | 9.2 |  | 173.788
| Total Qty in Sqm | Sqm |  |  |  |  | 173.788
| Total Qty in Sft | Sft |  |  |  | 10.764 | 1870.654
8 | Removing and Redoing Bision Board paneling and achive the level fixing of ms display and level toward 40 mm.
| Irish House | Sqm | 1 | 18.7 |  | 0.96 | 17.952
| Column Panelling | Sqm | 2 | 2.77 |  | 0.43 | 2.3822
| Total Qty in Sqm | Sqm |  |  |  |  | 20.3342
| Total Qty in Sft | Sft |  |  |  | 10.764 | 218.8773

## Rate analysis
Rate Analysis
1 | Providing and fixing on fire rated board inseart of normal gypsum board on Boq exesting item no-20, devitation price
| Gyproc premium board price | Sqm | 1 | 192.85 | 192.85
| Fire rated gyproc board price | Sqm | 1 | 426.07 | 426.07
| Rate Analysis / Cost for 1 Sqm |  |  |  | 233.22
| Per Sft Cost |  |  |  | 23
1 | Providing & fixing paneling made of 50x50mm MS framework @ 600mm c/c bothways fixed to the floor and soffit of slab/beam with MS cleats bolted as required, followed with 12mm thk. Bison board as base to receive tile cladding and different finishes over it as per design & details given in drawing/Architect instruction. Rate is inclusive of all necessary hardware & fixtures.
Rate Anaylsis for 10 Sqm Area (12 mm Cement Fibar Board panelling)
Price of Ply Board
| Rate Anaylsis for 10 Sqm Area (12 mm Cement Fibar Board panelling) | Sqm | 10 | 753 | 7530
| Wastage 5% | Sqm | 0.5 | 753 | 376.5
| MS Tubes Framing With MS cleat and Fastner @ 4 Kg / Sqft with Primer | Sqm | 126 | 120 | 15120
| Wastage 5% | Sqm | 6.3 | 120
| Screw & Pasting Adhesives & scaffolding | LS | 1 | 3000 | 2000
Labours
| Labour for Installation & Fixing @ 80/- Sqft | Nos | 10 | 861.12 | 8611.2
Tools & Plant Accessories @ 3%
| Total |  |  |  | 33637.7
Water & Electricity Charges @ 2%
| Total |  |  |  | 33637.7
| Add CPOH @ 20% | 20% |  |  | 6727.54
Add P.F. & ESI for Labours @ 4.25% as per CPWD
| Rate Analysis / Cost for 10 Sqm |  |  |  | 40365.24
| Per Sqm Cost |  |  |  | 4037
| Per Sqft Cost |  |  |  | 375
2 | Providing and laying cast in situ RCC in Vertical Jamb and Horizontal Bands Grade equivalent to design mix M-25 including curing complete to achieve smooth finish, size 150mm/250mm having required length as per site requirement.(Ultratech) .Steel, shuttering and deshuttering will be include item
| cement | kg | 14 | 9 | 126
| Dust | kg | 28 | 1.46 | 40.88
| Aggregates | kg | 28 | 1.56 | 43.68
| Steel | kg | 5.31 | 70 | 371.7
| Wastage 5% | Rmt | 1
| Binding Wire and scaffolding | Rmt. | 1 | 150
Labours
| Ply Shuttring with Labour | Rmt | 1 | 100 | 100
Tools & Plant Accessories @ 3%
| Labour for casting | Rmt | 1 | 350 | 350
| Total |  |  |  | 1032.26
Water & Electricity Charges @ 2%
| Total |  |  |  | 1032.26
| Add CPOH @ 20% | 20% |  |  | 206.452
Add P.F. & ESI for Labours @ 4.25% as per CPWD
| Rate Analysis / Cost for 1 Rmt. |  |  |  | 1238.712
| Per Rft Cost |  |  |  | 377.1961
3 | Exiting Ply Panelling Dismental with ms frame
| PLy removing for labour cost | Sft | 1 | 15 | 15
| MS framing removing fabricator cost | Sft | 1 | 15 | 15
| S.folding | Sft | 1 | 3 | 3
| Material shifting other side | Sft | 1 | 5
Labours
Tools & Plant Accessories @ 3%
| Total |  |  |  | 33
Water & Electricity Charges @ 2%
| Total |  |  |  | 33
Add P.F. & ESI for Labours @ 4.25% as per CPWD
| Rate Analysis / Cost for 1 sft. |  |  |  | 33
| Per sft cost |  |  |  | 33
4 | Providing ,Laying & fixing of Bricks Tile Dado/Cladding of specified size as per drawings, shade and pattern to true level, alignment on wall laid over Bison board panelling and fixed with kerakoll chemical OR LATICRETE'S adhesive (as per manufacturer’s specification)or equivalent, inclusive of cleaning of site , curing of surface , wetting of tiles, cutting of edges, cutting holes for CP Fittings & Electrical points , fixing true to proper line , level, and slope as per approved design including making groove . The joints to be cleaned filled and flushed with white cement using pigment to match the shade of tiles as required as per instructions and to the complete satisfaction of the Project Manager. Bison board panelling shall be paid in separate item. Base rate of Bricks Tiles 140\ Sft.
Price of Bricks tiles 1 sqm
| Rate Anaylsis for 1 Sqm Area | Sqm | 1 | 1345 | 1345
| Wastage 5% | Sqm | 0.05 | 1345 | 67.25
| Material shifting Gate to site 5% | Sqm | 0.05 | 1345
1412.25
Chemical or adhesive
| Kerakoll super flex PU adhesive (covrage 1.5kg /m2 per mm thik (Minimum Consider 2mm Thik Chemical ) | sqm | 1 | 1550 | 1550
| wastage 5% | Sqm | 0.05 | 1750
Labours
| Labour for Installation & Fixing @ 70/- Sqft | Sqm | 1 | 753.48 | 753.48
Tools & Plant Accessories @ 3%
| Total |  |  |  | 3715.73
Water & Electricity Charges @ 2%
| Total |  |  |  | 3715.73
| Add CPOH @ 15% | 20% |  |  | 743.146
Add P.F. & ESI for Labours @ 4.25% as per CPWD
| Rate Analysis / Cost for 10 Sqm |  |  |  | 4458.876
| Per Sqm Cost |  |  |  | 4458.876
| Per Sqft Cost |  |  |  | 414
5 | Providing and applying fire raidaint paint on ply surface whichever as per desire and as per project -in - charge.
Rate Analysis / Cost for 20 Sqm
Consumption Single Coat 5 Sqm / Per Kg
Materials
| Fire raidant paint | Litre | 4 | 575 | 2300
| Wastage @ 5% | Sqm | 0.2 | 575
| Sand Paper | Sqm | 20 | 20 | 400
| Mixing preparation of thinner or tarpin oil | Litre | 4 | 50 | 200
Labours
| Labour Rate for Painting @ 15/- Sqft | Sqft | 20 | 161.481 | 3229.62
| Helper for Cleaning | Nos | 1 | 550
Scaffolding,Blend Machine, Tools & Plant Accessories @ 10%
| Total |  |  |  | 6129.62
Water & Electricity Charges @ 2%
| Total |  |  |  | 6129.62
| Add CPOH @ 20% |  |  |  | 1225.924
Add P.F. & ESI for Labours @ 4.25% as per CPWD
| Rate Analysis / Cost for 20 Sqm |  |  |  | 7355.544
| Per Sqm Cost |  |  |  | 368
| Per Sqft Cost |  |  |  | 34
6 | P/fixing Veneer on exesting plyboard base or as per drawing and project in-charge . (Basic rate of Decorative plywood Veneer) - veneer as per approved sample ( The veneer company ,viyo) (Base rate of Veneer Rs. 125/- per Sq. ft.)(Quantity will be change after measurment,so far taken a close approximate)
Rate Anaylsis for 1 Sqm Area( 4mm thik decorative veneer)
| Rate Anaylsis for 1 Sqm Area (4 mm thic decorative veneer) | Sqm | 1 | 1345.5 | 1345.5
| Wastage 10% | Sqm | 0.1 | 1345.5 | 134.55
| Screw & Pasting Adhesives & scaffolding 15% | Sqm
Labours
| Labour for Installation & Fixing @ 60/- Sqft | sqm | 1 | 645.84 | 645.84
Tools & Plant Accessories @ 3%
| Polishing work | sqm | 1 | 1295 | 1295
| Total |  |  |  | 3420.89
Water & Electricity Charges @ 2%
| Total |  |  |  | 3420.89
| Add CPOH @ 20% | 20% |  |  | 684.178
Add P.F. & ESI for Labours @ 4.25% as per CPWD
| Rate Analysis / Cost for 1 Sqm |  |  |  | 4105.068
| Per Sft Cost |  |  |  | 411
7 | Removing and Redoing Bision Board paneling and achive the level fixing of ms display and level toward 40 mm.
Rate Anaylsis for 1 Sqm Area (12 mm Cement Fibar Board panelling)
Price of Ply Board
| MS Tubes Framing With MS cleat and Fastner @ 5 Kg / Sqm with Primer | Sqm | 5 | 110 | 550
| Screw & Pasting Adhesives & scaffolding for 1 sqm | LS | 1 | 300
Labours
| Labour for Installation & Fixing @ 80/- Sqft | Nos | 1 | 861.12 | 861.12
Tools & Plant Accessories @ 3%
| Total |  |  |  | 1411.12
Water & Electricity Charges @ 2%
| Total |  |  |  | 1411.12
| Add CPOH @ 15% | 20% |  |  | 282.224
Add P.F. & ESI for Labours @ 4.25% as per CPWD
| Rate Analysis / Cost for 1 Sqm |  |  |  | 1693.344
| Per Sqm Cost |  |  |  | 169