## Civil & Interior
Dominos ………………….Civil & Interiors BOQ¦ Ver 3.0
1. Partition, Panelling - Sq. Ft area – one side only
2. Storage Units - Sq. Ft area – Front elevation length x Front Finished height
3. False Ceiling - Sq. Ft area – Flat surface area in reflected ceiling plan
4. Flooring - Sq. Ft. area – Internal area contained within skirting
5. Pls Note Only Bison , Marine Ply and Wpc Board to be used instead of Commercial Ply
6. Chiseling work included in the items or else specified
7. Scaffolding will be in contractor scope upto 4mtr & Above 4mtr rate will be chargeable. If required for installation of civil & MEP.
8. All Items Rates are inclusive of material lead & lift charges.
A. CIVIL & INTERIOR BOQ-DOMINOS -Khalghat MP ( Franchise) |  |  |  |  | Area | 500
Task No. |  | Sub Task No. | Name of Item | Description of Item | Unit | Quantity | Rate | Amount
A |  |  |  | Civil Head
| A.1.0 |  |  | Dismantling and Demolitions
|  | a | Dismantling | Dismantling the existing flooring, ceiling, walls, partition, fixed & loose furniture, toilets, pantry, etc.Cost to include carting away all debris from site, lead and lifts, material, labours, transportation and all other incidental charges etc. complete and as directed by Site Engineer
|  | a.1 |  | Brick Wall ,Wall tiles, Floor tiles, including base,Partitions,Existing Wall Plaster ,Electrical conduits ,wiring,DB,sockets and Punning removing including old plumbing and sanitary lines | Sq.ft | 0 |  | 0
|  | a.2 |  | Removal PCC of thickness upto 5 inches | Sq.ft | 500 |  | 0
|  | a.3 |  | Removal PCC of thickness between 6 inches to 12 inches | Sq.ft | 0 |  | 0
|  | a.4 |  | False Ceiling removing inclusive wire & Light | Sq.ft | 0 |  | 0
|  | a.5 |  | Façade (Including Glass ,Signgage ,Window ,Frames and ACP boxing etc) | Sq.ft | 0 |  | 0
|  | a.6 |  | Existing Rolling shutter removing | Sq.ft | 0 |  | 0
|  | a.7 |  | Existing Cable Trays ,Duct Removing from the site and carting away from the site | Sq.ft | 0 |  | 0
|  | b | Making Core Cut | Making Core cut with Diamond cutter & clearing the debris and carting away the same from site.
|  | b.1 |  | Making core cutting of 75 dia | Nos. | 0.2 |  | 0
|  | b.2 |  | Making core cutting of 100 dia | Nos. | 0 |  | 0
|  | b.3 |  | Making core cutting of 150 dia | Nos. | 0.4 |  | 0
|  | b.4 |  | Making core cutting of 200 dia | Nos. | 0 |  | 0
|  | c | Making Cut -out & Opening | Making cutouts and openings in existing walls for ducts etc. The cost to be inclusive of making good all affected areas with smooth plaster and disposal of debris at an indicated location off site. | Nos. | 0.2 |  | 0
Sub Total of A.1.0 | [7 empty] | 0
| A.2.0 |  |  | RCC and PCC
|  | a | PCC | Providing & Laying Plain cement concrete specified grade (M10) including the cost of centering and shuttering & required curing. Approved make cement is PPC (ACC, Ultra tech , Birla) | cuft | 193 |  | 0
|  | b | RCC with reinforcement | Provinding & Laying in position Reinforced cement concrete of specified grade (M15) including the cost centering, shuttering , steel bending with binding wire (18 G annealed Steel wire) ,cutting & curing.Approved make cement is PPC (ACC, Ultra tech , Birla)
|  | b.1 |  | 1:2:4 (1 cement : 2 coarse sand :6 graded stone aggregate 20mm nominal size)- M15. In Shelves , counters, lintels, beams, waist slab etc. | cuft | 5 |  | 0
Sub Total of A.2.0 | [7 empty] | 0
| A.3.0 |  |  | Brick Wall and Plaster
|  | a |  | Autoclaved Aerated Concrete Block
|  | a.1 | 4" thick AAC (Autoclaved Aerated Concrete) Block | Providing and laying autoclaved aerated cement blocks masonry with 100 mm thick AAC blocks in super structure above plinth level in cement mortar 1:4 (1 cement : 4 coarse sand ). The rate includes providing and placing in position 2 Nos 8 mm dia M.S. bars at every third course of masonry work. | Sq.Ft | 0 |  | 0
|  | a.2 | 6" thick AAC (Autoclaved Aerated Concrete) Block | Providing and laying autoclaved aerated cement blocks masonry with 150 mm thick AAC blocks in super structure above plinth level in cement mortar 1:4 (1 cement : 4 coarse sand ). The rate includes providing and placing in position 2 Nos 8 mm dia M.S. bars at every third course of masonry work. | Sq.Ft | 0 |  | 0
|  | b |  | Brick Work
|  | b.1 | 115mm thick Brick Masonry | Providing & Constructing 115mm thick wall of class1 Brick with conventional IS type bricks in 1:4 cement mortar inclusive of RCC tie member at every one meter height interval in 1:3:6 Cement Concrete with 2no. of 6mm diameter mild steel reinforcement & 2 no. of hoop iron strips 25mm x 1.6mm, painted with anti-corrosive paint, properly bent and bonded at the end ,inclusive of shuttering, scaffolding, Raking of joints and proper curing etc. complete. | Sq.Ft | 248.55 |  | 0
|  | b.2 | 230 mm thick Brick Masonry | Providing and laying 9" brick masonry work with well burnt 1st class table moulded, good quality approved bricks in 1:6 Cement Mortar (1 Cement : 6 Coarse Sand by volume) in true line, level and plumb for wall foundations, trenches, pedestals, columns, compound walls, steps, pillars etc., complete with necessary scaffolding, raking of joints, curing etc., complete as directed and specified upto plinth level. Rate to include soaking of bricks adequately before construction, complete as directed and specified. | cuft | 10.1 |  | 0
|  | c |  | Plaster
|  | c.1 | 12mm to 15mm Plastering | Plastering the Siporex / brick masonry walls with 12mm to 15mm thk. Single coat cement plaster in 1: 4 (cement : sand proportion) with chickenmesh jali wherever required, including scaffolding and curing complete as specified and as directed by Site Engineer. | Sq.Ft | 517.3 |  | 0
Sub Total of A.3.0 | [7 empty] | 0
| A.4.0 |  |  | Brickbat Coba and Water proofing
|  | a | Raised Brickbat Coba (Toilets) | Providing and laying brick-bat coba system, cm 1:3 base coat, brick-bat coba filling as per site requirement & 1:4 top-finish coat. the mortar for the brick-bat koba filling shall be cm 1:4 and admixed with integral waterproofing compound and mortar plasticizer, properly compacted, curing, complete. The top-finish coat shall be broom-finished suitable for laying tiles. The cost should include sealing the annular space between the pipe and the masonary, making khurras, river sand screened and washed, at all leads, lifts, heights, with proper slope to drain-off water entirely, complete, etc. Curing shall be done for maximum for 7 days by ponding with water or after getting checked & satisfied by Site Engineer . | cuft | 0 |  | 0
|  | b | Cinder Filling | Filling motar Light weight cinder with cement salary - Providing and laying Cinder Coba,cm 1:3 base coat, cinder filling as per site requirement & 1:4 top-finish coat. the mortar for the cinder koba filling shall be cm 1:4 and admixed with integral waterproofing compound and mortar plasticizer, properly compacted, curing, complete. The top-finish coat shall be broom-finished suitable for laying tiles. The cost should include sealing the annular space between the pipe and the masonary, making khurras, river sand screened and washed, at all leads, lifts, heights, with proper slope to drain-off water entirely, complete, etc. Curing shall be done for maximum for 7 days by ponding with water or after getting checked & satisfied by Site Engineer . | cuft | 0 |  | 0
|  | c | Water proofing (Toilet & Kitchen sink area) | Providing of water proofing - chemical Treatment – the slab to be cleaned and apply 3 coats of chemical (FOSROC or equivalent) on the floor and on the peripheral walls up to 0.30m. b) Base coat – Applying base coat of 1:6 mortar over chemical treatment on the floor and on the peripheral walls up to 0.60m. Note - Warrantee to be provided up to 5 years | Sq. Ft | 0 |  | 0
|  | d | Water proofing (Toilet & Kitchen sink area)with Membrane | P/f one layer of 3mm APP membrane waterproofing ( 1 layer of membrane & Two coat adhesive) of approved make in toilet & kitchen area or as directed by the Site Engineer minimum 2 coats with requisite adhesive / compounds as per the manufacturers specifications on floor, sunken slab and up to height of 24” on wall. Waterproofing works to be carried out by company authorised installers and guarantee/warrantee provided for 5 years. Including protection plaster Ponding test to be carried out for minimum 48 hours. Approved makes : Zydex, sika | Sq. Ft | 0 |  | 0
|  | e | Water proofing (Toilet & Kitchen sink area)with Membrane | P/f 5mm to 6 mm membrane waterproofing ( 1 layer of membrane & Two coat adhesive) of approved make in toilet & kitchen area or as directed by the Site Engineer minimum 2 coats with requisite adhesive / compounds as per the manufacturers specifications on floor, sunken slab and up to height of 24” on wall. Waterproofing works to be carried out by company authorised installers and guarantee/warrantee provided for 5 years. Including protection plaster Ponding test to be carried out for minimum 48 hours. Approved makes : Zydex, sika | Sq. Ft | 0 |  | 0
Sub Total of A.4.0 | [7 empty] | 0
| A.5.0 |  |  | Rolling Shutter , Awning & Mild Steel work
|  | a | Motorized Rolling Shutter for entrance | Providing & fixing Rolling Shutter including motarized mechanism to be operated with key/switch of min. 20 guage MS sheet, including floor locks, guide rail, first quality enamel paint ( 1 coat of primer & 2 or more coat of paint until achieved smooth finish ). Rate including cost of transportation, loading, unloading, scaffolding, wastage, taxes etc. as mentioned in drawings directed by Site Engineer. | Sq. Ft | 0 |  | 0
|  | b | Manual Rolling Shutter with gear Box for entrance | Providing & fixing manual Rolling Shutter including manual gear box of min. 20 guage MS sheet, including floor locks, guide rail, first quality enamel paint ( 1 coat of primer & 2 or more coat of paint until achieved smooth finish ). Rate including cost of transportation, loading, unloading, scaffolding, wastage, taxes etc. as mentioned in drawings directed by Site Engineer. | Sq. Ft | 0 |  | 0
|  | c | HEAVY M.S Work & Framework | Providing, fabricating & erection of Steel work in built up section/ framed work i/c cutting, welding, hoisting, fixing in position & applying a priming coat of approved steel primer using steel etc, as required. In structure slab (ISMB, ISMC etc.) or stringers, treads, landing of stair case i/c use of chequered plate wherever required, all complete. Including primer and 2 coat paints, For 200 liters of water tank and HVAC units platform | KG | 1000 |  | 0
|  | d | M.s louvers with approved Paint | Providing and Fabricating M.S louvers as per detail drawing and site engineer for Gas Bank and AC Outdoor | KG | 0 |  | 0
|  | e | Aluminum louvers with approved Paint | Providing and Fabricating Aluminium louvers as per detail drawing and site engineer for Gas Bank and AC Outdoor / diffuser 2ft x 2ft in sqft. | KG | 0 |  | 0
|  | f | Motorized Poly Carbonate Shutter | Providing & fixing Motorized Poly carbonate (minimimum 3mm thickness) Rolling Shutter including motarized mechanism to be operated with key/switch of min. including floor locks, guide rail, Rate including cost of transportation, loading, unloading, scaffolding, wastage, taxes etc. as mentioned in drawings directed by Site Engineer. | Sq. Ft | 0 |  | 0
Sub Total of A.5.0 | [7 empty] | 0
| A.6.0 |  |  | Flooring and Cladding
|  | a | Tiles for Flooring (General seating area) FF 01 Kajaria -Fog Perla, cool cement, cool silver (Matt Finish) /Somany-Ethos grey (Details- Refer Material Spec. sheet) | Providing and fixing in position Glazed Vitrified Tile flooring as per detail in drawing. It shall be fixed with cement mortar of 1:4, (required mortar bed is 25mm to 50mm thk) with thick grey cement slurry, using cement grout. The job including cutting of tiles & making smooth edges wherever required for drain pipes. The work shall also include cost of materials, wastages, labour, all lead and lift at all levels, loading and unloading, transportation, curing etc. and all other incidental charges etc., complete and as directed by Engineer-in-charge. The cost should include PVC floor covering material. Including Corrugated sheet/Plastic sheet for tile Protection . (size - 600x600 mm) | Sq. Ft | 0 |  | 0
|  | b | Tiles for Flooring (Light) - (Booth seating) FF 04 - Kajaria Sheesham Rosewood/ RAK AMBER OAK or Somany Strio Verano wood Teak (Details- Refer Material Spec. sheet) | Providing and fixing in position Glazed Vitrified Tile flooring as per detail in drawing. It shall be fixed with cement mortar of 1 :4,(required mortar bed is 25mm to 50mm thk), with thick grey cement slurry, with hairline joints using cement grout. The job including cutting of tiles & making smooth edges wherever required for drain pipes. The work shall also include cost of materials, wastages, labour, all lead and lift at all levels, loading and unloading, transportation, curing etc. and all other incidental charges etc., complete and as directed by Engineer-in-charge. The cost should include PVC floor covering material. Including Corrugated Sheet /Plastic sheet for tile Tile Protection .(size - 130x800 mm)/ Option - RAK -AMBER OAK (SIZE-198X1200mm) | Sq. Ft | 0 |  | 0
|  | c | Tiles for Flooring (Dark) - (Booth seating) FF 05 - Kajaria Sheesham Nero /RAK CEDAR BROWN or Strio Benz wood Nero (Details- Refer Material Spec. sheet) | Providing and fixing in position Glazed Vitrified Tile flooring as per detail in drawing. It shall be fixed with cement mortar of 1 :4, (required mortar bed is 25mm to 50mm thk), with thick grey cement slurry, with hairline joints using cement grout. The job including cutting of tiles & making smooth edges wherever required for drain pipes. The work shall also include cost of materials, wastages, labour, all lead and lift at all levels, loading and unloading, transportation, curing etc. and all other incidental charges etc., complete and as directed by Engineer-in-charge. The cost should include PVC floor covering material. Including POP /Plastic sheet for Tile Protection ..(size - 130x800mm)/ Option 2 RAK -CEDAR BROWN (SIZE-198X1200mm) | Sq. Ft | 0 |  | 0
|  | d | Tiles for Flooring - FF02 Kajaria-Dessert grey, cool gris,cairo gris (Matt Finish) (Kitchen & BOH) or equivalent in somany (Details- Refer Material Spec. sheet) | Providing and fixing in position Glazed Vitrified Tile flooring as per detail in drawing. It shall be fixed with cement mortar of 1 :4, (required mortar bed is 25mm to 50mm thk),with thick grey cement slurry, with hairline joints using cement grout. The job including cutting of tiles & making smooth edges wherever required for drain pipes. The work shall also include cost of materials, wastages, labour, all lead and lift at all levels, loading and unloading, transportation, curing etc. and all other incidental charges etc., complete and as directed by Engineer-in-charge. The cost should include PVC floor covering material. Including Corrugated sheet /Plastic sheet for Tile Protection (Size - 600x600mm) | Sq. Ft | 0 |  | 0
|  | d.1 (opt.) | Tiles for Flooring -(Details- Refer Material Spec. sheet) no.- A (2a), FF02 (Kitchen & BOH) | Providing and fixing in position Glazed Vitrified Tile flooring as per detail in drawing. It shall be fixed with cement mortar of 1 :4, (required mortar bed is 25mm to 50mm thk),with thick grey cement slurry, with hairline joints using cement grout. The job including cutting of tiles & making smooth edges wherever required for drain pipes. The work shall also include cost of materials, wastages, labour, all lead and lift at all levels, loading and unloading, transportation, curing etc. and all other incidental charges etc., complete and as directed by Engineer-in-charge. The cost should include PVC floor covering material. Including Corrugated sheet /Plastic sheet for tile Protection. | Sq. Ft | 540 |  | 0
|  | e | Tiles for Flooring (Toilet areas) Johson- Quartz grey/Somany -EC sapphire matt (Details- Refer Material Spec. sheet) | Providing and fixing in position Tile flooring as per detail in drawing. It shall be fixed with cement mortar of 1 :4,(required mortar bed is 25mm to 50mm thk),with thick grey cement slurry, with hairline joints using cement grout. The job including cutting of tiles & making smooth edges wherever required for drain pipes. The work shall also include cost of materials, wastages, labour, all lead and lift at all levels, loading and unloading, transportation, curing etc. and all other incidental charges etc., complete and as directed by Engineer-in-charge. The cost should include PVC floor covering material. Including corrugated sheet /Plastic sheet for Tile Protection . | Sq. Ft | 0 |  | 0
|  | f | Tiles for Flooring FF 03 - Johnson Endura Stepping Stone - Dona Paula Plain (Outdoor Area) or Somany - Largo Stepon Verde (Details- Refer Material Spec. sheet) | Providing and fixing in position Glazed Vitrified Tile flooring as per detail in drawing. It shall be fixed with cement mortar of 1 :4,(required mortar bed is 25mm to 50mm thk),with thick grey cement slurry, with hairline joints using cement grout. The job including cutting of tiles & making smooth edges wherever required for drain pipes. The work shall also include cost of materials, wastages, labour, all lead and lift at all levels, loading and unloading, transportation, curing etc. and all other incidental charges etc., complete and as directed by Engineer-in-charge. The cost should include PVC floor covering material. Including Corrugated sheet /Plastic sheet for Tile Protection | Sq. Ft | 0 |  | 0
|  | g | Tread & Riser in Johnson Endura Stepping Stone - Dona Paula Plain (Outdoor area) | Providing and fixing in position Glazed Vitrified Tile flooring as per detail in drawing. It shall be fixed with cement mortar of 1 :4,(required mortar bed is 25mm thk) with thick grey cement slurry,with hairline joints using cement grout. The job including cutting of tiles & making smooth edges wherever required for drain pipes. The work shall also include cost of materials, wastages, labour, all lead and lift at all levels, loading and unloading, transportation, curing etc. and all other incidental charges etc., complete and as directed by Engineer-in-charge. The cost should include PVC floor covering material. | Sq. Ft | 0 |  | 0
|  | h | Tiles in Johnson Endura Stepping Stone - Dona Paula Tread (Outdoor area) or Largo Riser Verde | Providing and fixing in position Glazed Vitrified Tile flooring as per detail in drawing. It shall be fixed with cement mortar of 1 :4 ,(required mortar bed is 25mm to 50mm thkk) with thick grey cement slurrywith hairline joints using cement grout. The job including cutting of tiles & making smooth edges wherever required . The work shall also include cost of materials, wastages, labour, all lead and lift at all levels, loading and unloading, transportation, curing etc. and all other incidental charges etc., complete and as directed by Engineer-in-charge. | Rft | 0 |  | 0
|  | i | Skirting (General seating area) FF 01 - Kajaria - Fog Perla, cool cement, cool silver (Matt Finish) /Somany-Ethos grey. (Details- Refer Material Spec. sheet) | Providing and fixing in position 100 mm ht. Skirting as per detail in drawing. Over 20 mm thk bed of cement mortar 1:4 (cement : fine sand ) with thick grey cement slurry ,with hairline joints using cement grout. The job including cutting of tiles & making smooth edges wherever required for drain pipes. The work shall also include cost of materials, wastages, labour, all lead and lift at all levels, loading and unloading, transportation, curing etc. and all other incidental charges etc., complete and as directed by Engineer-in-charge. Finish of skirting to match with individual areas as per flooring plan. | Rft | 0 |  | 0
|  | j | Skirting FF02 - Kajaria-Dessert grey, cool gris,cairo gris (Matt Finish) (Kitchen & BOH) or equivalent in somany. (Details- Refer Material Spec. sheet) | Providing and fixing in position 100 mm ht. Skirting as per detail in drawing. Over 20 mm thk bed of cement mortar 1:4 (cement : fine sand ) with thick grey cement slurry, with hairline joints using cement grout. The job including cutting of tiles & making smooth edges wherever required for drain pipes. The work shall also include cost of materials, wastages, labour, all lead and lift at all levels, loading and unloading, transportation, curing etc. and all other incidental charges etc., complete and as directed by Engineer-in-charge. Finish of skirting to match with individual areas as per flooring plan. | Rft | 110 |  | 0
|  | j.1 op 1 | Skirting -(Details- Refer Material Spec. sheet) no.- 2a, FF02 (Kitchen & BOH) | Providing and fixing in position 100 mm ht. Skirting as per detail in drawing. Over 20 mm thk bed of cement mortar 1:4 (cement : fine sand ) with thick grey cement slurry, with hairline joints using cement grout. The job including cutting of tiles & making smooth edges wherever required for drain pipes. The work shall also include cost of materials, wastages, labour, all lead and lift at all levels, loading and unloading, transportation, curing etc. and all other incidental charges etc., complete and as directed by Engineer-in-charge. Finish of skirting to match with individual areas as per flooring plan. | Rft | 0 |  | 0
|  | k | Skirting (Booth seating) FF 04 - Kajaria Sheesham Rosewood or Somany Strio Verano wood Teak . (Details- Refer Material Spec. sheet) | Providing and fixing in position 100 mm ht. Skirting as per detail in drawing.Over 20 mm thk bed of cement mortar 1:4 (cement : fine sand ) with thick grey cement slurry, with hairline joints using cement grout. The job including cutting of tiles & making smooth edges wherever required for drain pipes. The work shall also include cost of materials, wastages, labour, all lead and lift at all levels, loading and unloading, transportation, curing etc. and all other incidental charges etc., complete and as directed by Engineer-in-charge. Finish of skirting to match with individual areas as per flooring plan. | Rft | 0 |  | 0
|  | l | Wall Tile Cladding - 2 (Kitchen & BOH area). (Details- Refer Material Spec. sheet) no.B(3) | Providing and fixing in position dado tile of approved make & shade on any surface as per details in drawing and Over 12 mm thk bed of cement mortar 1:3 (cement : fine sand ) with thick grey cement slurry, with hairline joints using cement grout. The job including cutting of tiles & making smooth edges wherever required . The work shall also include cost of materials, wastages, labour, all lead and lift at all levels, loading and unloading, transportation, curing etc. and all other incidental charges etc. Complete as specified in the drawing & to the satisfaction of the Site Engineer. Ceramic wall tile (Printed) With customize line work | Sq. Ft | 238.95 |  | 0
|  | m | Wall Cladding - plain Tile (BOH & Staff changing room area). (Details- Refer Material Spec. sheet) no.B(4) | Providing and fixing in position dado tile of approved make & shade on any surface as per details in drawing and Over 12 mm thk bed of cement mortar 1:3 (cement : fine sand ) with thick grey cement slurry, with hairline joints using cement grout.The job including cutting of tiles & making smooth edges wherever required . The work shall also include cost of materials, wastages, labour, all lead and lift at all levels, loading and unloading, transportation, curing etc. and all other incidental charges etc. Complete as specified in the drawing & to the satisfaction of the Site Engineer. | Sq. Ft | 278.5 |  | 0
|  | n | Dado Tile Cladding Shesham Oak wood (Details- Refer Material Spec. sheet) | Providing and fixing in position dado tile of approved make & shade on any surface as per details in drawing and Over 12 mm thk bed of cement mortar 1:3 (cement : fine sand ) with thick grey cement slurry, with hairline joints using cement grout. The job including cutting of tiles & making smooth edges wherever required . The work shall also include cost of materials, wastages, labour, all lead and lift at all levels, loading and unloading, transportation, curing etc. and all other incidental charges etc. Complete as specified in the drawing & to the satisfaction of the Site Engineer. | Sq. Ft | 0 |  | 0
|  | o | Dado in Johnson Endura Stepping Stone - Dona Paula Plain (Outdoor area) or Somany Largo Riser Verde | Providing and fixing in position Glazed Vitrified Tile flooring as per detail in drawing. It shall be fixed with cement mortar of 1:3, required mortar bed is 25mm to 50mm thk), with thick grey cement slurry, using cement grout The job including cutting of tiles & making smooth edges wherever required . The work shall also include cost of materials, wastages, labour, all lead and lift at all levels, loading and unloading, transportation, curing etc. and all other incidental charges etc. Complete as specified in the drawing & to the satisfaction of the Site Engineer. | Sq. Ft | 0 |  | 0
|  | p | Dado Tile Cladding - Johson- Plain grey/Somany -EC sapphire matt(Toilets). (Details- Refer Material Spec. sheet) | Providing and fixing in position dado tile of approved make & shade on any surface as per details in drawing and Over 12 mm thk bed of cement mortar 1:3 (cement : fine sand ) with thick grey cement slurry.The job including cutting of tiles & making smooth edges wherever required . The work shall also include cost of materials, wastages, labour, all lead and lift at all levels, loading and unloading, transportation, curing etc. and all other incidental charges etc. Complete as specified in the drawing & to the satisfaction of the Site Engineer. | Sq. Ft | 0 |  | 0
|  | q | Dado Tile Cladding - White Tile in Staff Toilet or changing room | Providing and fixing in position dado tile (White Tile ) as per details in drawing and Over 12 mm thk bed of cement mortar 1:3 (cement : fine sand ) with thick grey cement slurry, with hairline joints using cement grout. The job including cutting of tiles & making smooth edges wherever required . The work shall also include cost of materials, wastages, labour, all lead and lift at all levels, loading and unloading, transportation, curing etc. and all other incidental charges etc. Complete as specified in the drawing & to the satisfaction of the Site Engineer. (Size - 200x250mm) | Sq. Ft |  |  | 0
|  | r | Granite (Jet Black) Frame | Providing and Fixing 19mm thick, upto 6" wide granite door frames with 6mm champhered edges machine polished edges externally and internally. Rate to include cutting/moulding/polishing/Transport etc. Complete as specified in the drawing & to the satisfaction of the Architect & Site-in-charge. (required mortar bed is 25mm to 50mm thk) | RFt | 8.2 |  | 0
|  | s | Granite (Jet Black/Steel grey) Band | Providing & Fixing 6" -8" wide band of granite of approved shade & sample. It shall be fixed along the doors. (it shall be flushed with finished edge of the wall) with 1:3 cement mortar as per detailed design & shall be flushed with adjoining flooring, etc. Minimum 15 mm | RFt | 0 |  | 0
|  | t | Jet Black Granite | Providing and Fixing 19mm thick black granite on floor. Rate to include cutting/moulding/polishing/Installation/Transport etc. Complete as specified in the drawing & to the satisfaction of the Architect & Site-in-charge.(required mortar bed is 25mm thk) | sq ft | 0 |  | 0
|  | u | Dado Tile Cladding on Counter- 130 x 800 mm - Sheesham Rosewood (Herringbone pattern).(Details- Refer Material Spec. sheet) | Providing and fixing in position Glazed Vitrified Tile Dado on Makeline & POS counter as per detail in drawing. Over 12 mm thk bed of cement mortar 1:4 (cement : fine sand ) with thick grey cement slurry, with hairline joints. The job including cutting of tiles & making smooth edges wherever required for drain pipes. The work shall also include cost of materials, wastages, labour, all lead and lift at all levels, loading and unloading, transportation, curing etc. and all other incidental charges etc., complete and as directed by Engineer-in-charge. The cost should include PVC floor covering material. | Sq. Ft | 60.25 |  | 0
Sub Total of A.6.0 | [7 empty] | 0
B |  |  |  | Interior Head
| B.1.0 |  |  | False Ceiling
|  | a | Gypsum False Ceiling | Gypsum Board false Ceiling: Providing, fabrication and fixing in position of false ceiling ( height will be decided on the spot as per site conditions) by fixing 12 mm Th. Gypsum Board sheets on frame work of GI sheet section. The main runners of 22 gauge GI sheet and cross runners of 24 gauge GI sheet must be framed to form a mesh of 2’0”x2’0” c/c. The Gypsum Board must be fixed to the GI frame and joint to be properly filled in with POP paste and paper tape to get a leveled smooth ceiling. Recessing of the Gypsum Board for light fixtures must be done along with extra frame work of GI sheet section to hold the concealed light fixtures etc. directed by the site engineer | Sq. Ft | 0 |  | 0
|  | b | Bison False ceiling | Providing and Fixing in position suspended type 12 mm Bison Board False Ceiling with required M.S frame (50x50 mm ,18 gauge with 1 coat of primer & 2 or more coat of paint until achieved smooth finish as per drawing) work/ fixing arrangement of 2'x2' c/c and accessories, including groove joint filler, tapes, cut out for lights, & fixing for cove/ pelmet / box of approved size with necessary M.S. brackets / supports for light fittings / A.C. grills / Blinds, cleaning etc. complete as per detail drawing, as specified and as directed by Site Engineer. | sqft | 0 |  | 0
|  | c | ACP Fale Ceiling. (Details- Refer Material Spec. sheet) | Providing and Fixing in position suspended type 4mm thk ACP False Ceiling with required M.S frame 50x50 mm ,18 Gauge and work/ fixing arrangement of 2'x2' c/c and accessories, including groove joint filler, tapes, cut out for lights, & fixing for cove/ pelmet / box of approved size with necessary M.S. brackets / supports for light fittings / Blinds, cleaning etc. complete as per detail drawing, as specified and as directed by Site Engineer. | sqft | 0 |  | 0
Sub Total of B.1.0 | [7 empty] | 0
| B.2.0 |  |  | Ceiling Elements
|  | a | Ceiling Suspended metal framing (Community Seating Ceiling ) | Providing and Fixing in position Ceiling Suspended Metal Grid frame (1500 x 900 ) made out of 25x25mm m.s. hollow box pipe finished with approved shade of .5 micron powder coat . Also to have 10 mm dia m.s. rods placed on every 110 mm c/c horizontaly & verticaly, finish with approved shade of powder coat. Necessary suspension arrangement to be done with m.s. string to fix with m.s. plate & anchor fasteners to the RCC slab. Complete as per detail drawing, as specified and as directed by SIte Engineer. | Sq. Ft | 0 |  | 0
|  | b | Baffles Ceiling -Wooden rafter with rubber wood/Ash wood (Booth seating) | Providing and Fixing 125mmX25mm thick wood finish with natural clear polish make suspended from ceiling. Complete as specified in the drawing & to the satisfaction of the Architect & Site-in-charge. | R.ft | 0 |  | 0
|  | c | Suspended Wooden Ceiling frame with mesh | Providing and fixing ceiling made with 40mm X 40mm thick seaonsal wood finished with polish and mesh as/appd. shade.Complete as specified in the drawing & to the satisfaction of the Architect & Site-in-charge. | Sq. Ft | 0
|  | d | Suspended Mesh Ceiling in MS frame for booth sofa | Providing and fixing 30X30 mm M.S. Hollow pipe frame with mess jali suspeneded from slab, finished with approved shade of semi-gloss powder coat.Complete as specified in the drawing & to the satisfaction of the Architect & Site-in-charge. | Sq. Ft | 0
Sub Total of B.2.0 | [7 empty] | 0
| B.3.0 |  |  | Wall Claddings / Wall Partitions /Claddings
|  | a | Bison Partition - P1 | Providing and fixing in position Bison Board Partition made out of 12mm thk. Bison Board both sides with necessary aluminum/M.S sections ( 40 mm x 40 mm x 1.5 mm ) framework at 600mm c/c both ways in partition included bolted or welded in built up section to recieve bison pallening . The rate should include applying of two or more coats of primer , putty , complete as per standard technical specification, instructions of site engineer and as per decoration plan. | Sq. Ft | 0 |  | 0
|  | a.(i) |  | Framing-Cutting of section & Providing and fixing M.S frame work in built up tubular section (square hollow tubes 40 mm x 40 mm x 1.5 mm ) framework at 600mm c/c both ways in partition included bolted or welded in built up section to recieve bison pallening . The rate should include applying of two or more coats of primer , putty , complete as per standard technical specification, instructions of site engineer and as per decoration plan.
|  | a.1 |  | Providing & Fixing 8 mm thk Bison board with above mentioned framing details - a.(i) (Rate will be include the cost of framing) | Sq. Ft | 0 |  | 0
|  | a.2 |  | Providing & Fixing 10 mm thk Bison board with above mention framing deatails - a.(i) (Rate will be include the cost of framing) | Sq. Ft | 0 |  | 0
|  | b | Ply Partition - P2 | Providing and fixing in position full height ply Partition as mentioned in drawing made out of 12mm thk. Marine ply to be fixed on both sides with necessary aluminum /M.S sections, framing details as mentioned above - a.(i). Items include making, cut-out for electrical swtich plates , swtich boxes and 4" ht skirting as per drawing and direction .Plyboard make should be GREEN, CENTURY 0R EQUIVALENT. (Surface area of single side will be consider for billing) | Sq. Ft | 0 |  | 0
|  | c | Bison Panelling - PN1 | Providing and fixing in position Panelling made out of 12 mm thk. Bison Board of approved make on one side with necessary aluminum/M.S sections, framing details as mentioned below - c.(i). (Surface area of single side will be consider for billing) | Sq. Ft | 0 |  | 0
|  | c.(i) |  | Framing-Cutting of section & Providing and fixing M.S frame work in built up tubular section (square hollow tubes 25 mm x 35 mm x 1.5 mm ) framework at 600mm c/c both ways in partition included bolted or welded in built up section to recieve bison pallening . The rate should include applying of two or more coats of primer , putty , complete as per standard technical specification, instructions of site engineer and as per decoration plan.
|  | d | Marine Ply | Providing & Fixing 12 mm Marine Ply on Existing Provided Surface. Rate will exclude cost of framing | Sqft | 0 |  | 0
|  | d.1 | Marine Ply | Providing & Fixing 19 mm Marine Ply on Existing Provided Surface. Rate will exclude cost of framing | Sq.ft | 0 |  | 0
|  | d.2 | Marine Ply | Providing & Fixing 19 mm marine ply to be fixed with wooden gitty and the wall undulation to be covered by cement plaster | Sqft | 0 |  | 0
|  | e | Bison Boxing - PN5 For Façade | Providing and fixing in position Panelling made out of 6 mm thk. Bison Board of approved make on one side with necessary aluminum /M.S sections ( 25 mm x 35 mm x 1.5 mm ) framework at 600mm c/c both ways bison joints to have 6x6mm groove . Complete as per decoration plan and as specified & directed by Site Engineer. (Surface Area of the partition shall be measured for billing) | Sq. Ft | 0 |  | 0
|  | f | Prelam Panelling (Base for Vinyl pasting) - PN2 Upto 2500mm level from FFL | Providing and fixing in position Panelling made out of 12mm thk. Prelam Board on one side with necessary aluminum /M.S sections ( 25 mm x 35 mm x 1.5 mm ) framework at 600mm c/c both ways. Wood work to be treated with anti termite treatment.and edges to be finish with matching PVC Tape . Complete as per decoration plan and as specified & directed by Site Engineer. (Surface Area of the partition shall be measured for billing) | Sq. Ft | 0 |  | 0
|  | g | Prelam on Existing Surface | Providing and fixing in position Panelling made out of 12mm thk. Prelam Board on Existing Provided Surface. edges to be finish with matching PVC Tape . Complete as per decoration plan and as specified & directed by Site Engineer. (Surface Area of the partition shall be measured for billing) & (Rate will exclude the cost of framing) | Sq. Ft | 0 |  | 0
|  | h | WPC board (Base for Vinyl Pasting)PN2.2 | Providing and fixing in position Panelling made out of 8mm thk. WPC on one side with necessary Aluminium /M.S sections ( 25 mm x 35 mm x 1.5 mm ) framework at 600mm c/c both ways. Complete as per decoration plan and as specified & directed by Site Engineer. (Surface Area of the partition shall be measured for billing) | Sft | 0 |  | 0
|  | h.1 | WPC board on Existing Surface | Providing and fixing in position Panelling made out of 8mm thk. WPC on Existing Surface. Complete as per decoration plan and as specified & directed by Site Engineer. (Surface Area of the partition shall be measured for billing).Rate will exclude cost of framing | Sft | 0 |  | 0
|  | i | Ply Panelling - PN3 | Providing and fixing in position Panelling made out of 12mm thk. Marine ply on one side with necessary aluminum /M.S sections ( 25 mm x 35 mm x 1.5 mm )framework at 600mm c/c both ways. Wood work to be treated with anti termite treatment. Complete as per decoration plan and as specified & directed by Site Engineer. (Surface Area of the partition shall be measured for billing) | Sq. Ft | 0 |  | 0
|  | j | Laminate on panelling | Providing and fixing in position 1mm Thk. Laminate (14554 RH Hooked Holz Acasia) of merinolam make. Complete as per details in drawing and as specified & directed by Site Engineer. (surface area shall be measured for billing) on Columns upto 2500 mm & Booth seating cladding upto 900 mm of customer area | Sq. Ft | 0 |  | 0
|  | k | Laminate (in Staff changing room) | Providing and fixing in position 1mm Thk. Laminate (21141 Snow White) of Merinolam make. Complete as per details in drawing and as specified & directed by Site Engineer. (surface area shall be measured for billing) | Sq. Ft | 0 |  | 0
|  | l | Wall Corner Guard | Providing & fixing 15mmX15mm anodized Aluminium finish corner guard in approved shade powder coat matching to tile color above skirting level upto 2500 mm. | R. Ft | 61.3 |  | 0
|  | m | MS Tube Wall guards for articlad | Providing & fixing MS Tube 25mmX25mm finish in black Powder coat (0.5 micron) for Booth area articlad wall till skirting level as/drawing. | R. Ft | 40.05 |  | 0
|  | n | Floor Transition strip | Providing & fixing 15mm wide 'T' shape anodized Aluminium Transition strip | R. Ft | 0 |  | 0
|  | o op1 | Dado Brick / Tile Cladding - 3 (Booth seating area)-(ACG 795 Articlad-Aggregate Material-German Handmade) | Providing and fixing in position Brick / Brick finish dado tile as per drawing . Its shall be fixed with chemical (Laticrete L335) & grout -Roff Rainbow -khaki of approved make & shade directly on wall. Complete as specified in the drawing & to the satisfaction of the Architect & Site-in-charge.(Cost will include of Articlad directly on wall, Moratar Mixture Average thich 12-15mm , 1:4) | Sq. Ft | 0 |  | 0
|  | o op2 | Dado Brick / Tile Cladding - 3 (Booth seating area)-(ACG 795 Articlad- Aggregate Material-German Handmade) | Providing and fixing in position Brick / Brick finish dado tile with grout -Roff Rainbow -khaki of approved make of approved make & shade on Existing provided surface as per details in drawing and as specified & directed by Site Engineer. (Cost will include of Articlad & Moratar Mixture Average thich 12-15mm , 1:4) | Sq. Ft | 0 |  | 0
|  | o op3 | Dado Brick / Tile Cladding - 3 (Booth seating area)-Unistone (Zara cotswold) | Providing and fixing in Unistone Wall Cladding Tile as per drawing . Its shall be fixed with chemical (Laticrete L335) & matching grout of approved make & shade on brick wall surface and as specified & directed by Site Engineer.( Moratar Mixture Average thich 12-15mm , 1:4) | Sq. Ft | 0 |  | 0
|  | o op4 | Dado Brick / Tile Cladding - 3 (Booth seating area)-MCM(Code -A Series Brick 54058) | Providing and fixing in position Brick / Brick finish dado Clay tile as per drawings . Its shall be fixed with chemical (Laticrete L335) & matching grout of approved make & shade on brick Wall Surface details as mentioned above on any surface as per details in drawing and as specified & directed by Site Engineer.((Cost will include of tiles cladding, Mortar Mixture Thick 12-15 mm, 1:4) | Sq. Ft | 0 |  | 0
|  | p op1 | Dado Brick / Tile Cladding - White Brick at Entrance area-Articlad ACG 555 Exterior Grade-Aggregate Material-German Handmade | Providing and fixing in position Brick / Brick finish dado tile coated with exterior grade sealer with 8mmX4mm . Its shall be fixed with chemical (Laticrete L335) & grout- Roff Snow White on brick wall surface. Complete as specified in the drawing & to the satisfaction of the Architect & Site-in-charge.(Cost will include of Articlad. Mortar Mixture Thick 12-15 mm, 1:4) | Sq. Ft | 0 |  | 0
|  | p op2 | Dado Brick / Tile Cladding - White Brick at Entrance area-MCM Clay Tile(Code -K series ,facing brick /052) | Providing and fixing in position Brick / Brick finish dado clay tile on brick wall surface Complete as specified in the drawing & to the satisfaction of the Architect & Site-in-charge.(Cost will include Mortar Mixture Thick 12-15 mm, 1:4) | Sq. Ft | 0 |  | 0
|  | p op3 | Dado Brick / Tile Cladding - White Brick at Entrance area- Unistone (Dholpur) | Providing and fixing in position Brick / Brick finish dado clay tile on direcet brick wall surface Complete as specified in the drawing & to the satisfaction of the Architect & Site-in-charge. (Cost will include Mortar Mixture Thick 12-15 mm, 1:4) | Sq. Ft | 0 |  | 0
|  | q | Framing for articlad | Providing and fixing 10 mm shera board with MS section of 25 mm * 25mm *1.5 mm(18 guage) as per drawings . | sq.ft | 0 |  | 0
|  | r | Exterior Textured Paint (Spectrum/Equivalent -Graniplast stone dust finish) on facade portal- Refer material specification sheet | Providing and applying textured Paint on wall including 10-12 mm groove (as per drawing) of two coats of approved make & shade . Filling the dents with approved Acrylic putty gypsum / or approved crack filler, binder, cleaning and making the surface dust free, preparing surfaces, applying a coat of sealer or primer as per the manufacturers specifications. Applying two under coats and one finished coat of paint to achieve the required finish including scrapping the existing paint, scaffolding, cleaning etc. Complete as per detail drawing and as directed by Engineer-in-charge. | Sq. Ft | 0 |  | 0
New Items |  | m | ACP Cladding for exterior |  | sq.ft | 0
Sub Total of B.3.0 | [7 empty] | 0
| B.4.0 |  |  | Doors & Windows
|  | a | Main Entry Glass Door with metal frame as per drawing- 6 ft wide | Providing and Fixing in position Main Entry Door as per details in drawings including outer Alunimium sections 70 mm x 50 mm and 8 mm toughened clear glass to be fixed rubber beading and hardware including S.S Brush Finish Handle 1200 mm ht (square one) with inbuilt locking and Aluminium Frame to be finish in powder coated grey (Shade-Graphite Black RAL 9011) . (Cost will include all hardwares including Hinges ,Handle , Brush seal etc) | Sq.ft | 0 |  | 0
|  | b | Frameless toughened glass door with patch fittings and lock | Providing and fixing 12 mm toufghed glass door with patch fitting ,Pivot , lock and floor spring (Ozone FS-9400 STD), SS Handle H Type Ozone/Equivalent 12 Inches ,Collar seal. | Sq.ft |  |  | 0
|  | c | Single Leaf Flush Door -With Vision Panel (SDP Entry) With Teak wood frame- 3ft wide | Providing and Fixing in position 35 mm Thk. wooden flush door including Vision Panel size of ( 300 x 500 mm ) & section on Teak Wood Door Frame of specified size, section well notched & screwed with cutting of grooves, edges, mouldings over rough ground including necessary hardware, fittings, fixtures, conch bolt, 150 mm high, 2mm thick s.s kick Plate, Door closure ,Handle,Lock as mentioned in drg,bitumen paint to non exposed surface, lacquer/melamine polish matching to Laminate on door frames & Horizontal grain Laminate on the panel from both sides of approved make & shade, etc. complete as per detail drawing, as specified and as directed by engineer-in-charge.(Cost will include all the hardwares mentioned above including brush seal) | Sq.ft | 0 |  | 0
|  | c.1 | Single Leaf Flush Door - With Vision Panel with Granite framing (SDP Entry) | Providing and Fixing in position 35 mm Thk. wooden flush door including Vision Panel size of ( 300 x 500 mm ) with Granite frame including necessary hardware, fittings,pivot hinges ,fixtures, conch bolt, 150 mm high ,2 mm thick s.s kick Plate, Door closure ,Handle,Lock as mentioned in drg,bitumen paint to non exposed surface, Lacquer/melamine polish matching to Laminate on door frames & Horizontal grain Laminate on the panel from both sides of approved make & shade, etc. complete as per detail drawing, as specified and as directed by engineer-in-charge. (Cost will include all the hardwares mentioned above and brush seal) | Sq.ft | 0 |  | 0
|  | c.2 | Single Leaf Fire Rated Flush Door -D2V With Vision Panel without door frame ( Back Exit) | Providing and Fixing in position 35 mm Thk. Fire Rated wooden flush door including vision panel (300*500 mm) including necessary hardware, fittings, fixtures, conch bolt, 150 mm high ,2 mm thick s.s kick Plate, Door closure ,Handle,Lock as mentioned in drg, bitumen paint to non exposed surface, melamine polish matching to Laminate on door frames & Horizontal grain Laminate on the panel from both sides of approved make & shade, etc. complete as per detail drawing, as specified and as directed by engineer-in-charge.(Cost will include all the hardwares mentioned above) size as per site | Sq.ft | 0 |  | 0
|  | d | Single Leaf Flush Door -D2(Back Exit Door ,Toilet ) | Providing and Fixing in position 35 mm Thk. wooden flush door & section on Teak Wood Door Frame of specified size, section well notched & screwed with cutting of grooves, edges, mouldings over rough ground including necessary hardware, fittings, fixtures, conch bolt, 150 mm high s.s kick Plate (1.5 thickness), Door closure ,Handle,Lock as mentioned in drg, bitumen paint to non exposed surface, matt melamine polish matching to Laminate on door frames & Horizontal grain Laminate on the panel from both sides of approved make & shade, etc. complete as per detail drawing, as specified and as directed by engineer-in-charge. (Cost will include all the hardwares mentioned above) | Sq.ft | 21 |  | 0
|  | d.1 | Single Leaf Flush Door -D2 without Door Frame (Back Exit Door ,Toilet ) | Providing and Fixing in position 35 mm Thk. wooden flush door including necessary hardware, fittings, fixtures, conch bolt, 150 mm high s.s kick Plate (1.5 thickness), Door closure ,Handle,Lock as mentioned in drg, bitumen paint to non exposed surface, matt Lacquer /melamine polish matching to Laminate on door frames & Horizontal grain Laminate on the panel from both sides of approved make & shade, etc. complete as per detail drawing, as specified and as directed by engineer-in-charge. (Cost will include all the hardwares mentioned above, including brush seal) | Sq.ft | 0 |  | 0
|  | e | Swing Single Leaf Flush Door -D2SV with Vision Panel (Kitchen to BOH) | Providing and Fixing Wooden Swing door in position 35 mm Thk. wooden flush door including Vision Panel size of (300 x 500 )& section on Teak Wood Door Frame of specified size, section well notched & screwed with cutting of grooves, edges, mouldings over rough ground wooden frame cutting of grooves, edges, mouldings including necessary hardware including floor spring ,150 mm high s.s kick Plate,Handle,Lock as mentioned in drg, bitumen paint to non exposed surface, melamine polish matching to Laminate on door frames & Horizontal grain Laminate on the panel from both sides of approved make & shade etc. complete as per detail drawing, as specified and as directed by engineer-in-charge. (Cost will include all the hardwares mentioned above) | Sq.ft | 20.95 |  | 0
|  | f | Fire Exit door | Metal fire door 2 hr fire rating with 35-40 mm thickness , vision panel (300*300) mm with push type panic bar, powder coated (Off white)As specified by project incharge(Navair/Shakti/Radiant)(FRG Glass- Saint Gobain/Asahi/Equivalent) | sqft | 0 |  | 0
|  | g | Swing Single Leaf Flush Door -D2SV without door Frame (Kitchen to BOH) | Providing and Fixing Wooden Swing door in position 35 mm Thk. wooden flush door including Vision Panel size of (300 x 500 ) including necessary hardware including floor spring ,150 mm high s.s kick Plate,Handle,Lock as mentioned in drg,bitumen paint to non exposed surface, lacquer/melamine polish matching to Laminate on door frames & Horizontal grain Laminate on the panel from both sides of approved make & shade etc. complete as per detail drawing, as specified and as directed by engineer-in-charge. (Cost will include all the hardwares mentioned above) | Sq.ft | 0 |  | 0
|  | h | Counter Swing Door | 19 MM Thk Solid Core Counter Swing Door with double side Piano S.S hinge 2 nos as mention in the detail drawing and as directed by Site Engineer .Door Front finish to be done with as / Approved Tile with 38 mm corian Profile in all the sides of tile and top of Swing Door and Door inside finish with Approved Laminate. 19 MM thick patti on all the edges on all three sides (Cost will include all the hardwares mentioned above) | Sq.ft | 0 |  | 0
Sub Total of B.4.0 | [7 empty] | 0
| B.5.0 |  |  | P.O.P/Painting
|  | a | POP Punning | Providing & applying wall punning up to 12mm to 15mm thick layer of super fine Plaster of Paris applied on specified area over existing plastered surface on walls and columns, to be finished smooth. Surface to be prepared by hacking, sand papering and applying coat of cement slurry if required including all incidentals, making grooves, patties, sills etc. complete and as directed by engineer in charge. The finish surface should be smooth, cover up all the patch work done by electrical agencies so as to avoid unevenness and ready to take on paint. Rate including cost of transportation, loading, unloading, scaffolding, wastage, taxes etc. as directed by Engineer-in-charge. | Sq. Ft | 360.15 |  | 0
|  | a.1 | POP Punning | Providing & applying wall punning up to 6 mm thick layer of super fine Plaster of Paris applied on specified area over existing plastered surface on walls and columns, to be finished smooth. Surface to be prepared by hacking, sand papering and applying coat of cement slurry if required including all incidentals, making grooves, patties, sills etc. complete and as directed by engineer in charge. The finish surface should be smooth, cover up all the patch work done by electrical agencies so as to avoid unevenness and ready to take on paint. Rate including cost of transportation, loading, unloading, scaffolding, wastage, taxes etc. as directed by Engineer-in-charge. | Sq. Ft | 0 |  | 0
|  | b | Painting - Asain coal mine 8301 (Vertical Exposed Surfaces) | Providing and applying Lustre Paint on wall of approved make & shade filling the dents with approved Acrylic putty gypsum / or approved crack filler, binder, cleaning and making the surface dust free, preparing surfaces, applying a coat of sealer or primer as per the manufacturers specifications, applying two under coats and one finished coat of paint to achieve the required finish including scrapping the existing paint, scaffolding, cleaning etc. complete as per detail drawing, as specified and as directed by Engineer-in-charge. | Sq. Ft | 186.25 |  | 0
|  |  | Painting - Solen grey 8302 Dark Shade -Highlighter wall (Vertical Exposed Surfaces) | Providing and applying asain Paint on wall of approved make & shade filling the dents with approved Acrylic putty gypsum / or approved crack filler, binder, cleaning and making the surface dust free, preparing surfaces, applying a coat of sealer or primer as per the manufacturers specifications, applying two under coats and one finished coat of paint to achieve the required finish including scrapping the existing paint, scaffolding, cleaning etc. complete as per detail drawing, as specified and as directed by Engineer-in-charge.
|  |  | Painting -Grey Matter 8304 Light Shade (Vertical Exposed Surfaces) | Providing and applying asain Paint on wall of approved make & shade filling the dents with approved Acrylic putty gypsum / or approved crack filler, binder, cleaning and making the surface dust free, preparing surfaces, applying a coat of sealer or primer as per the manufacturers specifications, applying two under coats and one finished coat of paint to achieve the required finish including scrapping the existing paint, scaffolding, cleaning etc. complete as per detail drawing, as specified and as directed by Engineer-in-charge. | sqft | 0
|  | c | Painting - Textured Paint -(Details- Refer Material Spec. sheet) (Vertical Exposed Surfaces) | Providing and applying textured Paint on wall of two coates of approved make & shade filling the dents with approved Acrylic putty gypsum / or approved crack filler, binder, cleaning and making the surface dust free, preparing surfaces, applying a coat of sealer or primer as per the manufacturers specifications, applying two under coats and one finished coat of paint to achieve the required finish including scrapping the existing paint, scaffolding, cleaning etc. complete as per detail drawing, as specified and as directed by Engineer-in-charge. | Sq. Ft | 0 |  | 0
|  | d | Painting - Plastic Emulsion Paint (Ceiling) | Providing and applying Plastic Emulsion Paint on Ceiling of approved make & shade filling the dents with approved Acrylic putty gypsum / or approved crack filler, binder, cleaning and making the surface dust free, preparing surfaces, applying a coat of sealer or primer as per the manufacturers specifications, applying two under coats and one finished coat of paint to achieve the required finish including scrapping the existing paint, scaffolding, cleaning etc. complete as per detail drawing, as specified and as directed by Engineer-in-charge. | Sq. Ft | 500 |  | 0
|  | e | Enamel Paint | Providing and Applying synthetic enamel paint (Armada Blue) of approved make & Shade on Metal surfaces.to be prepared by rubbing with coarser sand paper suitable for painting by filling all dents and crack & two coat of primer .The rate includes scrapping ,Filling with Putty etc complete. - Colour and pattern to be specified at site by site supervisor.Approved make - Asain paint | sq.ft | 146.3 |  | 0
|  | f | Duco Paint | Providing and Applying Duco spray paint (Armada Blue) of approved make on Wooden /Expose metal frame. Surface to be prepared by rubbing wooden surface with coarser sand paper suitable duco paint putty to be applied and finish with priemer .The rate includes scrapping ,Filling with Putty etc completein spec. Approved make - Asain paint | sq.ft | 0 |  | 0
Sub Total of B.5.0 | [7 empty] | 0
C |  |  |  | Exterior Head
| C.1.0 |  |  | Façade Work
|  | a | Corrugated Sheet with Aluminium Framing | Providing and fixing in position GI sheet made out of 22 gauage GI-V shape round banding sheet & finished with powder coating (Armada Blue) to be fixed on 100x50x60 mm Aluminium/MS frameWORK with 2mm thk & 50x50 mm aluminium/MS angle to be painted with anti- corrosion paint on all side and powder coated aluminium rectangular tube border size 100x25x1.5 to be fixed all round the signage. Complete as per store front details and specified in drawing. | Sq. Ft | 49.58 |  | 0
|  | b | Shera board Paneling for Textured paint /White Paint at Façade | Providing and fixing in position Shera Board Panelling made out 8 mm thk. Shera board with 25mm x 50mm aluminum sections/M.S framework at 600mm x 1200 mm c/c with two coat of primer . Complete as per decoration plan and as specified & directed by Site Engineer. (Surface area of the partition shall be measured for billing) | Sq. Ft | 0 |  | 0
|  | c | Screen Module at Entrance | Providing and fixing in position screen module as per details in drawing . Provision for Glass panel shutter made up from 19 mm Marine PLY frame & 10 mm toughened Glass and Ply framing boxing to be made with necessary locking arrangement, Hinges,150x 150 mm ,fastener & Dorma Patch Fitting for Shutter .Complete as per detail drawing and as specified & directed by Site Engineer. (Length & width of the partition shall be measured for billing.) | Nos | 0 |  | 0
|  | d | Promo Panel | Proving & Fixing of heavy duty cable turnking box at the floor and ceiling/ beam with help of nessacary arrangement. Fixing of at digital display (LED TV) approved size at cable turnking box witg nessacary arrangement and powder coating to be done for cable trunking box in approved shade. All the necessary arrangements to be done for thinclient fixing, Also all the cables to be trunked in the cable trucking box. | Nos |  |  | 0
|  | e | Fixed Glass with Aluminium Frame at entrance | Providing and fixing in position fixed 10 mm toughened glass pratition with As/approved powder coated (ARMADA BLUE) or colout matching to pantone shade PMS 2965 C aluminium outer frame of 40x45x1.5mm from inside with toughened glass. | Sq. Ft | 0 |  | 0
|  | f | Fixed Glass with Aluminium Frame at entrance | Providing and fixing in position fixed 10 mm Toughened glass partition with As/approved poweder coated on Aluminium frame of 45 x 25 mm section with glazing rubber and intermediate sections of 45 x 25 from outside and 45 x 25 from inside with toughened glass. Complete as per details in drawing. (Surface area of the partition shall be measured for billing.) | Sq. Ft |  |  | 0
|  | g | 25 x 25mm Duco Painted | Providing and fixing in position metal section of 25 x 25 x1.5 mm Duco Painted in matt finish blue Paint. | R. Ft | 21.2767 |  | 0
|  | h | Trap door for rolling shutter | Providing and fixing in position Trap door for rolling shutter made out of 8mm thk bison board finished with approved paint, shade to match white brick cladding. complete as per details in drawing and as specified & directed by Site Engineer. | Sq. Ft | 0 |  | 0
Sub Total of C.1.0 | [7 empty] | 0
D |  |  |  | Wood Work
| D.1.0 |  |  | Furniture /WOOD Work
|  | a | Order Counter | Providing and fixing in position Order counter : Counter top finished in 6mm thick Acrylic Solid Surface LG Hausys-HI-MACS G109 Beige Island over 19 mm thick WPC/Marine Ply. 150mm height Drawers (2 nos )to be provided below each POS.Internal area to be finish with 1 mm thick approved laminate with necessary hardwares(Lock ,Telescopic channel etc). MS powder coated framework (40x40x1.5mm) as per detail drawing to be provided with necessay arrangement and Ledge having LED cove strip as per detail drawing Complete in all respect . Cost to include all materials, DMB Framing ,labours and necessary leads & lift etc. -Counter Height-3'6" | RFT | 8.446 |  | 0
|  | a.1 | Order Counter with Glass Slider/Openable | Providing and fixing in position Order counter : Counter top finished in 6mm thick Acrylic Solid Surface LG Hausys-HI-MACS G109 Beige Island over 19 mm thick WPC/Marine Ply. 150mm height Drawers (2 nos)to be provided below each POS.Internal area to be finish with 1 mm thick approved laminate with necessary hardwares (Lock ,Telescopic channel etc). MS powder coated framework (40 x40 x 1.5 mm) with 10 mm toughened glass and having provision of sliding glass opening with necceaasy fittings and channels as per detail drawing and Ledge having LED cove strip as per detail drawing Complete in all respect . Cost to include all materials, DMB Framing ,labours and necessary leads & lift etc. Counter Height-3'6" | RFT | 0 |  | 0
|  | b | Make line | Providing and fixing in position Makeline : Counter top finished in 6mm thick Acrylic Solid Surface LG Hausys-HI-MACS G109 Beige Island over 19 mm thick Marine Ply / WPC and Ledge having LED cove strip as per detail drawing Complete in all respect. Duco Paint M.S framework with 10 mm toughened Glass as per detail drawing above counter Cost to include all materials, labours and necessary leads & lift etc. | RFT | 13.53 |  | 0
|  | c | MOP/Janitor storage | Providing and fixing in position MOP storage made of 18mm thk. Marine ply in appd. Laminate from outside and white laminate inside with necessary support framework. Cost to include shelves in 18 mm thk. marine ply finished in white laminate with all hardware, fasteners, and rubber / PVC leveller etc. complete in all respect as per detailed drawing and size to be considered in Width x Height for Billing Depth 500 mm | Sq.ft | 0 |  | 0
|  | d | SoftBoard | Providing and Fixing in position softboard as specified size. complete in all respect as per detailed drawing. Panel Size : 1200 x 900 | Nos. | 0 |  | 0
|  | e | Staff Lunch Table | Providing and placing foldable staff table in position 40mm thk table top made out of 2 nos 19mm thk marine ply finished with 1mm thk laminate LAM01 on both side and edges to be finished with PVC edge bending to be sopported on L bracket with Table bracket (HAFFLE ) complete in all respect as per detailed drawing. Size- 4'x1'6", width can be adjusted as per site. Fixing of table to be kept 3' from thr floor. | Sq.ft | 0 |  | 0
|  | f | M S railing | Providing and fixing in position M. S. Railing made out of 25 x 25 x1.5 MS hollow section for vertical sections and 12 x 12 x1.5 mm midrails finished in matt duco paint as per approved shade and wooden section Hardwood oak 50 x 25 mm (With Malamine Matt Polished) Handrail to be fixed on 6 mm x 50 mm M.S flat and End to End Main Balusters will be in size of 50 x 50 mm Cost to include all hardware and fasteners etc. complete in all respect as per detailed drawing. | R. Ft | 0 |  | 0
|  | g | S S railing | Providing and fixing in position S. S. Railing made out of ss grade 304 hollow section for vertical sections and midrails and S.S Hollow handrail . Cost to include all hardware and fasteners etc. complete in all respect as per detailed drawing. | R. Ft | 0 |  | 0
|  | h | Removing & Re-fixing existing M.s/ S. S. Railing | Removing and re-fixing in position existig S. S. Railing/M.S Railing with glass panels for installation of finishing material of tread & riser. Cost to include all hardware, fasteners, and rubber / PVC leveller etc. complete in all respect as per detailed drawing. | LS | 0 |  | 0
|  | i | Mirror | Providing and placing in position 6mm thk extra clear mirror of size 450mm x 1200 mm with 12mm thk marine ply at back to be fixed over ss stud on wall. Cost to include all hardware, fasteners, and rubber / PVC leveller etc. complete in all respect as per detailed drawing. | No. | 0 |  | 0
|  | j | Hood Graphic Panel | Providing and fixing in place Hood Graphic Panel made out of approved shade powder coated sheet metal Complete as per details in drawing Reference Drawing No. 960 | sq ft | 0 |  | 0
|  | k | Computer Holder above Dough Tray & Router | Fixing ceiling mounted ,Metal fabricated Computer Holder for Thin clients above Dough Tray & Router. Complete in all respect as per detailed drawing. | Nos. | 1 |  | 0
|  | l | Computer Holder Wall Mounted for SDP & Makeline | Fixing Wall mounted ,Metal fabricated Computer Holder for Thin clients above Dough Tray & Router. Complete in all respect as per detailed drawing. | Nos. | 1 |  | 0
|  | m | Corian -6 MM THK.LG HAUSYS G-109 Foldable Ledge- Take away (Samsung aspen glow - AG636/ Rehau frost white 180L) | Providing & fixing in position Corian foldable ledge to be made up of 6mm corian with necessary angle & bracket support required to fix on m.s frame. It shall be fixed with Chemical Adhesive . The job including cutting of corian & making smooth edges wherever required . The work shall also include cost of materials, wastages,bracket, labour, all lead and lift at all levels, loading and unloading, transportation, etc. and all other incidental charges etc., complete and as directed by Engineer-in-charge. Measurement to be calculated basis on Actual area in running feet. | rft | 0 |  | 0
|  | n | Take away counter | Providing and placing in position Take away table made out of 19mm thk. Marine ply finished with appd. Laminate (Outside Laminate- 1mm THK. 14554 RH HOOKED ACACIA LAMINATE, MERINO WITH 2mm THK. REHAU MAKE MATCHING EDGE BAND & Inisde laminate Merino Lam 21141 snow white ) and table top to be finish with 6 mm thk LG Hausys -109 Hi Macs over marine Ply with necessary support framework as approved, Cost to include all hardware, fasteners, and rubber / PVC leveller etc..Cost to inlude of making 1 drawer and shelve ,as per shared detailed drawing and Size 900 x 550 x 975 mm ht | rft | 0 |  | 0
Sub Total of D.1.0 | [7 empty] | 0
E |  |  |  | Plumbing
| E.1.0 |  |  | INTERNAL WATER SUPPLY SYSTEM
|  | a |  | Providing & fixing on walls / ceiling / floors, medium grade having embossed ISI Mark CPVC pipes of diameter as mentioned below with fittings i.e.connector, clamps, tees, elbows, reducers, male-female etc. necessary fittings. (Supreme / Prince/Astral or as approved. )
|  | a.1 |  | 15mm nominal bore | RMT | 0 |  | 0
|  | a.2 |  | 20mm nominal bore for sink+ gyser+ RO+ Basin+papsi machine | RMT | 34 |  | 0
|  | a.3 |  | 25mm nominal bore for main water supply | RMT | 33.5 |  | 0
|  | a.4 |  | 32mm nominal bore | RMT | 1 |  | 0
|  | a.5 |  | 40mm nominal bore | RMT | 4.5 |  | 0
|  | b |  | Providing & fixing of ISI Mark CPVC ball valves of followig dia pipes as mentioned below (Make - supreme/prince/astral or as approved)
|  | b.1 |  | 15mm nominal bore | Nos. | 0 |  | 0
|  | b.2 |  | 20mm nominal bore for sink+ gyser+ RO+ Basin+papsi machine | Nos. | 0 |  | 0
|  | b.3 |  | 25mm nominal bore for main water supply | Nos. | 0 |  | 0
|  | b.4 |  | 32mm nominal bore | Nos. | 0 |  | 0
|  | b.5 |  | 40mm nominal bore | Nos. | 0 |  | 0
|  | c |  | Providing & fixing on walls / ceiling / floors,C class G I C class pipe of diameter as mentioned below with screwed sockets, joints & necessary. (Supreme / Prince/Astral or as approved. )
|  | c.1 |  | 25MM nominal bore | RMT | 0 |  | 0
|  | c.2 |  | 50 MM nominal bore | RMT | 0 |  | 0
|  | d |  | Providing, Fixing, testing and commissioning of ISI marked Gun Metal Screwed pattern full way Gate valve with wheel tested to non shock cold working pressure upto 10 kg /sq cm(Stop Valve) conforming to IS 778 class 1 including jointing, supporting etc complete and as directed.(Danfoss/Jayhiwa/Zoloto or equivalent)
|  | d.1 |  | 20mm class 1.0 | Nos | 2.8065 |  | 0
|  | d.2 |  | 25mm class 1.0 | Nos | 3.205 |  | 0
|  | c.3 |  | 32mm class 1.0 | Nos | 2 |  | 0
|  | c.4 |  | 40mm class 1.0 | Nos | 0 |  | 0
|  | c.5 |  | 50 mm class 1.0 | Nos | 0 |  | 0
|  | e |  | Providing & Fixing 15 mm C.P brass angle valve with C.P copper connecting pipe 375 mm long and nuts washer and C.P brass flange complete ,including cutting and making good the walls where required | Nos | 0 |  | 0
|  | f |  | Providing and fixing brass ball balve with SS 304 stem and ball,teflon seat complete.
|  | f.1 |  | 25 mm nominal bore | Nos | 0 |  | 0
|  | f.2 |  | 32 mm nominal bore | Nos | 0 |  | 0
|  | f.3 |  | 40 mm nominal bore | Nos | 0 |  | 0
Sub Total of E.1.0 | [7 empty] | 0
| E.2.0 |  |  | INTERNAL DRAINAGE SYSTEM
|  | a |  | Providing and fixing UPVC SOIL / VENT / WASTE SWR pipe of required diameter conforming to I.S.-13592, and I.S.-4985 to withstand continous internal hydroulic pressure of 4 kg/cm2 including necessary fixtures and fittings, such as bends, tees,Clean out plugs (for the downtakes near bends). single junctions, double junctions and joining with rubber rings and lubricants, on wall by means of clips or in ground including necessary excavation, laying refilling, trench testing etc. complete. (Prior approval of sample and brand by Ex.Engineer is necessary before use.) (Supreme / Prince/Astral or as approved. )
|  | a.1 |  | 32 mm dia | m | 0 |  | 0
|  | a.2 |  | 40 mm dia | m | 10.8 |  | 0
|  | a.3 |  | 50 mm dia. | m | 0 |  | 0
|  | a.4 |  | 65mm dia | m | 0 |  | 0
|  | a.5 |  | 75 mm dia. | m | 15.6 |  | 0
|  | a.6 |  | 110 mm dia. | m | 15.6 |  | 0
|  | a.7 |  | 150 mm dia. | m | 0 |  | 0
|  | b |  | Providing ,laying, testing & commissioning of approved Multi floor trap / Nahani trap with Chilly trap of required sizes, including jointing etc. complete and as directed. (GMGR/Chilly or equivalent) | Nos. | 4 |  | 0
|  | e |  | SITC RO Water booster pump upto 1 HP Auto Cut Type , mounting with rubber pad & nut bolt (Make Crompton Grundfoss,Danfoss ,Kirloskar or equivalent) | Nos. | 0.4 |  | 0
|  | d |  | SITC RO Water booster pump 0.5 HP Auto Cut Type , mounting with rubber pad & nut bolt (Make Crompton Grundfoss,Danfoss ,Kirloskar or equivalent) |  | 0 |  | 0
|  | f |  | Providing and fixing of PVC water vertical type storage tanks of the approved quality, including making solid work complete in all respects with gate valve, float valve and necessary accessiories .(Sintex or equivalent make of Capacity - 200-250 ltrs) | Nos | 0.4 |  | 0
|  | g |  | Providing and fixing of PVC water storage tanks of the approved quality, including making solid work complete in all respects with gate valve and necessary accessiories(Sintex or equivalent make ) | Ltr | 0 |  | 0
Sub Total of E.2.0 | [7 empty] | 0
| E.3.0 |  |  | EXTERNAL SEWERAGE
|  | a |  | Constructing brick masonry manhole with 1st class bricks in cement mortar 1:5(1 cement:5 fine sand) RCC top slab with 1:2:4 mix (1 cement :2coarse sand:4graded stone aggregate 20mm nominal size) foundation concrete 1:4:8 mix (1 cement:4 coarse sand :8 graded stone aggregate 40mm nominal size) inside and out side plastering 12mm thick with cement mortar 1:3(1 cement :3 coarse sand) finished with a floating coat of neat cement inside and rough plaster on outside and making channels in cement concrete 1:2:4 mix(1 cement:2 coarse sand:4 graded stone aggregate 20mm nominal size) neatly finished complete as per standard design including excavation refilling and disposal of surplus earth.Inside size 80X80 cms and 60 cms deep including C.I cover with frame (light duty) 455 x 610 mm internal dimensions total weight of cover and frame not less than 38 kg(wt. Of cover 23 kg and wt.of frame15kg). | Each | 0 |  | 0
|  | b |  | Gt (18" x18") with 1 st Class brick in cement mortar 1:5 (1 cement : 5 cement) m.s grating with pcc & SS Cover, 18" x 18" inside size complete and inside chamber base finish in PCC and brick surface to be finished with tile | Each | 0.4 |  | 0
Sub Total of E.3.0 | [7 empty] | 0
| E.4.0 |  |  | Sanitarywares & Fittings
|  | a |  | Providing & Fixing following fixtures, the rate for the following shall be inclusive of all necessary fixtures, accessories & attachments to make them operational, etc. complete to the satisfaction of the Architect COST EXCLUDES INTERNAL CONCEALED PLUMBING WITH C.P.V.C. / P.V.C. PIPES ONLY (part of plumbing boq)
|  | a.1 | WC (Details - Refer Toilet Specs.) | Hindware - Enigma or equivalent- wall mounted closet with Quiet-Close seat and cover (Catalogue no. 92024, Colour - Star white) | No. | 0 |  | 0
|  | a.2 | Cocealed Cistern with flush plate | Hindware or equivalent- Conceale Cistern (Concealo) and Face Plate (Concealo - Shell) / Flushing cistern can be identify from Vendor according to WC. | No. | 0 |  | 0
|  | a.3 | Wash Basin (Details - Refer Toilet Specs.) | Hindware Magma -1719 Artistic Basin-510X360X120 wall hung (white) or equivalent. | No. | 0 |  | 0
|  | a.4 | Wash Basin | Hindware table top wash basin Fornte white 91043 or equivalent | No. | 0 |  | 0
|  | a.5 | Toilet accessories | Toilet paper holder with cover - Hindware - (Catalogue no. F880003) or equivalent | No. | 0 |  | 0
|  | a.6 | Soap Dispenser Wash Basin (Details - Refer Toilet Specs.) | Dolphy White ABS Wall Mounted 400 ml Liquid Soap Dispenser/ Dolphy – DSDR 0065 which is manual not automatic. But the alternative specs are mentioned for Automatic.- will use current only of Dolphy/censor one will be use for flagship stores only. | No. | 0 |  | 0
|  | a.7 | Tissue Dispenser | Dolphy Multifold Stainless Steel Towel Paper Dispenser | No. | 1 |  | 0
|  | a.8 | Pillar Cock for Wash Basin | Hindware - Quadra Pillar cock - (Catalogue no. F380001CP, Finish - Chrome) or equivalent | No. | 1 |  | 0
|  | a.9 | Bib cock | Hindware -Quadra which is actually “Quadra Bib Cock 2 in 1 with wall flange” or equivalent | No. | 1 |  | 0
|  | a.10 | Jet Spray (Health Faucet) (Details - Refer Toilet Specs.) | Hindware-Health Faucet F 160013 CP ABS With Rubbit Cleaning System | No. | 0 |  | 0
|  | a.11 | Bottle Trap | Hindware-Addons - Bottle Trap 32mm With 125mm & 175mm Long Wall Connection Pipe &Wall Flange (ECONOMY MODEL) | No. | 1 |  | 0
|  | a.12 | Sink Mixer For 3 way Sink | Providing and fixing C.P brass wall mounted sink mixer with swinging spout including cutting and making good the walls where required. (3 way Sink ) | Each | 1 |  | 0
|  | a.13 | 40 mm Dia Pipe | 40 mm CPVC Dia Pipe for 3 way sink for all inclusive fittings | Each | 1 |  | 0
|  | a.14 | Kitchen Paper Holder | SS Kitchen Paper Holder 9" (Make : Hindware chrome F840008CP or equivalent) | Each | 1 |  | 0
|  | a.15 | Waste Coupling | Waste Coupling for 3Way sink and Makeline sink | No. | 1 |  | 0
|  | a.16 | Waste Flexible Pipe | PVC Waste flexible Pipe of 1.0m length and 25 mm dia (make :SBD/Shineman etc) | No. | 0 |  | 0
|  | a.17 | Conceal Coak | Conceal coak for makeline sink (Make- Hindware F310003ACP OR equivalent) Regular Body Suitable for 15mm Pipe Line with Spindle Extension & Plastic Protection Cap (without Exposed Parts) OR equivalent | NO. | 1 |  | 0
Sub Total of E.4.0 | [7 empty] | 0
F |  |  |  | Electrical
| F.1.0 |  |  | VTPN DB
|  | a.1 | 16 Way VTPN DB - Kitchen Equipment+ Lighting+Power DB | Triple pole and neutral distribution board (VTPNDB with vertical busbar) with Double door surface/flush mounted comprising of following:- | Each | 0 |  | 0
Incomer :
100A , TM based MCCB of 25kA with O/L, S/C & E/F Protection - 01 No
Outgoing :
6/32A SP MCB - 24 Nos
6/32 Amp TP MCB- 8 Nos
With all necessary connections
|  | a.2 | 12 Way VTPN DB - Kitchen Equipment+ Lighting+Power DB | Triple pole and neutral distribution board (VTPNDB with vertical busbar) with Double door surface/flush mounted comprising of following:- | Each | 0 |  | 0
Incomer :
63A , TM based MCCB of 25kA with O/L, S/C & E/F Protection - 01 No
Outgoing :
6/32A SP MCB - 18 Nos
6/32 Amp TP MCB- 6 Nos
With all necessary connections
|  | a.3 | 8 Way VTPN DB - Kitchen Equipment+ Lighting+Power DB | Triple pole and neutral distribution board (VTPNDB with vertical busbar) with Double door surface/flush mounted comprising of following:- | Each | 0 |  | 0
Incomer :
63A , TM based MCCB of 25kA with O/L, S/C & E/F Protection - 01 No
Outgoing :
6/32A SP MCB - 12 Nos
6/32 Amp TP MCB- 4 Nos
With all necessary connections
Sub Total of F.1.0 | [7 empty] | 0
| F.2.0 |  |  | TPN DB
|  | b.1 | 12 Way TPN DB - Kitchen Equipment+ Lighting+Power DB | DB shall have separate neutral links of rating not less than 100A for each phase. The main incoming neutral link shall be in addition to three outgoing neutral links and shall be of 125A. | Each | 0 |  | 0
Incomer :
63A FP, MCB of 10kA - 01 No
Sub Incomer
3Nos, DP, 63A, RCBO (30mA).
Outgoing :
6/32A SP MCB - 30 Nos
With all necessary connections
|  | b.2 | 8 Way TPN DB - Kitchen Equipment+ Lighting+Power DB | Triple pole and neutral distribution board (TPNDB) with Double door surface/flush mounted of 8 way (4+ 24 Module) 4 Horizontal Rows in 4 Vertical tiers configuration comprising of following:- | Each | 0 |  | 0
DB shall have separate neutral links of rating not less than 100A for each phase. The main incoming neutral link shall be in addition to three outgoing neutral links and shall be of 125A.
8 Way TPN Double door type DB for Power comprising of following:-
Incomer :
40A FP MCB,10kA - 01 No
Sub Incomer
3Nos, DP, 40A, RCBO (30mA).
Outgoing :
6/32A SP MCB - 18 Nos
With all necessary connections
|  | b.3 | 6 way TPN DB | Triple pole and neutral distribution board (TPNDB) with Double door surface/flush mounted of 6 way (4+ 18 Module) 4 Horizontal Rows in 4 Vertical tiers configuration comprising of following:- | Each | 0 |  | 0
DB shall have separate neutral links of rating not less than 100A for each phase. The main incoming neutral link shall be in addition to three outgoing neutral links and shall be of 125A.
8 Way TPN Double door type DB for Power comprising of following:-
Incomer :
40A FP MCB,10kA - 01 No
Sub Incomer
3Nos, DP, 40A, RCBO (30mA).
Outgoing :
6/32A SP MCB - 12 Nos
With all necessary connections
Sub Total of F.2.0 | [7 empty] | 0
| F.3.0 |  |  | SPN DB
|  | c.1 | 12 Way SPN DB - UPS DB | 12 Way SPN Double door type DB for Power comprising of following:- | Each | 0 |  | 0
Incomer :
32A DP MCB - 01 No
Outgoing :
6/32A SP MCB - 12 Nos
16A SP MCB -05 Nos
With all necessary connections
|  | c.2 | 8 Way SPN DB - UPS DB | 8 Way SPN Double door type DB for Power comprising of following:- | Each | 1 |  | 0
Incomer :
25A DP MCB - 01 No
Outgoing :
16A SP MCB - 04 Nos
10A SP MCB - 02 Nos
With all necessary connections
|  | c.3 | 6 Way SPN DB - UPS DB | 6 Way SPN Double door type DB for Power comprising of following:- | Each | 0 |  | 0
Incomer :
16A DP MCB - 01 No
Outgoing :
10A SP MCB - 03 Nos
16A SP MCB - 1 No
With all necessary connections
|  | e.4 | VTPN DB | 12 Way SPN Double door type DB for Power comprising of following:- | Each | 1
Incomer :
64A FP MCB - 04 No
Outgoing :
6/32A SP MCB - 12 Nos
16A SP MCB -10 Nos
With all necessary connections
Sub Total of F.3.0 | [7 empty] | 0
| F.4.0 |  |  | Isolators /ELCB /RCBO & SWITCH SOCKETS
|  | a.1 |  | Supply , installation, testing comissioning of DP isolator of 25 A | Each | 0 |  | 0
|  | a.2 |  | Supply , installation, testing comissioning of DP isolator of 32 A | Each | 2.4 |  | 0
|  | a.3 |  | Supply , installation, testing comissioning of DP isolator of 40 A | Each | 0 |  | 0
|  | a.4 |  | Supply , installation, testing comissioning of DP MCB of 25 A | Each | 0 |  | 0
|  | a.5 |  | Supply , installation, testing comissioning of DP MCB of 32 A | Each | 2.4 |  | 0
|  | a.6 |  | Supply , installation, testing comissioning of DP MCB of 40 A | Each | 1.2 |  | 0
|  | a.7 |  | Supply , installation, testing comissioning of FP ELCB of 25 A, 100mA | Each | 0 |  | 0
|  | a.8 |  | Supply , installation, testing comissioning of FP ELCB of 40 A, 100mA | Each | 0 |  | 0
|  | a.9 |  | Supply , installation, testing comissioning of FP RCBO of 63 A, 100mA | Each | 0 |  | 0
|  | a.10 |  | Supply, Installation, testing comissioning of 10 amp TPN MCB | Each | 0 |  | 0
|  | a.11 |  | Supply, Installation, testing comissioning of 32 amp TPN MCB | Each | 0 |  | 0
|  | a.12 |  | Supply, Installation, testing comissioning of 40 amp TPN MCB | Each | 0 |  | 0
|  | a.13 |  | Providing and fixing TPN/DP enclosure box for indoor purpose | Each | 0 |  | 0
|  | a.14 |  | Providing and fixing TPN/DP enclosure box (Wheather Proof) for outdoor purposes | Each | 0 |  | 0
|  | a.15 |  | Providing and Fixing 16 amp single phase Industrial socket | Each | 0 |  | 0
|  | a.16 |  | Providing and Fixing 25 amp single phase Industrial socket | Each | 0 |  | 0
|  | a.17 |  | Providing and Fixing 25 amp three phase Industrial socket | Each | 0 |  | 0
|  | b |  | ISOLATOR - (BEFORE SERVO STABILIZER) |  |  |  | 0
|  | b.1 |  | 125A FP, 25kA Thermal Magnetic based MCCB with LSIG Protection with Box (As per the instruction of the Engineer Inchrge) | Each | 0 |  | 0
|  | b.2 |  | 100A FP, 25kA Thermal magneticr based MCCB with LSIG Protection with Box(As per the instruction of the Engineer Inchrge) | Each | 1 |  | 0
|  | c |  | 6/16 Amp Electrical Top | Each | 4.8 |  | 0
|  |  | Light Point Wiring Specifications | Point wiring shall include FRLS wire with all necessary "MMS PVC CONDUIT", with all fittings , accessories , couplings,collars etc., junction / pull / inspection boxes, wires, supports,bushings lamp holders, ceiling rose, flexible conduit, fan hooks wherever required, modular switch, switch box, Fan electronic regulator & terminations using tinned copper lugs of crimping type with cheisling and scaffolding. The scope of sub mains wiring from Panel to DB are excluded.All wiring should be terminated with coupler & connectors.All lighting fixture wiring shall be carried out for primary point using 1.5sqmm copper stranded & for secondary wiring 1sqmm copper stranded conductor 660/1100V grade PVC insulated wire in "PVC Conduit". Individual junction/inspection boxes shall be provided for each lighting fitting for the purpose of looping from fitting to fitting. From switch board/DB to first light fitting will be termed as primary point and First fitting to subsequent fitting on the same circuit shall be as termed secondary point. Light point wiring shall excluded submains wiring from Panel to DB. The scope of light point wiring starts after switch board/DB where switching control is directly from DB.
|  | d | Lighting points with PVC conduit | Wiring for the following light points with 2X1.5 sq mm PVC insulated copper conductor 650V grade FRLS wires in concealed or surface mounted 20/25mm dia MMS PVC conduit as required including providing 6 amps flush type PVC moulded switches, cover plate,5 sided 1.2mm thick G.I. Box one module for housing switches and earthing of the fixtures and outlet box with 1.5 mm PVC insulated copper conductor 650V grade green earth wire.(switches-as/approved make)- upto 10 Mt. wire length is inclusive.
|  | d.1 |  | Primary (First) light point controlled by a 6A switch. | Nos | 4 |  | 0
|  | d.2 |  | Primary (First) light point controlled by a MCB in the DB. | Nos | 4 |  | 0
|  | d.3 |  | Secondary (Loop) light point looped to first point and so on.(upto 6 mtr) wire length | Nos | 8 |  | 0
|  | d.4 |  | Supply, Installation, Testing & Commissioning of mains with 2 X 1.5 sq.mm and earth wire 1.5 sqmm FRLS PVC copper wire ,in rigid MMS PVC conduit min.25 mm dia, for light/fan/exhaust point from DB to point including all required accessories,etc as per specification.(If wire length increase above 10 mt mentioned in lighting circuit) | RMT | 8 |  | 0
|  | d.5 |  | Supply, Installation, Testing & Commissioning of mains with 2 X 2.5 sq.mm and earth wire 2.5 sqmm FRLS PVC copper wire ,in rigid MMS PVC conduit min.20 mm dia,including all required accessories,etc as per specification. | RMT | 0 |  | 0
|  | d.6 |  | Supplying & erecting mains with 2x4 sq.mm and earth wire 2.5 sqmm FRLS PVC copper wire laid with conduit/trunking/inside pole/Bus bars or any other places. | RMT | 4 |  | 0
|  | e | Lighting points with MS conduit | Wiring for the following light points with 2X1.5 sq mm PVC insulated copper conductor 650V grade FRLS wires in concealed or surface mounted 20/25mm dia MS conduit as required including providing 6 amps flush type PVC moulded switches, cover plate,5 sided 1.2mm thick G.I. Box one module for housing switches and earthing of the fixtures and outlet box with 1.5 mm PVC insulated copper conductor 650V grade green earth wire.(switches-as/approved make)- upto 10 Mt. wire length is inclusive.
|  | e.1 |  | Primary (First) light point controlled by a 6A switch. | Nos. | 0 |  | 0
|  | e.2 |  | Primary (First) light point controlled by a MCB in the DB. | Nos. | 0 |  | 0
|  | e.3 |  | Secondary (Loop) light point looped to first point and so on.(upto 6 mtr) wire length | Nos. | 0 |  | 0
|  | e.4 |  | Supply, Installation, Testing & Commissioning of mains with 2 X 1.5 sq.mm and earth wire 1.5 sqmm FRLS PVC copper wire ,in rigid MS conduit min.25 mm dia, for light/fan/exhaust point from DB to point including all required accessories,etc as per specification.(If wire length increase above 10 mt mentioned in lighting circuit) | Rmtr | 0 |  | 0
|  | e.5 |  | Supply, Installation, Testing & Commissioning of mains with 2 X 2.5 sq.mm and earth wire 2.5 sqmm FRLS PVC copper wire ,in rigid MS conduit min.20 mm dia,including all required accessories,etc as per specification. | Rmtr | 0 |  | 0
|  | f |  | Power Point wiring
All switch socket wiring shall be carried out for primary point using 3x2.5 sq mm wire in "PVC Conduit" for connection of 6/16amp socket. Individual junction/inspection boxes shall be provided for each Power Point for the purpose of looping with cheisling and scaffolding work if required .Inclusive of all G.I. Boxing and wire termination & MMS conduit etc. From DB to first switch socket will be termed as primary point and First socket to subsequent looping on the same circuit shall be as termed secondary point. Power point wiring shall excluded submains wiring from Panel to D.B. The scope of Power point wiring starts after DB where switching control is directly from DB.upto 10 Mt. wire length is inclusive.
|  | f.1 |  | First Point wiring with 6A,5pin wall socket outlet and controlled by a 6A switch | Nos | 2.4 |  | 0
|  | f.2 |  | Extra loop point wiring with 6A, 5 pin wall socket outlet and controlled by a 6A switch upto 6 mtr length | Nos | 8 |  | 0
|  | f.3 |  | First Point wiring with 16A,5pin wall socket outlet and controlled by a 16A switch | Nos | 1.6 |  | 0
|  | f.4 |  | Extra loop point wiring with 16A, 5 pin wall socket outlet and controlled by a 16A switch upto 6 mtr length | Nos | 4 |  | 0
|  | f.5 |  | Additional 6 Amp Switch & socket outlet in G.I. Box on modular cover plate adjoining and looped from the existing point. (Note:-additional means switch socket in modular box and plate adjoining the existing one on the same circuit.) Wire will be paid in Rmt separately | Nos |  |  | 0
|  | g |  | All switch socket wiring shall be carried out for primary point using 3X4 sq mm wire in "PVC Conduit" for connection of 16 amp socket . Individual junction/inspection boxes shall be provided for each Power Point for the purpose of looping with cheisling and scaffolding work if required .Inclusive of all G.I. Boxing and wire termination & MMS PVC conduit etc. From DB to first switch socket will be termed as primary point and First socket to subsequent looping on the same circuit shall be as termed secondary point. Power point wiring shall excluded submains wiring from Panel to D.B. The scope of Power point wiring starts after DB where switching control is directly from DB.upto 12 Mt. wire length is inclusive.
|  | g.1 |  | First Point wiring with 16A, 3Pin combined shuttered wall socket outlet and controlled by a 16A one way switch with indicator. | Nos | 4 |  | 0
|  | g.2 |  | Extra loop point wiring with 16A, 3Pin combined shuttered wall socket outlet and controlled by a 16A one way switch with indicator.upto 6 mtr wiring | Nos | 12.05 |  | 0
|  | g.3 |  | Additional 16 Amp Switch & socket outlet in G.I. Box on modular cover plate adjoining and looped from the existing point. (Note:-additional means switch socket in modular box and plate adjoining the existing one on the same circuit.) . Wire will be paid in Rmt separately | Nos |  |  | 0
|  | g.4 |  | Supply and Laying of Wiring for light/ power plug with 4X4 sq. mm FRLS PVC insulated copper conductor single core wire in surface/recessed medium class MMS PVC conduit alongwith 2 Nos. 4 sq. mm FRLS PVC insulated copper conductor single core cable for loop earthing as required. | Rmtr | 112.25 |  | 0
|  | h |  | Power Point wiring(MS conduit)
All switch socket wiring shall be carried out for primary point using 3x2.5 sq mm wire in "MS Conduit" for connection of 6/16amp socket. Individual junction/inspection boxes shall be provided for each Power Point for the purpose of looping with cheisling and scaffolding work if required .Inclusive of all G.I. Boxing and wire termination & MMS conduit etc. From DB to first switch socket will be termed as primary point and First socket to subsequent looping on the same circuit shall be as termed secondary point. Power point wiring shall excluded submains wiring from Panel to D.B. The scope of Power point wiring starts after DB where switching control is directly from DB.upto 10 Mt. wire length is inclusive.
|  | h.1 |  | First Point wiring with 6A,5pin wall socket outlet and controlled by a 6A switch | Nos | 0 |  | 0
|  | h.2 |  | Extra loop point wiring with 6A, 5 pin wall socket outlet and controlled by a 6A switch upto 6 mtr length | Nos | 0 |  | 0
|  | h.3 |  | First Point wiring with 16A,5pin wall socket outlet and controlled by a 16A switch | Nos | 0 |  | 0
|  | h.4 |  | Extra loop point wiring with 16A, 5 pin wall socket outlet and controlled by a 16A switch upto 6 mtr length | Nos | 0 |  | 0
|  | i |  | All switch socket wiring shall be carried out for primary point using 3X4 sq mm wire in "MS Conduit" for connection of 16 amp socket . Individual junction/inspection boxes shall be provided for each Power Point for the purpose of looping with cheisling and scaffolding work if required .Inclusive of all G.I. Boxing and wire termination & MMS PVC conduit etc. From DB to first switch socket will be termed as primary point and First socket to subsequent looping on the same circuit shall be as termed secondary point. Power point wiring shall excluded submains wiring from Panel to D.B. The scope of Power point wiring starts after DB where switching control is directly from DB.upto 12 Mt. wire length is inclusive.
|  | i.1 |  | First Point wiring with 16A, 3Pin combined shuttered wall socket outlet and controlled by a 16A one way switch with indicator. | Nos | 0 |  | 0
|  | i.2 |  | Extra loop point wiring with 16A, 3Pin combined shuttered wall socket outlet and controlled by a 16A one way switch with indicator.upto 6 mtr wiring | Nos | 0 |  | 0
|  | j | Conduiting | Supplying and fixing of following sizes of medium class PVC conduit along with accessories in surface/recess including cutting the wall/floor and making good the same in case of recessed conduit as required.
|  | j.1 |  | 20 mm | Rmtr | 50.0047 |  | 0
|  | j.2 |  | 25 mm | Rmtr | 50.0047 |  | 0
|  | j.3 |  | 32 mm | Rmtr | 0 |  | 0
|  | j.4 |  | 40 mm | Rmtr | 0 |  | 0
|  | j.5 |  | 50 mm | Rmtr | 0 |  | 0
|  | k |  | Supplying and fixing of following sizes of MS conduit along with accessories in surface/recess including painting in case of surface conduit, or cutting the wall and making good the same in case of recessed conduit as required.
|  | k.1 |  | 20 mm | Rmtr | 0 |  | 0
|  | k.2 |  | 25 mm | Rmtr | 0 |  | 0
|  | k.3 |  | 32 mm | Rmtr | 0 |  | 0
|  | k.4 |  | 40 mm | Rmtr | 0 |  | 0
|  | k.5 |  | 50 mm | Rmtr | 0 |  | 0
|  | l |  | Supplying & erecting MMS PVC flexible Conduit 25 mm dia.conforming to I.S. and approved make with required number of couplings, bushes, check nuts etc. | Rmtr | 0 |  | 0
|  | m |  | Supplying & erecting G.I. flexible Conduit 25 mm dia.conforming to I.S. and approved make with required number of couplings, bushes, check nuts etc. | Rmtr | 13.65 |  | 0
|  | n |  | Supplying & erecting PVC flexible Conduit 50 mm dia.conforming to I.S. and approved make with required number of couplings, bushes, check nuts etc. | Rmtr | 5 |  | 0
|  | o |  | Supply, Installation, Testing & Commissioning of G.I Conduit 32mm dia with necessary accessories in wall/floor with chiselling appropriately as per specification. | Rmtr | 0 |  | 0
|  | p |  | Supply, Installation, Testing & Commissioning of G.I conduit 25 mm in dia with necessary accessories in RCC work/false ceiling/false flooring as per specification | Rmtr | 0 |  | 0
Sub Total of F.4.0 | [7 empty] | 0
| F.5.0 |  |  | LT CABLES & TERMINATIONS
|  | a | SUPPLY AND LAYING OF THE CABLES | Supply, Errecting, Termination & Commissioning of following sizes of 1.1 KV grade FRLS Armoured/Unarmoured Copper/ Aluminum conductor cables laid over MS supports cable racks/trays or fixing on walls including clamping the cable to supports cable racks or fixing on walls including lugs, double compression gland and joints complete in an approved manner as required .
|  | a.1 |  | 4Cx16 Sq.mm AL Arm. XLPE | Rmtr |  |  | 0
|  | a.2 |  | 4Cx25 Sq.mm AL Arm. XLPE | Rmtr |  |  | 0
|  | a.3 |  | 3Cx2.5 Sqmm Cu. Arm. XLPE | Rmtr |  |  | 0
|  | a.4 |  | 3Cx4 Sqmm Cu. Arm. XLPE | Rmtr |  |  | 0
|  | a.5 |  | 3.5Cx35 Sq.mm AL Arm. XLPE | Rmtr |  |  | 0
|  | a.6 |  | 3.5Cx50 Sq.mm AL Arm. XLPE | Rmtr | 5 |  | 0
|  | a.7 |  | 3.5Cx70 Sq.mm AL Arm. XLPE | Rmtr | 0 |  | 0
|  | a.8 |  | 3.5Cx95 Sq.mm AL Arm. XLPE | Rmtr |  |  | 0
|  | a.9 |  | 4Cx2.5 Sq.mm Cu. Arm. XLPE | Rmtr |  |  | 0
|  | a.10 |  | 4Cx4 Sq.mm Cu. Arm. XLPE | Rmtr |  |  | 0
|  | a.11 |  | 4C x 6 sq.mm Cu. Arm. XLPE | Rmtr | 0 |  | 0
|  | a.12 |  | 4Cx10 Sq.mm Cu. Arm. XLPE | Rmtr | 5 |  | 0
|  | a.13 |  | 4C x 16 sq.mm Cu. Arm. XLPE | Rmtr | 0 |  | 0
|  |  | CABLE TERMINATION | Supplying and making indoor Cable end Termination of following sizes 1.1kV grade LT XLPE insulated, HR PVC sheathed, stranded Aluminum/copper conductor, Armoured/ Unarmoured cables as per IS:7098 part-I including cost of tinned copper / Aluminium heavy duty crimpping lugs, double compression weatherproof glands, insulation tape, Name Plate at Both Ends and all necessary material to complete the termination.
|  | b |  | 2/3/3.5/4 CORES AL. CABLE WITH AL. LUGS
|  | b.1 |  | 35 sq.mm. | Jt | 0 |  | 0
|  | b.2 |  | 50 sq.mm. | Jt | 0 |  | 0
|  | b.3 |  | 70 sq.mm. | Jt | 0 |  | 0
|  | c |  | Multicore Flexible Cables : 1100 Volt Annealed Bare Electrolytic High, Conductivity Copper Conductor Flexible PVC Type 'A' Insulated & PVC ST-1 Sheathed Cables in existing Conduit. Conforming to IS: 694:1990 including Making Both End terminations with copper lugs. | Rmtr | 0
|  | c.1 |  | 3C x 2.5mm2 1100V grade flexible copper conductor sheathed FLRS PVC cable (P, N, IG)- IS 694/1990. | Rmtr |  |  | 0
|  | c.2 |  | 3C x 4.0mm2 1100V grade flexible copper conductor sheathed FLRS PVC cable (P, N, IG)- IS 694/1990. | Rmtr | 0 |  | 0
Sub Total of F.5.0 | [7 empty] | 0
| F.6.0 |  |  | EARTHING (In absence of D.G.Vendor)
|  | a.1 |  | Supply & Laying of 25mmX3mm GI strips with necessary G. I. Clamps fixed on wall/cable/ conduit with screws in an approved manner. | Mtrs | 0 |  | 0
|  | a.2 |  | Supply & Laying of 25mmX3mm CU strips with necessary G. I. Clamps fixed on wall/cable/ conduit with screws in an approved manner. | Mtrs | 0 |  | 0
|  | a.3 |  | 25X4 sqmm Earth Alu.Armd cable(For RoofTop) with necessary G. I. Clamps fixed on wall/cable/ conduit with screws in an approved manner. | Mtrs | 0 |  | 0
|  | a.4 |  | 35X4 sqmm Earth Alu.Armd cable(For RoofTop) with necessary G. I. Clamps fixed on wall/cable/ conduit with screws in an approved manner. | Mtrs | 0 |  | 0
|  | a.5 |  | 8 SWG GI Earth Wire with necessary G. I. Clamps fixed on wall/cable/ conduit with screws in an approved manner. | Mtrs | 0 |  | 0
|  | a.6 |  | 8 SWG Cu Wire with necessary G. I. Clamps fixed on wall/cable/ conduit with screws in an approved manner. | Mtrs | 0 |  | 0
|  | a.7 |  | Supply, Installation, Testing & Commissioning of long life, Maintenance Free advance chemical Earthing System with 20 year service warranty with 8 feet Vertical Pipe in pipe GI Not less than 1.5” (40mm) ID and not less than 1.5mm wall thickness, & 20x2mm tape inside, which does not require manual addition of water including earthing chamber (300m x 300mm x 300 deep)with cover. The complete systems supported by SEM-20 STRONG based certified advance soil enhancement material. Including all civil works for pit. UOM - Each. This should be done till upto 3 mtr.(Earth resistance value shall be <1 Ohm) | No.'s | 0 |  | 0
|  | a.8 |  | Supply, Installation, testing and commissioning of earth pits comprising 600x600x 3mm thick G.I. electrode/plate 25 mm dia medium class watering G.I. pipe, G.I. funnel with 20 gauge GI wire mesh, masonary chamber with concrete base, CI manhole cover with frame (300m x 300mm x 300 deep) strip from earth palte to link painted with bitumastic paint, test link joint packing the mixture with salt &charcoal 150 mm all around plate electrode complete as required as per IS:3043..(Earth resistance value shall be <1 Ohm) | No.'s | 0 |  | 0
|  | a.9 |  | 4.0 sq.mm. Cu. Flexible cable | Rmtr | 0 |  | 0
|  | a.10 |  | 6.0 sq.mm. Cu. Flexible cable | Rmtr | 0 |  | 0
|  | a.11 |  | 10 sq.mm. Cu. Flexible cable | Rmtr | 0 |  | 0
|  | a.12 | D.G Foundation | Generator bedding incl of floor raising with debris (4" to 6" )with necessary brickwork at all sides/ with 1:2:4 cement sand metal morter bed as PCC/ IPS/plaster on vertical edges, complete in all respects | Sqft | 0 |  | 0
Sub Total of F 6.0 | [7 empty] | 0
| F.7.0 |  |  | Cable Trays
|  | a.1 |  | Providing & erecting Hot deeped Galvanised Perforated type Cable tray manufactured from 18 swg (1.6 mm thick) GI sheet of 300 mm width & 50 mm height complete with necessary coupler plates & hardware in approved manner. Including Paints | Rmtr | 15.6 |  | 0
|  | a.2 | Cable Tray -Non Perforated for Kitchen | Providing & erecting Hot deeped Galvanised Non -Perforated type Cable tray manufactured from 18 swg (1.6 mm thick) GI sheet of 300 mm width & 50 mm height complete with necessary coupler plates & hardware in approved manner Including Paint | Rmtr | 0 |  | 0
|  | a.3 |  | Providing & erecting Hot deeped Galvanised Perforated type Cable tray manufactured from 18 swg (1.6 mm thick) GI sheet of 200 mm width & 50 mm height complete with necessary coupler plates & hardware in approved manner.Including Paint | Rmtr |  |  | 0
|  | a.4 | Cable Tray -Non Perforated for Kitchen | Providing & erecting Hot deeped Galvanised Non -Perforated type Cable tray manufactured from 18 swg (1.6 mm thick) GI sheet of 200 mm width & 50 mm height complete with necessary coupler plates & hardware in approved manner.Including Paint | Rmtr | 0 |  | 0
|  | a.5 |  | Providing & erecting Hot deeped Galvanised Perforated type Cable tray manufactured from 18 swg (1.6 mm thick) GI sheet of 100 mm width & 50 mm height complete with necessary coupler plates & hardware in approved manner.Including Paint | Rmtr |  |  | 0
|  | a.6 | Cable Tray -Non Perforated for Kitchen | Providing & erecting Hot deeped Galvanised Non- Perforated type Cable tray manufactured from 18 swg (1.6 mm thick) GI sheet of 100 mm width & 50 mm height complete with necessary coupler plates & hardware in approved manner.Including Paint | Rmtr |  |  | 0
|  | a.7 |  | Providing & erecting Hot deeped Galvanised Perforated type Cable tray manufactured from 18 swg (1.6 mm thick) GI sheet of 50 mm width & 50 mm height complete with necessary coupler plates & hardware in approved manner.Including Paint | Rmtr |  |  | 0
|  | a.8 | Cable Tray -Non Perforated for Kitchen | Providing & erecting Hot deeped Galvanised Non -Perforated type Cable tray manufactured from 18 swg (1.6 mm thick) GI sheet of 50 mm width & 50 mm height complete with necessary coupler plates & hardware in approved manner.Including Paint | Rmtr | 0 |  | 0
|  | b | Raceway | Provind and laying of 2MM thick GI factory fabricated raceways in partition of the following sizes including providing removable 3 mm thick GI cover knock our holes and fixing accessories complete required including floor supports, bends, access boxes and tap of boxes as per instruction from site supervision.
|  | b.1 |  | 300mm wide x 40mm deep | Rmtr |  |  | 0
|  | b.2 |  | 150mm wide x 40mm deep | Rmtr |  |  | 0
|  | b.3 |  | 100mm wide x 40mm deep | Rmtr |  |  | 0
|  | b.4 |  | 50mm wide x 40mm deep | Rmtr |  |  | 0
Sub Total of F.7.0 | [7 empty] | 0
| F.8.0 |  |  | Electrical Related Civil work
|  | a.1 |  | Excavation/ Cheselling under floor for laying cables/ conduits in wall or floor as per requirement, complete with finishing etc | Sq.Mtr | 21.0805 |  | 0
Sub Total of F.8.0 | [7 empty] | 0
| F.9.0 | a |  | Geyser
|  | a.1 |  | SITC of Digital instant GEYSER ABOVE SINK 3 ltr (Ao Smith or equivalent)instant with required accessories) | No. | 0 |  | 0
|  | a.2 |  | SITC of Storage Geyser (25 ltr) AO smith or equivalent used above 3 way sink with required accessories | No | 1 |  | 0
Sub Total of F.9.0 | [7 empty] | 0
| F.10.0 | a |  | Music System/ CONDUITING/WIRING FOR TELEPHONE/DATA/ MUSIC AND COMPUTER SYSTEM
|  | a.1 |  | SITC of Sony Music System (DAV DZ - 350) or Equivalent Make 5.1 | no | 0 |  | 0
|  | a.2 |  | Wiring to music speakers with 2 pairs 40/0.076 flexible wire (PVC insulator, annealed or surface mounted 20/25 mm PVC conduit as directed (from speaker outlet to music junction box). | Rmtr | 0 |  | 0
|  | a.3 |  | Two nos. telephone jack outlet in 2 module GI outlet -{Refer Details- Electrical (C) below} | Nos | 0 |  | 0
|  | a.4 |  | Providing and drawing RG-58 co-axial cable for computer system in existing PVC conduit. | Rmtr | 150 |  | 0
|  | a.5 |  | Cat-6 Cable for Switch to Camera inlcuding conduit. | Rmtr | 200 |  | 0
|  | a.6 |  | I O Plate including necessary Jack and connections | Nos | 4 |  | 0
|  | a.7 |  | VGA cable Including spliter | Rmtr | 0 |  | 0
|  | b | Data Modular Box
|  | b.1 |  | 150mm x 200 x 40mm (W x H) - (18 SWG - 2 mm) with cover with one partition. | Each | 2 |  | 0
|  | b.2 |  | 100 x 100 x 40mm deep with cover plate for makeline /Slap Table/Biometric | Each | 20 |  | 0
|  | b.3 |  | 300 x 300 x 100 mm deep boxes with cover plate for Electrical Panel | Each | 5 |  | 0
|  | b.4 |  | Supplying and fixing 1.6 mm thick MS junction/outlet 450X300X100 mm deep boxes with cover plate | Each | 0 |  | 0
Sub Total of F.10.0 | [7 empty] | 0
G |  |  |  | Fire Detection and Alarm System
G.1.0
|  | a |  | Supply, installation, testing & commissioning of Conventional Type optical Smoke Detector with inbuilt scattered light measurement, rate of rise and fixed temperature based technology and LED indication should be on the centre of the detector with mounting base complete as required. | No. | 5 |  | 0
|  | a.1 |  | Supply, Installation, testing & commissioning of addressable type smoke Detector with floating sensitivity Complete with all accessories like base, base box, etc. to be installed under / above false ceiling, roof and concealed space, etc. complete as required. | No. | 0 |  | 0
|  | b |  | Supply, Installation, testing & commissioning of addressable type Heat Detector (fixed cum-rate of rise type) with fix temperature at 78 o C complete with all fixing accessories like base, base box, etc to be installed under /above false ceiling, roof and concealed space, etc complete as required. | No. | 0 |  | 0
|  | c |  | Supply, installation, testing & commissioning of conventional Manual Call Point (break glass type)complete with push button,enclosed in box with provision of conduit/cable coupling.The unit to be painted fire red outside ,white inside and written "in case of fire break glass" or as required. | No. | 1 |  | 0
|  | c.1 |  | Supply, Installation, testing & commissioning of addressable type manual call point (break glass type) complete with push button, enclosed in box with provision for cable or conduit coupling. The unit to be painted fire red outside, white inside and written 'In case of fire break glass'. | No. | 0 |  | 0
|  | d |  | Supply, installation, testing & commissioning of Conventional Hooter cum Strobe complete as required.110 cd light & 85 dB adjustable at different locations complete with all fixing accessories etc under false ceiling ,roof,wall etc complete as required. | No. | 1 |  | 0
|  | d.1 |  | Supply, Installation, testing & commissioning of hoooters (Specification :- 110 cd light & 85 dB with adjustable DB) at different locations complete with all fixing accessories, etc under false ceiling roof, wall etc. complete as required. | No. | 0 |  | 0
|  | e |  | Supply, installation, testing & commissioning of 2 zone based conventional Fire alarm control panel with standard set complete as required. | Set | 1 |  | 0
|  | e.1 |  | Supplying, erecting, testing and commissioning the addressable type Fire Alarm Control Panel (FACP) with standard accessories complete | Set | 0 |  | 0
|  | f |  | Supplying and erecting PVC armoured cable 2 core 1.5 sq. mm FRLS copper conductor complete erected on wall / celling as per specification | Mtr. | 40 |  | 0
|  | g |  | Supply installation testing and comissioning of Hood supression system(Ceasefire or equivalent). | No. | 0 |  | 0
Sub Total of G.1.0 | [7 empty] | 0
H |  |  |  | HVAC LOW SIDE
| H.1.0 |  |  | DUCTING : ( MAKE: ZECO/TATA/JINDAL/SAIL/ROLASTAR/NUTECH)
|  |  | a | Supply, Installation, Testing and Commissioning of factory made lock-forming quality flat oval spiral ducting of approved makes complying with IS: 277 and having 120 GSM coating classification with elbows, turning vanes, volume control dampers, G.I. supports, hangers, etc. required accessories . The price shall include the cost of threaded rod supports/Gripples for open ceiling area etc. The item also include providing & applying two coat of approved make anti corrosive paint over a coat of primer as per manufacturers/architect's recommendations.
|  |  | a.1 | 24 gauge galvanized sheet(Thickness - 0.6 mm) - Up to 750 mm | Sq.mtr | 0 |  | 0
|  |  | a.3 | 22 gauge galvanised sheet(Thickness - 0.8 mm) - Up to 1500 mm | Sq.mtr | 0 |  | 0
|  |  | b | Supply, Installation, Testing and Commissioning of Site Fabricated rectangular GI ducting of approved makes complying with IS: 277 and having 120 GSM coating classification. The price shall include the cost of necessary accessories & supports (like flanges, neoprene gaskets, wire ropes, corner saddles, guide vanes, vibration isolators, fire retardant canvas connection in all fan outlet connections, joints, sealing around the duct at wall crossings, labeling, (M.S supports / M.S Frame For Duct travelling Vertical up to Terrace, necessary flange type opening at specific interval for duct cleaning etc. for kitchen exhaust duct )as per specifications. The price shall include the cost of threaded rod support. The item also include providing & applying two coat of approved make anti corrosive paint over a coat of primer as per manufacturers/architect's recommendations,also with cheisling and scaffolding if required.
|  |  | b.1 | 22 gauge galvanized sheet - For Exhaust & fresh Air Duct | Sq.mtr | 24 |  | 0
|  |  | b.2 | 24 gauge galvanized sheet - For Exhaust & fresh Air Duct | Sq.mtr | 13 |  | 0
|  |  | b.3 | SITC of Canvas cloth at fan mouth for Exhaust & Fresh air unit as per detail specification | Nos | 1 |  | 0
Sub Total of H.1.0 | [7 empty] | 0
| H.2.0 |  |  | THERMAL INSULATION
|  | a |  | Supply & Installation of closed cell structure Elastomeric foam based on synthetic nitrile rubber. The insulation material shall have fire performance of Class O acc. to building regulations. Fire propagation shall be tested acc. to BS476 Part 6:1989. It shall be FM approved & UL94 tested.
|  | a.1 |  | 13 mm thick for External Insulation of duct | Sq.mtr | 0 |  | 0
|  | a.2 |  | 09 mm thick for Internal Insulation of duct | Sq.mtr | 24 |  | 0
|  | a.3 |  | 09 mm thick for External Insulation of Exhaust duct | Sq.mtr | 13 |  | 0
Sub Total of H.2.0 | [7 empty] | 0
| H.3.0 |  |  | AIR DISTRIBUTION SYSTEM (MAKE: CARRIYAIR, AIRMASTER,COSMOS, RAVISTAR )
|  | a |  | Air Grille : Supply, installation, testing and commissioning of extruded aluminium powder coated linear grill without volume control dampers as perthe approved drawings and specifications. Colour of the Grille should be match with the False ceiling colour. It should be zero degree deflection. Return air grille should be four side flange & also should have flange end at the end of the grille, If required use perforated sheet in black colour of necessary thickness to avoid light refection. (Colour should be match with the colour code of ceiling/ducting). | Sqft | 0 |  | 0
|  | b |  | VCD :- Supply, installation, testing and commissioning of 150mm wide GSS Volume Control Dampers with 18G GI casing & 20G GI Blade, complete with chrome plated Spindle lubricating bush and quadrent to suit Manual operation. | Sqft | 0 |  | 0
|  | c |  | Collar Damper for Supply air Grill :- Supply, Installation, Testing & Commissioning of opposite balde collar with black matt finish for fresh air supply grill. | Sqft | 0 |  | 0
Sub Total of H.3.0 | [7 empty] | 0
| H.4.0 |  |  | Exhaust Fan for Toilet supply
|  | a.1 |  | Supplying and erecting fresh air cum Exhaust fan of light duty 250 V A.C. 50 cycles 300mm/400mm. 1400 RPM rust proof body & blades, wiremesh, duly erected in an approved manner.(Havells/Usha/Crompton or Orient.) | Each | 0 |  | 0
|  | a.2 |  | Heavy Duty 450 mm Dia Exhaust Fan (Make Cromptoon & Equivalent) | Each | 0 |  | 0
|  | a.3 |  | Inline Industrial Fan 1000 CFM matching existing duct dimension | Each | 0 |  | 0
|  | a.4 |  | S/I/T/C of Bracket fan- 400mm in M.S as per specs | Each | 0 |  | 0
|  | a.5 |  | Providing & Fixing of Limit Switches for Mizwah Air Curtain | Each |  |  | 0
Sub Total of H.4.0 | [7 empty] | 0
I |  |  |  | Miscellaneous work
| I.1.0 |  |  | Extra Frequent Item
|  | a | 4" x 4" S.S Pole | SS Brush Finish pole 4" x 4" and ht as per site (and as per drawing) with Sheet thickness of 1.6 mm minimum and to be fixed on floor with S.S plate with fastner and above M.S member support to be taken from Slab till 2500 mm ht .It shall be fixed with the top slab where ever possible with minimum 6" SS 2 mm thick plate with 4 Nos 8mm Fastners and Wire should run through conduit inside pole and socket to be placed above 300 mm from finished floor level. All The material must be SS 304 and the vendor shall share the certifcate for the same. the installation shall be as per enginner incharge. | R Ft | 0 |  | 0
|  | b |  | Providing stand and fixing Micro wave Oven above staff lunch table to be source locally & as approved. | NOS | 0 |  | 0
|  | c | Rubber Matt | 3mm shock proof rubber mat with 11 kVA certification required | sq ft | 12 |  | 0
|  | d |  | P/F applying Silicon sealant of approved make and colour to junctions of wall tiling with aluminium frame 5mm size. | R ft | 0 |  | 0
|  | e |  | P/Laying epoxy grouting in floor | Sq. ft | 0 |  | 0
|  | f |  | Supply, installation, testing & commissioning of sensor with 180 deg coverage & 1 mtr range used for air curtain complete with all required accessories. Make: Any make readily available with min warranty of 1 year. | Nos | 4 |  | 0
|  | g |  | S S chequered plate cladding on cold room panel as per detail drawing | sq.ft | 0 |  | 0
|  | h |  | Providing and fixing water level sensor fully automatic with high and low indicator with alarm (Make : microtail ,OS or equivalent ) | Nos | 2 |  | 0
|  | i |  | S.S Buffing in Brush Finish | sq ft | 0 |  | 0
Sub Total of I.1.0 | [7 empty] | 0
| I.2.0 |  |  | Fitting / Fixing of following item with necessary arrangement as directed
|  | a |  | Table top fitting | Each | 0 |  | 0
|  | b |  | Safe/Furniture /Staff locker/IT Rack | Each | 0 |  | 0
|  | c |  | Money box fixing | Each | 0 |  | 0
|  | d |  | Air Curtain with all fixing arrangement | Each | 2 |  | 0
|  | e |  | Suspension & hanging of Exhaust hood from ceiling | Each | 1 |  | 0
|  | f |  | Speaker fitting | Each | 0 |  | 0
|  | g |  | Pesto flash | Each | 3 |  | 0
|  | h |  | Computer rack | Each | 3 |  | 0
|  | i |  | Strip curtain for oven hood | Job | 1 |  | 0
|  | j |  | Strip curtain for cold room | Job | 1 |  | 0
|  | k |  | Makeline SS sink with fastener | Each | 1 |  | 0
|  | l |  | Loading/Unloading of truck (Domino's material/equipment) | Nos | 1 |  | 0
|  | m |  | Loading/Unloading & disposable of debris (per truck) | Nos | 1 |  | 0
|  | n |  | Loading / Unloading of Servo | Nos | 0 |  | 0
|  | o |  | Water dispenser connection with fittings | Each | 0 |  | 0
|  | p |  | Fixing of Provided Extinguisher | Each | 0 |  | 0
|  | q |  | P/F Door Stopper for Makeline /Slap Table | Each | 3 |  | 0
|  | r |  | Fixing Wall Shelf above Slap Table /Sink | Each | 2 |  | 0
|  | s |  | Fixing of Tissue Paper Holder /Helmet Stand | Each | 2 |  | 0
|  | t |  | L.T Panel commisioning as per site requirement | Each | 0 |  | 0
|  | u |  | Servo connections as per site requirement | Each | 0 |  | 0
|  | v |  | Housekeeping | Sqft | RO |  | 0
|  | w |  | Installation of Fresh air and Exhaust Unit | Each | RO |  | 0
|  | x |  | Sanitizer Stand | Each |  |  | 0
|  | y |  | Bike Fixing with providing nutbolt and labour charge | Each | RO |  | 0
|  | z |  | 200watt Led light | Each |  |  | 0
|  | aa |  | Sensor Tap | Each |  |  | 0
|  | ab |  | Keyboard and Mouse | Each |  |  | 0
|  | ac |  | Fixing of Light Fixtures Provided by TFS (Hood lights are in hood vendor scope) | Each | 45 |  | 0
|  | ad |  | Fixing of T-5 4FT water proof light | no | 0 |  | 0
|  | ae |  | Supplying and erecting double pole metal clad switch with fuse and neutral link 240V, 25A on iron / GI frame switch socket with ISI mark approved make duly erected with modular box , cover plate & all wiring connections complete. (Single phase) | Each | 5 |  | 0
|  | af |  | Fixing and installation of fresh air fan | Each |  |  | 0
|  | ag |  | Fixing and installation of Exhaust air fan | Each |  |  | 0
|  | ah |  | OGT Installation with all required plumbing fittings (CPVC) pipe of 32mm dia under three sink unit | Each | 1
Sub Total of I.2.0 | [7 empty] | 0
0
Note on E169: Dheeraj Yadav: Require detail for the same.

## Material Specifications
Dominos - Standard schedule of Materials
SR.NO | Item | Material Code | Materials | Size in MM | Vendor /Code (OPT-01) | Vendor / Code (OPT -02) | Refer dwg no
A | Floor Tiles
1 | Floor Tiles - (Customer Area) | FF01 | Vitrified Tiles | 600 x 600 | Kajaria -Fog Perla (Approved). Cool cement/ cool silver (Subject to POC approval) (Matt Finish) (Size-600x600)mm | Somany -Ethos grey 600 x 600 mm | Drawing no. -130
2 | Floor Tiles - (Kitchen & Back area) | FF02 | Polished Vitrified Tiles | 600 x 600 | Kajaria-Dessert grey (Approved). Cool gris/cairo gris -(Subject to POC approval) (Matt Finish) (Size-600x600)mm |  | Drawing no. -130
2(a) | Floor Tiles - (Kitchen & Back area) | FF02a |  |  | Kajaria- Terrazzo grey (Full Body) (Size-600x600)mm (Subject to POC approval) | Johnson Endura- Grey plus/ Coated Grey/ Coated grey plus (Size-300x300)mm -(Subject to POC approval)
3 | Floor Tiles | FF03 | Full bodied Vitrified Tiles | 300X1200(tread); 600X1200 (slab size) | Johnson Endura Stepping Stone -DONAPAULA PLAIN 600x600 | Somany - Largo Stepon Verde 300 x 1200 & Largo Riser Verde 200 x 1200 | Drawing no. -130
4 | Floor Tiles | FF04 | Vitrified Tiles | 130X800 | Kajaria - Shesham Rosewood 130 x 800 mm | Somany - Strio Hector Wood Teak 196x1200 | Drawing no. -130
5 | Floor Tiles | FF05 | Vitrified Tiles | 130X800 | Kajaria -Shesham Nero 130 x 800 mm | Somany - Strio Salis Wood Wange 196x1200 | Drawing no. -130
B | Wall Tiles
1 | Brick Tiles | BK01 | Exterior Grade-Aggregate Material-German Handmade | 12mmX8"X2.5" | Articlad - ACG 795 | Unistone (Zara cotswold) / MCM(Code -A Series Brick 54058) | Booth Seating Area Wall
2 | Brick Tiles | BK02 | Exterior Grade-Aggregate Material-German Handmade | 12mmX8"X2.5" | Articlad -ACG 555 | MCM Clay Tile(Code -K series ,facing brick /052)/Unistone (Dholpur) | Storefront
3 | Kitchen Wall tile | TL01 |  |  | Loft Toupe -300x600 Make - Kajaria
4 | Back Wall Tile | TL02 |  |  | Ceramic wall tile white/ Satin white 300x600mm (Plain) Make : -Johnson
C | Counter Cladding Tiles
1 | Tiles |  | Vitrified Tiles | 130X800 | Kajaria -Shesham Oak 130 x 800 mm | Somany - Strio Carrisa Wood Robble 196x1200 | Counter Fascia
2 | Tiles | FF05 | Vitrified Tiles | 130X800 | Kajaria -Shesham Nero 130 x 800 mm | Somany - Strio Salis Wood Wange 196x1200 | Counter & Floor
3 | Tiles |  | Vitrified Tiles | 130X800 | Kajaria - Mahogany 130 x 800 mm | Somany - Strio Rovver wood teak 196x1200 | Counter Fascia
4 | Tiles | FF04 | Vitrified Tiles | 130X800 | Shesham Rosewood 130 x 800 mm | Somany - Strio Hector Wood Teak 196x1200 | Counter & Floor
D | Toilet Tiles
1 | Floor Tile |  | Vetrified Tiles | 300X600 | Kajaria -Fog Perla , Cool cement/ cool silver (Matt Finish) (Size-600x600)mm | Somany -EC sapphire matt 300x300mm | Toilet Detail-770
2 | Wall Tile |  | Vetrified Tiles | 300X600 | Johson- Plain grey 200x300mm | Somany -EC sapphire matt 300x300mm | Toilet Detail-770
3 | Granite |  | Granite stone |  | Jet Black Granite/ Steel grey Granite |  | Toilet Detail-770
E | Corian
1 | Corian Counter |  |  |  | LG ASPEN SNOW - AS 610 | SAMSUNG ASPEN GLOW -AG 636 | REHAU -FORST WHITE 180L
G | Laminates / Veneer
1 | Laminate | LAM 01 | Laminate |  | 14554 RH Hooked Holz Acasia MERINOLAM (Subject to management approval) |  | Generic Drawing
2 | Laminate | LAM 02 | Laminate |  | 21141 Snow White MERINOLAM (Subject to management approval) |  | Generic Drawing
3 | Laminate | LAM |  |  | 5082 LOUSIANA OAK (Subject to management approval)
H | ACP Sheet
1 | ACP sheet for extrnal ceiling |  |  |  | Euro bond- Pure white , code- ER111/ Milky white ER908 (Matt) - Thk 4mm
Alu Décor- Milky white AD202 Matt finish- Thk 4mm
Alstrong-Pure White AL05 Matt finish
I | Paint
| Paint shade | WF 01 | Lustre paint |  | coal mine 8301 Asian Paints |  | Decoration Plan - 140
| Paint shade | WF 02 |  |  | Solemn Grey 8302 (Dark Shade) Asain paint
| Paint shade | WFO3 |  |  | Grey Mtter 8304 Light Shade Asain paint
| Texture | WF 02 | Lustre paint |  | Rain Drop L143, Nickle grey 6126, Grey tint 8435 Asian Paints |  | Decoration Plan - 140
| Metal Paint |  |  |  | Graphite black RAL 9011 Asain Paints (Woodtech spectra)
| Exterior Textured Paint |  | Lustre paint |  | Asain-Fine sand
Spectrum- Grani plast
Grey Mtter 8304 Light Shade
Sl. No. | Product Description | UOM | Qty. per Store | Approved Make | Approved Model No. | Approved Make | Qty per store
1 | 25x25x1500 mm ht. SS Brush finish square handle with lock | Nos. | 2 | Ozone | OGHC-S5(35X1500)SSS | Ozone | 2
2 | Top Pivot Fitting for Glass Door | Nos. | 2 | Ozone | OFS-ACC-TP | Ozone | 2
3 | Floor Spring | Nos. | 2 | Ozone | FS-9400 STD | Ozone | 2
4 | 100 mm wide Double Action SS Hinges | Nos. | 5 | Ozone | OZ-SSBH-SSS | Ozone | 5
5 | Door Closure | Nos. | RO | Dorma | TS 72 |  | RO
6 | Door Handle (22mm Ø x 300mm length) – Single Leaf Flush Door | Nos. | 1 | Dorma | ART No. TGDI30033S | Dorma | 1
7 | Door Lock (for flush doors other than Toilet) | Nos. | RO | Ozone | OZ-NL-22-STD SSS | Ozone | RO
8 | New Chrome Bathroom Vacant –Engaged Indicator Door Lock | Nos. | 1 | DOORCRAFT | SILVER LSTN-10 | Doorcraft | 1
9 | Tower Bolt | Nos. | RO | Ozone | OZ-B-SII | Ozone | RO
I | Adhesives
| Fevicol (Adhesive) | Make - Jivanjor (Multi-purpose Wood Adhesive for long lasting bonds)
| All Rounder (Synthetic Resin Adhesive) | Make - Jivanjor All Rounder is a ready to use premium quality white adhesive specially formulated to give unmatched bond strength, it is also enriched with special preservatives to prevent any bacterial growth during storage therefore providing it with a prolonged life.
| Termilok (Anti Termite wood Preservative) | (Prevents and kills Termites and Borers instantly,Penetrates deep into the wood Eco- Friendly and easy to apply product)
| Champion Super (Synthetic Rubber Adhesive) | Make - Jivanjor (Champion is a high performance synthetic rubber based adhesive with Solvent based Adhesive Fast curing & drying properties ,Delivers superior bond strength.)

## Electrical ,CCTV & PA Make
Approved Make List for Electrical / Instrument works
Sr. No | Item Description | Approved Make
1 | Transformer / CSS | Volt amp/ ABB/ Kirloskar/ CG
2 | VCB /HT Breaker Panel | ABB / L&T /Megavin/ Siemens / Schneider
3 | RMU with Cubicle | ABB / L&T /Megavin/ Siemens / Schneider
4 | CT’s / PT’s | L&T/ Siemens/ AE / Indcoil / Kappa / Ricco / Pragati / Megavin
5 | HT Metering | Huphen
6 | LT panels | ABB/ L&T/ Seimens/ Schneider/ Legrand/ Rettal Urmi Technology/Kulaswaminee or Vendors Shall be CPRI / ERDA Approved)
7 | D.B. | Legrand,Schneider,Siemens
8 | Air circuit Breaker | L&T/ ABB / Legrand/ Schneider/ Seimens
9 | MCB / ELCB / RCCB / ISOLATORS / MCCB /DISTRIBUTION BOARDS | L&T/ ABB / Legrand/ Schneider/ Seimens
10 | Surge Protection Device | L&T/ABB/Legrand.
11 | SFU / Fuse Switch Unit | L&T/ ABB / Legrand/ Schneider/ Seimens / Crompton
12 | HRC Fuses | L&T/ ABB / Legrand/ Schneider/ Seimens / Crompton
13 | Capacitor | L & T / Malde/ Epcos/ Trinity
14 | APFC Relay | L & T / GEC / Emercon / Alstom
15 | Contactor / Timer / Starter | L & T / ABB
16 | Relays | L&T/ ABB / Legrand/ Schneider/ Seimens / Crompton
17 | Timer | L&T/ ABB / Legrand/ Schneider/ Seimens / Crompton
18 | Ammeter / Voltmeter / Power factor meter / Frequency meter / Energy meter | Elmeasure/ ABB/ L&T/ Legrand/ Trinity/ Schnieder
20 | Changeover Switch | L&T/ ABB/ C& S
21 | Rotary Switch / Selector Switch | Siemens / L & T / GE / Kaycee
22 | Lightning Pro. System | ABB/ Synergy / Indelec / Stormaster(LPI)/ JEF
23 | UPS | Eaton/ Emerson/ Socomech
24 | Batteries | Exide / Amaron / Panasonic
25 | HT /LT Cables | Polycab/ RR/ KEI/havells
26 | Cables & Wires | Polycab/ RR/ KEI/havells/panasonic
27 | Fire survival cable | AFW / FR Tek / Ravin / Bontn / Tyco
28 | Cable Glands- Double Compression | Dowels / Bracco / Comet
29 | Cable Jointing | Raychem / M Seal
30 | Copper multi-strand wires | Polycab / KEI / RR /Finolex / Gloster
31 | Lugs | Dowels / Bracco / Comet
32 | Cable Tray & Race Ways (Factory Fabricated)& JB | Indiana/ Legrand/ MK/ Globe / Rico Steel
33 | PVC pipes and accessories | Precision / Avonplast / AKG / Modi / Polycab
34 | GI pipes | Zenith / Tata / Jindal
35 | GI Octagonal Poles | Bajaj / Aster / KL Industries
36 | High mast | Bajaj / Transrail
37 | Switches / Sockets / TV, Telephone Socket, etc. (modular)- | L&T/ Legrand / Indoasian/ Anchor ( Wood/Roma ) / MK (Wrapround) / Crabtree (Anthena)
38 | Fan Regulator | MK /Legrand/MDS (To match with the switch / sockets)
39 | Outdoor Boxes | MK/ Clipsal / Henzel / Hunter / Sintex / National
40 | Thermometers
41 | Indicating Meters
42 | Signal Lamps
43 | Push Buttons
44 | Motor / Motor Used in Air wahser | Siemens/ ABB/ Crompton/
45 | Main Fire Alarm Panel (UL / FM / LPCB Approved) | Notifier/Edwards/Simplex/Apollo
46 | Smoke / Heat Detectors with Base (UL / FM / LPCB Approved) | Notifier/Edwards/Simplex/Apollo
47 | Devices & Modules (UL / FM / LPCB Approved) | Notifier/Edwards/Simplex/Apollo
48 | Ceiling fans | Crompton / Havells/ Bajaj / Anchor / Orient / Usha / Khaitan
49 | Exhaust / Pedestal Fan | Crompton / Bajaj / Anchor / Orient / Usha / Khaitan
50 | Fixture | Philips / Crompton /Bajaj / Wipro / LT/ Sudhir
ELV
51 | Telephone Wire / Cables | Finolex / Tata (Lucent) / ITL / Skytone / Gemscab / Delton / National / L&T / Polycab
52 | Television Coaxial Cable | Polycab/ Finolex / RR /RPG / L&T
53 | Network cable | Digisol / Schneider / Avaya/ Systemec / Finolex / Legrand / Dlink
54 | Telephone Instrument | BPL / Tata / Siemens /Avaya / Beetel
55 | Telephone Tag Box | ITL or any equivalent approved make
56 | Automatic Voltage Corrector | Jindal / GES / Muskaan
57 | Annunciator | Areva/ Minilec / Alan
58 | Terminal Blocks | Connect well/ Elmex / Technoplast
59 | Ethernet switch | Sony / Bosch / AVAYA/ Cisco/ Dlink / DigiSol
60 | Patch Panel | AVAYA/ Siemens / Dlink / DigiSol / Legrand
61 | Rack for patch panel & switches | HCL/ Rittal / President / Valrack / Legrand / Digilink
62 | Occupancy Sensor / Day Light Sensor | Siemens, Legrand
63 | BMS system | Siemens.
64 | Cat 6 UTP wire | Legrand, d-link, amps, polycab
65 | Telephone/data wiring accessories | Legrand, d-link, amps, polycab,
66 | 24 port Patch Panel | D-LINK or any other equivalent make
67 | UTP Patch cord | D-LINK or any other equivalent make
68 | Telephone/ TV/ Network poert (modular)- | Legrand/L&T/systimax or Equivalent
69 | Telephone Wire / Cables | L&T / Polycab/ Finolex/ D-link or equivalent
70 | Television Coaxial Cable | Polycab/ Finolex / RR /RPG / L&T
71 | Network cable | Legrand / Dlink/ Digisol / Schneider / Avaya/ Systemec / Finolex /
72 | EPABX | Panasonic/ Systimax/ Avaya / NEC / LG Aria / Siemens / Alcatel
73 | Telephone Instrument | Panasonic/ Systimax/Avaya / Beetel
74 | Telephone Tag Box | ITL or any equivalent
75 | Terminal Blocks | Connect well/ Elmex / Technoplast
76 | Ethernet switch | Sony / Bosch / AVAYA/ Cisco/ Dlink / DigiSol
77 | Patch Panel | AVAYA/ Siemens / Dlink / DigiSol / Legrand
78 | Rack for patch panel & switches | HCL/ Rittal / President / Valrack / Legrand / Digilink
79 | Cat 6 UTP wire | Legrand, d-link, amps, polycab
80 | Telephone/data wiring accessories | Legrand, d-link, amps, polycab,
81 | Conduit | Panasonic/AKG
CCTV
82 | IP IR Box/Bullet Camera | Bosch / Panasonic/ Sony/ Honey well
83 | IP IR Fixed Dome Camera | Bosch / Panasonic/ Sony/ Honey well
84 | IP PTZ Camera | Bosch / Panasonic/ Sony/ Honey well
85 | Network Video Recorder | Bosch / Panasonic/ Sony/ Honey well
86 | POE layer 2 Switch | CISCO/ D-LINK/ ALLIED TELESIS
87 | UTP networking Cat-6 cable | MOLEX/ DLINK/COMSCOPE
88 | Hard disk | WD/ SEAGATE/ Honey well
89 | 40" LED Monitor, Display Resolution : Full HD | LG/ Samsung / Sony
90 | I.S.I. mark Rigid P.V.C. conduit | Precision
91 | POE injector | CISCO or any other equivalent make
92 | Router | D-LINK or any other equivalent make
Emergency Items
93 | Rechargeable torch | Energizer,prolite
94 | Exit signage | Prolite,philips, bajaj
95 | Main Fire Alarm Panel (UL / FM / LPCB Approved) | Notifier/Edwards/Simplex/Morley/System Sensor/Apollo/Ravel
96 | Smoke / Heat Detectors with Base (UL / FM / LPCB Approved) | Simplex /Notifier/Edwards /Morley/ System Sensor/Apollo/Ravel