## KFC T2
TRAVEL FOOD SERVICES
BOQ STANDARDISATION, IMPLEMENTATION AND COST CONSULTANCY |  | CIVIL Dismantiling BOQ OF KFC - -T2-BIAL-BENGALURU
[7 empty] | Purchase |  |  |  |  | Execution team 15/12/22
SR. NO. | SHORT ITEM DESCRIPTION | PARTICULARS | UOM | QTY. | Fixing Rate | Total Amount | Rate | Amount | Remark | Remarks | Comments from Execution team 12/12/22 | Comments from exe. team & along with M&A 15/12/22 | Rate | Amount
|  | GENERAL NOTES | [11 empty] | 0
1 | Breaking & demolishing brick masonry/concrete blocks | Dismantling and demolishing brick/ block work in lime or cement mortar including plaster, paint, etc. manually/ by mechanical means including stacking of serviceable material and disposal of unserviceable material within 125 metres lead as per direction of Engineer-in-charge. | sqmt | 80 | 1300 | 104000 | 1150 | 92000 | Dezincon rates | add rate | Item is ok. Please check the rate. Qty also incorrect. It should be approximately 70sqm only | Dezincon rates | 1150 | 92000
2 | RCC members colum | Dismantling and demolishing any R.C.C. structure, member, etc., in any thickness and size manually/ by mechanical means including stacking of steel bars and disposal of unserviceable material within 125 metres lead as per direction of Engineer - in- charge. | RM | 50 | 1500 | 75000 | 920.36 | 46018 | Dezincon rates | add rate | Pleae check the rate. The unit to be in RM and qty to be approximately 32RM. | Desincon rates | 300 | 15000
3 | Debris | Removing Debris out of site included loading, unloading & shifting as per statutory rules and regulations. | NO | 4 | 7500 | 30000 |  | 30000 | On actuals | add rate | This to be part of item 1& 2 | This work done in short notice due to PM visit and work to be completed before security sweep alos. Normal route was blocked due to PM visit and vendor has to take debris in differenct long route. For this we have to pay extra. | 7500 | 30000
|  | TOTAL OF A. Dismantling WORK |  |  |  | 209000 |  | 168018 | 0 | 0 | 0 | 0 |  | 137000