## Extra Item
EXTRA ITEM
Sr No. | Item Description | UOM | Qty | Unit price | Amount | REMARKS (APPROVAL FOR QTY ONLY)
1 | P/F Nani Trap with Clamps | Nos | 2 | 1500 | 3000 |  | Note: All Extra Items rate needs to be dicussed with procurement team.
2 | P/F Drain pipe 3" (75mm) | RMT | 11.3289 | 150 | 1699.335
3 | P/F Drain Jali (SS Grating) | Nos | 2 | 600 | 1200
4 | P/F Entrance door with all Necessary fittings (.950x2.020) & View Panel | Nos | 1 | 20000 | 20000 | Door provided by TFS. Door Amount to be deducted.
5 | P/F Partition with both side laminate | SFT | 13.2456 | 450 | 5960.502
6 | P/F Door frame (section 3"x1.5") | RFT | 16.3672 | 150 | 2455.08
7 | P/F of new MCBs of 16A | Nos | 10 | 200 | 2000
8 | P/F of new MCBs of 32A | Nos | 4 | 600 | 2400
9 | P/F of new MCBs of 10A | Nos | 2 | 175 | 350
10 | P/F of new MCBs of 63A of 4 pole | Nos | 1 | 1900 | 1900
11 | P/F 20mm PVC Conduits for laying wires with necessary clamping & fittings | RFT | 500 | 0 | 0 | It’s the part of the point wiring work. |  | 25
12 | Wiring for equipments, lights, etc (3 nos ) |  |  |  | 0
13 | Installation of LED bulb lights as per drawing and specs given | Nos | 64 | 125 | 8000
14 | Installation of Lights (Wall Light) | Nos | 2 | 500 | 1000
15 | Led strip light ( Buffet Counter) | Nos | 2 | 500 | 1000
16 | Led strip light ( Bar Counter ) | Nos | 1 | 500 | 500
17 | Neon Light fixing | Nos | 15 | 200 | 3000
18 | P/F of Enemal paint | SFT |  | 60 | 0
19 | Gate Valve (20mm) | Nos | 2 | 500 | 1000
20 | Brass Elbow (20mm) | Nos | 5 | 0 | 0 | Elbow is a part of BOQ plumbing supply (CPVC) line. |  | 800
21 | P/F Instant Gyser Racold 3Ltr | Nos | 1 | 6000 | 6000
22 | P/F Connection pipes | Nos | 2 | 0 | 0 | Its part of P/F Geyser inatllation |  | 200
23 | Vinyl protection with wooden beading | RFT | 57.4328 | 50 | 2871.64
24 | Sink Installation | Nos | 1 | 1000 | 1000
25 | P/F Cable manager |  | 2 | 0 | 0 | Its cost should be included in main counter |  | 200
26 | Malba removal from site |  | 1 | 5000 | 5000
27 | Site Deep CLeaning | SFT | 2000 | 10 | 20000
28 | Point wiring switch to DB (Circuits for lights-Star Points 2, neon, cocktail & neon lights 15nos & bulb 2 circuit points from switch socket, ) | Nos | 7 | 1200 | 8400
29 | Looping for Star Points 2, neon, cocktail & neon lights 15nos & bulb 2 circuit points from switch socket, | Nos | 85 | 250 | 21250 | Plz correct the MB as well |  | 62+13+1+1+13
30 | Db dressing with thimble | Nos | 1 | 8000 | 8000
31 | Vynl flooring protection from polythene | SFT | 201.033 | 10 | 2010.3295
32 | LAN and switch plate installation (IO Port) | Nos | 1 | 1500 | 1500
33 | Wooden floor grrove filling with fevicol and wood powder | SFT | 1242.3496 | 18 | 22362.2928
34 | Wooden flooring top layer grinding | SFT | 1242.3496 | 18 | 22362.2928
35 | White laminate installation for cove | SFT | 83.2566 | 90 | 7493.0918
36 | P/F Glass Hanger SS 400mm on Bar shelf | Nos | 18 | 500 | 9000 | QTY ok, As its not part of BOQ
37 | Differential for Item No. 42 & 43 of Main Boq | L/S | 1 | 25000 | 25000 | To be given only after dicsusion and approval from Procurement team
25 | P/f New Buffet counter Made with 19MM Ply with counter top finish with 12mm thick corian (Staron EG595 Metallic or Staron FR148 Radiance Shimmer or may be both), as approved make with as approved design and details with salad counter. | SFT | 64.2 | 3800 | 243960 | Rate needs to be dicussed with Procurement team
|  |  |  | total | 461674.564

## Items as per site requirement
S.No | ITEM | AREA | UOM | L | B/H | NOS | QTY | SFT | Rate
1 | 2nos Nanitrap with clamp -4" | FOH | Nos | 1 | 1 | 2 | 2 | 6.56
| TOTAL 4" PVC DRAIN PIPE QTY | [6 empty] | 6.56
2 | Drain pipe 3" (75mm) | FOH - 1.3989+2.361+0.15+0.12+0.12+3.6+0.529+2.25+0.8 | RMTR | 11.3289 | 1 | 1 | 11.3289 |  |  | Includes PVC band, socket, tee band, Reducer, plain tee, holes set, clamp 3" , Araldite, extension nipple.
| TOTAL 3" PVC DRAIN PIPE QTY | [5 empty] | 11.3289
3 | Drain Jali (SS Grating) |  | nos | 1 | 1 | 2 | 2 | 2
2
4 | Entrance door with Necessary fitting | .950x2.020 | nos | 1 | 1 | 1 | 1 | 1
1
5 | Partition with both side laminate |  | sft | 2.25 | 1.4 | 1 | 3.15 | 33.894
|  |  | SFt | 0.95 | 2.02 | -1 | -1.919 | -20.6484
| TOTAL Partition QTY | [6 empty] | 13.2456 |  | 40
3 | Door frame |  | rft | 4.99 | 1 | 1 | 4.99 | 16.3672 | With ply door frame made.
16.3672
4 | Increase in number of MCB | MCB 16 | nos | 1 | 1 | 10 | 10
|  | MCB 32 |  | 1 | 1 | 4 | 4
|  | MCB 10 |  | 1 | 1 | 2 | 2
|  | 64 4 pole TPN |  | 1 | 1 | 1 | 1
17
4 | Wiring for equipments, lights, etc | Wiring 300x3x1green | rft | 300 | 1 | 4 | 1200
5 | Installation of LED bulb lights and separte circuit and looping points with as per drawing and specs given |  | Nos | 1 |  | 64 | 64
| TOTAL QTY | [5 empty] | 64
6 | Installation of Lights | Wall Light | Nos | 1 |  | 2 | 2
| Led strip light | Buffet Counter | Rmtr | 1 |  | 1 | 1
|  | Bar Counter | Rmtr | 1 |  | 1 | 1
| Neon Light fixing |  | Lot | 1 |  | 1 | 1
5
7 | Enamle Paint | Railing of balcony-1 | sft | 6.08 | 0.9 | 2 | 10.944 | 117.7574
|  | Railing of balcony-1 | sft | 3.38 | 0.9 | 1 | 3.042 | 32.7319
|  | Railing of balcony-2 | sft | 3.58 | 1.04 | 2 | 7.4464 | 80.1233
|  | Railing of balcony-2 | sft | 4.09 | 1.04 | 1 | 4.2536 | 45.7687
|  | Railing of balcony-3 | sft | 1.3 | 1.05 | 2 | 2.73 | 29.3748
|  | Railing of balcony-3 | sft | 3.3 | 1.05 | 1 | 3.465 | 37.2834
|  | Railing of balcony-3 | sft | 3.5 | 1.3 | 1 | 4.55 | 48.958
5 |  | Toilet door (Back side) | sft | 0.68 | 2.08 | 1 | 1.4144 | 15.2189
|  | Drain pipe line painted | RFT | 11.328 | 1 | 1 | 11.328 | 37.1558
[7 empty] | 49.1734 | 444.3723
6 | Plumbing line | Needs to be included with bends,elbow, | Nos.
| Elbow 20mm |  | Nos. | 10 |  |  |  |  | Its a part of BOQ plumbing line.
| Socket -20mm |  | Nos. | 13 |  |  |  |  | Its a part of BOQ plumbing line.
| Gate Valve |  | Nos. | 2 |  |  |  |  | ok
| Union |  | Nos. | 2 |  |  |  |  | Its a part of BOQ plumbing line.
| CPVC Pipe -20mm |  | Nos | 22 | 10 |  |  |  | Its a part of BOQ plumbing line.
| CPVC Pipe -Solvent |  | Nos | 8 |  |  |  |  | Its a part of BOQ plumbing line.
| CPVC -Clamp |  | Nos | 8 |  |  |  |  | Its a part of BOQ plumbing line.
| Brass Elbow |  | Nos | 5 |  |  |  |  | Its a part of BOQ plumbing line.
7 | P/F Instant Geyser 3Ltr |  | Nos |  |  | 1
8 | Vynal protection with wooden beading |  | rft |  |  | 17.51 | 57.4328
9 | Sink Installation |  | Nos |  |  | 1 |  | 1
10 | Cable manager installation |  | Nos |  |  | 2 |  | 2
11 | Malba removal from site |  | Nos |  |  | 1 |  | 1
| Site Deep cleaning |  | Nos |  |  | 1 |  | 1
12 | Point wiring switch to DB
| Electrical point for Graphics area | Star Points 2, neon, cocktail & neon lights 15nos & bulb 2 circuit points from switch socket & 64bulbs | Nos |  |  | 85 |  | 85
14 | Db dressing with thimble |  | NOs |  |  | 1 |  | 1
15 | Vynl flooring protection from polythene |  | SFT | 5.077 | 3.68 | 1 | 18.6834 | 201.033
16 | LAN and switch plate installation |  | nos |  |  | 1
17 | Wooden floor grrove filling with fevicol and wood powder |  | SFT | 115.46 | 1 | 1 | 115.46 | 1242.3496
18 | Wooden flooring top layer grinding |  | SFT | 115.46 | 1 | 1 | 115.46 | 1242.3496
19 | White laminate installation for cove |  | sft | 4.67 | 0.24 | 2 | 2.2416 | 24.1196
|  |  | sft | 1.2 | 0.24 | 1 | 0.288 | 3.0989
|  |  | sft | 5 | 0.24 | 4 | 4.8 | 51.648
|  |  | sft | 0.85 | 0.24 | 2 | 0.408 | 4.3901
83.2566
20 | Bar Hanger SS 400mm |  | Nos | 1 | 1 | 18 | 18
21 | Differential for Item No. 42 & 43 of Main Boq
25 | Buffet Counter Modifications |  | SFT | 3.824 | 1.1 | 1 | 4.2064 | 45.2609 | Modifications work in counter & new laminate & corian installation and LED strip installation,dismantlling of existing counter
| New Buffet Counter |  | SFT | 1.6 | 1.1 | 1 | 1.76 | 18.9376
64.1985