## Summary
SUMMARY OF PLUMBING WORK, Copper Chimney, Oberoi Mall, Goregaon, Mumbai
DATE: 20-04-2024
S.NO | Description | BOQ AMOUNT | RA-01 (60%) | RA-02 (15%) | FINAL BILL | CUMULATIVE BILL 100%
A | PLUMBING WORKS | 434290 | 260574 | 65143.5 | 72248.1 | 397965.6
| Total | 434290 | 260574 | 65143.5 | 72248.1 | 397965.6
| i) GST on Work Contracts | 78172.2 | 46903.32 | 11725.83 | 13004.658 | 71633.808
| Total with Taxes (A) | 512462.2 | 307477.32 | 76869.33 | 85252.758 | 469599.408

## KITCHEN AND BAR PLUMBING BOQ
PLUMBING BOQ FOR COPPER CHIMNEY (OBEROI MALL)
|  |  |  | AS PER ORDER |  |  | AS PER SITE
SR. NO. | MATERIAL | DESCRIPTION | UNIT | QTY. | RATE | AMOUNT | QTY | AMOUNT
1 | CPVC pipes | Supply, laying, testing and commissioning of FOOD GRADE CPVC pipes FOR RO WATER PIPING conforming to CTS (copper tube size) SDR-11 as per ASTM D 2846 with necessary fittings up to the size of 50 mm dia , jointing with CPVC solvent cement of medium body IPS brand or equivalent conform
a |  | 20mm dia | RFT | 222 | 100 | 22200 | 128.79 | 12879
b |  | 25mm dia | RFT | 88 | 120 | 10560 | 184.3 | 22116
c |  | 32mm dia | RFT | 15 | 140 | 2100 | 59.66 | 8352.4
d |  | 40mm dia | RFT |  |  |  | 0 | 0
2 | CPVC pipes (HOT WATER) | Supply, laying, testing and commissioning of CPVC - Schedule 80 pipes and fittings suitable for domestic hot water application (max. temp.85 Deg.C) rated for a working pressure of 5 kg/cm2 and conforming to latest Indian / International Standards for Ver
a |  | 20mm dia | RFT | 84 | 115 | 9660 | 50.32 | 5786.8
b |  | 25mm dia | RFT | 8 | 140 | 1120 | 39.66 | 5552.4
3 | Thermal Insulation (HOT WATER) | Supply and covering (Thermal Insulation) hot water pipes with 13 mm thick performed closed cell nitrite rubber pipe section insulation having density not less than 60 kg/cm2 and "K" valve not more than 0.034 w/m Deg. K @ 20 Deg C mean temperature, jointin
a |  | 20mm dia | RFT | 84 | 100 | 8400 | 38.64 | 3864
b |  | 25mm dia | RFT | 8 | 120 | 960 |  | 0
4 | G.I. `C' class pipes | Supply, laying, testing and commissioning of G.I. `C' class pipes and fittings 'suitable for domestic cold water application rated for a working pressure of 5 kg/cm2 and conforming to IS 1239 (Part-I)-1979 for and equipments, including bitumastic hessia
a |  | 15mm dia | RFT |  |  | 0 |  | 0
b |  | 20mm dia | RFT |  |  | 0 |  | 0
c |  | 25mm dia | RFT |  |  | 0 |  | 0
d |  | 32mm dia | RFT |  |  | 0 |  | 0
e |  | 40mm dia | RFT |  |  | 0 |  | 0
4 | Ball Valves | Supply, installing testing and commissioning of ISI marked gun metal screwed pattern non-return Valve conforming to IS 778 Class 1 including jointing, supporting etc. complete and as directed.
a |  | 15mm dia | nos |  |  | 0
a |  | 20mm dia | Nos | 23 | 900 | 20700 | 18 | 16200
b |  | 25mm dia | Nos | 1 | 1050 | 1050 | 4 | 4200
c |  | 32mm dia | Nos | 2 | 1575 | 3150 | 3 | 4725
e |  | 40mm dia | nos |  |  | 0
f |  | 50mm dia | nos |  |  | 0
g |  | 65mm dia | nos |  |  | 0
5 | UPVC SWR PIPES | Supply, laying , testing & commissioning of UPVC-SWR pipes conforming to IS 13592/92 and fittings conforming to IS-14935/99, cutting the pipes to required lengths, laying in position to required grade and level, jointing, making holes, pockets, chases in TYPE B 6 KG
a |  | 100mm dia | RFT | 63 | 575 | 36225 | 61.28 | 35236
|  | 90mm dia | RFT |  | 400 | 0 |  | 0
b |  | 75mm dia | RFT | 37 | 400 | 14800 | 36.91 | 14764
|  | 63mm dia | RFT |  |  | 0 |  | 0
c |  | 50mm dia | RFT | 55 | 365 | 20075 |  | 0
b | RAIN WATER PIPE | 100mm dia RAIN WATER PIPE | rft |  |  | 0
6 | FLEXIBLE PIPES | Supply, laying ,OF FLEXIBALE PIPES pipes to required lengths, laying in position to required grade and level, jointing, making holes, pockets, chases in
a |  | 50mm dia | RFT | 15 | 105 | 1575
7 | FLOOR TRAP/ MULTI FLOOR TRAP | Supply, laying, testing & commissioning of approved Cast iron FLOOR TRAP/ MULTI FLOOR TRAP with aproved make leavy duty round or square s.s. grating etc. complete. | Nos | 7 | 1125 | 7875
7 | Deep Seal trap | Supply, laying, testing & commissioning of approved C I make Deep Seal Trap with aproved make leavy duty round or square s.s. grating etc. complete. | nos |  |  | 0
9 | P/S trap | Supply, laying, testing & commissioning of approved uPVC /C I P/S trap with aproved make AS PER DRAWING & REQUIREMENT |  |  |  | 0
8 | Jali | Jali with cokroch trap above nhani trap & clean out POP up type | Nos | 7 | 575 | 4025 | 3 | 1725
8 | Floor Clean Out/Rodding Eye | Supply, laying, testing & commissioning of approved uPVC Floor Clean Out/Rodding Eye with aproved make leavy duty round or square s.s. grating etc. complete. Or ceiling eye for cleaning
a |  | 160mm dia | nos |  |  | 0
a |  | 110mm dia | nos |  |  | 0
c |  | 75mm dia | nos |  |  | 0
d | Gully Trap | Supply, laying, testing & commissioning of patel patatent c.I. Gully trap of outlet size 100MM dia consisting of CI black inlet chambers with 100 dia branch inlet as required with deep seal 'P' trap CI cover size 200 X 200 with SS crews etc complete an | nos |  |  | 0
9 | Chamber | Supply, laying, creating & commissioning of SS chamber 16 G SS PLATE WITH SUITABLE DEPTH 5MM THK MS PIPE WELDED TO CHAMBER WITH SUITABLE THREAD AND LOCATION AS PER DRAWING WITH TOP GRATING AND PERFOARETED JALI AS PER DESIGN
a |  | SIZE 14" X 14" | Nos | 6 | 5250 | 31500 | 12 | 63000
b |  | SIZE 87" X 08" | Nos | 2 | 16700 | 33400 | 2 | 33400
c |  | SIZE 12" X 54" | nos |  |  | 0
|  | SIZE 18 X 26 | nos |  |  | 0
10 | Hooper | Providing & fixing of GI inlet hooper with two or three inlets fittings to receive waste pipes from fixture waste including joints etc complete and as directed | nos |  |  | 0
10 | W.C. | Providing and fixing of Wall hung water closet ( hindware,parryware) with M.s frame, c.p bolt, nuts and solid seat cover and lid with c.p hinges and rubber buffers,brown clour | nos |  |  | 0 | Rate to vary as per architectspecification
11 | Wash Basin | Providing and fixing of Wash basin ABOVE counter, 15mm coupling with plug chain 32mm dia c.p bottle trap cold water supply connecting pipe, AS PER ARCHITECTS SPECIFICAION | nos |  |  | 0 | Rate to vary as per architectspecification
12 | Urinal | Providing and fixing Sensor urinal (hindwear) with bottletrap | nos |  |  | 0 | Rate to vary as per architectspecification
13 | Health faucet | Providing and fixing Health faucet of closet mounting type with angle valve | nos |  |  | 0 | Rate to vary as per architectspecification
10 | Bib cock | Providing and fixing Bib cock with wall flange | Nos | 11 | 2450 | 26950 | 0 | 0
11 | Stop cock | Providing and fixing Stop cock with wall flange | Nos | 4 | 1580 | 6320 | 0 | 0
12 | Angle cock | Providing and fixing Angle cock with wall flange | Nos | 17 | 1875 | 31875 | 17 | 31875
18 | Piller cock | Providing and fixing Pillar cock of approved make for Wash room | Nos |  |  | 0
19 | Piller cock | Providing and fixing Pillar cock of approved make | Nos |  |  | 0
13 | Geyser storage | Providing and supplying 25 litrs geyser with c.p angle cock of hot and cold pvc connection & coupper pipes c.p elbows non return valves mounting bolts etc | Nos | 2 | 13500 | 27000 | 2 | 27000
18 | Geyser storage | Providing and supplying 15 litrs geyser with c.p angle cock of hot and cold pvc connection & coupper pipes c.p elbows non return valves mounting bolts etc | Nos |  |  | 0
27 | Geyser storage | Providing and supplying 15 litrs geyser with c.p angle cock of hot and cold pvc connection pipes c.p elbows non return valves mounting bolts etc | Nos |  |  | 0
|  | Providing and supplying 25 litrs geyser with c.p angle cock of hot and cold pvc connection pipes c.p elbows non return valves mounting bolts etc | Nos |  |  | 0
19 | Toilet paper holder | Providing and fixing Toilet paper holder | Nos |  |  | 0 | Local Make
20 | Soap dispenser | Providing and fixing Soap dispenser | Nos |  |  | 0 | Local Make
21 | Paper napkin dispenser | Providing and fixing Paper napkin dispenser | Nos |  |  | 0 | Local Make
22 | Hand dryer | Providing and fixing Hand dryer | Nos |  |  | 0 | Russel Make
14 | Sink mixture | Providing and fixing Sink mixture | Nos | 3 | 4450 | 13350 | 5 | 22250
15 | Sink Tap | Providing and fixing counter top tap ( Swan Neck ) | Nos | 3 | 3840 | 11520 | 1 | 3840
16 | Rinse Mixture | Providing and fixing Rinse Mixture | Nos | 2 | 5000 | 10000 | 2 | 10000
15 | Equipment connection | Doing Equipment connection And Insallation (labour charges only) | Nos | 10 | 1000 | 10000 | 10 | 10000
33 | Channel Drain | Supply ,laying,testing & commissing of heavy quility SS Grating of thickness 38MM with MS angle runners including fixing with hold fast applaying three coats of anti corrosive Bitumastic paint etc complete and as directed
34 |  | 300X200mm size and 38mm thick | MTR |  |  | 0
35 |  | 1000X150mm size and 38mm thk. & weighing more than 35Kg. | nos |  |  | 0
16 | Sink connection | Providing & fixing Sink Drain outlet Connection with valve & drain pipe complete with all necessary fittings | Nos | 6 | 2400 | 14400 | 8 | 19200
17 | Grease Trap | Providing & fixing SS MADE Greece Trap MAKE Bombay Iron Works or any approved make. OR CONSTRUCTING THE SAME AS PER DRAWING
a |  | Size 18" X 24" | Nos | 3 | 10500 | 31500 | 2 | 21000
37 |  | Size 3'-0" X 2'-0" | Nos |  |  | 0
a | Foot paddle operated faucet | foot paddle operated faucet | Nos |  |  | 0 |  | 0
b | Water level sensor indicative panel | Water level sensor indicative panel | Nos |  |  | 0 |  | 0
18 | RO Plant | RO connection only | Nos | 2 | 1000 | 2000 | 1 | 1000
19 | Water Tank | Providing and fixing 500 LTR water tank for RO water | Nos | 1 | 10000 | 10000 | 1 | 10000
20 | Pressure Pump | Providing and fixing of 1HP pressure pump in RO water line | Nos | 1 | 10000 | 10000 | 1 | 10000
28 | WATER TANK | TANK 1500 LTR | Nos | 0 |  | 0 |  | 0
|  | TOTAL |  |  |  | 434290 |  | 397965.6
|  | GST 18% |  |  |  | 78172.2 |  | 71633.808
|  | SUB TOTAL |  |  |  | 512462.2 |  | 469599.408
Note on C4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: RO Water & RAW Water Piping Considered

## MB KITCHEN AND BAR PLUMBING
MEASUREMENT SHEET OF PLUMBING OF KITCHEN AND BAR, COPPER CHIMNEY (OBEROI MALL)
SR. NO. | MATERIAL | DESCRIPTION | UNIT | NOS | LENGTH | WIDTH/HEIGHT | TOTAL
1 | CPVC pipes | Supply, laying, testing and commissioning of FOOD GRADE CPVC pipes FOR RO WATER PIPING conforming to CTS (copper tube size) SDR-11 as per ASTM D 2846 with necessary fittings up to the size of 50 mm dia , jointing with CPVC solvent cement of medium body IPS brand or equivalent conform
a |  | 20mm dia RO WATER SUPPLY | RFT
|  | Bar 25mmm dia => 20mm to Angle Cock | RFT | 1 | 6.16 |  | 6.16
|  | Supply to angle cock | RFT | 1 | 1.66 |  | 1.66
|  | 25mm dia to 20mm dia Live Kitchen outer sink | RFT | 1 | 13.91 |  | 13.91
|  |  | RFT | 1 | 8.5 |  | 8.5
|  |  | RFT | 1 | 9.66 |  | 9.66
|  |  | RFT | 1 | 12.33 |  | 12.33
|  |  | RFT | 1 | 13.75 |  | 13.75
|  |  | RFT | 1 | 18.83 |  | 18.83
|  |  | RFT | 1 | 4.5 |  | 4.5
|  |  | RFT | 1 | 3.83 |  | 3.83
|  |  | RFT | 1 | 17.75 |  | 17.75
|  |  | RFT | 1 | 8.66 |  | 8.66
|  |  | RFT | 1 | 9.25 |  | 9.25
20mm dia RAW WATER SUPPLY
|  | Bar Sink drop | RFT | 1 | 10.5 |  | 10.5
|  | bar | RFT | 1 | 4.83 |  | 4.83
|  | Live Kitchen sink drop | RFT | 1 | 8.5 |  | 8.5
|  | Potwash sink drop | RFT | 1 | 8.5 |  | 8.5
|  | Hot section sink drop | RFT | 1 | 8.5 |  | 8.5
|  | Dishwash sink drop | RFT | 3 | 8.5 |  | 25.5
|  | Dishwasher drop | RFT | 1 | 8.5 |  | 8.5
|  | Water cooler sink drop | RFT | 1 | 8.5 |  | 8.5
|  | TOTAL | RFT |  |  |  | 128.79
b |  | 25mm dia | RFT
|  | Main line 32mm to 25mm dia=> BAR | RFT | 1 | 38.83 |  | 38.83
|  | Main line to Loft tank => RO | RFT | 1 | 18.33 |  | 18.33
|  | RO towards Water cooler=> Kitchen door | RFT | 1 | 22.33 |  | 22.33
|  | Kitchen door=> Sink outside Live kitchen | RFT | 1 | 14.58 |  | 14.58
|  |  | RFT | 1 | 16.58 |  | 16.58
|  |  | RFT | 1 | 13.33 |  | 13.33
25mm DIA RAW WATER SUPPLY
|  | Main connection line to Live Kitchen & BAR | RFT | 1 | 31.91 |  | 31.91
|  | Dishwash | RFT | 1 | 13.83 |  | 13.83
|  | Kitchen door=> Sink outside Live kitchen | RFT | 1 | 14.58 |  | 14.58
|  | TOTAL |  |  |  |  | 184.3
c |  | 32mm dia RO WATER SUPPLY | RFT
|  | Main line towards BAR | RFT | 1 | 9.25 |  | 9.25
|  | 32MM Dia RAW WATER SUPPLY | RFT
|  | Main supply Towards Bar | RFT | 1 | 14.83 |  | 14.83
|  | Main supply => Towards Hot section=>Dishwash | RFT | 1 | 35.58 |  | 35.58
|  | TOTAL |  |  |  |  | 59.66
d |  | 40mm dia | RFT
2 | CPVC pipes (HOT WATER) | Supply, laying, testing and commissioning of CPVC - Schedule 80 pipes and fittings suitable for domestic hot water application (max. temp.85 Deg.C) rated for a working pressure of 5 kg/cm2 and conforming to latest Indian / International Standards for Ver
a |  | 20mm dia | RFT
|  | Potwash Drop to angle cock | RFT | 1 | 10.25 |  | 10.25
|  | Geyser to Main line | RFT | 1 | 8.66 |  | 8.66
|  | '' | RFT | 1 | 12.75 |  | 12.75
|  | Dishwash Drop | RFT | 2 | 9.33 |  | 18.66
|  | TOTAL |  |  |  |  | 50.32
b |  | 25mm dia | RFT
|  | Main line from 32 to 25 Towards Potwash | RFT | 1 | 10.83 |  | 10.83
|  | Geyser to potwash | RFT | 1 | 17.25 |  | 17.25
|  | Dishwash | RFT | 1 | 7.25 |  | 7.25
|  | Dishwash | RFT | 1 | 4.33 |  | 4.33
|  | TOTAL |  |  |  |  | 39.66
3 | Thermal Insulation (HOT WATER) | Supply and covering (Thermal Insulation) hot water pipes with 13 mm thick performed closed cell nitrite rubber pipe section insulation having density not less than 60 kg/cm2 and "K" valve not more than 0.034 w/m Deg. K @ 20 Deg C mean temperature, jointin
a |  | 20mm dia | RFT
|  | Potwash & Dishwash | RFT | 4 | 9.66 |  | 38.64
|  | TOTAL |  |  |  |  | 38.64
b |  | 25mm dia | RFT
4 | G.I. `C' class pipes | Supply, laying, testing and commissioning of G.I. `C' class pipes and fittings 'suitable for domestic cold water application rated for a working pressure of 5 kg/cm2 and conforming to IS 1239 (Part-I)-1979 for and equipments, including bitumastic hessia
a |  | 15mm dia | RFT
b |  | 20mm dia | RFT
c |  | 25mm dia | RFT
d |  | 32mm dia | RFT
e |  | 40mm dia | RFT
4 | Ball Valves | Supply, installing testing and commissioning of ISI marked gun metal screwed pattern non-return Valve conforming to IS 778 Class 1 including jointing, supporting etc. complete and as directed.
a |  | 15mm dia | nos
a |  | 20mm dia | Nos | 18 |  |  | 18
b |  | 25mm dia | Nos | 4 |  |  | 4
c |  | 32mm dia | Nos | 3 |  |  | 3
e |  | 40mm dia | nos
f |  | 50mm dia | nos
g |  | 65mm dia | nos
5 | UPVC SWR PIPES | Supply, laying , testing & commissioning of UPVC-SWR pipes conforming to IS 13592/92 and fittings conforming to IS-14935/99, cutting the pipes to required lengths, laying in position to required grade and level, jointing, making holes, pockets, chases in TYPE B 6 KG
a |  | 100mm dia | RFT
|  | Water cooler to Dishwash Drain nali | RFT | 1 | 4 |  | 4
|  | Dishwash drain nali to Hot section chamber | RFT | 1 | 3 |  | 3
|  | Hot section chamber to other chamber | RFT | 1 | 3.16 |  | 3.16
|  | Burner chamber to chamber near long jali | RFT | 1 | 7.58 |  | 7.58
|  | chamber to long drain | RFT | 1 | 2.16 |  | 2.16
|  |  | RFT | 1 | 4.91 |  | 4.91
|  | long drain to grease chamber | RFT | 1 | 7.66 |  | 7.66
|  | Grease chamber to end point | RFT | 1 | 3.91 |  | 3.91
|  | cold room to grease chamber | RFT | 1 | 7.66 |  | 7.66
|  |  | RFT | 1 | 3.83 |  | 3.83
|  | Main kitchen freezer => | RFT | 1 | 5.33 |  | 5.33
|  | Live kitchen outer sink to chamber | RFT | 1 | 8.08 |  | 8.08
61.28
|  | 90mm dia | RFT
b |  | 75mm dia | RFT
|  | BAR NANHI TRAP=> CHAMBER | RFT | 1 | 7.33 |  | 7.33
|  |  | RFT | 1 | 3.5 |  | 3.5
|  |  | RFT | 1 | 21.58 |  | 21.58
|  |  | RFT | 1 | 4.5 |  | 4.5
|  | TOTAL |  |  |  |  | 36.91
|  | 63mm dia | RFT
c |  | 50mm dia | RFT
b | RAIN WATER PIPE | 100mm dia RAIN WATER PIPE | rft
6 | FLEXIBLE PIPES | Supply, laying ,OF FLEXIBALE PIPES pipes to required lengths, laying in position to required grade and level, jointing, making holes, pockets, chases in
a |  | 50mm dia | RFT
7 | FLOOR TRAP/ MULTI FLOOR TRAP | Supply, laying, testing & commissioning of approved Cast iron FLOOR TRAP/ MULTI FLOOR TRAP with aproved make leavy duty round or square s.s. grating etc. complete. | Nos
7 | Deep Seal trap | Supply, laying, testing & commissioning of approved C I make Deep Seal Trap with aproved make leavy duty round or square s.s. grating etc. complete. | nos
9 | P/S trap | Supply, laying, testing & commissioning of approved uPVC /C I P/S trap with aproved make AS PER DRAWING & REQUIREMENT
8 | Jali | Jali with cokroch trap above nhani trap & clean out POP up type | Nos
|  | BAR | Nos | 2 |  |  | 2
|  | POTWASH | Nos | 1 |  |  | 1
|  | TOTAL |  |  |  |  | 3
8 | Floor Clean Out/Rodding Eye | Supply, laying, testing & commissioning of approved uPVC Floor Clean Out/Rodding Eye with aproved make leavy duty round or square s.s. grating etc. complete. Or ceiling eye for cleaning
a |  | 160mm dia | Nos
a |  | 110mm dia | Nos
c |  | 75mm dia | Nos
d | Gully Trap | Supply, laying, testing & commissioning of patel patatent c.I. Gully trap of outlet size 100MM dia consisting of CI black inlet chambers with 100 dia branch inlet as required with deep seal 'P' trap CI cover size 200 X 200 with SS crews etc complete an | Nos
9 | Chamber | Supply, laying, creating & commissioning of SS chamber 16 G SS PLATE WITH SUITABLE DEPTH 5MM THK MS PIPE WELDED TO CHAMBER WITH SUITABLE THREAD AND LOCATION AS PER DRAWING WITH TOP GRATING AND PERFOARETED JALI AS PER DESIGN
a |  | SIZE 14" X 14" | Nos
|  | Live Kitchen | Nos | 3 |  |  | 3
|  | Main Kitchen | Nos | 9 |  |  | 9
|  | TOTAL |  |  |  |  | 12
b |  | SIZE 87" X 08" | Nos
c |  | SIZE 12" X 54" | Nos
|  | SIZE 18 X 26 | Nos
|  | POTWASH | Nos | 1 |  |  | 1
|  | DISHWASH | Nos | 1 |  |  | 1
|  | TOTAL |  |  |  |  | 2
10 | Hooper | Providing & fixing of GI inlet hooper with two or three inlets fittings to receive waste pipes from fixture waste including joints etc complete and as directed | nos
10 | W.C. | Providing and fixing of Wall hung water closet ( hindware,parryware) with M.s frame, c.p bolt, nuts and solid seat cover and lid with c.p hinges and rubber buffers,brown clour | nos
11 | Wash Basin | Providing and fixing of Wash basin ABOVE counter, 15mm coupling with plug chain 32mm dia c.p bottle trap cold water supply connecting pipe, AS PER ARCHITECTS SPECIFICAION | nos
12 | Urinal | Providing and fixing Sensor urinal (hindwear) with bottletrap | nos
13 | Health faucet | Providing and fixing Health faucet of closet mounting type with angle valve | nos
10 | Bib cock | Providing and fixing Bib cock with wall flange | Nos
11 | Stop cock | Providing and fixing Stop cock with wall flange | Nos
12 | Angle cock | Providing and fixing Angle cock with wall flange | Nos
|  | BAR | Nos | 4 |  |  | 4
|  | Live Kitchen | Nos | 1 |  |  | 1
|  | Live kitchen outer near freezer | Nos | 2 |  |  | 2
|  | Potwash | Nos | 2 |  |  | 2
|  | Hot section sink | Nos | 2 |  |  | 2
|  | Water cooler | Nos | 1 |  |  | 1
|  | Dishwash | Nos | 5 |  |  | 5
|  | TOTAL | Nos |  |  |  | 17
| Piller cock | Providing and fixing Pillar cock of approved make for Wash room | nos |  |  |  | Rate to vary as per architectspecification
| Piller cock | Providing and fixing Pillar cock of approved make | nos
13 | Geyser storage | Providing and supplying 25 litrs geyser with c.p angle cock of hot and cold pvc connection & coupper pipes c.p elbows non return valves mounting bolts etc | Nos | 2 |  |  | 2
18 | Geyser storage | Providing and supplying 15 litrs geyser with c.p angle cock of hot and cold pvc connection & coupper pipes c.p elbows non return valves mounting bolts etc | nos
27 | Geyser storage | Providing and supplying 15 litrs geyser with c.p angle cock of hot and cold pvc connection pipes c.p elbows non return valves mounting bolts etc | nos
|  | Providing and supplying 25 litrs geyser with c.p angle cock of hot and cold pvc connection pipes c.p elbows non return valves mounting bolts etc | nos
19 | Toilet paper holder | Providing and fixing Toilet paper holder | nos |  |  |  | Local Make
20 | Soap dispenser | Providing and fixing Soap dispenser | nos |  |  |  | Local Make
21 | Paper napkin dispenser | Providing and fixing Paper napkin dispenser | nos |  |  |  | Local Make
22 | Hand dryer | Providing and fixing Hand dryer | nos |  |  |  | Russel Make
14 | Sink mixture | Providing and fixing Sink mixture | Nos
|  | BAR | Nos | 1 |  |  | 1
|  | Live kitchen outer sink | Nos | 1 |  |  | 1
|  | Potwash | Nos | 1 |  |  | 1
|  | Hot section sink | Nos | 1 |  |  | 1
|  | Dishwash | Nos | 1 |  |  | 1
|  | TOTAL |  |  |  |  | 5
15 | Sink Tap | Providing and fixing counter top tap ( Swan Neck ) | Nos
|  | Live Kitchen | Nos | 1 |  |  | 1
16 | Rinse Mixture | Providing and fixing Rinse Mixture | Nos
|  | POTWASH | Nos | 1 |  |  | 1
|  | DISHWASH | Nos | 1 |  |  | 1
|  | TOTAL |  |  |  |  | 2
15 | Equipment connection | Doing Equipment connection And Insallation (labour charges only) | Nos | 10 |  |  | 10
33 | Channel Drain | Supply ,laying,testing & commissing of heavy quility SS Grating of thickness 38MM with MS angle runners including fixing with hold fast applaying three coats of anti corrosive Bitumastic paint etc complete and as directed
34 |  | 300X200mm size and 38mm thick | MTR
35 |  | 1000X150mm size and 38mm thk. & weighing more than 35Kg. | nos
16 | Sink connection | Providing & fixing Sink Drain outlet Connection with valve & drain pipe complete with all necessary fittings | Nos | 8 |  |  | 8
17 | Grease Trap | Providing & fixing SS MADE Greece Trap MAKE Bombay Iron Works or any approved make. OR CONSTRUCTING THE SAME AS PER DRAWING
a |  | Size 18" X 24" | Nos | 2 |  |  | 2
37 |  | Size 3'-0" X 2'-0" | nos
a | Foot paddle operated faucet | foot paddle operated faucet | nos
b | Water level sensor indicative panel | Water level sensor indicative panel | nos
18 | RO Plant | RO connection only | Nos | 1 |  |  | 1
19 | Water Tank | Providing and fixing 500 LTR water tank for RO water | Nos | 1 |  |  | 1
20 | Pressure Pump | Providing and fixing of 1HP pressure pump in RO water line | Nos | 1 |  |  | 1
28 | WATER TANK | TANK 1500 LTR | nos
Note on E167: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Potwash and Dishwash
Note on H201: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pot wash and Dish wash