## Deviation Sheet
DSF-11 CURATED BAKERY
SUMMARY
Sr No | Particulars | PO | Executed | NT Items | Deviation
|  | Amount | Amount
1 | Total for Civil-Fabrication | 1423552.3995 | 1418194.4695 |  | -5357.9299
2 | Total for Additional |  |  | 1119734.7795 | 1119734.7795
| Grand Total (Without Tax) | 1423552.3995 | 1418194.4695 | 1119734.7795 | 1114376.8495

## Interior BOQ
DETAILED BOQ OF PROPOSED JHAKKAS + BAOWICH, MOPA AIRPORT, GOA
Sl / no | Item | Description | Qty | Unit | Rate | Amount | Nos. | L | W | Qty | Amount | Remarks
CIVIL WORKS
A | PARTITIONS
1 | 115mm thk. Brick wall partition | Provision and fixing of 115mm thk. first class brick (max height 1050mm), finished with 12.5mm thk. plaster on both sides. Plaster to be used in (cement and sand in 1:3 ratio.) | 210.34 | Sq.Ft. | 264 | 55529.76 |  | 3 | 3.83 | 11.49 |  | Wall Changed to Ply partition with aluminium framework
[8 empty] | 6.5 | 3.83 | 24.895
[8 empty] | 7 | 3.83 | 26.81
[8 empty] | 7.92 | 3.83 | 30.3336
[8 empty] | 5.83 | 3.83 | 22.3289
[8 empty] | 10.5 | 3.83 | 40.215
[8 empty] | 20.167 | 3.83 | 77.2396
[8 empty] | 7.67 | 3.25 | 24.9275
[8 empty] | 5.42 | 3.25 | 17.615
[10 empty] | 275.8546 | 72825.617
2 | Glazed Bevelled Tiles | P&F 3" x 12" Glazed Bevelled tiles fix (two colours as MAT 1 & 2 ) as per design with adhesive over the back ply partition grout of approved shade filled into 3mm spacer including all necessary hardwares and fixtures etc. complete as directed by PM. Basic Rate of tiles: Rs 300/Sqft. (ref dwg- TFS-MOPA-DG-05 to 07 - R0 dt. 13.10.22) | 210.34 | Sq.Ft. | 320 | 67308.8 |  | 3 | 3.25 | 9.75
[8 empty] | 6.5 | 3.25 | 21.125
[8 empty] | 2.5 | 3.25 | 8.125
[8 empty] | 7 | 3.25 | 22.75
[8 empty] | 5.83 | 1 | 5.83
[8 empty] | 10.5 | 3.25 | 34.125
[10 empty] | 101.705 | 32545.6
3 | Internal SS Skirting | P&F SS strip of 16 SWG in flooring interspace including all necessary hardwares and fixtures etc. complete as directed by PM. (ref dwg-TFS-MOPA-DG-03 - R0 dt. 13.10.22) | 54 | R.Ft. | 450 | 24300 |  | 21.99 |  | 21.99 | 9895.5
4 | MS C Insert | P&F in position powder coated MS C inserts on front & back counter fascia of approved sectional dimensions as per detailed design, drawings and as per specification sheet with material cose MAT 4 and colour RAL 9005 including all necessary hardwares and fixtures, etc. complete as directed by PM. | 128.2 | R.Ft. | 225 | 28845 | 2 | 3 |  | 6
[7 empty] | 2 | 6.5 |  | 13
[7 empty] | 2 | 2.5 |  | 5
[7 empty] | 2 | 7 |  | 14
[7 empty] | 2 | 10.5 |  | 21
[10 empty] | 59 | 13275
5 | External SS Skirting | P&F in position SS L shaped SS Matt 18 SWG skirting of height 150mm to be fixed as per detailed drawing, desigh and specifications. Material code for same is MAT 8 as per specification sheet including all necessary hardwares and fixtures, etc. complete as directed by PM. Ref Dwg. TFS-MOPA-DG-02 - R0 dt. 13.10.22 and TFS-MOPA-DG-05 - R0 dt. 13.10.22 | 64.08 | R.Ft. | 650 | 41652 |  | 3 |  | 3
[8 empty] | 6.5 |  | 6.5
[8 empty] | 2.5 |  | 2.5
[8 empty] | 7 |  | 7
[8 empty] | 7.92 |  | 7.92
[8 empty] | 5.83 |  | 5.83
[8 empty] | 10.5 |  | 10.5
[10 empty] | 43.25 | 28112.5
B | COUNTER/STORAGE UNITS/BOXING/FLOORING
1 | Front Counter @ P.O.S (counter 1) | Providing & Fixing of 75mm thk. Counter top made of 18mm thk. Marine ply board (Century/Greenply/Equivalent) and finished in app. Corian (Merino/Equivalent) as per schedule. | 1 | Nos. | 63000 | 63000 | 1 |  |  | 1 | 63000
Provision and fixing of all hardware, channels, box hinges (Hettich/hafele/equivalent), locks (Hettich/hafele/godrej/equivalent) etc.
Providing & Fixing of 150mm high & 2mm thk. Brushed finish S.S. plain skirting at the bottom from inner side of the counter.
Contractor to coordinate with electrical contractor for fixing of switch & sockets.
2 | Back Counter (counter 2) | Providing & fixing of 75mm thk. Counter top made of marine plywood (Century/Greenply/equivalent) and finished in app. Corian (Merino /equivalent). (Kindly consider necessary cut-outs for deep fryer, sink etc as per exact equipment sizes/cut-outs required approved by kitchen consultant.) | 1 | Nos. | 133639.2 | 133639.2 | 1 |  |  | 1 | 133639.2
length - 5445mm. Depth - 700mm, height - 950mm
Under counter units to be finished with app. oak wood laminate (Merino/Greenlam/equivalent) internally with provision of drawers & shelves for storage. All ply edges to be bounded with matching laminate & 18mm thk shutter to be made of plyboard (Century/Greenply/equivalent) finished in app. Laminate (Merino/Greenlam/equivalent) from outside.
length - 3500mm. Depth - 700mm, height - 775mm
Provision and fixing of all hardware, channels, box hinges (hettich/hafele/equivalent), locks (hettich/hafele/godrej/equivalent) etc.
Providing & Fixing of 150mm high & 2mm thk. Brushed finish S.S. plain skirting at the bottom.
3 | Mid counter (counter 3) | Providing & fixing of 75mm thk. Counter top made of marine plywood (Century/Greenply/equivalent) and finished in app. Corian (Merino/equivalent). (Kindly consider necessary cut-outs for deep fryer, sink etc as per exact equipment sizes/cut-outs required approved by kitchen consultant.) | 2 | Nos. | 61009.2 | 122018.4 | 2 |  |  | 2 | 122018.4
length - 5445mm. Depth - 700mm, height - 950mm
Under counter units to be finished with app. oak wood laminate (Merino/Greenlam/equivalent) internally with provision of drawers & shelves for storage. All ply edges to be bounded with matching laminate & 18mm thk shutter to be made of plyboard (Century/Greenply/equivalent) finished in app. Laminate (Merino/Greenlam/equivalent) from outside.
length - 450mm. Depth - 700mm, height - 775mm
Provision and fixing of all hardware, channels, box hinges (hettich/hafele/equivalent), locks (hettich/hafele/godrej/equivalent) etc.
Providing & Fixing of 150mm high & 2mm thk. Brushed finish S.S. plain skirting at the bottom.
4 | Counter - 4 | Providing & fixing of 75mm thk. Counter top made of 18mm thk. marine plywood (Century/Greenply/equivalent) and finished in app. Corian 18mm thk. (Merino/equivalent). (Kindly consider necessary cut-outs for deep fryer, sink etc as per exact equipment sizes/cut-outs required approved by kitchen consultant.) | 1 | Nos. | 116208 | 116208 | 1 |  |  | 1 | 116208
length - 1430mm. Depth - 600mm, height - 950mm
Under counter units to be finished with app. oak wood laminate (Merino/Greenlam/equivalent) internally with provision of drawers & shelves for storage. All ply edges to be bounded with matching laminate & 18mm thk shutter to be made of plyboard (Century/Greenply/equivalent) finished in app. Laminate (Merino/Greenlam/equivalent) from outside.
length - 1430mm. Depth - 600mm, height - 775mm
Provision and fixing of all hardware, channels, box hinges (hettich/hafele/equivalent), locks (hettich/hafele/godrej/equivalent) etc.
Providing & Fixing of 150mm high & 2mm thk. Brushed finish S.S. plain skirting at the bottom.
4 | Wicket Door | Providing & Fixing of 75mm thk. Wicket door made up of 18mm thk. Plyboard (Century/Greenply/equivalent) finished in app. paint ral code: 9003 on all sides as per design & as per schedule. | 1 | Nos. |  | 0 | 1 |  |  | 1
length - 750mm, height - 950mm (counter level)
Providing & Fixing of all hardware, channels, box hinges (hettich/hafele/equivalent), locks (hettich/hafele/godrej/equivalent) etc.
Providing & fixing of 150mm high & 2mm thk. Brushed Finish SS skirting from innner side as per detail.
Providing & fixing of 150mm high & 18mm thk ashwood skirting in matte finish paint ral code: 9003 as per design detail and schedule.
5 | Flooring | Providing & Laying antiskid floor tiles - Size - 600 x 600 mm ( thickness to be specified by the manufacturer ) with tile adhesive, with necessary epoxy grouting. (orientbell/cera/equivalent) | 27 | Sq.Mt. | 2400 | 64800 |  | 4.75 | 5.85 | 27.7875 | 66690
6 | Ceiling (Area - 25.50 Sq.mt.) | The internal ceiling members are 50mm x 50mm , 16 SWG MS box section finished in PDR coated to MAT -5 shade placed as per shown in detailed design and drawing. 15mm dia. MS canopy intermediate bars fixed to intermediate frames in PDR coated MAT - 5 shade. These members are supported on bulkhead main frame of 50mm x 50mm MS canopy edge frame PDR coated to MAT - 5 shade. All necessary provisions and hardware to be provided to receive the electrical fittings and digital screens. The cost to include painting of any ducts or ceiling members complete. (ref dwg-- TFS-MOPA-DG-03 - R0 dt. 13.10.22) Rate shall include support system for suspended digital menu display and brand signage, light fittings as shown in drawing. Rate also include for additional support and framework for fixing chimney unit as shown in detailed design and drawing as directed by PM. | 10.3122 | Sq.Mtr | 5920 | 61047.9376 |  | 3.65 | 3.23 | 11.7895 | 69793.84
Providing, fabricating and fixing in position support column members of whole frame of canopy of size 75mm x100mm with base plate as per approved thickness in PDR coated to MAT - 5 shade and total numbers of supporting back columns are 4 and supporting columns of size 75mm x 75mm of 2 numbers at intermediate part with PDR coated to MAT - 5 as shown in drawings including all fabrication and proper cleaning as directed by PM.
| Coloumns | 100mm x75mm Columns - Back side columns | 4 | Nos. | 10500 | 42000 | 4 |  |  | 4 | 42000
| Columns | 75mm x 75mm columns - Intermediate columns | 2 | Nos. | 9500 | 19000 | 2 |  |  | 2 | 19000 | 50mm x 50mm columns
| Arches | Providing, fabricating and fixing in position 3 nos. 25mm x 25mm MS arched framing with PDR coating black Matt 4, fabricated to supporting columns as shown in detailed drawings with all necessary hardwares and fixtures etc. complete as directed by PM. | 1 | Nos. | 28500 | 28500 | 1 |  |  | 1 | 28500
7 | Ring | Providing and fixing in position for signage bulkheads with top and bottom MS box sections with connecting 15mm dia MS powder coated rings as per architectural design including cost of fabrication, proper finish with all necessary hardwares and fixtures etc. complete as directed by PM. | 1 | No. | 55800 | 55800 | 1 |  |  | 1 | 55800
8 | Digital Menu Display | Provision of electrical wires for the digital screen. Provision of cut out and necessary support in the ceiling for the screen.(ref dwg-TFS-MOPA - DG - 03 - R0 dt. 13.10.2022) | 1 | Nos | 8500 | 8500 | 1 |  |  | 1 | 8500
Digital Screen fixed as per design and detailing. The screen nos. and the fixing detail of the screen will be as per the vendor details
B | ACCESSORIES
1 | Plumbing | Providing & fixing of handmade sink size (305 x 305 x 125mm) (Hafele/Franke/equivalent) as per specifications. | 0 | Nos. | 13608 | 0
|  | Providing & fixing of kitchen faucet (Kohler/equivalent). | 0 | Nos. | 4500 | 0 | [5 empty] | Kohler Kumin wall mounted Kitchen Faucet
2 | Sneeze Guard | Providing & fixing of 10mm toughened glass with 18mm thk metal profile. | 0 | Nos. | 6300 | 0
3 | Guard Rail | Providing & fixing of 50mm dia Guardrail in front of POS counter SS 18SWG, 1.27mm thkness brushed finish to be fixed on the counter. (ref dwg-TFS-MOPA - DG - 07 - R0 dt. 13.10.2022) | 60.6242 | Rft | 1550 | 93967.572 |  | 42.75 |  | 42.75 | 66262.5
FINISHES
C | WALL CLADDING / WALL PAINT/ COUNTER TOP/FALSE CEILING
1 | Corian counter top (Servery Front counter, mid counter, back counter) | Providing & Fixing of 18mm thk Corian counter top (Merino/ equivalent) | 15.61 | Sq.Mt | 17276.4 | 269684.604 |  |  |  | 21.5 | 371442.6
2 | Corian Ledge | Ledge finish & fascia of the service counter finish at side of opening - Providing and fixing in position 150mm wide, 12mm thk solid acrylic over 18mm thk marine fire retardant plywood backing with pencil rounding to be fixed on the top surface with 50mm fascia running horizontally around the counter & vertically at the service access side.6mm thk solid acrylic with 18mm thk marine fire retardant plywood backing to be used on vertical surfaces including all lighting, adhesives, hardwares and fixtures etc. complete as per architectural detail & as directed by PM. (ref dwg- TFS-BBN-K-F11-01 & 02,09,10) | 95 | R.Ft. | 1250 | 118750 |  | 70.5 |  | 70.5 | 88125
3 | PU Paint on counter | Front side of POS counter unit finished with 6mm thk MDF over 18mm thk marine, fire retardent plywood, finished in matt PU paint in approved colour fitted with digital signage & lighting inside the signages with necessary fixing arrangement on exterior side plywood framing including all necessary hardwares and fixtures, etc. complete as directed by PM. | 21.6895 | Sqft | 415 | 9001.1259 |  | 7.83 | 3.25 | 25.4475 | 10560.7125
|  | Total Value |  |  |  | 1423552.3995 |  |  |  |  | 1418194.4695
Discount
|  | Total After Discount |  |  |  | 1423552.3995 |  |  |  |  | 1418194.4695
|  | IGST |  |  | 18% | 256239.4319 |  |  |  |  | 255275.0045
|  | Total With Taxes |  |  |  | 1679791.8314 |  |  |  |  | 1673469.4741
MISCELLANEOUS
1 | Pest Control treatment |  |  | LS
2 | Debris Removal from site | Removal of debris from site post construction |  | LS
3 | Cleaning of site post completion |  |  | LS
All componets of carpentry (Plywood / Gypsum boards) to be of 1Hr Fire rating
IMP NOTE: The description of works provided above along with the drawings are meant only to describe the intent for the design. The vendor/ contractor is expected to develop his/her details/shop drawings as required to fulfil the design intent whilst ensuring functional compliance and structural stability. These details are to be reviewed with the architect/ project manager prior to commencement of work at site. If there are any discrepancies between the drawing and the BOQ provided, please consult/ clarify with the designer.All componets of carpentry (Plywood / Gypsum boards) to be of 1Hr Fire rating.

## NT Items
|  | Bikanerwala Additional | [5 empty] | Proposed
SR.NO. | ITEM | DESCRIPTION | Unit | Nos | L | W | Qty | Rate | Amount
1 | Sneeze Guard | Providing & fixing of 10mm toughened glass with 18mm thk metal profile. | Nos | 1 |  |  | 1 | 16500 | 16500 | ITEM Sneeze Guard DESCRIPTION Providing & fixing of 10mm toughened glass with 18mm thk metal profile. L W
2 | Counter - 5 | Providing & fixing of 75mm thk. Counter top made of 18mm thk. marine plywood (Century/Greenply/equivalent) and finished in app. Corian 18mm thk. (Merino/equivalent). (Kindly consider necessary cut-outs for deep fryer, sink etc as per exact equipment sizes/cut-outs required approved by kitchen consultant.) | Nos. | 1 |  |  | 1 | 200722.9 | 200722.9 | ITEM Counter - 5 DESCRIPTION Providing & fixing of 75mm thk. Counter top made of 18mm thk. marine plywood (Century/Greenply/equivalent) and finished in app. Corian 18mm thk. (Merino/equivalent). (Kindly consider necessary cut-outs for deep fryer, sink etc as per exact equipment sizes/cut-outs required approved by kitchen consultant.) L W
|  | length - 2470mm. Depth - 730mm, height - 970mm | [7 empty] | ITEM DESCRIPTION length - 2470mm. Depth - 730mm, height - 970mm L W
3 | Sink | Providing & fixing of handmade sink size (305 x 305 x 125mm) (Hafele/Franke/equivalent) as per specifications. | Nos. | 2 |  |  | 2 | 13608 | 27216 | ITEM Sink DESCRIPTION Providing & fixing of handmade sink size (305 x 305 x 125mm) (Hafele/Franke/equivalent) as per specifications. L W
4 | Faucet | Providing & fixing of kitchen faucet (Kohler/equivalent). | Nos. | 2 |  |  | 2 | 4500 | 9000 | ITEM Faucet DESCRIPTION Providing & fixing of kitchen faucet (Kohler/equivalent). L W
5 | Counter Modification | Modication of counter by dismantling whole structure and remaking as per new details. | Sq.Ft. |  | 89.22 | 3 | 267.66 | 950 | 254277 | ITEM Counter Modification DESCRIPTION Modication of counter by dismantling whole structure and remaking as per new details. L 89.22 W 3
6 | Cost Difference Brick wall partition to Ply Partition | As per instruction made in FR ply with aluminium framework | Sq.Ft. |  | 3 | 3.83 | 11.49 |  |  | ITEM Cost Difference Brick wall partition to Ply Partition DESCRIPTION As per instruction made in FR ply with aluminium framework L 3 W 3.83
|  | (650-264) |  |  | 6.5 | 3.83 | 24.895 |  |  | ITEM DESCRIPTION (650-264) L 6.5 W 3.83
[5 empty] | 7 | 3.83 | 26.81 |  |  | ITEM DESCRIPTION L 7 W 3.83
[5 empty] | 7.92 | 3.83 | 30.3336 |  |  | ITEM DESCRIPTION L 7.92 W 3.83
[5 empty] | 5.83 | 3.83 | 22.3289 |  |  | ITEM DESCRIPTION L 5.83 W 3.83
[5 empty] | 10.5 | 3.83 | 40.215 |  |  | ITEM DESCRIPTION L 10.5 W 3.83
[5 empty] | 20.167 | 3.83 | 77.2396 |  |  | ITEM DESCRIPTION L 20.167 W 3.83
[5 empty] | 7.67 | 3.25 | 24.9275 |  |  | ITEM DESCRIPTION L 7.67 W 3.25
[5 empty] | 5.42 | 3.25 | 17.615 |  |  | ITEM DESCRIPTION L 5.42 W 3.25
[7 empty] | 275.8546 | 386 | 106479.8795 | ITEM DESCRIPTION L W
ITEM DESCRIPTION L W
7 | Wicket Door | Providing & Fixing of 75mm thk. Wicket door made up of 18mm thk. Plyboard (Century/Greenply/equivalent) finished in app. paint ral code: 9003 on all sides as per design & as per schedule. | Nos. | 1 |  |  | 1 | 15171 | 15171 | ITEM Wicket Door DESCRIPTION Providing & Fixing of 75mm thk. Wicket door made up of 18mm thk. Plyboard (Century/Greenply/equivalent) finished in app. paint ral code: 9003 on all sides as per design & as per schedule. L W
|  | length - 750mm, height - 950mm (counter level) | [7 empty] | ITEM DESCRIPTION length - 750mm, height - 950mm (counter level) L W
ITEM DESCRIPTION L W
8 | Pressure Pump | P&F of pressure pump | Nos. | 2 |  |  | 2 | 15500 | 31000 | ITEM Pressure Pump DESCRIPTION P&F of pressure pump L W
ITEM DESCRIPTION L W
9 | MS Framework | Fabrication of MS frame for chimney | Nos. | 1 |  |  | 1 | 10500 | 10500 | ITEM MS Framework DESCRIPTION Fabrication of MS frame for chimney L W
ITEM DESCRIPTION L W
10 | Temporary Partition | P&F of temporary partition | Sq.Ft. | 2 | 24 | 12 | 576 |  |  | ITEM Temporary Partition DESCRIPTION P&F of temporary partition L 24 W 12
|  | flex changed twice |  | 2 | 20 | 12 | 480 |  |  | ITEM DESCRIPTION flex changed twice L 20 W 12
[7 empty] | 1056 | 270 | 285120 | ITEM DESCRIPTION L W
ITEM DESCRIPTION L W
11 | Equipment Shifting | Shifting of equipment | Job | 1 |  |  | 1 | 45000 | 45000 | ITEM Equipment Shifting DESCRIPTION Shifting of equipment L W
ITEM DESCRIPTION L W
12 | Material loss | Tiles | Box | 18 |  |  | 18 | 2025 | 36450 | ITEM Material loss DESCRIPTION Tiles L W
|  | MS Material | KG | 45 |  |  | 45 | 150 | 6750 | ITEM DESCRIPTION MS Material L W
|  | Ply 8mm | Nos. | 6 |  |  | 6 | 2318 | 13908 | ITEM DESCRIPTION Ply 8mm L W
|  | Corian Joint chemical | Nos. | 18 |  |  | 18 | 650 | 11700 | ITEM DESCRIPTION Corian Joint chemical L W
|  | SS Skirting inside | R.Ft. | 22 |  |  | 22 | 450 | 9900 | ITEM DESCRIPTION SS Skirting inside L W
ITEM DESCRIPTION L W
13 | Refixing and removing of flap door | Refixing and removing of flap door | Nos. | 2 |  |  | 2 | 800 | 1600 | ITEM Refixing and removing of flap door DESCRIPTION Refixing and removing of flap door L W
ITEM DESCRIPTION L W
14 | Ceiling Allignment | Reallignmenmt of ceiling | Labour | 6 |  |  | 6 | 1000 | 6000 | ITEM Ceiling Allignment DESCRIPTION Reallignmenmt of ceiling L W
ITEM DESCRIPTION L W
15 | Shutter fixing | Refixing of cabinet shutters | Labour | 2 |  |  | 2 | 1000 | 2000 | ITEM Shutter fixing DESCRIPTION Refixing of cabinet shutters L W
ITEM DESCRIPTION L W
16 | Hanging Light Paint | Painting of hanging light (Duco Paint) | Nos. | 4 |  |  | 4 | 850 | 3400 | ITEM Hanging Light Paint DESCRIPTION Painting of hanging light (Duco Paint) L W
ITEM DESCRIPTION L W
17 | Barrication Removing | Removal of barrication | Sq.Ft. | 2 | 24 | 12 | 576 |  |  | ITEM Barrication Removing DESCRIPTION Removal of barrication L 24 W 12
|  |  |  | 2 | 20 | 12 | 480 |  |  | ITEM DESCRIPTION L 20 W 12
[7 empty] | 1056 | 15 | 15840 | ITEM DESCRIPTION L W
ITEM DESCRIPTION L W
18 | Conter Top | P&F of counter top for chaat counter in laminate finish | Sq.Ft. |  | 8 | 4 | 32 | 350 | 11200 | ITEM Conter Top DESCRIPTION P&F of counter top for chaat counter in laminate finish L 8 W 4
1119734.7795