## NT Work Bill
SL NO | DESCRIPTION OF WORK | UNIT | QTY | RATE | AMOUNT | REMARKS | SEMOLINA REMARKS
A | C&I WORK
1 | SS shelf fixing | L/M | 1 | 3800 | 3800 | Kitchen
(providing anchor fastener with all necessary fittings & worker)
2 | METAL CNC CUT JALI WITH MS FRAMING BENDING | Sqm | 5.208 | 10222 | 53236.176 | TOILET ENTRANCE AREA
3 | HALF PARTITION WITH CNC CUT JALI WOODEN FRAMING (1200X150X200 mm WOODEN BOXING WITH LAMINATES FINISH) | Sqm | 6.25 | 14526 | 90787.5 | FOH AREA
0
4 | LIVE KITCHEN TOUGHENED GLASS | Sqm | 1.596 | 8070 | 12879.72 | LIVE KITCHEN WINDOW
0
5 | TOUGHENED GLASS | Sqm | 9.1642 | 8070 | 73955.4168 | MOH AREA
0
0
6 | Toilet lobby basin counter ( 5 FT X 1 FT with all necessary fittings ) with Storage Bellow | Nos | 1 | 28000 | 28000
0
7 | P F Frame work with 50mmX50mm X16gauge Ms tube framing out of vertical members at 600mm C C with horizontal members at 600mm cc the frame work b or w main members Area Note: Ms pipe work note consider for BOQ item No- 6.03 |  |  |  | 0
|  | KG | 2653 | 230 | 610190
| Total pipe use 758 R.mtr |  |  |  | 0
Consideration- 3.5 kg/mtr (50X50; 2mm thick hollow ms section) |  |  |  |  | 0
8 | Providing & fixing HDMR 6mm paneling between for laveling concreet panel Extra Work | SQM | 31.0936 | 1345 | 41820.892 | Sofa back wall
10 | Providing & fixing HDMR 6mm for use grooves looking smooth Extra Work ( BOQ item no 6.07 )ON CONCRETE PANELLING | SQM | 14.4565 | 1345 | 19443.9925 | Toilet entry façade
0
0
0
12 | Granite work | Rmt | 19.665 | 2250 | 44246.25
0
0
13 | Ms work for support duct kitchen area | Rmt | 12.192 |  | 0 | Kitchen area
|  | Kg | 42 | 230 | 9660 | Consideration- 3.5 kg/mtr (50X50; 2mm thick hollow ms section)
0
0
14 | Door frame ply with febric finish | Sqm | 1 | 15602 | 15602 | Toilet lobby entry avobe
0
15 | Laminate finish pedistal (ACTUAL SIZE INCREASED AS PER BOQ) | Nos | 2 | 16500 | 33000 | Under maneger table
0
16 | Loft storage | Nos | 1 | 23500 | 23500 | Above drumpster
0
17 | Commercial tiles 600X600mm New Tile ( Under Carpet Flooring Area) | Sqm | 24 | 2400 | 57600 | Under Carpet Flooring Area
0
0
18 | All furniture liffting charges | L/m | 20000 |  | 20000
| ( approx fifteen workers ) |  |  |  | 0
0
19 | Ms bar Patti for rafter ms framing One side fixing ( 6mmX 50mm) BOQ Item No 4.03 as per drawing required | RMTR |  |  | 0 | Rafter with ms patti ( both side)
| Consideration - 2.355 Kg per RMTR | KG | 245.9 | 230 | 56557
0
20 | Ms Pol 100mm X 100mm claiding 12mm ply with laminate | RMTR | 11.2 | 2740 | 30688
0
0
22 | 50x50 mm ss corner guard | RMTR | 19.2 | 1050 | 20160 | Kitchen Area
0
23 | Debris ( Per Vehicle ) | NOS | 7 | 7500 | 52500
0
24 | Demolation Work ( 300mm Thick Brick wall ) | SQM | 18.24 | 1644 | 29986.56
0
25 | HVAC ( Old ducting demolation ) | Nos | 1 | 8000 | 8000 | Kitchen Area
0
26 | HVAC old ACP sheet & Ms work frame demolation | Nos | 2 | 4000 | 8000 | Sofa back & toilet Back area
0
27 | Exiting barrication extand for lounge 1job & second job demolation same barricate refixing for TWC | Nos | 1 | 10000 | 10000
0
28 | Aluminum corner guard ( Black Cotted ) | Nos | 1 | 2000 | 2000 | Bar Counter front floor stap
0
0
B | PLUMBING WORK |  |  |  | 0
i) | Sink mixer(need to change rate as per boq) | Nos | 3 | 4900 | 14700 | Kitchen area
ii) | Table tap | Nos | 1 | 7500 | 7500 | Toilet Lobby area
iii) | Wash basin | Nos | 1 | 18500 | 18500 | Toilet Lobby area
iv) | Sink | Nos | 1 | 12500 | 12500 | Bar back counter
v) | Sink instalation kitchen area & exchange from barista outlet once again reinstalation | L/M | 1 | 3000 | 3000 | Kitchen area
vi) | Hand Drier(nned to revise rateaper boq) | Nos | 1 | 9000 | 9000 | Toilet Lobby area
0
vii) | Drain line Trench (125 mm wide) connection from water cooler to kitchen | Job | 1 | 23500 | 23500
| (12 mm ceramic tiles) |  |  |  | 0
0
C | ELECTRICAL WORK |  |  |  | 0
i) | Wiring for secondary MCB controlled Emergency light points/ Wall Point/ Floor Point( Looped from above point) with 1.5 sq. mm PVC insulated stranded copper conductor 1100 Volt grade FRLS wires in 25 mm 16 SWG MS conduit in wall / ceiling including cost of cutting and filling chases for recessed conduiting and supports in case of surface conduit including all bends , saddles , Junction boxes etc and including the cost of running 1.5 Sq mm PVC insulated copper conductor wire for loop earthing etc. complete as required. | Pt | 3 | 4200 | 12600
ii) | Supply installation testing and fixing 40A , Three Phase metal Clad industrial socket outlet with 63 A FP MCB and complete in all respects( Wiring Excluded from scope of this item) | Nos. | 2 | 5500 | 11000
iii) | Square conceal panel led light | Nos. | 6 | 1450 | 8700
0
iv) | 95 sq.mm 4 core copper cable | Mtrs | 17 | 5727.5 | 97367.5
0
v) | 95 copper lag | Nos. | 14 | 1250 | 17500
0
vi) | 95 gland | Nos. | 3 | 1865 | 5595
0
vii) | 16 gland | Nos. | 3 | 1150 | 3450
0
viii) | 16 lag pin top | Nos. | 25 | 170 | 4250
0
ix) | Labour charges for appliancens shifting, | L/M | 0 | 35000 | 35000
0
x) | Strip light profile | Mtrs | 40 | 575 | 23000
0
xi) | Bus bar(instaaled on celing above vip area) | Nos. | 1 | 14500 | 14500
xii) | Electric main panel connection from exiting | L/M | 1 | 6000 | 6000
| line & Providing 12mm nut bolt, with all nesecary fittings |  |  |  | 0
0
0
D | HVAC WORK |  |  |  | 0
i) | RETURN AIR GRILL | Sqm | 15 | 1600 | 24000
0
ii) | G.I. Sheet Metal Ducting - Factory Fabricated(add ducting done for ac throw connection) | Sqm | 55 | 1210 | 66550
| 0.63 MM (24 Gauge) |  |  |  | 0
iii) | Nitrile Rubber Insulation- Class 'O' | Sqm | 55 | 900 | 49500
| 19 mm thick (AC Supply / Return ducts) |  |  |  | 0
0
0
0
E 1) | water cooler box (590 X610X150 ) | Lms |  | 3800 | 3800
0
2) | Buffet Cunter HDMR JALI wooden frame | sqft | 1.176 | 19500 | 22932
0
3) | Fly Catcher Surface Box 3 Model Looping Connection | No | 1 | 6500 | 6500
0
4) | Industrial Socket Single Phase Removing | No | 1 | 500 | 500
0
5) | 3 model plate 16 amp switch socket providing and fixing | No | 1 | 5500 | 5500
0
6) | RAMP providing and Fixing | sqm | 0.575 | 38198 | 21963.85
0
7) | RAMP providing and Fixing | sqm | 0.44 | 38198 | 16807.12
0
8) | TV FIXING | No | 2 | 600 | 1200
0
9) | FLY Catcher Fixing | No | 2 | 600 | 1200
0
10) | MS Structure Paint (please check rate) | sqm | 64.66 | 860 | 55607.6
0
11) | Transportation & Packing Charge |  |  |  | 0
0
A | Main Lt Panel ( Mumbai To Trivandrum ) |  |  | 16000 | 16000
B | Tile ( Delhi To Trivandrum ) |  |  | 90400 | 90400
C | Tile ( Delhi To Trivandrum ) |  |  | 95000 | 95000
D | Natural Marbles Slabs Lime Stone ( Silvasa To Trivandrum) |  |  | 80000 | 80000
E | Copper Bowl ( Muradabad Up To Trivandrum ) |  |  | 12000 | 12000
| Total Amount |  |  |  | 2252736.5773

## NT Work MSRMNT
MEASUREMENT FORM WORK : ALL NT WORK MEASUREMENT SHEEET | [6 empty] | DATE: 30/10/2024
SL NO | DESCRIPTION OF WORK | UNIT | NO | LENGTH | BREADTH | HEIGHT |  | QUANTITY | REMARKS
A | C&I WORK
1 | SS shelf fixing | L/M | [5 empty] | 3,800/- | Kitchen
(providing anchor fastener with all necessary fittings & worker)
2 | METAL CNC CUT JALI | sqm | 1 | 2.17 |  | 2.4 |  | 5.208 | TOILET ENTRANCE AREA
3 | HALF PARTITION WITH CNC CUT JALI | sqm | 4 | 1.25 |  | 1.25 |  | 6.25 | FOH AREA
4 | LIVE KITCHEN TOUGHENED GLASS | sqm | 1 | 2.1 |  | 0.76 |  | 1.596 | LIVE KITCHEN WINDOW
5 | TOUGHENED GLASS | sqm | 1 | 0.467 |  | 2.58 |  | 1.2049 | MOH AREA
|  |  | 1 | 1.715 |  | 2.783 |  | 4.7728
|  |  | 1 | 1.145 |  | 2.783 |  | 3.1865
9.1642
6 | Toilet lobby basin counter | Nos | 1 |  |  |  |  | 1
12 | Granite work | Rmt | 1 | 0.985 |  | 0 |  | 0.985 | Toillet (His) wc ledge wall
|  |  | 1 | 0.72 |  |  |  | 0.72 | Toillet (Her) wc ledge wall
|  |  | 2 |  |  | 1.075 |  | 2.15 | Live kitchen window frame
|  |  | 2 | 2.14 |  |  |  | 4.28 | Live kitchen window frame
|  |  | 1 | 3.05 |  |  |  | 3.05 | Bar outside wall skirting
|  |  | 1 | 4.25 |  |  |  | 4.25 | Outside round arch panel beside floor
|  |  | 1 | 1.2 |  |  |  | 1.2 | exposed toilet entry lobby raiser
|  |  | 1 | 1.15 |  |  |  | 1.15 | exposed toilet entry lobby raiser
|  |  | 1 | 1.88 |  |  |  | 1.88 | exposed toilet entry lobby raiser
19.665
13 | Ms work for support duct | Rmt | 2 | 6.096 |  |  |  | 12.192 | Kitchen area
|  | Kg | [5 empty] | 42 | Consideration- 3.5 kg/mtr (50X50; 2mm thick hollow ms section)
14 | Door frame ply with febric finish | Sqm | 1 | 1.16 | 530 |  |  | 1 | Toilet lobby entry avobe
15 | Laminate finish pedistal | Nos | 2 |  |  |  |  | 2 | Under maneger table
16 | Loft storage | Nos | 1 |  |  |  |  | 1 | Avobe drumpster
17 | Commercial tiles | Sqm | 1 | 4.5 | 3700 |  |  | 17 | Lounge area
|  |  | 1 | 1.28 | 2240 |  |  | 3
|  |  | 1 | 1.47 | 1560 |  |  | 2
|  |  | 1 | 1.46 | 1560 |  |  | 2
24
18 | All eqipment & furniture liffting charges | L/m | [5 empty] | 20,000/-
( approx fifteen workers )
7 | P F Framework with 50mmX50mm X16gauge Ms tube framing out of vertical members at 600mm C C with horizontal members at 600mm cc the frame work b or w main members Area Note: Ms pipe work note consider for BOQ item No- 6.03 | SQM
|  | SQM | 1 | 4.77 | - | 2.8 |  | 13.356 | Sofa back FOH
|  | SQM | 2 | 0.72 | - | 2.8 |  | 4.032 | Drumseater
|  | SQM | 1 | 1.51 | - | 2.8 |  | 4.228 | Drumseater Left
|  | SQM | 1 | 4.62 | - | 2.8 |  | 12.936 | Reception back wall to façade
|  | SQM | 2 | 2.72 | - | 2.8 |  | 15.232 | Reception & maneger room wall
|  | SQM | -2 | 0.79 | - | 2.1 |  | -3.318 | door
|  | SQM | 1 | 4.22 | - | 2.8 |  | 11.816 | Maneger room table wall
|  | SQM | 1 | 3.53 | - | 2.8 |  | 9.884 | Buffet-2 Back
|  | SQM | 1 | 1.55 | - | 2.8 |  | 4.34 | Buffet counter beside wall
|  | SQM | 1 | 4.03 | - | 2.8 |  | 11.284 | Beside buffet counter c shape inside
|  | SQM | 1 | 4.78 | - | 2.8 |  | 13.384 | Beside buffet counter c shape outside
|  | SQM | 1 | 5.88 | - | 2.8 |  | 16.464 | Executive lounge back
|  | SQM | -1 | 0.75 | - | 1.8 |  | -1.35 | Bond room door
|  | SQM | 1 | 1.88 | - | 2.07 |  | 3.8916 | Bond room inside
|  | SQM | -1 | 0.75 | - | 1.8 |  | -1.35 | Bond room door
|  | SQM | 1 | 5.52 | - | 2.8 |  | 15.456 | Bar back
|  | SQM | 2 | 2.82 | - | 2.8 |  | 15.792 | Bar beside duct cover panel
|  | SQM | 2 | 4.35 | - | 2.9 |  | 25.23 | Curve façade
|  | SQM | 1 | 2.43 | - | 2.9 |  | 7.047 | Beside curve façade
|  | SQM | 2 | 5.02 | - | 0.3 |  | 3.012 | Teracota jali top
|  | SQM | 1 | 27.06 | - | 0.5 |  | 13.53 | Façade top
|  | SQM | -1 | 1.2 | - | 1.8 |  | -2.16 | Toilet Door
192.7366
Total pipe use 758 R.mtr
| Consideration- 3.5 kg/mtr (50X50; 2mm thick hollow ms section) |  |  |  |  | KG |  | 2653
8 | Providing & fixing HDMR 6mm paneling between for laveling concreet panel & auther area grooves Extra Work | sqm | 1 | 4.78 | - | 2.54 |  | 12.1412 | Sofa back wall
| Note : Only laminate consider in BOQ item No 6.13 |  | 5 | 0.3 | - | 2.68 |  | 4.02 | Toilet entry wall
|  |  | 2 | 0.3 | - | 0.66 |  | 0.396 | Toilet entry wall
|  |  | 1 | 0.59 | - | 2.55 |  | 1.5045 | Live kitchen wall
|  |  | 1 | 1.49 | - | 2.55 |  | 3.7995 | Live kitchen wall
|  |  | 1 | 1.19 | - | 2.55 |  | 3.0345 | Live kitchen wall
|  |  | -1 | 1.08 | - | 1.1 |  | -1.188 | Live kitchen window
|  |  | 1 | 1.02 | - | 2.55 |  | 2.601 | Live kitchen wall
|  |  | -1 | 0.75 | - | 1.1 |  | -0.825 | Live kitchen window
|  |  | 1 | 2.74 | - | 2.65 |  | 7.261 | Maneger room entry wall
|  |  | -1 | 0.79 | - | 2.09 |  | -1.6511 | Maneger room door
31.0936
10 | Providing & fixing HDMR 6mm for use grooves looking smooth Extra Work ( BOQ item no 6.07 ) | Sqm
|  |  | 1 | 2.43 | 2.9 |  |  | 7.047 | Toilet entry façade
|  |  | 1 | 2.05 | 2.9 |  |  | 5.945 | Toilet entry façade
|  |  | 1 | 5.05 | 0.29 |  |  | 1.4645 | Toilet entry façade
14.4565
19 | Ms bar Patti for rafter ms framing One side fixing ( 6mmX 50mm) BOQ Item No 4.03 as per drawing required
|  | Rmtr |  | 28.2 | 24 |  |  | 52.2 | FOH
|  |  |  | 5.64 | 2.12 |  |  | 7.76 | FOH
|  |  |  | 5.64 | 1.64 |  |  | 7.28 | FOH
|  |  |  | 2.28 | 2.2 |  |  | 4.48 | Executive Lounge
|  |  |  | 4.6 | 5.6 |  |  | 10.2 | Executive Lounge
|  |  |  | 2.28 | 3.56 |  |  | 5.84 | Executive Lounge
|  |  |  | 2.3 | 2.62 |  |  | 4.92 | Executive Lounge
|  |  |  | 2.56 | 5 |  |  | 7.56 | Executive Lounge
|  |  |  | 2.3 | 1.88 |  |  | 4.18 | Executive Lounge
| Consideration- 3.5 kg | [6 empty] | Rmtr- 104.42
|  | Consideration - 2.355 Kg per RMTR | [5 empty] | 245.9 | KG
20 | Ms Pol 100mm X 100mm claiding 12mm ply with laminate | RMTR | 4 |  |  | 2.8 |  | 11.2
22 | 50x50 mm ss corner guard | RMTR | 8 | 2.4 |  |  |  | 19.2 | Kitchen Area
23 | Debris ( Per Vehicle ) | NOS | 7 |  |  |  |  | 7
24 | Demolation Work ( 300mm Thick Brick wall ) | sqm | 1 | 2.1 |  | 3.2 |  | 6.72 | Bond Room Wall
|  | sqm | 1 | 3.6 |  | 3.2 |  | 11.52 | Bufey counter B side
18.24
25 | HVAC ( Old ducting demolation ) | Nos | 1 |  |  |  |  | 1 | Kitchen Area
26 | HVAC old ACP sheet & Ms work frame demolation | Nos | 2 |  |  |  |  | 2 | Sofa back & toilet Back area
27 | Exiting barrication extand for lounge 1job & second job demolation same barricate refixing for TWC | Nos | 1 |  |  |  |  | 1
28 | Aluminum corner guard ( Black Cotted ) | Nos | 1 |  |  |  |  | 1 | Bar Counter front floor stap
B | PLUMBING WORK
i) | Sink mixer | Nos | 3 |  |  |  |  | 3 | Kitchen area
ii) | Table tap | Nos | 1 |  |  |  |  | 1 | Toilet Lobby area
iii) | Wash basin | Nos | 1 |  |  |  |  | 1 | Toilet Lobby area
iv) | Sink | Nos | 1 |  |  |  |  | 1 | Bar back counter
v) | Sink instalation kitchen area & exchange from barista outlet once again reinstalation | L/M | 3000 |  |  |  |  | 3000 | Kitchen area
vi) | Hand Drier | Nos | 1 |  |  |  |  | 1 | Toilet Lobby area
vii) | Drain line Trench (125 mm wide) | 1Job | 16 | 0.44 |  |  |  | 7
| (12 mm ceramic tiles) |  | 4 | 0.44 | 0.44 |  |  | 1
8
C | ELECTRICAL WORK
i) | Wiring for secondary MCB controlled Emergency light points/ Wall Point/ Floor Point( Looped from above point) with 1.5 sq. mm PVC insulated stranded copper conductor 1100 Volt grade FRLS wires in 25 mm 16 SWG MS conduit in wall / ceiling including cost of cutting and filling chases for recessed conduiting and supports in case of surface conduit including all bends , saddles , Junction boxes etc and including the cost of running 1.5 Sq mm PVC insulated copper conductor wire for loop earthing etc. complete as required. | Pt | 3 |  |  |  |  | 3
ii) | Supply installation testing and fixing 40A , Three Phase metal Clad industrial socket outlet with 63 A FP MCB and complete in all respects( Wiring Excluded from scope of this item) | Nos. | 3 |  |  |  |  | 2
iii) | Square conceal panel led light | Nos. | 6 |  |  |  |  | 6
iv) | 95 sq.mm 4 core copper cable | Mtrs | 17 |  |  |  |  | 17
v) | 95 copper lag | Nos. | 14 |  |  |  |  | 14
vi) | 95 gland | Nos. | 3 |  |  |  |  | 3
vii) | 16 gland | Nos. | 3 |  |  |  |  | 3
viii) | 16 lag pin top | Nos. | 25 |  |  |  |  | 25
ix) | Transport & labour charges | L/M
x) | Strip light profile | Mtrs | 40 |  |  |  |  | 40
xi) | Bus bar | Nos. | 1 |  |  |  |  | 1
xii) | Electric main panel connection from exiting | L/M | [5 empty] | 6,000/-
line & Providing 12mm nut bolt, with all nesecary fittings
D | HVAC WORK
i) | RETURN AIR GRILL | Sqm | 15 |  |  |  |  | 15
ii) | G.I. Sheet Metal Ducting - Factory Fabricated | Sqm | 55 |  |  |  |  | 55
0.63 MM (24 Gauge)
iii) | Nitrile Rubber Insulation- Class 'O' | Sqm | 55 |  |  |  |  | 55
19 mm thick (AC Supply / Return ducts)
E 1) | water cooler box | sqm |  | 0.59 | 0.61 | 0.15 |  | 0.053985
2) | Buffet Cunter HDMR JALI wooden frame | sqft |  | 0.48 |  | 2.45 |  | 1.176
3) | Fly Catcher Surface Box 3 Model Looping Connection | No | 1 |  |  |  |  | 1
4) | Industrial Socket Single Phase Removing | No | 1 |  |  |  |  | 1
5) | 3 model plate 16 amp switch socket providing and fixing | No | 1 |  |  |  |  | 1
6) | RAMP providing and Fixing | sqm |  | 1.15 | 0.5 |  |  | 0.575
7) | RAMP providing and Fixing | sqm |  | 1.1 | 0.4 |  |  | 0.44
8) | TV FIXING | No | 2 |  |  |  |  | 2
9) | FLY Catcher Fixing | No | 2 |  |  |  |  | 2
10 ) | MS Structure Paint | sqm | 1 | 6.91 | 0.84 |  |  | 5.8044
|  |  | 1 | 12.71 | 0.84 |  |  | 10.6764
|  |  | 4 | 12.71 | 0.39 |  |  | 19.8276
|  |  | 4 | 10.06 | 0.39 |  |  | 15.6936
|  |  | 4 | 9.5 | 0.2 |  |  | 7.6
|  |  | 3 | 8.43 | 0.2 |  |  | 5.058
64.66
11) | Transportaton
A | Main Lt Panel ( Mumbai To Trivandrum ) | [6 empty] | 16000
B | Tile ( Delhi To Trivandrum ) | [6 empty] | 90400
C | Tile ( Delhi To Trivandrum ) | [6 empty] | 95000
D | Natural Marbles Slabs Lime Stone ( Silvasa To Trivandrum) | [6 empty] | 80000
E | Copper Bowl ( Muradabad Up To Trivandrum ) | [6 empty] | 12000