## Sheet1
Measurement Sheet
Sub - Interior Work for MUM Good Times Bar - T1B
WO No. Semolina/PO/23-24/000781
1st RA & Final Bill
Sr. No. | Description of work | No. | L | B | H | Total
Part - 1
1 | Veneer finish (PolisH)
| Door Entrance Toilet Side | 1 | 1.96 |  | 0.73 | 1.4308
| Side Patta | 1 | 0.7 |  | 1.9 | 1.33
|  | 1 | 0.9 |  | 1.9 | 1.71
| Bottom patta | 1 | 0.7 |  | 1.7 | 1.19
| Mirror Side | 1 | 0.88 |  | 2.6 | 2.288
|  | 1 | 0.96 |  | 2.6 | 2.496
|  | 1 | 0.96 |  | 2.6 | 2.496
| LHS wall | 1 | 7.54 |  | 2.6 | 19.604
| Door patta | 2 | 0.24 |  | 2.1 | 1.008
|  | 1 | 1.12 |  | 0.24 | 0.2688
| Door | 1 | 1.09 |  | 2.1 | 2.289
| Tv unit framing | 2 | 0.14 |  | 1.96 | 0.5488
|  | 2 | 0.1 |  | 1.84 | 0.368
| Bottom | 1 | 0.24 |  | 1.73 | 0.4152
| Top | 1 | 0.14 |  | 1.73 | 0.2422
| Column | 1 | 3.18 |  | 2.05 | 6.519
|  | 1 | 1.82 |  | 2.05 | 3.731
|  | 1 | 2.68 |  | 2.38 | 6.3784
|  | 1 | 2.52 |  | 2.38 | 5.9976
|  | 1 | 1.2 |  | 2.38 | 2.856
| Door opening | 1 | 1.02 |  | 2.38 | 2.4276
|  | 1 | 0.23 |  | 2.38 | 0.5474
|  | 1 | 0.23 |  | 2.38 | 0.5474
| Side patta | 1 | 1 |  | 2.26 | 2.26
|  | 1 | 1.14 |  | 2.26 | 2.5764
| Patta | 1 | 1.62 |  | 0.12 | 0.1944
| Top | 1 | 1.62 |  | 0.8 | 1.296
| Door | 1 | 0.9 |  | 1.8 | 1.62
|  | 1 | 0.9 |  | 2 | 1.8
| Mirror side patta | 2 | 0.15 |  | 2.05 | 0.615
| Window framing | 2 | 3.25 |  | 0.425 | 2.7625
|  | 2 | 1.09 |  | 0.425 | 0.9265
|  | 2 | 3.39 |  | 0.07 | 0.4746
|  | 2 | 1.09 |  | 0.07 | 0.1526
| Window top and bottom | 2 | 3.19 |  | 0.495 | 3.1581
| Tv side | 2 | 1.07 |  | 0.495 | 1.0593
| Patta | 2 | 3.33 |  | 0.07 | 0.4662
|  | 2 | 1.21 |  | 0.07 | 0.1694
| Door RHS Side | 1 | 2.13 |  | 2.63 | 5.6019
| Door | 1 | 1.84 |  | 0.94 | 1.7296
| Counter area | 1 | 0.62 |  | 2.83 | 1.7546
|  | 1 | 0.87 |  | 2.25 | 1.9575
| Beside Basin | 1 | 1.35 |  | 1.01 | 1.3635
| Vertical | 2 | 1.35 |  | 0.17 | 0.459
| Horizontal | 2 | 1.01 |  | 0.17 | 0.3434
| Patta | 2 | 1.44 |  | 0.04 | 0.1152
| Kitchen door side | 1 | 1.6 |  | 2.25 | 3.6
| Counter corner | 1 | 1.06 |  | 1.35 | 1.431
|  | 1 | 0.26 |  | 0.9 | 0.234
| Kitchen door | 2 | 0.78 |  | 2.25 | 3.51
| Door frame | 2 | 0.09 |  | 2.25 | 0.405
| Above counter | 1 | 0.61 |  | 2.34 | 1.4274
|  | 1 | 0.8 |  | 2.34 | 1.872
| Shutter door | 2 | 2.82 |  | 0.8 | 4.512
|  | 1 | 1.22 |  | 0.87 | 1.0614
|  | 1 | 0.96 |  | 0.87 | 0.8352
|  | 1 | 0.5 |  | 0.87 | 0.435
|  | 1 | 2.36 |  | 0.8 | 1.888
[6 empty] | 120.7559 | M2
2 | buffing- solid acrylic surfaces -
| Top | 1 | 4.78 |  | 0.54 | 2.5812
|  | 1 | 2.76 |  | 1.37 | 3.7812
| Side | 1 | 0.76 |  | 0.22 | 0.1672
|  | 1 | 1.07 |  | 0.89 | 0.9523
|  | 1 | 0.35 |  | 0.22 | 0.077
|  | 1 | 0.85 |  | 0.22 | 0.187
| Counter front | 1 | 0.7 |  | 2.76 | 1.932
|  | 1 | 0.93 |  | 4.7 | 4.371
| Side | 1 | 0.25 |  | 0.97 | 0.2425
| Mirror self area | 2 | 2.08 |  | 1.3 | 5.408
| Less | -2 | 1.65 |  | 1.09 | -3.597
| Horizontal | 2 | 1.65 |  | 0.15 | 0.495
| Vertical | 4 | 1.09 |  | 0.15 | 0.654
| Beside basin | 1 | 1.44 |  | 0.2 | 0.288
[6 empty] | 17.5394 | M2
3 | re-painting of wall, ceiling
| Toilet side entrance | 1 | 1.4 |  | 2 | 2.8
| Ceiling | 1 | 4.1 |  | 9.12 | 37.392
| Beam | 1 | 9.12 |  | 0.57 | 5.1984
|  | 1 | 4.1 |  | 0.33 | 1.353
| BEam | 1 | 2.05 |  | 0.57 | 1.1685
| Door patta | 1 | 0.78 |  | 0.11 | 0.0858
| Patta | 1 | 1.65 |  | 0.15 | 0.2475
| Wall | 1 | 4.1 |  | 2.3 | 9.43
| Deduct window | -1 | 3.38 |  | 1.22 | -4.1236
| Ceiling | 1 | 9.65 |  | 6.6 | 63.69
| Deduct column | -1 | 0.67 |  | 0.67 | -0.4489
|  | -1 | 0.43 |  | 0.83 | -0.3569
| Deduct column | -1 | 0.99 |  | 0.6 | -0.594
|  | -1 | 0.63 |  | 0.6 | -0.378
|  | -1 | 0.22 |  | 0.66 | -0.1452
| Door entrance | 1 | 0.32 |  | 2.55 | 0.816
| Beam | 1 | 9.65 |  | 0.35 | 3.3775
|  | 1 | 6.6 |  | 0.35 | 2.31
| Wall | 1 | 4.26 |  | 2.3 | 9.798
| Deduct window | -1 | 3.98 |  | 1.22 | -4.8556
| Wall | 1 | 1.49 |  | 2.3 | 3.427
|  | 1 | 6.6 |  | 2.3 | 15.18
| Deduct door | -1 | 0.89 |  | 1.81 | -1.6109
| Deduct ac grill | -1 | 0.15 |  | 6.6 | -0.99
| Wall | 1 | 0.59 |  | 0.9 | 0.531
| Counter ceiling | 1 | 2.35 |  | 5.4 | 12.69
| Beam | 2 | 0.35 |  | 2.35 | 1.645
|  | 1 | 0.35 |  | 2.35 | 0.8225
| Kitchen ceiling | 1 | 3.72 |  | 1.75 | 6.51
| Wall | 1 | 3.72 |  | 2.25 | 8.37
[6 empty] | 173.3391 | M2
4 | Louvrers shutter to be re polished
|  | 1 | 2.82 |  | 0.88 | 2.4816
|  | 1 | 1.73 |  | 0.88 | 1.5224
|  | 1 | 0.62 |  | 0.63 | 0.3906
|  | 1 | 2.83 |  | 0.88 | 2.4904
[6 empty] | 6.885 | M2
5 | Increase lux level of existing lightsReplacement of old dull lights
| Ceiling light | 1 | 53 |  |  | 53
|  | 1 | 7 |  |  | 7
| Ktichen | 1 | 4 |  |  | 4
[6 empty] | 64 | EA
6 | Buffing of existing 220MM high SS skirting
| Skirting | 1 | 10.03 |  | 0.22 | 2.2066
|  | 1 | 14.51 |  | 0.22 | 3.1922
|  | 1 | 7.82 |  | 0.22 | 1.7204
|  | 1 | 3.92 |  | 0.22 | 0.8624
|  | 1 | 7.76 |  | 0.22 | 1.7072
|  | 1 | 2.84 |  | 0.22 | 0.6248
|  | 1 | 7.56 |  | 0.22 | 1.6632
|  | 1 | 0.8 |  | 0.22 | 0.176
|  | 1 | 0.9 |  | 0.22 | 0.198
|  | 1 | 3.28 |  | 0.22 | 0.7216
|  | 1 | 2.6 |  | 0.22 | 0.572
|  | 1 | 2.76 |  | 0.22 | 0.6072
[6 empty] | 14.2516 | M2
7 | New Signages - providing and fixing of new signages | 1 | 2 |  |  | 2 | EA
Part - 2
9 | Cleaning of existing flooring - Deep Cleaning of existing flooring | 1 | 9.24 |  | 13.69 | 126.4956
|  | 1 | 2.1 |  | 1.94 | 4.074
[6 empty] | 130.5696 | M2
11 | New glass shutter - Providing fixing 12 mm thick extra clear
| glass shutter | 1 | 0.85 |  | 2.08 | 1.768 | M2
12 | Replacement of damaged floor tiles if required
| Kitchen | 1 | 3.72 |  | 2.25 | 8.37
|  | 1 | 0.95 |  | 2.25 | 2.1375
|  | 1 | 1.75 |  | 2.25 | 3.9375
[6 empty] | 14.445 | M2
13 | 6mm ply fire rated ply - providing and fixing 6 mm fire rated ply on the existing ply
|  | 12 | 0.9 |  | 0.6 | 6.48 | M2
14 | 12 mm fire rated ply - providing and packing pest open area
| Kitchen | 1 | 3.72 |  | 2.25 | 8.37
|  | 1 | 0.95 |  | 2.25 | 2.1375
|  | 1 | 1.75 |  | 2.25 | 3.9375
|  | 19 | 0.6 |  | 0.6 | 6.84
[6 empty] | 21.285 | M2
15 | white solid acrylic surface matching with existing | 1 | 2.76 |  | 0.74 | 2.0424 | M2
EXTRA ITEMS
1 | Repair of Chairs/Single seater Sofa ,Replacing old Leatherite with Sarom Bently make ,approved Shade ,Providing 2" Foam if required including all necessary hardware etc Complete.
|  | 1 | 35 |  |  | 35 | Nos
2 | Repairing the existing tables , replacing the mica & Buffing/Polishing as per instruction of engineer incharge etc complete.
|  | 1 | 20 |  |  | 20 | Nos
3 | Dismantling concrete , removing exisitng damaged/ chocked drain line . Providing & Fixing 63mm PVC Pipe and re concreting the same including cleaning the site , removal of debris outside airport premise etc complete.
|  | 1 | 1 |  |  | 1 | Lump
4 | Providing & Fixing SS Sink with drain board of approved make and quality Including removing the existing damaged sink.
|  | 1 | 1 |  |  | 1 | Lump
5 | Swan neck sink cock of Jaguar make
|  | 1 | 1 |  |  | 1 | No
6 | Providing & fixing 12mm thick toughened glass in fixed windows including making cutouts for Glass holders.
| Fix Window | 1 | 3.25 |  | 1.08 | 3.51
|  | 1 | 3.2 |  | 1.08 | 3.456
[6 empty] | 6.966 | M2
7 | Providing & fixing Reception Table as per Drawing, Made with 19mm Marine ply ,1mm laminate Marino make both side i/c all necessary Hardware etc Complete.
|  | 1 | 2 |  |  | 2 | Nos
8 | Providing & fixing SS Glass Holders .
| Fix Window | 2 | 10 |  |  | 20
| Shelve | 3 | 2 |  |  | 6
[6 empty] | 26 | Nos
9 | Supplying Single seater Sofa with side covered rest, match to existing design and Leatherite.
|  | 1 | 5 |  |  | 5 | Nos
10 | Supply & Fixing Wall Mounted Flat Exhaust Chimney with Carbon Filter, Duct less as approved by In charge. Size- 600 x 540mm
|  | 1 | 2 |  |  | 2 | Nos
11 | Supply & Fixing 1200 watt Induction Plate of Prestige Make.
|  | 1 | 6 |  |  | 6 | Nos
12 | Supply & Fixing Dish Washer Celfrost B-30. Size- 600 x 600 x 800mm
|  | 1 | 1 |  |  | 1 | Nos
13 | Supply & Fixing Open Deck Chiller of Blue Star Make.
|  | 1 | 1 |  |  | 1 | Nos
14 | Equipment Loading , Unloading & Shifting the same inside airport Premises SHA area including Transport charges .
|  | 1 | 1 |  |  | 1 | LS
15 | Making core cutting 50mm dia in Corian finished main counter.
|  | 1 | 8 |  |  | 8 | Nos
16 | Dismantling Gyp board ceiling
|  | 1 | 3.72 |  | 1.75 | 6.51 | M2
17 | Providing and fixing at all height false ceilling of 12.5mm thick tapered edge gypsum board conforming to IS : 2095 including providing and fixing of frame work
|  | 1 | 3.72 |  | 1.75 | 6.51 | M2
18 | Making Cut /Opening in Gypboard Ceiling for Laying IT cables and Fixing 12.5 mm Gyp board after finishing the same .
|  | 1 | 8 |  |  | 8 | Nos
19 | Fixing of SS Racks in Kitchen walls with all necessary hardwares.
|  | 1 | 2 |  |  | 2 | Nos
PLUMBING WORK
1 | Providing & fixing CPVC FTA of Size 40MM of Approved make including necessary fittings etc complete
|  | 1 | 3 |  |  | 3 | Nos
2 | SUPPLYING AND FIXING ON WALL FACE UNPLASTICISED RIGID PVC PIPES OF M/S SUPREME INDUSTRIES/FINOLEX IN TOILET AND SHAFT CONFORMING TO IS:13592 TYPE A INCLUDING JOINTING WITH SEALED RING CONFORMING TO IS:5382 LEAVING 10 MM GAP FOR THERMAL EXPANSION. SINGLE SOCKETED PIPES SIZE:DN40
|  | 1 | 1.5 |  |  | 1.5
|  | 1 | 0.6 |  |  | 0.6
[6 empty] | 2.1 | RMT
3 | Providing & fixng PVC Reducer socket of size 50mm x 40 mm
|  | 1 | 3 |  |  | 3 | Nos
4 | Providing & fixing PVC connector Pipe.
|  | 1 | 3 |  |  | 3 | Nos
5 | Providing & fixing CP Brass Jaguar Pillar tap.
|  | 1 | 1 |  |  | 1 | Nos
6 | Providing & fixing 100 ltr water tank i/c making hole ,Nipple ,checknut etc Comp.
|  | 1 | 1 |  |  | 1 | Nos
7 | Providing & fixing 1/2 HP Booster/Pressure pump of Crompton make with all necessary fittings.
|  | 1 | 1 |  |  | 1 | Nos
8 | Providing & fixng CP Brass Angle cock.
|  | 1 | 2 |  |  | 2 | Nos
9 | Providing & fixing Brass FTA of Size 32MM of Approved make including necessary fittings etc complete
|  | 1 | 2 |  |  | 2 | Nos
10 | Providing & fixing Brass MTA of Size 20MM of Approved make including necessary fittings etc complete
|  | 1 | 3 |  |  | 3 | Nos
11 | Fixing Greece Trap supplied by client with all necessary fittings & Hardware.
|  | 1 | 1 |  |  | 1 | No
ELECTRICAL WORK
1 | Supplying and erecting PVC flexible cable 4sqmm 3 core FRLS copper conductor complete erected on wall / celling as per specification
| DB to Kitchen | 1 | 23.7 |  |  | 23.7 | RMT
2 | Supply, Installation, Testing & Commissioning of 32A Industrial Point Three Phase with Powder coated MS Box,MCB ,3 Pin Industrial Socket & Top of Legrand make.
| Reception counter | 1 | 1 |  |  | 1 | No
3 | Supply, Installation, Testing & Commissioning of 20 A Industrial Point Single Phase with Powder coated MS Box,MCB ,3 Pin Industrial Socket & Top of Legrand make.
| Ktichen Area | 1 | 3 |  |  | 3 | Nos
4 | Wiring for the light points with 2X1.5 sq mm PVC insulated copper conductor 650V grade FRLS wires
a | Primary (First) light point controlled by a 6A switch.
| Ktichen Area | 1 | 1 |  |  | 1
| Signage | 2 | 1 |  |  | 2
[6 empty] | 3 | Points
b | Secondary (Loop) light point looped to first point
| Ktichen Area | 1 | 3 |  |  | 3 | Points
c | First Point wiring with 6A,5pin wall socket outlet and controlled by a 6A switch
| Reception counter | 2 | 1 |  |  | 2 | Nos
d | Extra loop point wiring with 6A, 5 pin wall socket outlet and controlled by a 6A switch
| Reception counter | 2 | 2 |  |  | 4 | Nos
e | First Point wiring with 16A,5pin wall socket outlet and controlled by a 16A switch
| Kitchen area | 1 | 7 |  |  | 7
| Reception counter | 1 | 1 |  |  | 1
| Main counter | 1 | 4 |  |  | 4
| Behind Fridge | 1 | 1 |  |  | 1
[6 empty] | 13 | Nos
f | Extra loop point wiring with 16A, 5 pin wall socket outlet and controlled by a 16A switch
| Kitchen area | 1 | 5 |  |  | 5
| Reception counter | 1 | 1 |  |  | 1
| Main counter | 1 | 4 |  |  | 4
| Behind Fridge | 1 | 1 |  |  | 1
[6 empty] | 11 | Nos
5 | Supply, Installation, Testing & Commissioning of mains with 2 X 2.5 sq.mm and earth wire 1.5 sqmm FRLS PVC copper wire ,in rigid conduit min.20 mm dia,including all required accessories,etc as per specification.
| Reception counter -1 | 1 | 8.5 |  |  | 8.5
| Reception counter -2 | 1
6 | Supplying and erecting Metal LED Hanging Lights of approved design.
|  | 1 | 4 |  |  | 4 | Nos
7 | Supply, Installation, Testing & Commissioning LED Strip Light.
| Main counter strip light | 1 | 16.6 |  |  | 16.6 | RMT
8 | Providing & Fixing 12W LED Driver.
| Main counter strip light | 1 | 2 |  |  | 2 | Nos