## MEASUREMENT SHEET
measurement sheet
CAFECCINO_T1B
1 | red vinyl print | 2.925 | 0.95 |  | 2.7787
|  | 1.5 | 0.95 |  | 1.425
|  | 1 | 0.95 |  | 0.95
5.1537
2 | Vinyl finish
| Vinyl finish on rafters | 0.75 | 1.225 | 11 | 10.1063 | sides
|  | 0.75 | 2.2 | 6 | 9.9
|  | 0.15 | 0.225 | 17 | 0.57375 | front
20.58
| Vinyl print on visual | 1.5 | 1.5 |  | 2.25
| total vinyl print |  |  |  | 22.83
3 | new overhead ply shutter | 0.92 | 0.95 | 3 | 2.622
4 | red corian | 1.21 | 2.56 |  | 3.0976
5 | fixing glass on SS finish | 1.52 | 0.33 |  | 0.5016
6 | ply partition with white corian finish | 1.83 | 0.6 |  | 1.098
7 | relaminate
| back wall | 4.42 | 3 |  | 13.26
8 | flooring mat |  |  |  | 7.5
9 | Increase luv level of lights
| spot light |  |  |  | 16
| hanging lights |  |  |  | 4
20
10 | replace old LED ight of signage with new LED light
11 | SS Trolley fender |  |  |  | 1.6
| Menu board- Translate | 1.25 | 0.95 | 3 | 3.5625
12 | Tension rod supporting the signage to be strengthened or replaced as per existing condition
13 | garbage bin

## BOQ_CAFECCINO T1 B SHA
BOQ of Interior Items for CAFECCINO, Mumbai T1 B - SHA
DATE: 26-02-2024
SR.NO. | ITEM | DESCRIPTION | LOCATION | IMAGE REF | DRAWING NO | DIMENSION | UNIT | QTY. | Rate | Amount | REMARKS
1 | Red Solid acrylic (Corian) | Providing and fixing red solid acryllic (corian) of approved shade on existing corian surface complete as per detail drawing and specification. Location- Top and front side of front counter. | In the place of existing dark brown solid acrylic at front counter. |  |  |  | SQMT | 3.0976 | 18500 | 57305.6
0
2 | Relaminate | Providing and fixing 6mm ply with new laminate over existing laminate all over the back wall of the outlet and all internal surfaces complete as per instruction from EIC. | back wall of the outlet |  |  |  | SQMT | 13.26 | 7500 | 99450
0
3 | Vinyl print | Provinding and fixing vinyl matching with oak veneer polish finish over rafters of approved shade complete as per detail drawing or as per instruction from EIC. | 1. on the rafters of the ceiling 2. on the visual |  |  |  | SQMT | 20.58 | 5500 | 113190
3 | Vinyl print | Provinding and fixing vinyl over existing surface of approved shade complete as per detail drawing or as per instruction from EIC. (Marketing team will provide CDR file for vinyl) |  |  |  | 1500 x 1500 (mm) - 1 no | SQMT | 2.25 | 4000 | 9000
0
4 | red back painted glass | removing exisiting back painted glass with damaging the structure and Provinding and fixing new red back painted glass matching with existing over existing surface of approved shade complete as per detail drawing or as per instruction from EIC. | behind existing signage |  |  |  | SQMT | 5.1537 | 7500 | 38653.125
0
5 | Menu board- Translate | 1. Removing exsting menu boards and handover to EIC or supervisor. 2. Providing and fixing new menu boards (translate) of size 1250X 950mm - 3Nos suspended fron the rafters . With all accessories and fittings complete as per satisfaction of EIC. |  |  |  | 1250mm x 950mm (3 nos) | Nos | 3 | 15000 | 45000 | -
6 | New overhead ply shutter's | 1. Removing of existing ply shutters, 2. Providing fixing of 12mm fire rated ply shutters of size 920mm x 950mm with approved laminate finish with all fitting accessories complete as per instruction from EIC. | Location-backside of menu boards. |  |  | 920mm x 950mm (3 nos) | SQMT | 2.622 | 12000 | 31464
0
6 | fire rated ply partition finished with white solid acrylic | Provind and fixing fire rated ply of 18mm thick over existing counter front side finished with white corian complete as per detail drawing or as per instruction from EIC. | Front side of front counter below red corian. |  |  |  | SQMT | 1.098 | 12350 | 13560.3
0
7 | fixing of Frosted glass above SS skirting | Providing and fixing 10mm frosted glass over exsting S.S. suface above skirting of front side of front counter complete as per detail drawing or as per instruction from EIC. | between shirting and existing dark brown solid acrylic. |  |  |  | SQMT | 0.5016 | 8000 | 4012.8 | -
0
8 | flooring mat | 1. Removing of existing flooring mat 2. Providing and fixing new grey rubber mat of approved shade complete as per instruction from EIC. | replace existing flooring mat |  |  |  | SQMT | 7.5 | 2000 | 15000
0
9 | New spot lights | 1. Removing of existing spot lights - 16Nos and handover to site incharge or supervisor, 2. Providing and fixing of New spot lights with increase lux level (5 Watt -white) at existing location |  |  |  |  | Nos | 16 | 2500 | 40000
0
| New hang lights | 1. Removing of existing hanging lights- 4Nos and handover to site incharge or supervisor, 2. Providing and fixing of new hanging lights with increase lux level (5 watt each-white ) at existing location |  |  |  |  | nos | 4 | 8000 | 32000
0
10 | New LED light of signage | 1. Removing of existing LED light of the signage 2. Providing and fixing new LED light of the signage as per detail drawing. | Store front signage of 1 no | [6 empty] | 0
0
11 | SS Trolley fender | Providing and fixing 50mm SS trolley fender at the perifery above existing ss skirting as shown in drawing. |  |  |  |  | RMT | 1.6 | 3250 | 5200
0
12 | Tension rod supporting the signage to be strengthened or replaced as per existing condition | [5 empty] | rmt |  | 16000 | 0
0
13 | garbage bin | providing garbage bin of detail shared with EIC |  |  |  | 750(l)x 700(w)x 1200(h) |  |  |  | 0
503835.825
90690.4485
594526.2735