## Final work to be done
Work head | Work Description | Amount Requested | Apprroval status | Remark
Water proofing work | Kitchen Water proofing | 15.5 | Approved | Necessary
Civil/ Electrical/signage/Fire compliance work | Design tiles Flooring work |  | Approval needed | Necessary
| Electrical work |  | Approval needed | Necessary
| Fire compliance |  | Approval needed | Necessary
| Miscellaneous civil work |  | Approval needed | Necessary
| Plumbing work |  | Approval needed | Necessary
| Supply of SS rack |  | Approval needed | Necessary
Interior Work | Furniture work |  | Approval needed | Required for imagery
| Live kitchen glass and frame work |  | Approval needed | Required for imagery
| Live kitchen Tiling work |  | Approval needed | Required for imagery
| Decorative Hanging Light |  | Approval needed | Required for imagery
| CHEF Photo Frame |  | Approval needed | Required for imagery
| Wall paper wall light to be changed |  | Approval needed | Required for imagery
Grand Total
Interior work – Optional | Pot For Plants |  | Approval needed | Optional -Suggested by mall
| Planter Box |  | Approval needed | Optional -Suggested by mall
| Signage work |  | Approval needed | Optional -Suggested by mall
Grand Total

## civil work
Sr No | Desscription | Qty | unit
1 | Supply and installation of In-Panel tube based suppression system direct high pressure (CO2) | 3 | Nos
2 | supply and installation of sprinkler at Dine in | 1 | No
3 | Providing and of Fire Retardant door | 1 | No
4 | Providingt and fixing of 16 Amps Industria sockets to the existing panel box | 8 | Nos
5 | Preparing the ceiling surfaces and applying two coats of Emulsion paints of approved make at dining | 1500 | SFT
6 | Supplying of L shaped sofa seaters | 28 | RFT
7 | Supplying of 2 seater table | 4 | Nos
8 | Supplying of wooden chairs with pvc wire nette back as per the existing chairs at restaurent | 10 | Nos
9 | Dismantling of existing aluminium partions | 225 | SFT
10 | Dismantling of existing floor tiles and Supply and fixing of new tiles as per design at dine area | 150 | SFT
11 | Supply of led bulbs for tracks | 45 | Nos
12 | Supply of side stations | 1 | No
| Preparing the wooden surfaces and applying wood polish | 300 | SFT
13 | Preparing the wooden surfaces and applying wood polish for Chairs | 60 | N0s
14 | Preparing the wall surfaces and applying two coats of emulsion paints at center hall | 450 | Sft
15 | Side station shutters replacing of pvc wire netting | 3 | nos
16 | Providing and installation of fresh air blower | 1 | Nos
17 | Dismantling of existing wall dado tiles and the clearing the debris at tandoor kithchen | 275 | SFT
18 | Supplying and fixing of Wall dado tiles of approved make at tandoor kitchen | 275 | SFT
19 | Preparing the ceiling and wall surfaces and applying two coats of enamel paints at tandoor kitchen | 350 | SFT
20 | Providng and fixing of sign board ( Letters ) and LED light and driver | 1 | Nos
23 | Supplying and fixing of C P two-in-one mixter tap | 1 | No
24 | Supplying and fixing of C P sink tap | 2 | Nos
25 | Dismantling of existing wall dado tiles and the clearing the debris at washing areas | 175 | SFT
26 | Supplying and fixing of Wall dado tiles of approved make at washing area | 175 | SFT
27 | Supplying and fixing of S S rack at Bar Counter | 1 | No
28 | Shifting of existing S S rack at Bar Counter | 1 | No
29 | False celing repair works at front dining | 2 | Nos
30 | Providing and fixing of false ceiling at kitchen | 850 | SFT
31 | Providing and fixing of Live kithchen window | 90 | SFT
32 | Music system repair works | 1 | LS
33 | Repairing of existing aluminium door (balcony door) | 1 | No
34 | Repairing of sofas | 1 | No
35 | Foam filling at cold room | 50 | RFT
36 | One ss shelf need to fix for Microwave (700mm X 450 mm ) | 1 | Nos
37 | SS storag rack ( 700X700X 1700) | 1 | Nos

## Interior
BOQ of Carpentry & LiGHTING work for Copper Chimney Project, PMC, Chennai | [6 empty] | 29/06/2023
|  | GROUND FLOOR |  |  |  |  | FT
SR.NO. | ITEM | DESCRIPTION | LOCATION | DIMENSION | UNIT | QTY. | RATE | AMOUNT | REMARK | IMAGE
PLANTER
1 | Pot For Plants | Providing and fixing of Pots for Plants made of 300mm diameter and 900mm height. Cost to include soil and live plants. | Outdoor Area | 300mm (Dia) 900mm (H) | Nos. | 6 |  |  | pending
2 | Planter Box | Providing and fixing FRP planter box as per given size with all necessary required groove, wooden framing, approved make adhesive and cutting/ chamfering/ groove/rounding wherever required, at all height with lead and lift, finishing, cleaning as per design and drawing etc. all complete. | Outdoor Area & Glass Façade (Ledge Wall) | 1350mm (L) x 400mm (W) x 450mm (HT) | Nos. | 10 |  |  | pending
TOTAL PLANTER BOX / POT | [7 empty] | 0
CARPENTRY
3 | Cane Panel | P/F bamboo Cane paneling on existing wall from Single side, internal ply finished with laminate. structure to be made out of 40x20mm thk wooden frame with 12mm, intermidiate member size of 40 x 20mm wooden frame/ bidding to be finished with melamine polish. to be finished with duco paint finish with necessary fittings as per design and details. | Entrance | 4500 x 3600 HT | SFT | 200 |  |  | pending |  | ok
Plywood - branded Commercial Ply (MR Calibrated, IS 303) -- Greenply or Equivalent brand
5 | Cane Roller Blinds | P & F of Cane manual folding curtains as per approval | Glass Façade (Ledge Wall) | 1100mm (L) x 3700mm (HT) | SFT Nos. | 400 |  |  | pending |  | need to check for celling suspension
6 | Fabric Roller Blinds | P & F of Fabric manual folding curtains as per approval Basic rate- | Banquet Seating Area |  | Sqft | 150 |  |  | pending |  | need to check for approved
|  | Basic rate- 150/Sq Ft |  | 450mm (HT)
TOTAL CARPENTRY WORK | [7 empty] | 0
METAL FURNITURE & SCREENS |  | CARPENTRY WORK | [5 empty] | #REF!
7 | Framework For Sheer Curtain | Providing and fixing 20 x 20mm MS box section finished in black powder caot framework fixed on walls finishing/supporting/cutting/required fixture & fasteners etc. as per design, drawing & as directed by Project Manager etc. complete. | Banquet Seating Area |  | RFT | 45 |  |  | pending |  | cancelled
TOTAL METAL FURNITURE & SCREENS | [7 empty] | 0
LIGHTS
8 | Decorative Hanging Light | Copper welded metal pipe with backlit fabric | Near Buffet Counter | 800mm (Dia) 300mm (H) | Nos. | 8 |  |  | pending |  | 4 nos
MISCELLANEOUS - 1
6 | CHEF Photo Frame | P & F of Chef Photo frame in the cetre of frame on wallpaper wall between lights. | Banquet Seating Area |  | Nos | 4 |  |  | pending |  | ok
TOTAL MISCELLANEOUS - 1 | [7 empty] | 0
Total Amount | [7 empty] | 0