## Sheet1
AJ1881 CAFÉ LUCKNOW AIRPORT
SR.NO. | DESCRIPTION | LOCATION | SIZE | CODE | BRAND | IMAGE | REMARK BY ARA | REMARK | REMARK BY ARA
FLOOR FINISHES
1.1 | Kota stone Flooring | KITCHEN | 600 (W) X 600 (L) MM | LOCALLY SOURCED (Sample to be shown before Approval) | LOCALLY SOURCED (Sample to be shown before Approval) |  | SAMPLE AWAITED | Sample list received on - 18/12/23 Sample arranged at lucknow airport - 21/12/23 Sample courier from lucknow to mumbai - 22/12/23 Sample received at mumbai - 25/12/23 Changes in Code by client - 27/12/23 We can provide samples by - 04/01/24 | SAMPLE APPROVED ON 2-1-24 BY ARUN DAS
1.2 | SPC Wooden flooring | FOH Dining Area | 183(W) X 1524 (L) X 6(THK.) MM | SCANDINAVIAN FOSSIL GREY | LEBEN |  | SAMPLE APPROVED BY ARUN DAS (CLIENT) | Sample list received on - 18/12/23 Sample arranged at lucknow airport - 21/12/23 Sample courier from lucknow to mumbai - 22/12/23 Sample received at mumbai - 25/12/23 Sample approved date -27/12/23 Basic rate - 230/- per sft | SAMPLE APPROVED ON 27-12-23 BY ARUN DAS
1.3 | Matt Finish Designer Tile | FOH Dining Area | 300 (W) X 300 (L) X 6 (THK.) MM | 3287 | MYTILES |  | SAMPLE AWAITED | Sample list received on - 18/12/23 Sample arranged at lucknow airport - 27/12/23 We can provide samples in mumbai by - 03/01/24, As it is dispatched from bangalore Basic rate - 74.576 | SAMPLE APPROVED ON 2-1-24 BY ARUN DAS
1.4 | Wooden Skirting (Polish to be Matched with Flooring Colour) |  |  | LOCALLY SOURCED (Sample to be shown before Approval) | LOCALLY SOURCED (Sample to be shown before Approval) |  | SAMPLE NEEDS TO BE EXACT AS PER SHOWN IN IMAGE | Need brand,code and supplier detail too for exact as per shown image of sample Basic rate - 550/- RMT | CHECKING WITH ARUN DAS IF WE CAN CHANGE THE SKIRTING TO SOME OTHER AVAILABLE DESIGN
WALL FINISHES
Kitchen & Pot Wash areas
2.1 | White wall tile | KITCHEN & POT WASH | 300 (W) X 300 (L) MM | LOCALLY SOURCED (Sample to be shown before Approval) | LOCALLY SOURCED (Sample to be shown before Approval) |  | SAMPLE TO BE NORMAL PAINT WHITE TILE WITHOUT ANY TEXTURE | Sample list received on - 18/12/23 Sample arranged at lucknow airport - 21/12/23 Sample courier from lucknow to mumbai - 22/12/23 Sample received at mumbai - 25/12/23 Changes in Code by client - 27/12/23 Require Brand and code of tile Basic Rate - 40/- sft | THE TILE HAS TO BE LOCALLY SELECTED, SADA WHITE TILE
2.2 | SS corner beeding in kitchen wall tiles - Shades | KITCHEN |  | LOCALLY SOURCED (Sample to be shown before Approval) | LOCALLY SOURCED (Sample to be shown before Approval) |  | - | Sample list received on - 18/12/23 We can provide samples by - 03/01/24 | -
FOH Dining areas
2.3 | Matt Finish Paint for Walls | FOH Dining Area |  | RAL 9001 (CODE SHARED BY CLIENT ) | KANSAI NEROLAC | MUSLIN-W-112 | SAMPLE AWAITED | We can provide catlogue by 01/01/24 | WE JUST NEED A SMALL SAMPLE TO CHECKTHE FINISHING
2.4 | Wooden Moulding (Polish to be Matched with wall paint Colour) | FOH Dining Area |  | LOCALLY SOURCED (Sample to be shown before Approval) | LOCALLY SOURCED (Sample to be shown before Approval) |  | SAMPLE NEEDS TO BE EXACT AS PER SHOWN IN IMAGE | Sample list received on - 18/12/23 Sample arranged at lucknow airport - 21/12/23 Sample courier from lucknow to mumbai - 22/12/23 Sample received at mumbai - 25/12/23 Changes in Code by client - 27/12/23 Need brand,code and supplier detail for exact as per shown image of sample | HAVE SHARED ALTERNATE OPTIONS, AWAITING CONFIRMATION FROM ARUN DAS (CLIENT)
2.5 | Matt finish Oak wood veneer | FOH Dining Area |  | White Rovere 1.1 | VIYO The veneer Company |  | SAMPLE AWAITED | Sample list received on - 18/12/23 Sample arranged at lucknow airport - 24/12/23 We can provide samples in mumbai by - 01/01/24 Basic rate - 140/- Per sft | SAMPLE APPROVED ON 2-1-24 BY ARUN DAS
CEILING WORKS
3.1 | Metal Tile Ceiling | KITCHEN & POT WASH | 600 (W) X 600 (L) MM | Extra Microperforated (Rg 0701) | Knauf/ Armstrong |  | SAMPLE APPROVED - WHITE COLOUR BY ARUN DAS (CLIENT) ON 27-12-23 | Sample list received on - 18/12/23 Sample arranged at lucknow airport - 21/12/23 Sample courier from lucknow to mumbai - 22/12/23 Sample received at mumbai - 25/12/23 Sample approved date -27/12/23 Basic rate - 69.94/- per sft
3.2 | Matt Finish Paint on the Slab & Walls | VOID CEILING AREA |  | RAL 7021 (CODE SHARED BY CLIENT ) | KANSAI NEROLAC | BLACK HILLS - 2952 C | SAMPLE AWAITED | We can provide catlogue by 03/01/24
3.3 | Metal Mesh ceiling | FOH (FOR HANGING FLOWERS FROM CEILING) |  | LOCALLY SOURCED (Sample to be shown before Approval) | LOCALLY SOURCED (Sample to be shown before Approval) |  | SAMPLE APPROVED BY ARUN DAS (CLIENT)- ON 27-12-23 SAMPLE TO HAVE PROPER BLACK COLOUR COAT | Sample list received on - 18/12/23 Sample arranged at lucknow airport - 21/12/23 Sample courier from lucknow to mumbai - 22/12/23 Sample received at mumbai - 25/12/23 Sample approved date -27/12/23
DOORS & WINDOWS
4.1 | Hardware Samples |  |  |  | Hafele
CHAIRS & BANQUETTE SEATING
5.1 | Dining Chair: Fabric design samples | COLOUR : GREY & WHITE | These Images are for Reference as per the Renders provided. (Samples to be shown before approval) Fabric to be Washable |  |  |  | SAMPLE AWAITED | Sample list received on - 18/12/23 Sample arranged at lucknow airport - 24/12/23 We can provide samples in mumbai by - 01/01/24 | SAMPLE APPROVED ON 2-1-24 BY ARUN DAS
5.2 | Dining Chair: Fabric colour shades | GREY | These Images are for Reference as per the Renders provided. (Samples to be shown before approval) Fabric to be Washable |  |  |  | SAMPLE AWAITED | Sample list received on - 18/12/23 Sample arranged at lucknow airport - 24/12/23 We can provide samples in mumbai by - 01/01/24 | RAL 9022 (CODE SHARED BY CLIENT) TO BE MATCHED
5.3 | Dining Chair: Gold colour shades |  | As per 3D Render ( Gold Finish metal ) Sample to be showm before approval |  |  |  | SAMPLE AWAITED | Sample list received on - 18/12/23 We can provide catlogue by - 02/01/24
5.4 | Banquett Seating: Fabric texture and colour | GREY | These Images are for Reference as per the Renders provided. (Samples to be shown before approval) Fabric to be Washable |  |  |  | SAMPLE AWAITED | Sample list received on - 18/12/23 Sample arranged at lucknow airport - 24/12/23 We can provide samples in mumbai by - 01/01/24 | RAL 9022 (CODE SHARED BY CLIENT) TO BE MATCHED
TABLE
6.1 | Corian material shades |  |  |  | DUPONT CORIAN QUARTZ |  | SAMPLE AWAITED (PLEASE SEND ONLY SAMPLE AS PER CODE ) | Sample list received on - 18/12/23 Sample arranged at lucknow airport - 21/12/23 Sample courier from lucknow to mumbai - 22/12/23 Sample received at mumbai - 25/12/23 AS Corian mentioned in BOQ we have arranged catlogue of corian We can provide samples of Quartz by - 03/01/24 Basic rate - 1950/- per sft Installation charge- 450/- per sft | SAMPLE RECEIVED ON 2ND - REJECTED BY ARUN DAS(CLIENT). HAVE SHARED ALTERNATE OPTIONS
6.2 | Gold colour shades | Provide us shades catalogue to select - on site | [5 empty] | Sample list received on - 18/12/23 We can provide catlogue by - 02/01/24
JOINERY
7.1 | Corian material shades |  |  |  | DUPONT CORIAN QUARTZ |  | SAMPLE AWAITED (PLEASE SEND ONLY SAMPLE AS PER CODE ) | Sample list received on - 18/12/23 Sample arranged at lucknow airport - 21/12/23 Sample courier from lucknow to mumbai - 22/12/23 Sample received at mumbai - 25/12/23 AS Corian mentioned in BOQ we have arranged catlogue of corian We can provide samples of Quartz by - 03/01/24 Basic rate - 1950/- per sft Installation charge- 450/- per sft | SAMPLE RECEIVED ON 2ND - REJECTED BY ARUN DAS(CLIENT). HAVE SHARED ALTERNATE OPTIONS
7.2 | Charcoal panel / Leather finish Laminate | Provide us catalogue to select |  |  |  |  | SAMPLE AWAITED | Require Brand and code number of charcoal panel
7.3 | Matt finish Oak wood veneer |  |  | White Rovere 1.1 | VIYO The veneer Company |  | SAMPLE AWAITED | Sample list received on - 18/12/23 Sample arranged at lucknow airport - 24/12/23 We can provide samples in mumbai by - 01/01/24
7.4 | Metal Strip samples and shades | Provide us shades catalogue to select |  |  |  |  | SAMPLE AWAITED | Sample list received on - 18/12/23 We can provide catlogue by - 02/01/24
7.5 | Hardware samples | Hafele
SIGNAGES
8.1 | All material samples | To be provided by the vendor for approval
OTHER
9.1 | Hanging flowers (Custom made)- Sample |  |  | RAL 4008 for colours of flower to be mached |  |  |  | Sample list received on - 18/12/23 We can provide catlogue by - 02/01/24 | AMAZON LINK SHARED - 5-1-23 APPROVED BY ARUN DAS https://amzn.eu/d/dG5b7dr
9.2 | Tree (Custom made)- Sample | To be customized
9.3 | Plants (Custom made)- Sample | To be customized
9.4 | All Lights | Provide samples as per renders for approval
9.5 | Switches | Legrand