## Abstract Summary
Semolina Projects
Project : CIP Lounge, Lucknow
Details: Project invoicing
PO No : PO/SKPL/23-24/001793
CIP Lounge - Bill Summary
S.N | Item | PO Value | Previous bills | This Bill | Cumulative | Varition ( In Amt ) | % Billing | Po No. | JMR Status
1 | Civil & int | 18926619 | #REF! | #REF! | #REF! | #REF! | #REF! | PO/SKPL/23-24/001793 | Done
2 | Structure Steel Work | 546000 | #REF! | 0 | #REF! | #REF!
3 | ELECTRICAL WORKS | 4038720 | #REF! | #REF! | #REF! | #REF!
4 | PLUMBING WORKS & Fire | 1229775 | #REF! | #REF! | #REF! | #REF!
5 | HVAC WORKS | 1638700 |  | #REF! | #REF! | #REF!
6 | FIX FURNITURE | 3636500 |  | #REF! | #REF! | #REF!
7 | LIGHTS & PANELS | 1905480 |  | #REF! | #REF! | #REF!
| Subtotal = | 31921794 | #REF! | #REF! | #REF! | #REF!
GST @ 18% |  | 5745922.92 | #REF! | #REF! | #REF! | #REF!
Grand Total |  | 37667716.92 | #REF! | #REF! | #REF! | #REF!
* | Material Advance given Before Taxes |  | #REF! | 0 | #REF!
GST @ 18% |  | 0 | #REF! | 0 | #REF! | 0
As advance paid amount |  | 0 | #REF! | 0 | #REF! | 0
* | Balance Payable
| Payable before taxes |  |  |  | #REF!
GST @ 18% |  | 0 | 0 | 0 | #REF! | 0
Payable with Taxes |  | 0 | 0 | 0 | #REF! | 0

## Summary-2 (hidden)
Summary
#REF!
S. No. | Description of Item | #REF!
|  | PO Amount | RA=-01
1 | Civil & Interior
a | DISMENTLING & CLEANING WORKS | #REF!
b | CIVIL WORK | #REF!
c | FLOORING WORK/CLADDING WORK | #REF!
d | DOOR WINDOW WORK | #REF!
e | OTHER WOOD WORK FOR WALL PANELLING, PARTITIONS & STORAGES | #REF!
f | FALSE CEILING WORK | #REF!
g | FINISHING WORK | #REF!
h | MISC WORK | #REF!
2 | Structural Steel | 546000
3 | Electrical Work
a | SUB-HEAD I WIRING | 2253020
b | SUB-HEAD II CABLES & RACEWAYS | 424200
c | SUB-HEAD III DISTRIBUTION BOARD & ELECTRICAL PANEL | 727650
d | SUB-HEAD IV FIRE DETECTION & PA SYSTEM | 519300
e | SUB-HEAD V CCTV SYSTEM | 114550
4 | PHE and FF
a | SANITARY FIXTURES AND FITTINGS | 538400
b | WATER SUPPLY | 97725
c | DRAINAGE | 94480
d | FIRE FIGHTING | 499170
5 | HVAC
a | DUCTWORK AND AIR DISTRIBUTION | 1148700
b | VENTILATION FANS AND ARRANGEMENT | 490000
6 | Furniture | 3636500
7 | Light Fixtures | 1905480
| Total Basic Amount (in Rs.) | #REF!
| GST @18% | #REF!
| Total Amount (in Rs.) | #REF!

## Inv Summary
Semolina Projects
Project : CIP Lounge, Lucknow
Details: Project invoicing
PO No
CIP Lounge - Bill Summary
S.N | Item | PO Value | RA-09 Value | JMR status
| ELECTRICAL WORKS (EXTRA QTY |  | 1084968.5
| LIGHTS & PANELS (EXTRA QTY ) |  | 238820
8 | Civil & interior (EXTRA QTY ) |  | 1189566.56
Total |  | 0 | 2513355.06
GST @ 18% |  | 0 | 452403.9108
Grand Total |  | 0 | 2965758.9708

## JMR LIGHTS & PANELS
IMPULSE BRANDING SOLUTIONS
03/204, SUNDAR DARSHAN CHSL, MIRA BHAYANDER, THANE - 401107
Date:24/03/2024
Project : Adani CIP Lounge T3 Lok
W/O No : SKPL/23-24/001793
Name of the Work : Light Fixtures CIP Lounge T3 Lok
RA-1 MEASUREMENT SHEET OF Light Fixtures
S. No. | Item. Code | Specification | Unit | Location | Site Qty | WOQ | Rate | Amount | Extra Qty | Remarks
| A | Supply, assembling, erection, connecting, testing and commissioning of the following LED light fixtures complete with housing, reflectors, all accessories i.e. copper wound ballast, HPF condensors, starters, holders etc. complete as required
| 1 | Recessed Downlighter - 9W Ceiling light fixture LED Recessed 9W LED, colour temperature of 3000K-4000K, Ø = 100mm Base Price @ 1020/- each | Nos | Male Restroom=8 Female Restroom=4 Disable Restroom=2 Electrical Room=2 | 16 | 16 | 1560 | 24960
| 2 | Recessed Downlighter - 15W Ceiling light fixture LED Recessed 15W LED, colour temperature of 3000K-4000K, Ø = 100mm Base Price @ 1020/- each | Nos | Admin=2 | 2 | 2 | 1750 | 3500
| 4 | Recessed Downlighter - LED CRYSTA COB SWIVEL SPOTLIGHT 6 W 4000 K LED Recessed 6W LED, colour temperature of 3000K-4000K, Ø = 71mm Base Price @ 1045/- each | Nos | P,Lounge=11 BAR Area=4 Dinning Area=2 Passage=4 Female Restroom=1 | 20 | 22 | 1500 | 30000 |  | Balance=2 nos
| 6 | Recessed Downlighter - LED CRYSTA COB SWIVEL SPOTLIGHT 3 W 4000 K LED Recessed 3W LED, colour temperature of 3000K-4000K, Ø = 71mm Base Price @ 450/- each (All the Taxes Inclusive) | Nos | SPA=6 | 6 | 31 | 750 | 4500 |  | Balance=25 nos
| 7 | Recessed Downlighter - ASTRAL ROUND 2 W Warm Daylight (WDL) 4000 K LED Recessed 2W LED, colour temperature of 3000K-4000K, Ø = 41mm Base Price @ 215/- each (All the Taxes Inclusive) | Nos | BAR Wall=16 P LOUNG Wall=13 | 0 | 29 | 430 | 0 |  | Balance=29 nos
| 8 | Recessed Downlighter - LED recessed luminaire system power 18W, colour temperature of 4000K, L = 595mm, B = 595mm, H = 70mm Base Price @ 2500/- each | Nos | Kitchen=5 | 5 | 5 | 3600 | 18000
DECORATIVE LIGHTING - Supply & Installation Only (Brand & Make : Zolux / Truemoon / White Teak (Asian Paints) / Jainsons / Jaquar
| 2 | WALL DECORATIVE LIGHT : Marvel at this innovative design featuring an A classy leaf shaped, multicolor body paint with day lamp highlight the ornate finishing doubles as a wall hanging too. Switch it on for a warm glow, or let it add subtle elegance to your walls as it rests. Leaf metal shade that cover back LED lamp, The frame in diffrent color shade, housing the orb of light within itself as well. It's an incredible wall light for lounges. No. of Bulb Holders :1 Holder & Plug Type :E-27 Recommended Bulb :40 Watts (Max) Package Contents :1 Premium Wall Light. Bulb Provided: LED bulb Provided Product Material : Metal Body in Matte multicolor color Finish as approved. Product Weight (in Kg)0.5 Country Of Origin: custom / Imported Size & Shape : 225mm high x 100mm wide, Leaf shape Base Range : Rs. 2900/- each | Nos | P,Lounge=32 BAR Area=32 Survery Area=8 Expention Column=0 | 72 | 75 | 3600 | 259200 | 11 | Incresed due to change in Drawing of Buffar Counter COLUMN Balance=14
[7 empty] | Total Amount | 340160

## LIGHT FITTING JMR RA Bill 09
IMPULSE BRANDING SOLUTIONS
03/204, SUNDAR DARSHAN CHSL, MIRA BHAYANDER, THANE - 401107
Date:- 22.06.2024
Project : Adani CIP Lounge T3 Lok
W/O No : SKPL/23-24/001793
Name of the Work : Electrical CIP Lounge T3 Lok
RA-09 MEASUREMENT SHEET OF LIGHT FITTING
S. No. | Item. Code | Specification | Description | W | H | Unit | Nos | Qty.
1 |  | Electrical
Recessed Downlighter - 9W Ceiling light fixture LED Recessed 9W LED, colour temperature of 3000K-4000K, Ø = 100mm Base Price @ 1020/- each
|  | Male Washroom |  |  |  | Nos | 8
|  | Fmale Washroom |  |  |  | Nos | 6
|  | Handycap |  |  |  | Nos | 2
|  | Electrical Room |  |  |  | Nos | 2
|  | Total Qty |  |  |  |  | 18
|  | WO Qty |  |  |  |  | 16 | Nos
|  | RA 08Qty |  |  |  |  | 16
|  | RA 09Qty |  |  |  |  | 0
|  | RA 09 Extra Qty |  |  |  |  | 2
Recessed Downlighter - 15W Ceiling light fixture LED Recessed 15W LED, colour temperature of 3000K-4000K, Ø = 100mm Base Price @ 1020/- each
|  | Admin Room |  |  |  | Nos | 2
|  | Total Qty |  |  |  |  | 2
|  | WO Qty |  |  |  |  | 2 | Nos
|  | RA 08Qty |  |  |  |  | 2
|  | RA 09Qty |  |  |  |  | 0
|  | RA 09 Extra Qty |  |  |  |  | 0
Recessed Downlighter - LED CRYSTA COB SWIVEL SPOTLIGHT 3 W 4000 K LED Recessed 3W LED, colour temperature of 3000K-4000K, Ø = 62mm Base Price @ 810/- each (All the Taxes Inclusive)
|  | Admin Room |  |  |  | Nos
|  | Total Qty |  |  |  |  | 0
|  | WO Qty |  |  |  |  | 6 | Nos
RA 08Qty
RA 09Qty
Recessed Downlighter - LED CRYSTA COB SWIVEL SPOTLIGHT 6 W 4000 K LED Recessed 6W LED, colour temperature of 3000K-4000K, Ø = 71mm Base Price @ 1045/- each
|  | Male Washroom |  |  |  | Nos | 0
|  | Fmale Washroom |  |  |  | Nos | 0
|  | Passege |  |  |  | Nos | 7
|  | Baar Area |  |  |  | Nos | 4
|  | Premium Lounge |  |  |  | Nos | 11
22
|  | Total Qty |  |  |  |  | 22
|  | WO Qty |  |  |  |  | 22 | Nos
|  | RA 08Qty |  |  |  |  | 20
|  | RA 09Qty |  |  |  |  | 2
Recessed Downlighter - LED CRYSTA COB SWIVEL SPOTLIGHT 3 W 4000 K LED Recessed 3W LED, colour temperature of 3000K-4000K, Ø = 71mm Base Price @ 450/- each (All the Taxes Inclusive)
|  | Baar Counter Wall |  |  |  | Nos | 16
|  | Recepsion Wall |  |  |  | Nos | 13
29
|  | Total Qty |  |  |  |  | 29
|  | WO Qty |  |  |  |  | 29 | Nos
RA 08Qty
|  | RA 09Qty |  |  |  |  | 29
Recessed Downlighter - LED CRYSTA COB SWIVEL SPOTLIGHT 3 W 4000 K LED Recessed 3W LED, colour temperature of 3000K-4000K, Ø = 71mm Base Price @ 450/- each (All the Taxes Inclusive)
|  | Spa Room |  |  |  | Nos | 29
29
|  | Total Qty |  |  |  |  | 29
|  | WO Qty |  |  |  |  | 31 | Nos
|  | RA 08Qty |  |  |  |  | 6
|  | RA 09Qty |  |  |  |  | 23
Recessed Downlighter - LED recessed luminaire system power 18W, colour temperature of 4000K, L = 595mm, B = 595mm, H = 70mm Base Price @ 2500/- each
|  | Kitchen Ceilling Light |  |  |  | Nos | 5
5
|  | Total Qty |  |  |  |  | 5
|  | WO Qty |  |  |  |  | 5 | Nos
|  | RA 08Qty |  |  |  |  | 5
RA 09Qty
Profile Strip Light - FLEXION LED STRIP 22 W Warm Daylight (WDL) 4000K (5 Meter roll) + LED Driver LED Profile Strip Light , colour temperature of 3000- 4000K Base Price Strip @ 810/- Each Roll 5mtr Base Price Profile @ 550/- Per mtr
|  | Premium Lounge Cove Light |  | Rmt |  |  | 26.2
|  | Dinning Area Cove Light |  | Rmt |  |  | 11.5
|  | Recepsion Cove Light |  | Rmt |  |  | 6.5
|  | Male Washroom Cove Light |  | Rmt |  |  | 14
|  | Fmale Washroom Cove Light |  | Rmt |  |  | 11.4
|  | Recepsion Table Skerting |  | Rmt |  |  | 2.5
|  | Baar Table Skerting |  | Rmt |  |  | 11
|  | Dinning Area Table Skerting |  | Rmt |  |  | 28.5
|  | Spa Rom Cove Light |  | Rmt |  |  | 9
|  | Admin Room Cove Light |  | Rmt |  |  | 4
|  | Male Washroom Behind Mirror |  | Rmt |  |  | 4.8
|  | Fmale Washroom Behind Mirror |  | Rmt |  |  | 4.4
|  | Handycap Washroom Behind Mirror |  | Rmt |  |  | 3.5
137.3
|  | Total Qty |  |  |  |  | 137.3
|  | WO Qty |  |  |  |  | 175 | Rmt
|  | RA 08Qty |  |  |  |  | 0
|  | RA 09Qty |  |  |  |  | 137.3
Recessed Floor Light - LED Recessed 5W LED, colour temperature of 3000K- 4000K, Ø = 90mm Base Price Strip @ 2500/- Each
|  | Premium Lounge |  | Nos |  |  | 2
|  | Recepsion Garden |  | Nos |  |  | 4
|  | Baar Area Garden |  | Nos |  |  | 3
|  | Dinning Area Garden |  | Nos |  |  | 2
|  | Kitchen Passage |  | Nos |  |  | 1
12
|  | Total Qty |  |  |  |  | 12
|  | WO Qty |  |  |  |  | 12 | Nos
|  | RA 08Qty |  |  |  |  | 0
|  | RA 09Qty |  |  |  |  | 12
Table Lamp : Take a deep breath and move steadily while I fashion your spaces. A beauty that’s warm & attractive, growing on you slowly and steadily beyond comprehension and expression. A beauty that’s clad in black and gold, she’s sheer sophistication and elegance. Product Dimensions - Overall Dimensions- Height: 22.5" Length: 15" Width: 15" Shade Dimensions- Height: 6" Diameter: 15" Base Dimensions- Height: 1" Diameter: 9.5" Holder & Plug TypeE -27 Recommended BulbL ED Only. No. of Bulb Holders1
|  | Premium Lounge Table |  | Nos |  |  | 11
11
|  | Total Qty |  |  |  |  | 11
|  | WO Qty |  |  |  |  | 11 | Nos
RA 08Qty
|  | RA 09Qty |  |  |  |  | 11
WALL DECORATIVE LIGHT : Marvel at this innovative design featuring an A classy leaf shaped, multicolor body paint with day lamp highlight the ornate finishing doubles as a wall hanging too. Switch it on for a warm glow, or let it add subtle elegance to your walls as it rests. Leaf metal shade that cover back LED lamp, The frame in diffrent color shade, housing the orb of light within itself as well. It's an incredible wall light for lounges. No. of Bulb Holders :1 Holder & Plug Type :E -27 Recommended Bulb :4 0 Watts (Max) Package Contents :1 Premium Wall Light. Bulb Provided: LED bulb Provided Product Material : Metal Body in Matte multicolor color Finish as approved. Product Weight (in Kg)0 .5 Country Of Origin: custom / Imported Size & Shape : 225mm high x 100mm wide, Leaf shape Base Range : Rs. 2900/- each
|  | Premium Lounge Wall |  | Nos |  |  | 32
|  | Baar Area Wall |  | Nos |  |  | 32
|  | Dinning Area Wall |  | Nos |  |  | 16
80
|  | Total Qty |  |  |  |  | 80
|  | WO Qty |  |  |  |  | 75 | Nos
|  | RA 08Qty |  |  |  |  | 72
|  | RA 09Qty |  |  |  |  | 3
|  | RA 09 Extra Qty |  |  |  |  | 5
CEILING DECORATIVE LIGHTS : Providing, making & Installing The newest ddition custom curvy designs lights, custom Sleepover draws you in with its curvaceous profile, glistening gold finish and long lamp life of LEDs. This swoon- worthy beauty is perfect for all interiors and seamlessly blends across settings. Introduce the flexibility of shapes and ease of innovative features to your entryway with this modern light. The silicone diffuser houses the LEDs, thus creating a sleek appearance. Switch the colour temperatures of this dimmable LED light to suit your changing moods with the help of the remote that comes with the unit. Browse through our extensive range of LED chandeliers for more. ColourG old or As per Approved Temperature3 000K to 6500K Wattage5 Watts, 30 Watts Color TemperatureD ay Light
FOR BAR AREA
|  | L1 : Size 620mm Long x 275mm wide x 1 each |  |  |  | Nos | 11
|  | Total Qty |  |  |  |  | 11
|  | WO Qty |  |  |  |  | 11 | Nos
RA 08Qty
|  | RA 09Qty |  |  |  |  | 11
CEILING DECORATIVE LIGHTS : Providing, making & Installing The newest ddition custom curvy designs lights, custom Sleepover draws you in with its curvaceous profile, glistening gold finish and long lamp life of LEDs. This swoon- worthy beauty is perfect for all interiors and seamlessly blends across settings. Introduce the flexibility of shapes and ease of innovative features to your entryway with this modern light. The silicone diffuser houses the LEDs, thus creating a sleek appearance. Switch the colour temperatures of this dimmable LED light to suit your changing moods with the help of the remote that comes with the unit. Browse through our extensive range of LED chandeliers for more. ColourG old or As per Approved Temperature3 000K to 6500K Wattage5 Watts, 30 Watts Color TemperatureD ay Light
FOR BAR AREA
|  | L2 : Size395/530/620mm Long x 175/225/275mm wide x 1 each |  |  |  | Nos | 12
|  | Total Qty |  |  |  |  | 12
|  | WO Qty |  |  |  |  | 10 | Nos
RA 08Qty
|  | RA 09Qty |  |  |  |  | 10
|  | RA 09 Extra Qty |  |  |  |  | 2
CEILING DECORATIVE LIGHTS : Providing, making & Installing The newest ddition custom curvy designs lights, custom Sleepover draws you in with its curvaceous profile, glistening gold finish and long lamp life of LEDs. This swoon- worthy beauty is perfect for all interiors and seamlessly blends across settings. Introduce the flexibility of shapes and ease of innovative features to your entryway with this modern light. The silicone diffuser houses the LEDs, thus creating a sleek appearance. Switch the colour temperatures of this dimmable LED light to suit your changing moods with the help of the remote that comes with the unit. Browse through our extensive range of LED chandeliers for more. ColourG old or As per Approved Temperature3 000K to 6500K Wattage5 Watts, 30 Watts Color TemperatureD ay Light
FOR HIGH COUNTER AREA
|  | L1 : Size 615/700/800mm Long x 275/325/350mm wide x 1 each |  |  |  | Nos | 17
|  | Total Qty |  |  |  |  | 17
|  | WO Qty |  |  |  |  | 16 | Nos
RA 08Qty
|  | RA 09Qty |  |  |  |  | 16
|  | RA 09 Extra Qty |  |  |  |  | 1
CEILING DECORATIVE LIGHTS : Providing, making & Installing The newest ddition custom curvy designs lights, custom Sleepover draws you in with its curvaceous profile, glistening gold finish and long lamp life of LEDs. This swoon- worthy beauty is perfect for all interiors and seamlessly blends across settings. Introduce the flexibility of shapes and ease of innovative features to your entryway with this modern light. The silicone diffuser houses the LEDs, thus creating a sleek appearance. Switch the colour temperatures of this dimmable LED light to suit your changing moods with the help of the remote that comes with the unit. Browse through our extensive range of LED chandeliers for more. ColourG old or As per Approved Temperature3 000K to 6500K Wattage5 Watts, 30 Watts Color TemperatureD ay Light
FOR HIGH COUNTER AREA
|  | L2 : Size 475/620/700/800/810mm Long x 225/275/325/350/375mm wide x 1 each |  |  |  | Nos | 27
|  | Total Qty |  |  |  |  | 27
|  | WO Qty |  |  |  |  | 15 | Nos
RA 08Qty
|  | RA 09Qty |  |  |  |  | 15
|  | RA 09 Extra Qty |  |  |  |  | 12
CEILING DECORATIVE LIGHTS : Providing, making & Installing The newest ddition custom curvy designs lights, custom Sleepover draws you in with its curvaceous profile, glistening gold finish and long lamp life of LEDs. This swoon- worthy beauty is perfect for all interiors and seamlessly blends across settings. Introduce the flexibility of shapes and ease of innovative features to your entryway with this modern light. The silicone diffuser houses the LEDs, thus creating a sleek appearance. Switch the colour temperatures of this dimmable LED light to suit your changing moods with the help of the remote that comes with the unit. Browse through our extensive range of LED chandeliers for more. ColourG old or As per Approved Temperature3 000K to 6500K Wattage5 Watts, 30 Watts Color TemperatureD ay Light
FOR RECEPTION AREA
|  | L1 - Ceiling : Size 440/485/585/585mm Long x 130/190/225/255mm wide x 1 each |  |  |  | Nos | 15
|  | Total Qty |  |  |  |  | 15
|  | WO Qty |  |  |  |  | 17 | Nos
RA 08Qty
|  | RA 09Qty |  |  |  |  | 15
CEILING DECORATIVE LIGHTS : Providing, making & Installing The newest ddition custom curvy designs lights, custom Sleepover draws you in with its curvaceous profile, glistening gold finish and long lamp life of LEDs. This swoon- worthy beauty is perfect for all interiors and seamlessly blends across settings. Introduce the flexibility of shapes and ease of innovative features to your entryway with this modern light. The silicone diffuser houses the LEDs, thus creating a sleek appearance. Switch the colour temperatures of this dimmable LED light to suit your changing moods with the help of the remote that comes with the unit. Browse through our extensive range of LED chandeliers for more. ColourG old or As per Approved Temperature3 000K to 6500K Wattage5 Watts, 30 Watts Color TemperatureD ay Light
FOR RECEPTION AREA
|  | L2 - Ceiling : Size 290/440/525/640/mm Long x 110/160/190/255mm wide x 1 each |  |  |  | Nos | 15
|  | Total Qty |  |  |  |  | 15
|  | WO Qty |  |  |  |  | 17 | Nos
RA 08Qty
|  | RA 09Qty |  |  |  |  | 15

## Abstract LIGHTS & PANELS
Company Name : | LKO INTNL ARPT LTD
Project Name : | Finishing work for CIP Lounge at Terminal-03, CCSI Airport, Lucknow
Sr No | Particulars | Code / Area Specified | Qty. | UoM | Impulse Branding |  | RA-08 |  | RA 09 |  | Extra Qty RA 09 |  | Cumulative |  | Variance
[5 empty] | Unit Price | Total Amount | QTY | Amount | Qty | Amount | Qty | Amount | QTY | Amount | QTY | Amount
[5 empty] | INR | INR
LIGHT FITTING - Supply & Installation Only (Brands/Make : Havells / Philips /
Supply, assembling, erection, connecting, testing and commissioning of the following LED light fixtures complete with housing, reflectors, all accessories i.e. copper wound ballast, HPF condensors, starters, holders etc. complete as required
1 | Recessed Downlighter - 9W Ceiling light fixture LED Recessed 9W LED, colour temperature of 3000K-4000K, Ø = 100mm Base Price @ 1020/- each |  | 16 | nos | 1560 | 24960 | 16 | 24960 | 0 | 0 | 2 | 3120
2 | Recessed Downlighter - 15W Ceiling light fixture LED Recessed 15W LED, colour temperature of 3000K-4000K, Ø = 100mm Base Price @ 1020/- each |  | 2 | nos | 1750 | 3500 | 2 | 3500
3 | Recessed Downlighter - LED CRYSTA COB SWIVEL SPOTLIGHT 3 W 4000 K LED Recessed 3W LED, colour temperature of 3000K-4000K, Ø = 62mm Base Price @ 810/- each (All the Taxes Inclusive) |  | 6 | nos | 1250 | 7500
4 | Recessed Downlighter - LED CRYSTA COB SWIVEL SPOTLIGHT 6 W 4000 K LED Recessed 6W LED, colour temperature of 3000K-4000K, Ø = 71mm Base Price @ 1045/- each |  | 22 | nos | 1500 | 33000 | 20 | 30000 | 2 | 3000
5 | Recessed Downlighter - LED CRYSTA COB SWIVEL SPOTLIGHT 9 W 4000 K LED Recessed 9W LED, colour temperature of 3000K-4000K, Ø = 78mm Base Price @ 1395/- each |  | 0 | nos | 1850 | 0
6 | Recessed Downlighter - LED CRYSTA COB SWIVEL SPOTLIGHT 3 W 4000 K LED Recessed 3W LED, colour temperature of 3000K-4000K, Ø = 71mm Base Price @ 450/- each (All the Taxes Inclusive) |  | 31 | nos | 750 | 23250 | 6 | 4500 | 23 | 17250
7 | Recessed Downlighter - ASTRAL ROUND 2 W Warm Daylight (WDL) 4000 K LED Recessed 2W LED, colour temperature of 3000K-4000K, Ø = 41mm Base Price @ 215/- each (All the Taxes Inclusive) |  | 29 | nos | 430 | 12470 |  |  | 29 | 12470
8 | Recessed Downlighter - LED recessed luminaire system power 18W, colour temperature of 4000K, L = 595mm, B = 595mm, H = 70mm Base Price @ 2500/- each |  | 5 | nos | 3600 | 18000 | 5 | 18000
9 | Profile Strip Light - FLEXION LED STRIP 22 W Warm Daylight (WDL) 4000K (5 Meter roll) + LED Driver LED Profile Strip Light , colour temperature of 3000- 4000K Base Price Strip @ 810/- Each Roll 5mtr Base Price Profile @ 550/- Per mtr |  | 175 | Per Mtr | 420 | 73500 |  |  | 137.3 | 57666
10 | Recessed Floor Light - LED Recessed 5W LED, colour temperature of 3000K- 4000K, Ø = 90mm Base Price Strip @ 2500/- Each |  | 12 | nos | 3200 | 38400 |  |  | 12 | 38400
11 | DECORATIVE LIGHTING - Supply & Installation Only (Brand & Make : Zolux / Truemoon / White Teak (Asian Paints) / Jainsons / Jaquar) |  |  |  |  | 0
12 | Table Lamp : Take a deep breath and move steadily while I fashion your spaces. A beauty that’s warm & attractive, growing on you slowly and steadily beyond comprehension and expression. A beauty that’s clad in black and gold, she’s sheer sophistication and elegance. Product Dimensions - Overall Dimensions- Height: 22.5" Length: 15" Width: 15" Shade Dimensions- Height: 6" Diameter: 15" Base Dimensions- Height: 1" Diameter: 9.5" Holder & Plug TypeE -27 Recommended BulbL ED Only. No. of Bulb Holders1 Bulb ProvidedN ot Provided Package Contents1 Table Lamp. Product MaterialT he Metal in Matte Gold Finish with Metal Base and Fabric Shade. Product Weight (in Kg)4 .1 Country Of Origin: Imported Base Range : Rs. 16000/- each |  | 11 | Nos | 23000 | 253000 |  |  | 11 | 253000
13 | WALL DECORATIVE LIGHT : Marvel at this innovative design featuring an A classy leaf shaped, multicolor body paint with day lamp highlight the ornate finishing doubles as a wall hanging too. Switch it on for a warm glow, or let it add subtle elegance to your walls as it rests. Leaf metal shade that cover back LED lamp, The frame in diffrent color shade, housing the orb of light within itself as well. It's an incredible wall light for lounges. No. of Bulb Holders :1 Holder & Plug Type :E -27 Recommended Bulb :4 0 Watts (Max) Package Contents :1 Premium Wall Light. Bulb Provided: LED bulb Provided Product Material : Metal Body in Matte multicolor color Finish as approved. Product Weight (in Kg)0 .5 Country Of Origin: custom / Imported Size & Shape : 225mm high x 100mm wide, Leaf shape Base Range : Rs. 2900/- each |  | 75 | Nos | 3600 | 270000 | 72 | 259200 | 3 | 10800 | 5 | 18000
14 | CEILING DECORATIVE LIGHTS : Providing, making & Installing The newest ddition custom curvy designs lights, custom Sleepover draws you in with its curvaceous profile, glistening gold finish and long lamp life of LEDs. This swoon- worthy beauty is perfect for all interiors and seamlessly blends across settings. Introduce the flexibility of shapes and ease of innovative features to your entryway with this modern light. The silicone diffuser houses the LEDs, thus creating a sleek appearance. Switch the colour temperatures of this dimmable LED light to suit your changing moods with the help of the remote that comes with the unit. Browse through our extensive range of LED chandeliers for more. ColourG old or As per Approved Temperature3 000K to 6500K Wattage5 Watts, 30 Watts Color TemperatureD ay Light Holder & Plug TypeD immable Built in LED Package Contents1 Premium Dimmable Built-In LED With Remote Control, Bulb ProvidedD immable Built in LED Product Material: Metal Ceiling Cup In Gold Finish or as approved with Flexible Plastic Body in Good Finish and Silicon Diffuser. Product Weight (in Kg)0 .5 - 2.8 Country Of Origin: cutom / Imported Base Range : Rs. 7500/- small upto 400mm long, & Rs. 9500/- mid upto 600mm long & Rs. 12500/- 800mm long each |  |  |  |  | 0
15 | FOR BAR AREA |  |  |  |  | 0
16 | L1 : Size 620mm Long x 275mm wide x 1 each |  | 11 | Nos | 11500 | 126500 |  |  | 11 | 126500
17 | L2 : Size395/530/620mm Long x 175/225/275mm wide x 1 each |  | 10 | Nos | 10500 | 105000 |  |  | 10 | 105000 | 2 | 21000
18 | FOR HIGH COUNTER AREA |  |  |  |  | 0
19 | L1 : Size 615/700/800mm Long x 275/325/350mm wide x 1 each |  | 16 | Nos | 9500 | 152000 |  |  | 16 | 152000 | 1 | 9500
20 | L2 : Size 475/620/700/800/810mm Long x 225/275/325/350/375mm wide x 1 each |  | 15 | Nos | 15600 | 234000 |  |  | 15 | 234000 | 12 | 187200
21 | FOR RECEPTION AREA |  |  |  |  | 0
22 | L1 - Ceiling : Size 440/485/585/585mm Long x 130/190/225/255mm wide x 1 each |  | 17 | Nos | 15600 | 265200 |  |  | 15 | 234000
23 | L2 - Ceiling : Size 290/440/525/640/mm Long x 110/160/190/255mm wide x 1 each |  | 17 | Nos | 15600 | 265200 |  |  | 15 | 234000
24 |  |  |  |  | Sub Total | 1905480 |  | 340160 |  | 1478086 |  | 238820
25
26
27
28
29
30