## MEASUREMENT SHEET
measurement sheet
GOOD TIMES BAR_T1B
1 | Veneer polish
| left wall from entrance | 0.86 | 2.6 |  | 2.236
|  | 0.92 | 2.6 |  | 2.392
|  | 7.425 | 2.6 |  | 19.305
| column | 0.6 | 2.6 | 2 | 3.12
|  | 0.622 | 2.6 |  | 1.6172
|  | 0.6 | 2.6 | 2 | 3.12
|  | 0.99 | 2.6 | 2 | 5.148
|  | 0.67 | 2.6 | 2 | 3.484
|  | 0.665 | 2.6 | 2 | 3.458
|  | 0.43 | 2.6 | 2 | 2.236
|  | 0.825 | 2.6 | 2 | 4.29
|  | 0.65 | 2.6 |  | 1.69
|  | 0.32 | 2.6 |  | 0.832
| entry portal towards ramp | 0.43 | 2.6 |  | 1.118
|  | 0.7 | 2.6 |  | 1.82
|  | 0.85 | 2.6 | 2 | 4.42
|  | 0.23 | 2.6 |  | 0.598
|  | 1.62 | 0.85 |  | 1.377
| windows | 0.09 | 1.7 | 2 | 0.306
|  | 3.35 | 0.54 | 2 | 3.618
|  | 0.54 | 1.7 | 2 | 1.836
|  | 3.4 | 0.45 | 2 | 3.06
|  | 0.08 | 1.7 | 2 | 0.272
|  | 0.4 | 1.7 | 2 | 1.36
| back counter | 1.1 | 1.5 |  | 1.65
| top of counter | 7.5 | 0.3 |  | 2.25
|  | 7.5 | 1.05 |  | 7.875
| door | 0.9 | 2.1 | 2 | 3.78
| entry of kitchen | 2.65 | 2.6 |  | 6.89
| entry to back kitchen | 2.2 | 2.6 |  | 5.72
|  | 0.9 | 0.9 |  | 0.81
| entrance portal of oulet | 0.44 | 2.07 |  | 0.9108
|  | 0.69 | 2.07 |  | 1.4283
|  | 0.88 | 2.83 |  | 2.4904
|  | 0.7 | 2.07 | 2 | 2.898
|  | 1.7 | 0.7 |  | 1.19
|  | 0.7 | 2.6 | 2 | 3.64
|  | 1.7 | 0.7 |  | 1.19
| liquour storage door | 0.9 | 2.1 | 2 | 3.78
[5 empty] | 119.2157 | 132 | 120
2 | corian buffing
| top of front counter | 7.51 | 0.45 |  | 3.3795
| facade of front counter | 7.51 | 0.975 |  | 7.3222
| side | 0.975 | 0.45 |  | 0.43875
11.1405
3 | painting
| ceiling | 6.5 | 14.11 |  | 91.715
|  | 3.28 | 1.75 |  | 5.74
|  | 0.92 | 3.25 |  | 2.99
|  | 1.75 | 13.52 |  | 23.66
|  | 1.97 | 4.15 |  | 8.1755
wall
| kitchen | 1.75 | 2.82 | 2 | 9.87
|  | 3.605 | 2.82 | 2 | 20.3322
| liquor store | 6.53 | 2.82 | 2 | 36.8292
|  | 1.75 | 2.82 | 2 | 9.87
| dining | 5.6 | 2.6 |  | 14.56
|  | 0.9 | 3 |  | 2.7
|  | 1.03 | 3.31 |  | 3.4093
|  | 1.03 | 4.45 |  | 4.5835
|  | 1.91 | 2.6 |  | 4.966
|  | 0.45 | 2.6 | 2 | 2.34
|  | 0.68 | 2.6 |  | 1.768
| top of back counter | 0.3 | 1.1 | 4 | 1.32
|  | 0.23 | 6 |  | 1.38
246.2087
4 | louvers shutter repolished
| back counter | 0.98 | 2.82 |  | 2.7636 |  | 5 SHUTTERS
| front counter | 0.9 | 2.8 |  | 2.52 |  | 6 SHUTTERS
5.2836
5 | Increase luv level of lights
| spot light |  |  |  | 45
| hanging lights |  |  |  | 4
49
6 | polish existing ss finish
|  | 5.6 | 0.22 |  | 1.232
|  | 10.8 | 0.22 |  | 2.376
|  | 0.65 | 0.22 | 2 | 0.286
|  | 0.27 | 0.22 | 2 | 0.1188
|  | 14 | 0.22 |  | 3.08
| columns | 0.6 | 0.22 | 2 | 0.264
|  | 0.622 | 0.22 |  | 0.13684
|  | 0.6 | 0.22 | 2 | 0.264
|  | 0.99 | 0.22 | 2 | 0.4356
|  | 0.67 | 0.22 | 2 | 0.2948
|  | 0.665 | 0.22 | 2 | 0.2926
|  | 0.43 | 0.22 | 2 | 0.1892
|  | 0.825 | 0.22 | 2 | 0.363
|  | 0.65 | 0.22 |  | 0.143
|  | 0.32 | 0.22 |  | 0.0704
|  | 12.44 | 0.22 |  | 2.7368
12.283
7 | Loose Furniture
| tables | 9
| chairs | 18
| lounge seating | 17
| side tables | 18
| bar stools | 0
| sofa seating | 0
8 | SIGNAGES |  |  | 2 | 2
9 | cleaning/ polishing vinyl flooring |  |  |  | 100
10 | cleaning of existing tiles in kitchen, store, behind front counter and office area
| store |  |  |  | 8.8
| kitchen |  |  |  | 6.4
| behind front and back counter |  |  |  | 19.7
| smoking room |  |  |  | 3.8
38.7
11 | new glass shutter | 0.85 | 2.07 |  | 1.7595
12 | Replacement of damaged floor tiles if required | 0.6 | 0.6 | 15 | 5.4
13 | fire rated 6mm ply under front and back counters
| front counter | 7.5 | 0.6 |  | 4.5
|  | 0.9 | 2.8 |  | 2.52 | shutters area
| back counter | 7.5 | 0.7 |  | 5.25
|  | 0.98 | 2.82 |  | 2.7636 | shutter area
15.0336
14 | 12 mm fire rated ply |  |  |  | 9.75
15 | white solid acrylic surface matching with existing | 0.6 | 7.8 |  | 4.68
16 | Low height cane screen |  |  |  | 3.53

## BOQ_GTB T1 B
BOQ of Interior Items for GOOD TIMES BAR, Mumbai T1 B SHA
DATE: 28-07-23
SR.NO. | ITEM | DESCRIPTION | LOCATION | IMAGE REF | DIMENSION | UNIT | QTY. | Colossuem Associates |  | Lok Pratik Construction |  | VART Infracon |  | REMARKS
[8 empty] | Rate | Amount | Rate | Amount | Rate | Amount
1 | Veneer finish (Polish) | 1. Scraping of old veneer surface polish on existing veneer. 2. Doing New polish on surface of existing veneer in approved shade as per instruction from EIC. Include 2 coats of layer polish and 3rd coat of final polish. | Polishing all existing surfaces with veneer finish |  |  | SQMT | 131.1373 | 4000 | 524549.08 | 1500 | 196705.905 | 4950 | 649129.4865
[9 empty] | 0 |  | 0 |  | 0
2 | buffing- solid acrylic surfaces | Buffing entire white solid acrylic surfaces of front counter until uniform semi-gloss appearance is achieved. Including all required material for the activity. | Buffing white solid acrylic surfaces of front counter |  |  | SQMT | 12.2546 | 3500 | 42890.925 | 750 | 9190.9125 | 2200 | 26960.01
[9 empty] | 0 |  | 0 |  | 0
3 | re-painting of wall, ceiling | 1. Scraping of old wall paints / Ceiling paints. 2. Doing New paint on surface of existing walls/ ceiling in approved shade as per instruction from EIC.Include 2 coats of primer and 2rd coat of final paint.. | Entire outlet walls & ceilings |  |  | SQMT | 270.8296 | 550 | 148956.2635 | 280 | 75832.2796 | 440 | 119165.0108
[9 empty] | 0 |  | 0 |  | 0
4 | louvrers shutter to be re polished | polished on existing finish of lower back counter and lower front counter, complete as per instruction from EIC. | Lower back counter and lower front counter |  |  | SQMT | 5.2836 | 3000 | 15850.8 | 1500 | 7925.4 | 4950 | 26153.82
[9 empty] | 0 |  | 0 |  | 0
5 | Increase lux level of existing lightsReplacement of old dull lights with new lights of 9 watt warm white and 4000 lux level each | 1. Removing of existing light fittings & handingover to EIC. 2. Providing & fixing of new approved light fittings on same location as per instruction from EIC. Includes all neceassry electrical wirings & electrical hardware items. | dining area and counter (BOH) |  |  | NOS | 49 | 1900 | 93100 | 1200 | 58800 | 1500 | 73500
[9 empty] | 0 |  | 0 |  | 0
6 | Buffing of existing 220MM high SS skirting | Buffing of existing SS skirting 220 mm Ht. in entier outlet with neceassry cleaning agent. |  |  |  | SQMT | 13.5113 | 3500 | 47289.704 | 500 | 6755.672 | 2200 | 29724.9568
[9 empty] | 0 |  | 0 |  | 0
7 | New Signages | providing and fixing of new signages of height 500mm and length to be in proportion to the height. |  |  | ht=500mm | NOS | 2 |  | 0 | 60000 | 120000 | 35000 | 70000
|  |  |  | Total Basic Price (Excl. GST) |  |  |  |  | 872636.7725 |  | 475210.1691 |  | 994633.2841