## MEASUREMENT SHEET
measurement sheet
GOOD TIMES BAR_T1B
1 | Veneer polish
| left wall from entrance | 0.86 | 2.6 |  | 2.236
|  | 0.92 | 2.6 |  | 2.392
|  | 7.425 | 2.6 |  | 19.305
| column | 0.6 | 2.6 | 2 | 3.12
|  | 0.622 | 2.6 |  | 1.6172
|  | 0.6 | 2.6 | 2 | 3.12
|  | 0.99 | 2.6 | 2 | 5.148
|  | 0.67 | 2.6 | 2 | 3.484
|  | 0.665 | 2.6 | 2 | 3.458
|  | 0.43 | 2.6 | 2 | 2.236
|  | 0.825 | 2.6 | 2 | 4.29
|  | 0.65 | 2.6 |  | 1.69
|  | 0.32 | 2.6 |  | 0.832
| entry portal towards ramp | 0.43 | 2.6 |  | 1.118
|  | 0.7 | 2.6 |  | 1.82
|  | 0.85 | 2.6 | 2 | 4.42
|  | 0.23 | 2.6 |  | 0.598
|  | 1.62 | 0.85 |  | 1.377
| windows | 0.09 | 1.7 | 2 | 0.306
|  | 3.35 | 0.54 | 2 | 3.618
|  | 0.54 | 1.7 | 2 | 1.836
|  | 3.4 | 0.45 | 2 | 3.06
|  | 0.08 | 1.7 | 2 | 0.272
|  | 0.4 | 1.7 | 2 | 1.36
| back counter | 1.1 | 1.5 |  | 1.65
| top of counter | 7.5 | 0.3 |  | 2.25
|  | 7.5 | 1.05 |  | 7.875
| door | 0.9 | 2.1 | 2 | 3.78
| entry of kitchen | 2.65 | 2.6 |  | 6.89
| entry to back kitchen | 2.2 | 2.6 |  | 5.72
|  | 0.9 | 0.9 |  | 0.81
| entrance portal of oulet | 0.44 | 2.07 |  | 0.9108
|  | 0.69 | 2.07 |  | 1.4283
|  | 0.88 | 2.83 |  | 2.4904
|  | 0.7 | 2.07 | 2 | 2.898
|  | 1.7 | 0.7 |  | 1.19
|  | 0.7 | 2.6 | 2 | 3.64
|  | 1.7 | 0.7 |  | 1.19
| liquour storage door | 0.9 | 2.1 | 2 | 3.78
[5 empty] | 119.2157 | 132 | 120
2 | corian buffing
| top of front counter | 7.51 | 0.45 |  | 3.3795
| facade of front counter | 7.51 | 0.975 |  | 7.3222
| side | 0.975 | 0.45 |  | 0.43875
11.1405
3 | painting
| ceiling | 6.5 | 14.11 |  | 91.715
|  | 3.28 | 1.75 |  | 5.74
|  | 0.92 | 3.25 |  | 2.99
|  | 1.75 | 13.52 |  | 23.66
|  | 1.97 | 4.15 |  | 8.1755
wall
| kitchen | 1.75 | 2.82 | 2 | 9.87
|  | 3.605 | 2.82 | 2 | 20.3322
| liquor store | 6.53 | 2.82 | 2 | 36.8292
|  | 1.75 | 2.82 | 2 | 9.87
| dining | 5.6 | 2.6 |  | 14.56
|  | 0.9 | 3 |  | 2.7
|  | 1.03 | 3.31 |  | 3.4093
|  | 1.03 | 4.45 |  | 4.5835
|  | 1.91 | 2.6 |  | 4.966
|  | 0.45 | 2.6 | 2 | 2.34
|  | 0.68 | 2.6 |  | 1.768
| top of back counter | 0.3 | 1.1 | 4 | 1.32
|  | 0.23 | 6 |  | 1.38
246.2087
4 | louvers shutter repolished
| back counter | 0.98 | 2.82 |  | 2.7636 |  | 5 SHUTTERS
| front counter | 0.9 | 2.8 |  | 2.52 |  | 6 SHUTTERS
5.2836
5 | Increase luv level of lights
| spot light |  |  |  | 45
| hanging lights |  |  |  | 4
49
6 | polish existing ss finish
|  | 5.6 | 0.22 |  | 1.232
|  | 10.8 | 0.22 |  | 2.376
|  | 0.65 | 0.22 | 2 | 0.286
|  | 0.27 | 0.22 | 2 | 0.1188
|  | 14 | 0.22 |  | 3.08
| columns | 0.6 | 0.22 | 2 | 0.264
|  | 0.622 | 0.22 |  | 0.13684
|  | 0.6 | 0.22 | 2 | 0.264
|  | 0.99 | 0.22 | 2 | 0.4356
|  | 0.67 | 0.22 | 2 | 0.2948
|  | 0.665 | 0.22 | 2 | 0.2926
|  | 0.43 | 0.22 | 2 | 0.1892
|  | 0.825 | 0.22 | 2 | 0.363
|  | 0.65 | 0.22 |  | 0.143
|  | 0.32 | 0.22 |  | 0.0704
|  | 12.44 | 0.22 |  | 2.7368
12.283
7 | Loose Furniture
| tables | 10
| chairs | 20
| lounge seating | 20
| side tables | 20
| bar stools | 0
| sofa seating | 0
8 | SIGNAGES |  |  | 2 | 2
9 | cleaning/ polishing vinyl flooring |  |  |  | 100
10 | cleaning of existing tiles in kitchen, store, behind front counter and office area
| store |  |  |  | 8.8
| kitchen |  |  |  | 6.4
| behind front and back counter |  |  |  | 19.7
| smoking room |  |  |  | 3.8
38.7
11 | new glass shutter | 0.85 | 2.07 |  | 1.7595
12 | Replacement of damaged floor tiles if required | 0.6 | 0.6 | 15 | 5.4
13 | fire rated 6mm ply under front and back counters
| front counter | 7.5 | 0.6 |  | 4.5
|  | 0.9 | 2.8 |  | 2.52 | shutters area
| back counter | 7.5 | 0.7 |  | 5.25
|  | 0.98 | 2.82 |  | 2.7636 | shutter area
15.0336
14 | 12 mm fire rated ply |  |  |  | 9.75
15 | white solid acrylic surface matching with existing | 0.6 | 7.8 |  | 4.68
16 | Low height cane screen |  |  |  | 3.58

## BOQ_GTB T1 B
BOQ of Interior Items for GOOD TIMES BAR, Mumbai T1 B SHA
SR.NO. | ITEM | DESCRIPTION | LOCATION | IMAGE REF | DIMENSION | UNIT | QTY. | Lok Pratik Const.
[8 empty] | Rate | Amount
8 | new Loose furniture
8A | dining tables | Providing, Making & placing tables at seating area. as per approved DWGS. Includes all fittings accessories. instruction as per EIC. |  |  | 650x650(mm) | NOS | 10 |  | 0
8B | chairs | Providing, Making & placing chairs at seating area. as per approved DWGS. Includes all fittings accessories. instruction as per EIC. |  |  | ht=450mm | NOS | 20 |  | 0
8C | Lounge seating | Providing, Making & placing chairs at seating area. as per approved DWGS. Includes all fittings accessories. instruction as per EIC. |  |  | ht=450mm | NOS | 20 |  | 0
8D | side tables | Providing, Making & placing side tables at seating area. Plywood framework finish with grey william from all visible sides |  |  | LXB = 700X400X | NOS | 20 |  | 0
8E | bar stools | Providing, Making & placing side tables at seating area. as per approved DWGS. Includes all fittings accessories. instruction as per EIC. |  |  |  | NOS | 0 |  | 0
8F | sofa seating | Providing, making and fixing sofa made out of wooden frame work and cladded with 12mm thk approved make branded Commercial Ply (MR Calibrated, IS 303) -- Greenply or Equivalent brand & approved fabric with required wooden frame, Side arms required wodden frame finishing/cleaning/cutting/required fixture & fasteners etc. as per design & drawing & as directed by Project Manager etc. complete. Sofa will have high density memory foam.(Foam used should be approved and to be certified against poisonous and noxious fumes.) Rate includes upholstery of fabrics. |  |  | 10420mm (L) x 700 (W) x 900 HTto1500HT | RMT | 0 |  | 0
0
9 | Cleaning of existing flooring | Deep Cleaning of existing flooring with chemical including rectification of damages. | Dining area/ seating area |  |  | SQMT | 110 | 250 | 27500
0
10 | Cleaning of existing floor tiles/ dados in kitchen, store, behind front counter and smoking room | Deep Cleaning of existing floor tiles/ dados in kitchen, store, behind front counter and smoking room with chemical including rectification of damages. | kitchen, store, smoking room, behind front counter |  |  | SQMT | 38.7 | 150 | 5805
0
11 | New glass shutter | Providing & fixing 12 mm thick extra clear toughne glass door, as per detail dwg & onsite instruction by EIC. Include all necessary hardware & accessories fittings. | Extra clear toughen glass door. |  |  | SQMT | 1.7595 | 6000 | 10557
0
12 | Replacement of damaged floor tiles if required | 1. Removal of old damage floor tile. 2. Providing & Fixing of floor tile matching with the existing floor. | Replacement of existing floor tile |  |  | SQMT | 5.4 | 2200 | 11880
0
13 | 6mm ply fire rated ply | providing and fixing 6 mm fire rated ply on the existing ply under the front and back counters of BOH area | BOH - under front and back counters |  |  | SQMT | 15.0336 | 1500 | 22550.4
0
14 | 12 mm fire rated ply | providing and packing pest open area permanantly with 12 mm fire rated ply under the front and back counters of BOH area | BOH - under front and back counters |  |  | SQMT | 9.75 | 1600 | 15600
0
15 | white solid acrylic surface matching with existing | providing and fixing white solid acrylic surface (corian) on the existing front counter, finish to match with the existing surface.Cut out on it to be done as per the size of induction. | front serving counter |  |  | SQMT | 4.68 | 13500 | 63180
0
16 | Low height cane Screens | P/F of cane screen in 20 x 40mm thk MS frame in brown powder coating as per the design. | partition between lounge and dining seating |  | upto 1200mm height | RMT | 3.58 | 5000 | 17900
|  |  |  | Total Basic Price (Excl. GST) |  |  |  |  | 174972.4