## NT -Abstract
AHM_WOW China_NT Items
Sr No. | Item Name | UOM | Qty | Unit Price | Amount
527724
1 | Material Unloading , Loading & Shifting |  |  |  | 45000
1.1 | All equiment unloading from truck ,shifting & installation | Nos | 1 | 45000 | 45000
2 | Re-work - Due to rain leakage from roof |  |  |  | 57500
2.1 | Ceiling light - 2 nos | Lot | 1 | 57500 | 57500
2.2 | MCB make legrand- 5 nos
2.3 | RCCB 40amp 4 P make legrand - 3 Nos
2.4 | Wall and ceiling paint - 70 SQFT
2.5 | Ceiling gypsum repair - 40 SQFT
2.6 | Switch socket - 3 Nos
2.7 | Dismantling & Removing and replacement inclusive
3 | Sprinkler Work |  |  |  | 68300
3.1 | SITC of sprinkler plumbing line as per layout and site condition. | Nos | 4 | 7500 | 30000
3.2 | SITC of sprinkler rossette plate | Nos | 4 | 1350 | 5400
3.3 | SITC of U.L listed approved corrugated ss 304 | Nos | 4 | 3600 | 14400
3.4 | Re-work_ Shifting of sprinkler line due to HVAC ducting route post completion | Nos | 1 | 18500 | 18500
4 | Mis . |  |  |  | 289324
4.1 | M.S stand supply & fabrication above ceiling for R.O & tank (Sizes 3 fit x3 fitx2 fit) | Nos | 1 | 16500 | 16500
4.2 | WOW Momo counter signage:- Revised signage came according to revised drawing color. Cost inclusive of transportation/ labour/ loading & Unloading, etc. | Nos | 1 | 28500 | 28500
4.3 | Plumbing _Tap for R.O tap & Frier ( 2nos ) | Nos | 3 | 7500 | 22500
4.4 | Water meter | Nos | 1 | 9800 | 9800
4.5 | Gate valve | Nos | 2 | 8250 | 16500
4.6 | Grease trap installation | Nos | 2 | 8500 | 17000
4.7 | Dismentaling and re-fixing of gyser at new location | Job | 1 | 5500 | 5500
4.8 | 50mm drain pump re-work becouse fire supprassion team did damage 4.2 mtr piping with complete fitting | Nos | 1 | 3500 | 3500
4.9 | Frier drain 50mm dia pipe installation | Mtr | 1.5 | 850 | 1275
4.1 | Frier connection pipe | Nos | 2 | 900 | 1800
4.11 | Nahni trap jali (Chilly trap) | Nos | 2 | 1850 | 3700
4.12 | Gas meter MS pipe support | RFT | 5 | 750 | 3750
4.13 | T.V stand_ Supply & Installation of TV structure having 50x50mm MS structure with 19m fire rated ply on top finished with approved shade paint hanging from ceiling. | SFT | 12 | 2475 | 29700
4.14 | Re-work sink inlet piping becz drawing has mentined low hight & sink hight different dismantling tile & reinstallation pipe & tile for three tap | Nos | 1 | 18500 | 18500
4.15 | DB box modification & new shelf installation 0.8x0.75 mtr internally and externally packing behind the main signage board having laminate finish. | Job | 1 | 8500 | 8500
4.16 | Drain pump wooden boxing 0.51x0.32x0.39 mtr + counter cash drawer's modification. | Job | 1 | 5000 | 5000
4.17 | SS skirting 50mm hight 2.2+0.72+0.8 mtr | Mtr | 3.72 | 1200 | 4464
4.18 | SS plate neas sink for partition to avoid water 1.38x0.67 mtr | Mtr | 1 | 5500 | 5500
4.19 | SITC of 10mm thick toughened glass partition including all necessary hardware fitting. | SFT | 33 | 1350 | 44550
4.2 | RO pressure Tank | Nos | 1 | 28785 | 28785
4.21 | Drainage - 75 Dia CPVC - Additional drainage on floor due to lifting station | RMT | 8 | 1750 | 14000
5 | Electric work |  |  |  | 67600
5.1 | Wall electric signage point with wiring work including chisseling of wall for wiring all complete post completion of wall finishing | Point | 12 | 3850 | 46200
5.2 | Above ceiling RO, gyser electric & water metter wiring with 6amp switch and socket including 3 moduler box & 6 module | Nos | 3 | 1850 | 5550
5.3 | On wall, FAS switch socket including wiring & 8 moduler box | Nos | 1 | 3200 | 3200
5.4 | UPS socket 3M utility point incounter | Nos | 1 | 2500 | 2500
5.5 | Flier catcher electric box 3M | Nos | 1 | 950 | 950
5.6 | CCTV monitor | Nos | 1 | 9200 | 9200

## JMR
AHM_WOW China_NT Items
Sr No. | Item Name | UOM | Qty
1 | Material Unloading , Loading & Shifting
1.1 | All equiment unloading from truck ,shifting & installation | Nos | 1
2 | Re-work - Due to rain leakage from roof
2.1 | Ceiling light - 2 nos | Lot | 1
2.2 | MCB make legrand- 5 nos
2.3 | RCCB 40amp 4 P make legrand - 3 Nos
2.4 | Wall and ceiling paint - 70 SQFT
2.5 | Ceiling gypsum repair - 40 SQFT
2.6 | Switch socket - 3 Nos
2.7 | Dismantling & Removing and replacement inclusive
3 | Sprinkler Work
3.1 | SITC of sprinkler plumbing line as per layout and site condition. | Nos | 4
3.2 | SITC of sprinkler rossette plate | Nos | 4
3.3 | SITC of U.L listed approved corrugated ss 304 | Nos | 4
3.4 | Re-work_ Shifting of sprinkler line due to HVAC ducting route post completion | Nos | 1
4 | Mis .
4.1 | M.S stand supply & fabrication above ceiling for R.O & tank (Sizes 3 fit x3 fitx2 fit) | Nos | 1
4.2 | WOW Momo counter signage:- Revised signage came according to revised drawing color. Cost inclusive of transportation/ labour/ loading & Unloading, etc. | Nos | 1
4.3 | Plumbing _Tap for R.O tap & Frier ( 2nos ) | Nos | 3
4.4 | Water meter | Nos | 1
4.5 | Gate valve | Nos | 2
4.6 | Grease trap installation | Nos | 2
4.7 | Dismentaling and re-fixing of gyser at new location | Job | 1
4.8 | 50mm drain pump re-work becouse fire supprassion team did damage 4.2 mtr piping with complete fitting | Nos | 1
4.9 | Frier drain 50mm dia pipe installation | Mtr | 1.5
4.1 | Frier connection pipe | Nos | 2
4.11 | Nahni trap jali (Chilly trap) | Nos | 2
4.12 | Gas meter MS pipe support | RFT | 5
4.13 | T.V stand_ Supply & Installation of TV structure having 50x50mm MS structure with 19m fire rated ply on top finished with approved shade paint hanging from ceiling. | SFT | 12
4.14 | Re-work sink inlet piping becz drawing has mentined low hight & sink hight different dismantling tile & reinstallation pipe & tile for three tap | Nos | 1
4.15 | DB box modification & new shelf installation 0.8x0.75 mtr internally and externally packing behind the main signage board having laminate finish. | Job | 1
4.16 | Drain pump wooden boxing 0.51x0.32x0.39 mtr + counter cash drawer's modification. | Job | 1
4.17 | SS skirting 50mm hight 2.2+0.72+0.8 mtr | Mtr | 3.72
4.18 | SS plate neas sink for partition to avoid water 1.38x0.67 mtr | Mtr | 1
4.19 | SITC of 10mm thick toughened glass partition including all necessary hardware fitting. | SFT | 33
4.2 | RO pressure Tank | Nos | 1
4.21 | Drainage - 75 Dia CPVC - Additional drainage on floor due to lifting station | RMT | 8
5 | Electric work
5.1 | Wall electric signage point with wiring work including chisseling of wall for wiring all complete post completion of wall finishing | Point | 12
5.2 | Above ceiling RO, gyser electric & water metter wiring with 6amp switch and socket including 3 moduler box & 6 module | Nos | 3
5.3 | On wall, FAS switch socket including wiring & 8 moduler box | Nos | 1
5.4 | UPS socket 3M utility point incounter | Nos | 1
5.5 | Flier catcher electric box 3M | Nos | 1
5.6 | CCTV monitor | Nos | 1