## Final Sheet
PR _NT Items_HYD_Chai Point 26 | [13 empty] | Agrreed on 11.12.2024
[7 empty] | FALLOW DEZIENCE TREE LLP | Vendor Name : FALLOW DEZIENCE TREE LLP | TFS Target Prices | Vendor Name : FALLOW DEZIENCE TREE LLP | No regret Price -FDT | Vendor Name : FALLOW DEZIENCE TREE LLP | FDT Remarks | Revised PR Qty |  | No regret Price -FDT | Vendor Name : FALLOW DEZIENCE TREE LLP
Sr No. | Item Code | Category | Item Description | UOM | Qty | Minimum Amount | Unit Price | Amount | Unit Price | Amount | Unit Price | Amount | 22.11.2024 | UOM | Qty | Unit Price | Amount
1 |  | NT Items | NT Items | NOS | 1 |  |  | 678291 |  | 423101.4 |  | 655000 |  | NOS | 1 |  | 655000
1 | 1 | Barricade | LHS binaycal Side wall extension MS Structure +ply+flex | SQFT | 299 | 76245 | 255 | 76245 | 160 | 47840 | 250 | 74750 | Ok | SQFT | 299 | 250 | 74750
2 |  | Barricade | RHS Back wall extension MS Frame +flex+ply | SQFT | 96 | 24480 | 255 | 24480 | 160 | 15360 | 250 | 24000 | Ok | SQFT | 96 | 250 | 24000
3 |  | Barricade | above 8ft exiting barricade flex installation | SQFT | 160 | 12000 | 75 | 12000 | 55 | 8800 | 55 | 8800 | Ok | SQFT | 160 | 55 | 8800
4 |  | Barricade | LHS Wall barriade removal | SQFT | 416 | 27040 | 65 | 27040 | 40 | 16640 | 55 | 22880 | Ok | SQFT | 416 | 55 | 22880
5 | 2 | Civil & Interior | AC Grill installation | RM | 9.68 | 10212.4 | 1055 | 10212.4 | 1055 | 10212.4 | 1055 | 10212.4 | Ok | RM | 9.68 | 1055 | 10212.4
6 | 3 | Civil & Interior | Gurad Rail | RM | 21.7 | 62387.5 | 2875 | 62387.5 | 1500 | 32550 | 2875 | 62387.5 | Ok | RM | 21.7 | 2875 | 62387.5
7 | 4 | Civil & Interior | MS Pillar Cladding ( HDMR ) | SQM | 4.8 | 27768 | 5785 | 27768 | 3500 | 16800 | 5785 | 27768 | Ok | SQM | 4.8 | 5785 | 27768
8 | 5 | Civil & Interior | Fabrication of new ms partition +plywall +towards glass side | SQM | 12.31 | 83523.35 | 6785 | 83523.35 | 3500 | 43085 | 6785 | 83523.35 | It was done as site condition were not allow us to place any scaffolding or support system thus this was discuused with Mr. Sukri / Shabaz on agreement to do like this. | SQM | 12.31 | 6785 | 83523.35
9 | 6 | Civil & Interior | 8mm HDHMR Paneling for AC grill base | RMT | 22.7 | 49372.5 | 2175 | 49372.5 | 1800 | 40860 | 2175 | 49372.5 | As the structure behind the grill was visible and was humpering look and feel of the outlet . So This traetment was given with after concern with site team . | RMT | 22.7 | 2175 | 49372.5
10 | 7 | Civil & Interior | Above counter SS Powder Coated sheet installation | RMT | 7.4 | 16835 | 2275 | 16835 | 1800 | 13320 | 2100 | 15540 | Ok | RMT | 7.4 | 2100 | 15540
11 | 8 | Civil & Interior | DB Wall HDHMR Paneling & UPS Stand | SQFT | 20 | 13500 | 675 | 13500 | 250 | 5000 | 675 | 13500 | Ok | SQFT | 20 | 675 | 13500
12 | 9 | Civil & Interior | Base for ice cube machine ( Ply +Laminate ) | SQM | 0.24 | 2100 | 8750 | 2100 | 4500 | 1080 | 8750 | 2100 | Ok | SQM | 0.24 | 8750 | 2100
13 | 10 | Civil & Interior | Base for IT Cable box (ply +laminate ) | CUM | 0.01 | 87.5 | 8750 | 87.5 | 8750 | 87.5 | 8750 | 87.5 | Ok | CUM | 0.01 | 8750 | 87.5
14 | 11 | Civil & Interior | 12 mm HDHMR cladding in hood gap | SQFT | 9 | 6075 | 675 | 6075 | 250 | 2250 | 675 | 6075 | Ok | SQFT | 9 | 675 | 6075
15 | 12 | Civil & Interior | Stand for RO tank ( MS Frame + ply +paint ) | SQ FT | 2 | 14900 | 7450 | 14900 | 2500 | 5000 | 6500 | 13000 | Ok | SQ FT | 2 | 6500 | 13000
16 | 13 | Civil & Interior | Counter back wall finish in 12mm ply +laminate | SQ FT | 30 | 20250 | 675 | 20250 | 450 | 13500 | 600 | 18000 | It has been done on the basic of MOM with TFS & FDT Team - 04.06.2024- For Reference . Mail Attached . | SQ FT | 30 | 600 | 18000
17 | 14 | Civil & Interior | Re - Fabrication - counter hright increase approved by shadab sir | SQ FT | 1 | 65000 | 65000 | 65000 | 35000 | 35000 | 60000 | 60000 | Ok | SQ FT | 1 | 60000 | 60000
18 | 15 | Civil & Interior | Rubber Louvers - Laminate match with rubber finish in back ground | SQ FT | 130 | 35750 | 275 | 35750 | 275 | 35750 | 275 | 35750 | It has been done on the basic of MOM with TFS & FDT Team - 04.06.2024- For Reference . Mail Attached . | SQ FT | 130 | 275 | 35750
19 | 16 | Civil & Interior | White Quartz Stone counter top | SQ FT | 96.03 | 88827.75 | 925 | 88827.75 | 550 | 52816.5 | 925 | 88827.75 | Ok | SQ FT | 96.03 | 925 | 88827.75
20 | 17 | Plumbing | Sink | Nos | 1 | 9967 | 9967 | 9967 | 7500 | 7500 | 8800 | 8800 | Ok | Nos | 1 | 8800 | 8800
21 | 18 | Plumbing | S.S Grating - for drain ( Supply +Installation ) | Nos | 1 | 7985 | 7985 | 7985 | 6500 | 6500 | 7326 | 7326 | Ok | Nos | 1 | 7326 | 7326
22 | 19 | Plumbing | Supply cockroch jali in floor | Nos | 1 | 678 | 678 | 678 | 500 | 500 | 650 | 650 | Ok | Nos | 1 | 650 | 650
23 | 20 | Plumbing | Supply and installation ange cock | Nos | 11 | 10857 | 987 | 10857 | 450 | 4950 | 900 | 9900 | Ok | Nos | 11 | 900 | 9900
24 | 21 | Electrical | Supply Electrical Meter | Nos | 1 | 8975 | 8975 | 8975 | 6500 | 6500 | 8500 | 8500 | Ok | Nos | 1 | 8500 | 8500
25 | 22 | Electrical | Supply & installation -Rubber matt ISI Mark 1.1 kv | Nos | 1 | 3475 | 3475 | 3475 | 1200 | 1200 | 3250 | 3250 | Ok | Nos | 1 | 3250 | 3250