## MISCELLANEOUS (hidden)
BOQ of Civil work for Copper Chimney Project, Vishal Cinema, Delhi | [6 empty] | 2023-03-24 |  | R1
|  | GROUND FLOOR |  |  |  |  | FT
SR.NO. | ITEM | DESCRIPTION | DRAWING NO | DIMENSION | UNIT | QTY. | RATE | AMOUNT | REMARK
MISCELLANEOUS -2
1 | Story Wall Images | High Resolution Digital printing on HP Canvas STRETCHED on 1 inch wooden frame (stapling on sides)
Back: 3 mm sun board with leather finish vinyl pasted on it.
Size :
|  | Size : 440 x 600mm |  | 440 x 600mm | NOS |  |  | 0
|  | Size : 440 x 340mm |  | 440 x 340mm | NOS |  |  | 0
2 | Chef Photos | Size : 775 x 1050mm |  |  | NOS |  |  | 0
3 | Artifact | P & F of decorative artifact (approx cost - 250000) |  |  | LS |  |  | 0
4 | Natural & Artificial | P & F of planters (approx cost - 200000) |  |  | LS |  |  | 0
TOTAL MISCELLANEOUS - 2 | [7 empty] | 0

## Non Boq 3
Project : Charcoal Concept
Site Name :Copper Chimney Project, Vishal Cinema, Delhi
Work: Interior Finishing and MEP Work
Contractor: Stars and Merit Interiors Private Limited
Work order No : DCPL/Vishal Cinema/CC/23-24/CP-202
RA Bill No : 5
SR.NO. | ITEM | DESCRIPTION | UNIT | As Amendment |  |  | As per Bill Quantity |  |  |  |  | As per Bill Amount |  |  | Remarks
|  |  |  | QTY. | RATE | AMOUNT | Preious Bill | % OF Work | This Bill | Cumulative Bill | % of Works | Preious Bill | This Bill | Cumulative Bill
1 | 4C x 2.5 sqmm Copper Armed cable for main main façade signage | Supply and Laying,Testing and Comissioning of 4C x 2.5 sqmm Copper Armed cable for Main signage | Rmt | 100 | 160 | 16000 | 0 | 0 | 100 | 100 | 100% | 0 | 16000 | 16000
2 | converted into single phase | Three phase 20A, 400 V Industrial Socket & Plug Top Changed With Single Phase Modular Swith Socket | Each | 1 | 1400 | 1400 | 0 | 0 | 1 | 1 | 0% | 0 | 0 | 0 | Shifted to Main BOQ
3 | bar area additional items | Faucets For Dish Wash Area | Each | 1 | 6500 | 6500 | 0 | 0 | 1 | 1 | 100% | 0 | 6500 | 6500
4 | bar area additional items | Equipment Drain work With Mislanious Fittings | LS | 1 | 12350 | 12350 | 0 | 0 | 1 | 1 | 100% | 0 | 12350 | 12350
5 | Additional Switch Socket At Bar Area And Boh Area As per Site Requirement | Bar Area | Each | 5 | 1123 | 5615 | 0 | 0 | 5 | 5 | 0% | 0 | 0 | 0 | Shifted to Main BOQ
6 | Epoxy Paint On Ms Structure In Boh area | Boh area | Sqft | 485.4524 | 80 | 38836.1888 | 0 | 0 | 485.4524 | 485.4524 | 100% | 0 | 38836.1888 | 38836.1888
7 | Repair Of Back Side Duct Opening As per the site requirement and paint of the same with maching of exesting surface | Outside area | Each | 1 | 12600 | 12600 | 0 | 0 | 1 | 1 | 100% | 0 | 12600 | 12600
8 | Weather Proof Box | Outside area | Each | 3 | 2500 | 7500 | 0 | 0 | 3 | 3 | 100% | 0 | 7500 | 7500
9 | 1 Live Kitchen Glass Damaged Due to tandoor entry | Live Ktchen Area | Each | 1 | 5456 | 5456 | 0 | 0 | 1 | 1 | 100% | 0 | 5456 | 5456
10 | Fresh air Grill Required at live kitchen area | Live Ktchen Area | Each | 1 | 6756 | 6756 | 0 | 0 | 1 | 1 | 0% | 0 | 0 | 0 | Shifted to Main BOQ
11 | Difference in Basic prices for Sofa Uphostry | Customer Area. | Sqft | 266.945 | 150 | 40041.7468 | 0 | 0 | 266.945 | 266.945 | 100% | 0 | 40041.7468 | 40041.7468
12 | Extra Ducting Work | Kitchen and Customer area | Sqft | 19.8 | 1585 | 31383 | 0 | 0 | 19.8 | 19.8 | 100% | 0 | 31383 | 31383
13 | Gas Liasoning Work. |  | Each | 1 | 80000 | 80000 | 0 | 0 | 1 | 1 | 100% | 0 | 80000 | 80000
| Total:- | [11 empty] | 250666.9355 | 250666.9355

## Non Boq Mb 3
Measurement Book of Interior Work Copper Chimney Rajouri Garden
S.No. | Items | Descriptions | Unit | Measurement (mm) |  |  | Measurement (Feet)
|  |  |  | L | B | H | L | B | H | NO | TOTAL
1 | 4C x 2.5 sqmm Copper Armed cable for main main façade signage | Supply and Laying,Testing and Comissioning of 4C x 2.5 sqmm Copper Armed cable for Main signage | Rmt | 100 | [5 empty] | 1 | 100
2 | converted into single phase | Three phase 20A, 400 V Industrial Socket & Plug Top Changed With Single Phase Modular Swith Socket | Each | [6 empty] | 1 | 1
3 | bar area additional items | Faucets For Dish Wash Area | Each | [6 empty] | 1 | 1
4 | bar area additional items | Equipment Drain work With Mislanious Fittings | LS | [6 empty] | 1 | 1
5 | Additional SS Tables for Bar area | Bar Area | Each | [6 empty] | 2 | 2
6 | Additional Switch Socket At Bar Area And Boh Area As per Site Requirement | Bar Area | Each | [6 empty] | 5 | 5
7 | Epoxy Paint On Ms Structure In Boh area | Boh area | Sqft | 5000 | 4510 |  | 16.4042 | 14.7966 |  | 2 | 485.4524
8 | Repair Of Back Side Duct Opening As per the site requirement and paint of the same with maching of exesting surface | Outside area | Each | [6 empty] | 1 | 1
9 | Weather Proof Box |  | Each | [6 empty] | 3 | 3
10 | 1 Live Kitchen Glass Damaged Due to tandoor entry |  | Each | [6 empty] | 1 | 1
11 | Fresh air Grill Required at live kitchen area |  | Each | [6 empty] | 1 | 1
12 | Difference in Basic prices for Sofa Uphostry | Boh area | Sqft | 24800 | 1000 |  | 81.3648 | 3.2808 |  | 1 | 266.945
13 | Extra Ducting Work | Boh Area | Sqmt | 19.8 | 0 |  |  | 0 |  | 1 | 19.8
14 | Gas Liasoning Work. |  | Each | [6 empty] | 1 | 1