## MISCELLANEOUS (hidden)
BOQ of Civil work for Copper Chimney Project, Vishal Cinema, Delhi | [6 empty] | 2023-03-24 |  | R1
|  | GROUND FLOOR |  |  |  |  | FT
SR.NO. | ITEM | DESCRIPTION | DRAWING NO | DIMENSION | UNIT | QTY. | RATE | AMOUNT | REMARK
MISCELLANEOUS -2
1 | Story Wall Images | High Resolution Digital printing on HP Canvas STRETCHED on 1 inch wooden frame (stapling on sides)
Back: 3 mm sun board with leather finish vinyl pasted on it.
Size :
|  | Size : 440 x 600mm |  | 440 x 600mm | NOS |  |  | 0
|  | Size : 440 x 340mm |  | 440 x 340mm | NOS |  |  | 0
2 | Chef Photos | Size : 775 x 1050mm |  |  | NOS |  |  | 0
3 | Artifact | P & F of decorative artifact (approx cost - 250000) |  |  | LS |  |  | 0
4 | Natural & Artificial | P & F of planters (approx cost - 200000) |  |  | LS |  |  | 0
TOTAL MISCELLANEOUS - 2 | [7 empty] | 0

## Live Kitchen Ducting Work
Project : Charcoal Concept
Site Name :Copper Chimney Project, Vishal Cinema, Delhi
Work: Interior Finishing and MEP Work
Contractor: Stars and Merit Interiors Private Limited
Work order No :
Addition Work of Live kichen Ducting Work
SR.NO. | ITEM | DESCRIPTION | UNIT | [8 empty] | As per Bill Amount |  | Remarks
|  |  |  | QTY. | RATE | AMOUNT |  | % OF Work | This Bill | Cumulative Bill | % of Works | Preious Bill | This Bill
1 | Removal of Hood to work on exhust dust. | Live kitchen Area | Each | 1 | 4800 | 4800 | 0 | 0 | #REF! | #REF! | 100% | 0 | #REF! | Qty1
2 | Removal Of Complete Fresh air and exhaust duct From Live Kitchen area for addition of new ducts | Live kitchen Area | SQFT | 120 | 30 | 3600 | [7 empty] | Qty Given
3 | Reinstallational of Hood In Live Kitchen area after completion of Ducting Work. | Live kitchen Area | Each | 1 | 6500 | 6500 | [7 empty] | Qty 1
4 | Supply, Fabrication, Installation and Testing of sheet metal rectangular ducts complete with vanes, splitter damper hanging arrangement including check nuts in accordance with the approved shop drawings and specifications | Live kitchen Area |  | 0
4.a | 1.0mm (20 gauge) GSS | Live kitchen Area | Sqmtr | 0 | 1685 | 0 | [7 empty] | BOQ Rates
|  |  | Sqmtr | 0 | 1685 | 0 | [7 empty] | BOQ Rates
5 | Removal And Reinstallation of Entire Grid Cealing in live kitchen area inclduing Required frame work and tiels materials. | Live kitchen Area | SQFT | 0 | 172 | 0 | [7 empty] | BOQ Rates
6 | Making punctures in existing brick/siphorex/concrete wall block for passing A.C. copper pipes/drain pipes as required and making good the same with cement plaster/POP. | Live kitchen Area | Each | 0 | 3122 | 0 | [7 empty] | BOQ Rates
7 | Tiles repair work which was damaged while working | Live kitchen Area | SQFT | 0 | 105 | 0 | [7 empty] | BOQ Rates
| Total:- |  |  |  |  | 14900 | [6 empty] | #REF!
|  | Gst @ 18% |  |  |  | 2682
| Grand Total:- |  |  |  |  | 17582

## MB
Project : Charcoal Concept
Site Name :Copper Chimney Project, Vishal Cinema, Delhi
Work: Interior Finishing and MEP Work
Contractor: Stars and Merit Interiors Private Limited
Work order No :
MB Sheet
SR.NO. | ITEM | DESCRIPTION | UNIT | [6 empty] | As per Bill Amount |  | Remarks
|  |  |  | QTY. |  | % OF Work | This Bill | Cumulative Bill | % of Works | Preious Bill | This Bill
1 | Removal of Hood to work on exhust dust. | Live kitchen Area | Each | 1 | 0 | 0 | #REF! | #REF! | 100% | #REF! | #REF!
2 | Removal Of Complete Fresh air and exhaust duct From Live Kitchen area for addition of new ducts | Live kitchen Area | SQFT | 120
3 | Reinstallational of Hood In Live Kitchen area after completion of Ducting Work. | Live kitchen Area | Each | 1
4 | Supply, Fabrication, Installation and Testing of sheet metal rectangular ducts complete with vanes, splitter damper hanging arrangement including check nuts in accordance with the approved shop drawings and specifications | Live kitchen Area
4.a | 1.0mm (20 gauge) GSS | Live kitchen Area | Sqmtr | [8 empty] | 6.08 Shifted to Main BOQ
|  |  | Sqmtr | [8 empty] | 2*(0.6+0.2)*5.2, 8.32 Shifted to Main BOQ
5 | Removal And Reinstallation of Entire Grid Cealing in live kitchen area inclduing Required frame work and tiels materials. | Live kitchen Area | SQFT | [8 empty] | 213 Shifted to Main BOQ
6 | Making punctures in existing brick/siphorex/concrete wall block for passing A.C. copper pipes/drain pipes as required and making good the same with cement plaster/POP. | Live kitchen Area | Each | 0 | [7 empty] | Shifted to Main BOQ 01 no
7 | Tiles repair work which was damaged while working | Live kitchen Area | SQFT | 0 | [7 empty] | 31 Sqft Shifted to Main BOQ
| Total:- | [9 empty] | #REF!
Gst @ 18%
Grand Total:-