## SUMMARY
Project : Charcoal Concept
Site Name :Copper Chimney Project, Vishal Cinema, Delhi
Work:Civil ,Interior Finishing,Façade and MEP Works
Contractor: Stars and Merit Interiors Private Limited
Work order No : DCPL/Vishal Cinema/CC/23-24/CP-202
Bill NO. : RA-4 Bill
Sr. No. | Item Description | Work Order Amount | Previous Bill Amount | This Bill Amount | Cumulative Bill Amount | Remarks
1 | Civil Works | 1901229 | 1600565 | 634130.6683 | 2234695.6683
2 | Interior works | 2253467 | 1663830.5 | 341339.9334 | 2005170.4334
3 | Electrical Works | 1676413 | 1493608.9 | 333758.8 | 1827367.7
4 | Plumbing Works | 311371 | 243982.9 | 53278.7 | 297261.6
5 | HVAC( Upper side + Lower side) works | 1951350 | 1644442 | 586463.4 | 2230905.4
6 | Fire Fighting System | 207250 | 87883.95 | 64340.25 | 152224.2
7 | Façade | 306742 | 0 | 171974.5275 | 171974.5275
8 | Façade Sigange | 206130 | 0 | 206130 | 206130
9 | Bells | 201350 | 140945 | 60405 | 201350
10 | Miscellaneous (Non BOQ item) | 0 | 0 | 1285855.0257 | 1285855.0257
11 | Miscellaneous (Non BOQ item -2 |  |  | 172475 | 172475
| Subtotal amount INR. (without taxes) | 9015302 | 6875258.25 | 3737676.3049 | 10785409.5549
| GST @ 18 % | 1622754.36 | 1237546.485 | 672781.7349 | 1941373.7199
| Total Woth GST | 10638056.36 | 8112804.735 | 4410458.0398 | 12726783.2748

## CIVIL WORK
Project : Charcoal Concept
Site Name :Copper Chimney Project, Vishal Cinema, Delhi
Work: Civil Works
Contractor: Stars and Merit Interiors Private Limited
Work order No : DCPL/Vishal Cinema/CC/23-24/CP-202
Bill NO. :RA-4 Bill
SR.NO. | ITEM | DESCRIPTION |  |  | UNIT | As Per Work order |  |  | As per Bill Quantity |  |  |  |  | As per Bill Amount |  |  | Remarks
|  |  | DRAWING NO | DIMENSION |  | QTY. | RATE | AMOUNT | Preious Bill | % OF Work | This Bill | Cumulative Bill | % of Works | Preious Bill | This Bill | Cumulative Bill
GENERAL SITE WORKS
1 | Pest control at site | Providing Pest Control & Anti-termite treatment by appointing a specialized agency as per the specifications mentioned by the Bureau of Indian Standard & Agencies specification ( Whichever is higher ) for General Civil , Plumbing / Drainage & timber / Carpentry works , Gypsum related work including 5 Years guarantee under suitable undertaking on stamp paper etc complete as directed . ( Mode of Measurement to be on carpet area of floor & not the area of surface treated.) | N.A | N.A | SFT | 1950 | 12 | 23400 | 1950 | 100% | 163.7935 | 2113.7935 | 100% | 23400 | 1965.5217 | 25365.5217
2 | Site Barricading | Providing and fixing flex board out. Cost to include framework cost, opening for door, flex printing and installation. ( digital file provided by client ) Sizes as mentioned below | N.A | N.A | SFT | 360 | 142 | 51120 | 360 | 100% | 87.7787 | 447.7787 | 100% | 51120 | 12464.5716 | 63584.5716
[9 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
DEMOLITION WORKS | [8 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
3 | Core Cut | Core cuts in mother slab for drain pipes 200mm dia as per required and making good the same with cement plaster and waterproofing before slab waterproofing and kobah. | N.A | N.A | NO's | 3 | 2433 | 7299 | 3 | 100% | 2 | 5 | 100% | 7299 | 4866 | 12165
4 | Debris | Removing Debris out of site included loading, unloading & shifting as per statutory rules and regulations. | N.A | N.A | NO's | 5 | 5540 | 27700 | 5 | 100% | 4 | 9 | 100% | 27700 | 22160 | 49860
5 | Wall Puncture | Making punctures in existing brick/siphorex/concrete wall block for passing A.C. copper pipes/drain pipes as required and making good the same with cement plaster/POP. | N.A | N.A | NO's |  | 3122 | 0 | 0 | 0% | 5 | 5 | 100% | 0 | 15610 | 15610
[9 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
INTERIOR CIVIL WORK | [8 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
1 | Waterproofing | P&A Waterproofing on mother slabs & wall till 600mm height, with 4 coats of chemical (Zypex or Equivalent chemical to be used) treatment on the mother slab, before doing the treatment mother slab needs to clean properly up to the mark & dust free surface needs to achieve to apply the chemical (proof bond /BASF, Dr. Fixit / Equivalent make) & chemical needs to dry properly, After all there should be a water pond testing to be done for water tightness & rectifications of defects if any. Complete with 10 years performance guarantee with client's satisfaction. Entire process to be done under guideline & supervision of appointed engineering team. |  | N.A | SFT |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0
a |  | Kitchen -floor |  | N.A | SFT | 410 | 90 | 36900 | 410 | 100% | 18.1152 | 428.1152 | 100% | 36900 | 1630.3694 | 38530.3694
b |  | Kitchen -wall up to 600mm |  | N.A | SFT | 170 | 90 | 15300 | 170 | 100% | 68.539 | 238.539 | 100% | 15300 | 6168.5117 | 21468.5117
c |  | Show kitchen -floor |  | N.A | SFT | 100 | 90 | 9000 | 100 | 100% | -9.5832 | 90.4168 | 100% | 9000 | -862.4837 | 8137.5163
d |  | Show kitchen -wall up to 600mm |  | N.A | SFT | 65 | 90 | 5850 | 65 | 100% | 9.4001 | 74.4001 | 100% | 5850 | 846.0134 | 6696.0134
|  | Bar area |  |  |  |  | 90 | 0 | 0 | 0% | 124.3877 | 124.3877 | 100% | 0 | 11194.8974 | 11194.8974
[9 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
2 | Block Work | Providing and constructing Light weight blocks masonry in cement mortar 1:4 of approved make like Aerocon/Siporex etc. Job to include raking out joints, scaffolding, making openings walls, curing etc. in substructure and superstructure to its true line & level in cement mortar proportion as specified in all shapes, size, at all heights, depths, leads & locations etc. complete. The rate shall also include for cleaning of surface, hacking of RCC surface in contact with brickwork, racking of joints, providing, erecting, & dismantling steel scaffolding , curing for 10 days, including 75 mm thk. R.C.C. stiffener at approximately every 1000 mm ht. with required M.S. reinforcement bars and Lintels for Doors and wall openings etc. compete as per the drgs., details & specifications. | [6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
|  | Using 150mm thk Walls upto 3100mm |  | N.A | SFT | 280 | 145 | 40600 | 280 | 100% | 247.0466 | 527.0466 | 100% | 40600 | 35821.7549 | 76421.7549
[9 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
3 | Block Work | Specifications same as above (point no. 3). Wall height upto 1100mm | [6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
|  | Using 150mm thk |  | N.A | SFT | 45 | 141 | 6345 | 45 | 100% | 138.5677 | 183.5677 | 100% | 6345 | 19538.0497 | 25883.0497
[9 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
[9 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
4 | Internal Plaster | P&A of single coat backing plaster of 15-18 mm thick in CM 1:4 proportion to the walls & others surface including scaffolding, curing the joints, etc. The rates are inclusive of providing chicken mesh of 18mm gauge & 150mm width at junction of brick & RCC etc. at the walls, columns, beams etc., seven days water treatment as anti crack of plaster. Complete as per site engineer's instruction. | N.A | N.A | SFT | 115 | 43 | 4945 | 115 | 100% | 847.1478 | 962.1478 | 100% | 4945 | 36427.3575 | 41372.3575
[9 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
5 | PCC Work | Providing and laying up to 50-75 mm thick cement concrete flooring with 1:2:4 cement concrete laid to proper level and slope in alternate bays including compactions, filling joints, or as directed, finishing smooth with cement Mortar 1:1 of sufficient minimum thickness to give a smooth & even surface and curing etc. complete as per architects instructions. | N.A | N.A | SFT |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0
|  | kitchen floor(300mm) |  |  | SFT | 410 | 92 | 37720 | 410 | 100% | 18.1152 | 428.1152 | 100% | 37720 | 1666.5998 | 39386.5998
|  | live kitchen floor (300mm) |  |  | SFT | 100 | 92 | 9200 | 100 | 100% | 1301.9923 | 1401.9923 | 100% | 9200 | 119783.2948 | 128983.2948
|  | Bar area |  |  | SFT |  | 92 | 0 | 0 | 0% | 9.4722 | 9.4722 | 100% | 0 | 871.4462 | 871.4462
[9 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
6 | COBA Work | CINDER BLOCK COBA of Avg. thickness mentioned below; After laying of soil pipes, floor traps is completed the floor of the sunken portion shall be covered with cinder coba embedded manually with 15-20 mm wide joints in 20 mm thk. Waterproofing mortar 1:4 ( 1 cement : 4 coarse sand )in layers upto the full ht. of sunken portion, having top layer of 50 mm thk waterproof mortar 1:4 ( 1 cement : 4 coarse sand ) using specialized W.P. chemical, finished smooth / rough with floating coat of neat cement all complete and as per specification. | [6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
|  | Kitchen (300mm) | N.A | N.A | SFT | 85 | 263 | 22355 | 85 | 100% | 343.1152 | 428.1152 | 100% | 22355 | 90239.3017 | 112594.3017
|  | show kitchen (300mm) | N.A | N.A | SFT | 25 | 263 | 6575 | 25 | 100% | 103.1121 | 128.1121 | 100% | 6575 | 27118.4722 | 33693.4722
[9 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
7 | MS STRUCTURE | Providing and fixing M.S frame structure/ rack made out of 50mm X 50mm hollow pipe sections on walls finishing/supporting/cutting/required fixture & fasteners etc. as per design, drawing & as directed by Project Manager etc. complete. | KITCHEN LOFT |  | SFT | 400 | 197 | 78800 | 400 | 0% | -400 | 0 | 0% | 0 | 0 | 0
8 | Bison board/ PLY | Providing, making and fixing of wall panelling made of 12mm thk branded bison board/ PLY paneling on wall including ALU framework finish with all necessary required framing, approved make adhesive and fasteners, cutting/ chamfering/ groove/rounding wherever required, at all height with lead and lift, finishing, cleaning as per design and drawing etc. all complete. |  |  | SFT | 1500 | 285 | 427500 | 1500 | 95% | -7.8583 | 1492.1417 | 100% | 406125 | 19135.3844 | 425260.3844 | New area to be add
[9 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
[9 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
STONE & TILE WORKS | [8 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
1 | KOTA Flooring | Providing and Laying KOTA stone of 19mm thk. on avg 40 mm thk bed of 1:4 cement mortar in proper line and level including neat cement float, filling joints with neat cement slurry of appropriate colour, cleaning, curing, rubbing, complete. Scope includes laying of floor protective cover on the floor and removing of the same when directed along with supply of all necessary materials, labour, tools and tackles complete in line with the Technical Specification, Drawings and as per the direction of the Architect & PMC. Including Polishing. | [6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
|  | Size : 550x550 Basic Rate : 55 Per SFT | [6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
|  | Kitchen |  | N.A | SFT | 410 | 135 | 55350 | 410 | 95% | 5.543 | 415.543 | 100% | 52582.5 | 3515.8007 | 56098.3007
|  | live Kitchen |  | N.A | sft | 100 | 135 | 13500 | 100 | 95% | 189.3339 | 289.3339 | 100% | 12825 | 26235.0781 | 39060.0781
[9 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
2 | Wooden finish herringbone pattern Tile Flooring | Fixing & laying of tiles for flooring which includes --bedding of appropriate thickness with mortar of 1:6 ratio (1cement:6sand), spreading of grey cement slurry with minimum of 2kg/ Sq.mt. ratio over bedding mortar, including 3mm spacer with epoxy grout of approved colour, adhesive of bal Endura or approved equivalent, making of hole where ever required, in proper line and level in all direction, at all height with lead and lift, polishing/finishing/cleaning etc. as per design and drawing and directed by PMC etc. complete. |  | N.A | SFT | 1080 | 287 | 309960 | 1080 | 95% | 93.0456 | 1173.0456 | 100% | 294462 | 42202.0801 | 336664.0801
|  | size - 200x1200. Basic Rate : 150 Per SFT | [6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
|  | Restaurant area | [6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
[9 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
3 | Pattern Tile Flooring | Fixing & laying of tiles for flooring which includes --bedding of appropriate thickness with mortar of 1:6 ratio (1cement:6sand), spreading of grey cement slurry with minimum of 2kg/ Sq.mt. ratio over bedding mortar, including 3mm spacer with epoxy grout of approved colour, adhesive of bal Endura or approved equivalent, making of hole where ever required, in proper line and level in all direction, at all height with lead and lift, polishing/finishing/cleaning etc. as per design and drawing and directed by PMC etc. complete. |  | N.A | SFT | 230 | 326 | 74980 | 230 | 95% | -27.3532 | 202.6468 | 100% | 71231 | -5168.1564 | 66062.8436
|  | size - 300x300. Basic Rate : 220 Per SFT | [6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
|  | size - 300x300. Basic Rate : 220 Per SFT | [6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
[9 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
4 | Wooden finish Tile skiting | Fixing & laying of 100mm high tiles for skirting with bedding of appropriate approved make adhesive & colour joint filler inclusive of making all groove/chamfering/rounding/hole where ever required, in proper line and level in all direction, polishing/finishing/cleaning etc. Complete as per detail drawing, specification and as directed by PMC. |  | N.A | RFT | 65 | 142 | 9230 | 65 | 95% | 46.9127 | 111.9127 | 100% | 8768.5 | 7123.1076 | 15891.6076
|  | size - 200x1200. Basic Rate : 120 Per SFT | [6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
[9 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
[9 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
[9 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
[9 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
5 | Granite Threshold | P&F of Black leather finish Granite threshold at the edges of the mall and outlet flooring as per design drawing |  | door |  |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0
|  | 6" thk granite threshold | MAIN ENTRY & KITCHEN DOOR | 2400x2400x1500 | RFT | 2 | 375 | 750 | 2 | 0% | 55.231 | 57.231 | 100% | 0 | 21461.6142 | 21461.6142
|  | Basic Rate of marble : 230 per SFT | LIVE KITCHEN | 2400x2400x900 | RFT | 1 | 634 | 634 | 1 | 0% | -1 | 0 | 0% | 0 | 0 | 0
[9 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
[9 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
6 | Window sill & jamb in Marble | Providing and constructing Marble sill & jamb for window as per drawings. Inclusive of making all groove/chamfering/rounding/hole where ever required, in proper line and level in all direction, polishing/finishing etc. Complete as per detail drawing, specification and as directed by PMC. | [6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
|  | Basic Rate of marble : 650 per SFT | [6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
|  | upto 6"-8" thk marble | [6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
|  | Tandoor section upto 1100 |  | 19mm thk | RFT | 100 | 983 | 98300 | 100 | 60% | -53.6089 | 46.3911 | 100% | 58980 | -13377.5722 | 45602.4278
[9 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
7 | Decorative Wall Tiles | Providing and fixing Glazed Decorative wall tiles which includes-approved make of adhesive like bal Endura or equivalent, grey cement paste with backing coat of 1:3 cement mortar not less than 12mm thick as & where ever required, joint filler of approved make and colour, as and where ever required, in proper line and level in all direction, at all height with lead and lift, polishing/finishing/cleaning etc as per design, drawing and directed by PMC etc. all complete. | [6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
|  | Size : 75x300 Rate : 275per SFT | [6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
|  | Show kitchen Wall tiles upto 3100mm ht |  |  | SFT | 260 | 410 | 106600 | 260 | 95% | -55.5503 | 204.4497 | 100% | 101270 | -17445.6171 | 83824.3829
[9 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
8 | Sada Wall Tiles for kitchen | Providing and fixing Ceramic wall tiles which includes-approved make of adhesive like bal Endura or equivalent, grey cement paste with backing coat of 1:3 cement mortar not less than 12mm thick as & where ever required, joint filler of approved make and colour, as and where ever required, in proper line and level in all direction, at all height with lead and lift, polishing/finishing/cleaning etc as per design, drawing and directed by PMC etc. all complete. (Color - white/ ivory) | [6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
|  | Size : 300x600. Rate : 45per SFT | [6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
|  | Main kitchen and under counter wall tiles upto 3100mm ht |  |  | SFT | 860 | 107 | 92020 | 860 | 90% | -126.0318 | 733.9682 | 100% | 82818 | -4283.3992 | 78534.6008
[9 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
9 | SS Corner Guard | P&F of 304 grade 3mm thick SS Corner guard (30mm x 30mm, mat finished as per approved sample) fixing with conceal tile on each corner of the kitchen's wall before cladding of tiles, so that the corner may be protected from the damages. Complete in proper line & level and site engineer's instruction. |  | 30x30x2100 | RFT | 3 | 232 | 696 | 3 | 0% | 45.622 | 48.622 | 100% | 0 | 11280.315 | 11280.315
10 | Brass Corner Guard | P&F of 304 grade 3mm thick Brass Corner guard (30mm x 30mm, mat finished as per approved sample) fixing with conceal tile on each corner of the kitchen's wall before cladding of tiles, so that the corner may be protected from the damages. Complete in proper line & level and site engineer's instruction. |  |  | RFT |  | 345 |  | 0 | 0% | 0 |  | 0% | 0 | 0 | 0
[9 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
POP & PAINTING WORK | [8 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
[9 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
1 | POP Punning | Providing and applying Plaster of Paris punning of average thickness 20-25mm to existing wall surfaces/ on existing tiles including chicken mesh in true level and plumb complete as per design and drawing Cleaning the surface properly with sand paper, filling cracks/holes with plaster of Paris. Applying lambi / putty (lambi/putty will be of good quality) sand papering the putty work on chamfers, etc.at any / all heights. Rate include cost for making grooves up to 12mm thick if required in horizontal or vertical direction near doors, windows, skirting, floor covering, masking tape and cleaning the area all complete as per drawing, design & manufactures specification. |  | N.A | SFT |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0
| a | block work walls |  | N.A | SFT | 1340 | 38 | 50920 | 1340 | 95% | -766.1248 | 573.8752 | 100% | 48374 | -26566.7427 | 21807.2573
| b | Exposed ceiling |  | N.A | SFT | 1380 | 38 | 52440 | 1380 | 95% | -38.7 | 1341.3 | 100% | 49818 | 1151.401 | 50969.401
[9 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
2 | Gypsum Ceiling | Providing, making and fixing of POP false ceiling as per manufacturer design and drawing including cut-outs for hvac grille, lights etc.at any / all heights. Rate quoted should be including of vertical drop of any heights, mouldings and size mentioned in drawings with necessary required framing in 450x 900 ultra Gyproc sections, fittings, and fixtures, scaffolding, floor covering, masking tape and cleaning the area all complete as per drawing, design & manufactures specification all complete. Rates do not include painting work. |  | N.A | SFT | 120 | 105 | 12600 | 120 | 0% | 517.0459 | 637.0459 | 100% | 0 | 66889.8187 | 66889.8187
[9 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
3 | Metal Ceiling | Fitting of false ceiling consisting of 20g Aluminium planks made of pre-coated ( Top & Bottom ) & Size : 600mmx600mm tiles . False Ceiling with necessary supports , hangers etc. provided to install light fitting , fresh air grill etc. ( from Hunter Douglas or Armstrong ) | [6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
| a | live kitchen |  | N.A | SFT | 410 | 172 | 70520 | 410 | 70% | -355.4108 | 54.5892 | 100% | 49364 | -39974.6625 | 9389.3375
| b | Main kitchen |  | N.A | SFT | 100 | 172 | 17200 | 100 | 70% | 268.9583 | 368.9583 | 100% | 12040 | 51420.8319 | 63460.8319
| c | Basement |  | N.A | SFT |  | 172 | 0 | 0 | 0% | 155.517 | 155.517 | 100% | 0 | 26748.9202 | 26748.9202
[9 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
4 | Trap Door | Providing and fixing trap doors for access to the service areas. The trap door shall have an external frame made of 50mm x 50mm in good quality seasoned wood scantling on which the shutter is hinged. Shutter shall be made of 19 mm. Plywood. The exposed side & Internal side shall be laminate finish. Concealed heavy duty hinges shall be used to mount the shutters and locking shall be provided with Allen key and panel locks. Sufficient number of hinges and locks shall be provided to avoid sagging of the shutter. Key also shall be supplied | [6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
|  | Size : 3' x 3' |  | N.A | no. | 2 | 1860 | 3720 | 2 | 0% | 0 | 2 | 100% | 0 | 3720 | 3720
|  | Size : 4' x 2' | KITCHEN LOFT |  | no. | 2 | 1860 | 3720 | 2 | 0% | 0 | 2 | 100% | 0 | 3720 | 3720
[9 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
5 | Textured Wall Paint | Providing & applying three (03) coats of approved Plastic paint on walls including scraping, primer , filling with putty etc. complete with final coat no brush mark to be visible after painting colour shade as specified. |  | N.A | SFT | 1280 | 34 | 43520 | 1280 | 0% | -1280 | 0 | 0% | 0 | 0 | 0
[9 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
6 | Ceiling Paint ON Gypsum | Providing & applying three (03) coats of approved Plastic paint on exposed surface on ceiling including scraping, primer , filling with putty etc. complete with final coat no brush mark to be visible after painting colour shade as specified. |  | N.A | SFT | 120 | 34 | 4080 | 120 | 0% | 725.9734 | 845.9734 | 100% | 0 | 28763.0954 | 28763.0954 | New area to be add
[9 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
7 | Expose Ceiling Paint including all beams | Providing & applying Three (03) coats of approved Plastic paint on exposed surface on ceiling including HVAC ducts, Sprinkler Pipes etc. complete with final coat no brush mark to be visible after painting colour shade as specified. |  | N.A | SFT | 1320 | 34 | 44880 | 1320 | 85% | 81.9923 | 1401.9923 | 100% | 38148 | 9519.7394 | 47667.7394
[9 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
8 | Duct painting | Providing & applying Three (03) coats of powder coat (as per approved shade) on exposed surface on metal duct including removing of old paint, required zink oxide paint etc. complete with final coat no brush mark to be visible after painting colour shade as specified. |  |  | SFT | 500 | 27 | 13500 | 500 | 70% | 27.7761 | 527.7761 | 100% | 9450 | 4799.9535 | 14249.9535
[9 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
9 | Fire Sprinkler paint | Providing & applying Three (03) coats of fire rated paint as per standard on exposed surface on metal including removing of old paint etc. complete with final coat no brush mark to be visible after painting colour shade as specified. |  |  | SFT | 250 | 23 | 5750 | 250 | 0% | 0 | 250 | 100% | 0 | 5750 | 5750
[9 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0
10 | Rolling shutter painting | Providing & applying Three (03) coats of powder coat (as per approved shade) on exposed surface on metal rolling shutter including removing of old paint, required zink oxide paint etc. complete with final coat no brush mark to be visible after painting colour shade as specified. |  |  | SFT | 250 | 23 | 5750 | 250 | 0% | -250 | 0 | 0% | 0 | 0 | 0
Grand Total | [7 empty] | 1901229 | [5 empty] | 1600565 | 634130.6683 | 2234695.6683

## Civil MB
Measurement Book of Civil Work Copper Chimney Rajouri Garden
S.No. | Items | Descriptions | Unit | Measurement (mm) |  |  | Measurement (Feet)
|  |  |  | L | B | H | L | B | H | NO | TOTAL
GENERAL SITE WORKS
1 | Pest control at site | Providing Pest Control & Anti-termite treatment by appointing a specialized agency as per the specifications mentioned by the Bureau of Indian Standard & Agencies specification ( Whichever is higher ) for General Civil , Plumbing / Drainage & timber / Carpentry works , Gypsum related work including 5 Years guarantee under suitable undertaking on stamp paper etc complete as directed . ( Mode of Measurement to be on carpet area of floor & not the area of surface treated.) | Sqft
|  | Boh area | Sqft | 6483 | 6135 |  | 21.2697 | 20.128 |  | 1 | 428.1152
|  | Extra Fire exit Area | Sqft | 2505 | 2250 |  | 8.2185 | 7.3819 |  | 1 | 60.6681
|  | FOH area | Sqft | 18795 | 6930 |  | 61.6634 | 22.7362 |  | 1 | 1401.9923
|  | Basement area | Sqft | 7355 | 2817 |  | 24.1306 | 9.2421 |  | 1 | 223.0178
|  | Total:- | Sqft | [7 empty] | 2113.7935
2 | Site Barricading | Providing and fixing flex board out. Cost to include framework cost, opening for door, flex printing and installation. ( digital file provided by client ) Sizes as mentioned below | Sqft
|  | 1st Time | Sqft | 5700 |  | 3000 | 18.7008 |  | 9.8425 | 1 | 184.0629
|  | 2nd Time As per Mall Requirement | Sqft | 10000 |  | 2450 | 32.8084 |  | 8.0381 | 1 | 263.7158
|  | Total:- | Sqft | [7 empty] | 447.7787
DEMOLITION WORKS
3 | Core Cut | Core cuts in mother slab for drain pipes 200mm dia as per required and making good the same with cement plaster and waterproofing before slab waterproofing and kobah. | Nos.
|  | Boh area For Drain | Nos. | [7 empty] | 1
|  | Boh area For Supply Lines | Nos. | [7 empty] | 1
|  | Bar Area | Nos. | [7 empty] | 1
|  | Basement Area for cables | Nos. | [7 empty] | 1
|  | Basement Area for Gas Lines | Nos. | [7 empty] | 1
|  | Total:- | Nos. | [7 empty] | 5
4 | Debris | Removing Debris out of site included loading, unloading & shifting as per statutory rules and regulations.
|  | 2023-06-10 | Nos. | [7 empty] | 1
|  | 2023-06-13 | Nos. | [7 empty] | 1
|  |  | Nos. | [7 empty] | 3
4
|  | Total:- | Nos. | [7 empty] | 9
5 | Wall Puncture | Making punctures in existing brick/siphorex/concrete wall block for passing A.C. copper pipes/drain pipes as required and making good the same with cement plaster/POP. | [7 empty] | 5 | 5
INTERIOR CIVIL WORK
1 | Waterproofing | P&A Waterproofing on mother slabs & wall till 600mm height, with 4 coats of chemical (Zypex or Equivalent chemical to be used) treatment on the mother slab, before doing the treatment mother slab needs to clean properly up to the mark & dust free surface needs to achieve to apply the chemical (proof bond /BASF, Dr. Fixit / Equivalent make) & chemical needs to dry properly, After all there should be a water pond testing to be done for water tightness & rectifications of defects if any. Complete with 10 years performance guarantee with client's satisfaction. Entire process to be done under guideline & supervision of appointed engineering team. | Sqft
a. |  | Kitchen -floor | Sqft | 6483 | 6135 |  | 21.2697 | 20.128 |  | 1 | 428.1152
b. |  | Kitchen -wall up to 600mm
|  | Foh To Boh Area Gate wall | Sqft | 6483 |  | 600 | 21.2697 |  | 1.9685 | 1 | 41.8695
|  | Boh area Window Wall | Sqft | 5495 |  | 600 | 18.0282 |  | 1.9685 | 1 | 35.4886
|  | Pillar | Sqft | 390 |  | 600 | 1.2795 |  | 1.9685 | 1 | 2.5188
|  | Pillar | Sqft | 680 |  | 600 | 2.231 |  | 1.9685 | 1 | 4.3917
|  | Back Wall | Sqft | 5450 |  | 600 | 17.8806 |  | 1.9685 | 1 | 35.198
|  | Pillar | Sqft | 640 |  | 600 | 2.0997 |  | 1.9685 | 1 | 4.1333
|  | Pillar | Sqft | 570 |  | 600 | 1.8701 |  | 1.9685 | 1 | 3.6813
|  | Fire Exit Wall | Sqft | 5387 |  | 600 | 17.6739 |  | 1.9685 | 1 | 34.7911
|  | Mid Partation Wall | Sqft | 150 |  | 600 | 0.49213 |  | 1.9685 | 1 | 0.96875
|  |  | Sqft | 2610 |  | 600 | 8.563 |  | 1.9685 | 1 | 16.8563
|  |  | Sqft | 3340 |  | 600 | 10.958 |  | 1.9685 | 1 | 21.5709
|  |  | Sqft | 150 |  | 600 | 0.49213 |  | 1.9685 | 1 | 0.96875
|  |  | Sqft | 3160 |  | 600 | 10.3675 |  | 1.9685 | 1 | 20.4084
|  |  | Sqft | 2430 |  | 600 | 7.9724 |  | 1.9685 | 1 | 15.6938
|  | Total:- | Sqft | [7 empty] | 238.539
c. |  | Show kitchen -floor | Sqft | 2400 | 3500 |  | 7.874 | 11.4829 |  | 1 | 90.4168
d. |  | Show kitchen -wall up to 600mm | Sqft | 2505 |  | 600 | 8.2185 |  | 1.9685 | 1 | 16.1782
|  | Kitchen Front Wall | Sqft | 3500 |  | 600 | 11.4829 |  | 1.9685 | 1 | 22.6042
|  | Pillar | Sqft | 1020 |  | 600 | 3.3465 |  | 1.9685 | 1 | 6.5875
|  | Pillar | Sqft | 390 |  | 600 | 1.2795 |  | 1.9685 | 1 | 2.5188
|  |  | Sqft | 1005 |  | 600 | 3.2972 |  | 1.9685 | 1 | 6.4906
|  | Back Wall | Sqft | 3100 |  | 600 | 10.1706 |  | 1.9685 | 1 | 20.0209
|  | Total:- | Sqft | [7 empty] | 74.4001
e. |  | Bar Area | Sqft | 2400 | 2410 |  | 7.874 | 7.9068 |  | 1 | 62.2585
|  | Show kitchen -wall up to 600mm | Sqft | 2400 |  | 600 | 7.874 |  | 1.9685 | 2 | 31.0001
|  |  | Sqft | 2410 |  | 600 | 7.9068 |  | 1.9685 | 2 | 31.1292
|  | Total:- | Sqft | [7 empty] | 124.3877
2 | Block Work | Providing and constructing Light weight blocks masonry in cement mortar 1:4 of approved make like Aerocon/Siporex etc. Job to include raking out joints, scaffolding, making openings walls, curing etc. in substructure and superstructure to its true line & level in cement mortar proportion as specified in all shapes, size, at all heights, depths, leads & locations etc. complete. The rate shall also include for cleaning of surface, hacking of RCC surface in contact with brickwork, racking of joints, providing, erecting, & dismantling steel scaffolding , curing for 10 days, including 75 mm thk. R.C.C. stiffener at approximately every 1000 mm ht. with required M.S. reinforcement bars and Lintels for Doors and wall openings etc. compete as per the drgs., details & specifications.
|  | Kitchen Entry In house | Sqft | 6483 |  | 3810 | 21.2697 |  | 12.5 | 1 | 265.8711
|  | Less gate | Sqft | 1500 |  | 2400 | 4.9213 |  | 7.874 | -1 | -38.7501
|  |  | Sqft | 900 |  | 2400 | 2.9528 |  | 7.874 | -1 | -23.25
|  | Window Closer | Sqft | 3600 |  | 2400 | 11.811 |  | 7.874 | 1 | 93.0002
|  | Fan Area Closer | Sqft | 3000 |  | 1000 | 9.8425 |  | 3.2808 | 1 | 32.2917
|  | New Fire Exit Top closer | Sqft | 2200 |  | 1600 | 7.2178 |  | 5.2493 | 1 | 37.889
|  | Foh area | Sqft | 1460 |  | 4200 | 4.79 |  | 13.7795 | 2 | 132.0086
|  | Basement Area Above Door | Sqft | 1300 |  | 2000 | 4.2651 |  | 6.5617 | 1 | 27.9862
|  | Total:- | Sqft | [7 empty] | 527.0466
3 | Block Work | Specifications same as above (point no. 3). Wall height upto 1100mm
|  | Kicthen Area MID Partation | Sqft | 2500 |  | 1500 | 8.2021 |  | 4.9213 | 1 | 40.3647 | After Disscussion With Project Manager the Height Was Reduced As 1100
|  |  | Sqft | 3340 |  | 1500 | 10.958 |  | 4.9213 | 1 | 53.9272
|  | Live Kitchen | Sqft |  |  |  | 0 |  | 0 |  | 0
|  |  | Sqft | 3300 |  | 1100 | 10.8268 |  | 3.6089 | 1 | 39.073
|  | Bar Area | Sqft | 0 |  |  | 0 |  | 0 |  | 0 | Outer Wall Was Demolished As Per PMC team Instruction
|  |  | Sqft | 0 |  |  | 0 |  | 0 |  | 0
|  |  |  | 4240 |  | 1100 | 13.9108 |  | 3.6089 | 1 | 50.2029
|  | Total:- | Sqft | [7 empty] | 183.5677
4 | Internal Plaster | P&A of single coat backing plaster of 15-18 mm thick in CM 1:4 proportion to the walls & others surface including scaffolding, curing the joints, etc. The rates are inclusive of providing chicken mesh of 18mm gauge & 150mm width at junction of brick & RCC etc. at the walls, columns, beams etc., seven days water treatment as anti crack of plaster. Complete as per site engineer's instruction.
|  | Kitchen Entry In house | Sqft | 6483 |  | 3810 | 21.2697 |  | 12.5 | 2 | 531.7421
|  | Less gate | Sqft | 1500 |  | 2400 | 4.9213 |  | 7.874 | -2 | -77.5002
|  |  | Sqft | 900 |  | 2400 | 2.9528 |  | 7.874 | -2 | -46.5001
|  | Wall Edge | Sqft | 180 |  | 2400 | 0.59055 |  | 7.874 | 2 | 9.3
|  |  | Sqft | 180 |  | 1500 | 0.59055 |  | 4.9213 | 1 | 2.9063
|  |  | Sqft | 180 |  | 2400 | 0.59055 |  | 7.874 | 2 | 9.3
|  |  | Sqft | 180 |  | 900 | 0.59055 |  | 2.9528 | 1 | 1.7438
|  | Window Closer | Sqft | 3600 |  | 2400 | 11.811 |  | 7.874 | 1 | 93.0002
|  | Fan Area Closer | Sqft | 3000 |  | 1000 | 9.8425 |  | 3.2808 | 1 | 32.2917
|  | New Fire Exit Top closer | Sqft | 2200 |  | 1600 | 7.2178 |  | 5.2493 | 2 | 75.7779
0
|  | Kicthen Area MID Partation Wall Edge | Sqft | 180 |  | 1200 | 0.59055 |  | 3.937 | 1 | 2.325
|  | Kicthen Area MID Partation | Sqft | 2420 |  | 1200 | 7.9396 |  | 3.937 | 1 | 31.2584
|  |  | Sqft | 3300 |  | 1200 | 10.8268 |  | 3.937 | 1 | 42.6251
|  | Wall Edge | Sqft | 180 |  | 1200 | 0.59055 |  | 3.937 | 1 | 2.325
|  |  | Sqft | 3100 |  | 1200 | 10.1706 |  | 3.937 | 1 | 40.0417
|  |  | Sqft | 2400 |  | 1200 | 7.874 |  | 3.937 | 1 | 31.0001
|  | Live Kitchen | Sqft |  |  |  | 0 |  | 0 |  | 0
|  |  | Sqft | 3300 |  | 1100 | 10.8268 |  | 3.6089 | 2 | 78.146
|  | Bar Area | Sqft |  |  |  | 0 |  | 0 |  | 0
|  |  | Sqft |  |  |  | 0 |  | 0 |  | 0
|  | less Gate | Sqft | 300 |  | 900 | 0.98425 |  | 2.9528 | 1 | 2.9063
|  |  |  | 4200 |  | 1100 | 13.7795 |  | 3.6089 | 2 | 99.4585
|  | Total:- | Sqft | [7 empty] | 962.1478
5 | PCC Work | Providing and laying up to 50-75 mm thick cement concrete flooring with 1:2:4 cement concrete laid to proper level and slope in alternate bays including compactions, filling joints, or as directed, finishing smooth with cement Mortar 1:1 of sufficient minimum thickness to give a smooth & even surface and curing etc. complete as per architects instructions.
|  | kitchen floor(300mm) | Sqft | 6483 | 6135 |  | 21.2697 | 20.128 |  | 1 | 428.1152
|  | FOH area Including Bar and Live Kitchen | Sqft | 18795 | 6930 |  | 61.6634 | 22.7362 |  | 1 | 1401.9923
|  | Electrical Panle Area | Sqft | 2200 | 400 |  | 7.2178 | 1.3123 |  | 1 | 9.4722
|  | Total:- | Sqft
6 | COBA Work | CINDER BLOCK COBA of Avg. thickness mentioned below; After laying of soil pipes, floor traps is completed the floor of the sunken portion shall be covered with cinder coba embedded manually with 15-20 mm wide joints in 20 mm thk. Waterproofing mortar 1:4 ( 1 cement : 4 coarse sand )in layers upto the full ht. of sunken portion, having top layer of 50 mm thk waterproof mortar 1:4 ( 1 cement : 4 coarse sand ) using specialized W.P. chemical, finished smooth / rough with floating coat of neat cement all complete and as per specification.
|  | Boh Area | Sqft | 6483 | 6135 |  | 21.2697 | 20.128 |  | 1 | 428.1152
|  | Live Kitchen area | Sqft | 3200 | 2200 |  | 10.4987 | 7.2178 |  | 1 | 75.7779
|  | Bar Area | Sqft | 2200 | 2210 |  | 7.2178 | 7.2507 |  | 1 | 52.3341
|  | Total:- | Sqft | [7 empty] | 128.1121
7 | MS STRUCTURE | Providing and fixing M.S frame structure/ rack made out of 50mm X 50mm hollow pipe sections on walls finishing/supporting/cutting/required fixture & fasteners etc. as per design, drawing & as directed by Project Manager etc. complete. | [8 empty] | 0
8 | Bison board/ PLY | Providing, making and fixing of wall panelling made of 12mm thk branded bison board/ PLY paneling on wall including ALU framework finish with all necessary required framing, approved make adhesive and fasteners, cutting/ chamfering/ groove/rounding wherever required, at all height with lead and lift, finishing, cleaning as per design and drawing etc. all complete. | [8 empty] | 0
AHU Boxing
|  | Vertical | Sqft | 6850 | 4510 |  | 22.4738 | 14.7966 |  | 1 | 332.5349
|  | Less Opening | Sqft | 1500 | 1900 |  | 4.9213 | 6.2336 |  | -1 | -30.6771
|  | Horizontal | Sqft | 5350 | 1500 |  | 17.5525 | 4.9213 |  | 1 | 86.3804
|  |  | Sqft | 1900 | 1500 |  | 6.2336 | 4.9213 |  | 2 | 61.3543
|  |  | Sqft | 1500 | 1600 |  | 4.9213 | 5.2493 |  | 1 | 25.8334
|  | Main Wall Partition with MS Frame and WPS and Gypsum | Sqft | [7 empty] | 0
|  | Main Wall 1 | Sqft | 14905 | 4200 |  | 48.9009 | 13.7795 |  | 1 | 673.8316
|  | Main Wall 2 | Sqft | 3275 | 3800 |  | 10.7448 | 12.4672 |  | 1 | 133.9569
|  | Extended area Covering of Ahu Planeum | Sqft | 6850 | 2000 |  | 22.4738 | 6.5617 |  | 1 | 147.4656
|  | Less Opening | Sqft | 1500 | 1900 |  | 4.9213 | 6.2336 |  | -1 | -30.6771
|  | Horizontal | Sqft | 5350 | 1600 |  | 17.5525 | 5.2493 |  | 1 | 92.1391
Sqft
|  | Total Qty | Sqft | [7 empty] | 1492.1417
STONE & TILE WORKS
1 | KOTA Flooring | Providing and Laying KOTA stone of 19mm thk. on avg 40 mm thk bed of 1:4 cement mortar in proper line and level including neat cement float, filling joints with neat cement slurry of appropriate colour, cleaning, curing, rubbing, complete. Scope includes laying of floor protective cover on the floor and removing of the same when directed along with supply of all necessary materials, labour, tools and tackles complete in line with the Technical Specification, Drawings and as per the direction of the Architect & PMC. Including Polishing.
|  | Kitchen | Sqft | 6483 | 6135 |  | 21.2697 | 20.128 |  | 1 | 428.1152
|  | Ded. Of walls | Sqft | 5840 | 200 |  | 19.1601 | 0.65617 |  | -1 | -12.5722
|  | Total:- | Sqft | [7 empty] | 415.543
|  | live Kitchen | Sqft | 3200 | 2200 |  | 10.4987 | 7.2178 |  | 1 | 75.7779
|  | Basement Area | Sqft | 7000 | 2500 |  | 22.9659 | 8.2021 |  | 1 | 188.3684
|  |  | Sqft | 1300 | 1800 |  | 4.2651 | 5.9055 |  | 1 | 25.1876
|  | Total:- | Sqft | [7 empty] | 289.3339
2 | Wooden finish herringbone pattern Tile Flooring | Fixing & laying of tiles for flooring which includes --bedding of appropriate thickness with mortar of 1:6 ratio (1cement:6sand), spreading of grey cement slurry with minimum of 2kg/ Sq.mt. ratio over bedding mortar, including 3mm spacer with epoxy grout of approved colour, adhesive of bal Endura or approved equivalent, making of hole where ever required, in proper line and level in all direction, at all height with lead and lift, polishing/finishing/cleaning etc. as per design and drawing and directed by PMC etc. complete.
|  | FOH area Including Bar and Live Kitchen | Sqft | 18795 | 6800 |  | 61.6634 | 22.3097 |  | 1 | 1375.6923
|  | Less 300*300 Tiles area | Sqft | 9780 | 1925 |  | 32.0866 | 6.3156 |  | -1 | -202.6468
|  | Total:- | Sqft | [7 empty] | 1173.0456
3 | Pattern Tile Flooring | Fixing & laying of tiles for flooring which includes --bedding of appropriate thickness with mortar of 1:6 ratio (1cement:6sand), spreading of grey cement slurry with minimum of 2kg/ Sq.mt. ratio over bedding mortar, including 3mm spacer with epoxy grout of approved colour, adhesive of bal Endura or approved equivalent, making of hole where ever required, in proper line and level in all direction, at all height with lead and lift, polishing/finishing/cleaning etc. as per design and drawing and directed by PMC etc. complete.
|  | 300*300 Tiles area | Sqft | 9780 | 1925 |  | 32.0866 | 6.3156 |  | 1 | 202.6468
4 | Wooden finish Tile skiting | Fixing & laying of 100mm high tiles for skirting with bedding of appropriate approved make adhesive & colour joint filler inclusive of making all groove/chamfering/rounding/hole where ever required, in proper line and level in all direction, polishing/finishing/cleaning etc. Complete as per detail drawing, specification and as directed by PMC.
|  | Spice jar area | RFT | 2000 |  |  | 6.5617 |  |  | 1 | 6.5617
|  | L.h.s Wall | RFT | 1695 |  |  | 5.561 |  |  | 1 | 5.561
|  | After Dvr Rack Area | RFT | 14905 |  |  | 48.9009 |  |  | 1 | 48.9009
|  | Coloum | RFT | 900 |  |  | 2.9528 |  |  | 1 | 2.9528
|  | Coloum | RFT | 395 |  |  | 1.2959 |  |  | 1 | 1.2959
|  | Foh Area Window Bottom | RFT | 3400 |  |  | 11.1549 |  |  | 1 | 11.1549
|  | R.h.s Wall | RFT | 10816 |  |  | 35.4856 |  |  | 1 | 35.4856
|  | Total:- | RFT | [7 empty] | 111.9127
5 | Granite Threshold | P&F of Black leather finish Granite threshold at the edges of the mall and outlet flooring as per design drawing
|  | 6" thk granite threshold | MAIN ENTRY & KITCHEN DOOR
|  |  | RFT | 2596 |  |  | 8.5171 |  |  | 1 | 8.5171
|  |  | RFT | 3314 |  |  | 10.8727 |  |  | 1 | 10.8727
|  | Granite BOH kitchen wall | RFT | 5900 |  |  | 19.357 |  |  | 1 | 19.357
|  | Main Entrance below door and glazing | RFT | 5634 |  |  | 18.4843 |  |  | 1 | 18.4843
|  | Total:- | RFT | [7 empty] | 57.231
6 | Window sill & jamb in Marble | Providing and constructing Marble sill & jamb for window as per drawings. Inclusive of making all groove/chamfering/rounding/hole where ever required, in proper line and level in all direction, polishing/finishing etc. Complete as per detail drawing, specification and as directed by PMC.
Basic Rate of marble : 650 per SFT
upto 6"-8" thk marble
Tandoor section upto 1100
|  | FOH to BOH Stairs | RFT | 1535 |  |  | 5.0361 |  |  | 4 | 20.1444
|  | Electrical Room Stairs | RFT | 2000 |  |  | 6.5617 |  |  | 4 | 26.2467
0
|  | Total:- | RFT | [7 empty] | 46.3911
7 | Decorative Wall Tiles | Providing and fixing Glazed Decorative wall tiles which includes-approved make of adhesive like bal Endura or equivalent, grey cement paste with backing coat of 1:3 cement mortar not less than 12mm thick as & where ever required, joint filler of approved make and colour, as and where ever required, in proper line and level in all direction, at all height with lead and lift, polishing/finishing/cleaning etc as per design, drawing and directed by PMC etc. all complete.
|  | Pillar | Sqft | 1020 |  | 2800 | 3.3465 |  | 9.1864 | 1 | 30.7417
|  |  | Sqft | 390 |  | 2800 | 1.2795 |  | 9.1864 | 1 | 11.7542
|  |  | Sqft | 1480 |  | 2800 | 4.8556 |  | 9.1864 | 1 | 44.6056
|  | Back Wall | Sqft | 3665 |  | 2800 | 12.0243 |  | 9.1864 | 1 | 110.4592
|  |  | Sqft | 800 |  | 2400 | 2.6247 |  | 7.874 | -1 | -20.6667
|  |  | Sqft |  |  |  | 0 |  | 0 |  | 0
|  | Front Wall | Sqft | 3200 |  | 800 | 10.4987 |  | 2.6247 | 1 | 27.5556
|  | Total:- | Sqft | [7 empty] | 204.4497
8 | Sada Wall Tiles for kitchen | Providing and fixing Ceramic wall tiles which includes-approved make of adhesive like bal Endura or equivalent, grey cement paste with backing coat of 1:3 cement mortar not less than 12mm thick as & where ever required, joint filler of approved make and colour, as and where ever required, in proper line and level in all direction, at all height with lead and lift, polishing/finishing/cleaning etc as per design, drawing and directed by PMC etc. all complete. (Color - white/ ivory)
|  | Kitchen Entry Foh to Boh Area | Sqft | 6433 |  | 2440 | 21.1056 |  | 8.0052 | 1 | 168.9559
|  | Less Gates | Sqft | 1500 |  | 2440 | 4.9213 |  | 8.0052 | -1 | -39.3959
|  | Less Gates | Sqft | 900 |  | 2440 | 2.9528 |  | 8.0052 | -1 | -23.6375
|  | Boh area window wall | Sqft | 5375 |  | 2440 | 17.6345 |  | 8.0052 | 1 | 141.1687
|  | Pillar | Sqft | 390 |  | 2440 | 1.2795 |  | 8.0052 | 1 | 10.2429
|  | Pillar | Sqft | 640 |  | 2440 | 2.0997 |  | 8.0052 | 1 | 16.8089
|  | Back Wall | Sqft | 5511 |  | 2440 | 18.0807 |  | 8.0052 | 1 | 144.7406
|  | Pillar | Sqft | 640 |  | 2440 | 2.0997 |  | 8.0052 | 1 | 16.8089
|  | Pillar | Sqft | 570 |  | 2440 | 1.8701 |  | 8.0052 | 1 | 14.9704
|  | Fire Exit Wall | Sqft | 5368 |  | 2440 | 17.6115 |  | 8.0052 | 1 | 140.9848
|  | Less Gates | Sqft | 2000 |  | 2440 | 6.5617 |  | 8.0052 | -1 | -52.5279
|  | Wall Edge | Sqft | 200 |  | 1500 | 0.65617 |  | 4.9213 | 1 | 3.2292
|  | Low Height Partation | Sqft | 2570 |  | 1500 | 8.4318 |  | 4.9213 | 1 | 41.4949
|  | Low Height Partation | Sqft | 3358 |  | 1500 | 11.0171 |  | 4.9213 | 1 | 54.2178
|  | Low Height Partation | Sqft | 200 |  | 1500 | 0.65617 |  | 4.9213 | 1 | 3.2292
|  | Low Height Partation | Sqft | 3170 |  | 1500 | 10.4003 |  | 4.9213 | 1 | 51.1824
|  | Low Height Partation | Sqft | 2370 |  | 1500 | 7.7756 |  | 4.9213 | 1 | 38.2657 | Height was reduced after confirmation of Project manager
|  | Low Height Partation | Sqft | 200 |  | 1500 | 0.65617 |  | 4.9213 | 1 | 3.2292
|  | Total:- | Sqft | [7 empty] | 733.9682
9 | SS Corner Guard | P&F of 304 grade 3mm thick SS Corner guard (30mm x 30mm, mat finished as per approved sample) fixing with conceal tile on each corner of the kitchen's wall before cladding of tiles, so that the corner may be protected from the damages. Complete in proper line & level and site engineer's instruction. | RFT
|  | Fire Exit Edge | RFT | 2440 |  |  | 8.0052 |  |  | 1 | 8.0052
|  | Pillar | RFT | 2440 |  |  | 8.0052 |  |  | 1 | 8.0052
|  | Pillar | RFT | 2440 |  |  | 8.0052 |  |  | 1 | 8.0052
|  | Half Height Wall | RFT | 1500 |  |  | 4.9213 |  |  | 5 | 24.6063
|  | Total:- | RFT | [7 empty] | 48.622
10 | Brass Corner Guard | P&F of 304 grade 3mm thick Brass Corner guard (30mm x 30mm, mat finished as per approved sample) fixing with conceal tile on each corner of the kitchen's wall before cladding of tiles, so that the corner may be protected from the damages. Complete in proper line & level and site engineer's instruction.
POP & PAINTING WORK
1 | POP Punning | Providing and applying Plaster of Paris punning of average thickness 20-25mm to existing wall surfaces/ on existing tiles including chicken mesh in true level and plumb complete as per design and drawing Cleaning the surface properly with sand paper, filling cracks/holes with plaster of Paris. Applying lambi / putty (lambi/putty will be of good quality) sand papering the putty work on chamfers, etc.at any / all heights. Rate include cost for making grooves up to 12mm thick if required in horizontal or vertical direction near doors, windows, skirting, floor covering, masking tape and cleaning the area all complete as per drawing, design & manufactures specification.
| a | block work walls
|  | L.h.s Wall After Bar | Sqft | 12080 |  | 3810 | 39.6325 |  | 12.5 | 1 | 495.4068
|  | main Door Less | Sqft | 1300 |  | 2400 | 4.2651 |  | 7.874 | -1 | -33.5834
|  |  | Sqft |  |  |  | 0 |  | 0 |  | 0
|  | Pillar | Sqft | 700 |  | 3810 | 2.2966 |  | 12.5 | 1 | 28.7073
|  | Pillar | Sqft | 395 |  | 3810 | 1.2959 |  | 12.5 | 1 | 16.1991
|  | Window Wall | Sqft | 3650 |  | 3810 | 11.9751 |  | 12.5 | 1 | 149.6883
|  | Less Window | Sqft | 3130 |  | 2450 | 10.269 |  | 8.0381 | -1 | -82.543
|  | Total:- | Sqft | [7 empty] | 573.8752
| b | Exposed ceiling | Sqft | 18795 |  | 6630 | 61.6634 |  | 21.752 | 1 | 1341.3
2 | Gypsum Ceiling | Providing, making and fixing of POP false ceiling as per manufacturer design and drawing including cut-outs for hvac grille, lights etc.at any / all heights. Rate quoted should be including of vertical drop of any heights, mouldings and size mentioned in drawings with necessary required framing in 450x 900 ultra Gyproc sections, fittings, and fixtures, scaffolding, floor covering, masking tape and cleaning the area all complete as per drawing, design & manufactures specification all complete. Rates do not include painting work.
|  | Suspended Ceiling For Bells Hanging | Sqft | 10000 |  | 1410 | 32.8084 |  | 4.626 | 1 | 151.7711
|  | Vertical | Sqft | 6850 | 4510 |  | 22.4738 | 14.7966 |  | 1 | 332.5349
|  | Less Opening | Sqft | 1500 | 1900 |  | 4.9213 | 6.2336 |  | -1 | -30.6771
|  | Horizontal | Sqft | 5350 | 1600 |  | 17.5525 | 5.2493 |  | 1 | 92.1391
|  |  | Sqft | 1900 | 1600 |  | 6.2336 | 5.2493 |  | 2 | 65.4446
|  |  | Sqft | 1500 | 1600 |  | 4.9213 | 5.2493 |  | 1 | 25.8334
|  | Total:- | Sqft | [7 empty] | 637.0459
3 | Metal Ceiling | Fitting of false ceiling consisting of 20g Aluminium planks made of pre-coated ( Top & Bottom ) & Size : 600mmx600mm tiles . False Ceiling with necessary supports , hangers etc. provided to install light fitting , fresh air grill etc. ( from Hunter Douglas or Armstrong )
| a | live Kitchen | Sqft | 3675 | 1380 |  | 12.0571 | 4.5276 |  | 1 | 54.5892
| b | Main Kitchen | Sqft | 6015 | 6490 |  | 19.7343 | 21.2927 |  | 1 | 420.1945
|  | Ded. Of Hood | Sqft | 3200 | 1050 |  | 10.4987 | 3.4449 |  | -1 | -36.1667
|  |  | Sqft | 1000 | 1400 |  | 3.2808 | 4.5932 |  | -1 | -15.0695
|  | Total:- | Sqft | [7 empty] | 368.9583
| c | Basement | Sqft | 5160 | 2800 |  | 16.9291 | 9.1864 |  | 1 | 155.517
|  | Total:- | Sqft | [7 empty] | 155.517
3 | Trap Doors. | Trap Doors. | Nos
|  | Size : 3' x 3' | no. | [6 empty] | 2 | 2
|  | Size : 4' x 2' | no. | [6 empty] | 2 | 2
5 | Textured Wall Paint | Providing & applying three (03) coats of approved Plastic paint on walls including scraping, primer , filling with putty etc. complete with final coat no brush mark to be visible after painting colour shade as specified. | [7 empty] | 0 | 0
6 | Ceiling Paint ON Gypsum | Providing & applying three (03) coats of approved Plastic paint on exposed surface on ceiling including scraping, primer , filling with putty etc. complete with final coat no brush mark to be visible after painting colour shade as specified.
|  | Suspended Ceiling For Bells Hanging | Sqft | 10000 |  | 1410 | 32.8084 |  | 4.626 | 1 | 151.7711
|  | Vertical | Sqft | 6850 | 4510 |  | 22.4738 | 14.7966 |  | 1 | 332.5349
|  | Less Opening | Sqft | 1500 | 1900 |  | 4.9213 | 6.2336 |  | -1 | -30.6771
|  | Horizontal | Sqft | 5350 | 1600 |  | 17.5525 | 5.2493 |  | 1 | 92.1391
|  |  | Sqft | 1900 | 1600 |  | 6.2336 | 5.2493 |  | 2 | 65.4446
|  |  | Sqft | 1500 | 1600 |  | 4.9213 | 5.2493 |  | 1 | 25.8334
|  | Extended area Covering of Ahu Planeum | Sqft | 6850 | 2000 |  | 22.4738 | 6.5617 |  | 1 | 147.4656
|  | Less Opening | Sqft | 1500 | 1900 |  | 4.9213 | 6.2336 |  | -1 | -30.6771
|  | Horizontal | Sqft | 5350 | 1600 |  | 17.5525 | 5.2493 |  | 1 | 92.1391
Sqft
|  | Total:- | Sqft | [7 empty] | 845.9734
7 | Expose Ceiling Paint including all beams | Providing & applying Three (03) coats of approved Plastic paint on exposed surface on ceiling including HVAC ducts, Sprinkler Pipes etc. complete with final coat no brush mark to be visible after painting colour shade as specified.
|  |  | Sqft | 18795 | 6930 |  | 61.6634 | 22.7362 |  | 1 | 1401.9923
8 | Duct Paint | Providing & applying Three (03) coats of powder coat (as per approved shade) on exposed surface on metal duct including removing of old paint, required zink oxide paint etc. complete with final coat no brush mark to be visible after painting colour shade as specified.
|  | Duct-1 | Sqft | 12700 | 2160 |  | 41.6667 | 7.0866 |  | 1 | 295.2756
|  | Duct-2 | Sqft | 10000 | 2160 |  | 32.8084 | 7.0866 |  | 1 | 232.5005
|  | Total:- | Sqft | [7 empty] | 527.7761
9 | Fire Sprinkler paint | Providing & applying Three (03) coats of fire rated paint as per standard on exposed surface on metal including removing of old paint etc. complete with final coat no brush mark to be visible after painting colour shade as specified. | Sqft |  |  |  | 250 | 1 |  | 1 | 250
10 | Rolling shutter painting | Providing & applying Three (03) coats of powder coat (as per approved shade) on exposed surface on metal rolling shutter including removing of old paint, required zink oxide paint etc. complete with final coat no brush mark to be visible after painting colour shade as specified. | [7 empty] | 0 | 0

## INTERIOR WORK
Project : Charcoal Concept
Site Name :Copper Chimney Project, Vishal Cinema, Delhi
Work: Interior Finishing Work
Contractor: Stars and Merit Interiors Private Limited
Work order No : DCPL/Vishal Cinema/CC/23-24/CP-202
Bill NO. :RA-4 Bill
SR.NO. | ITEM | DESCRIPTION | LOCATION | DIMENSION | UNIT | As Per Work order |  |  | As per Bill Quantity |  |  |  |  | As per Bill Amount |  |  | UNIT
[6 empty] | QTY. | RATE | AMOUNT | Preious Bill | % OF Work | This Bill | Cumulative Bill | % of Works | Preious Bill | This Bill | Cumulative Bill
DOORS |  | CARPENTRY WORK
1 | Kitchen Door | Providing & fixing in position Double Leaf Door made up of 38mm thick commercial flush door shutter of approved make & thickness, Inner side finished with laminate and outer side with veneer finish including providing & fixing 750mm X 200mm glass Vision panel and 12mm thk Wooden lipping all around, including of 750mm X 200mm SS push plate and 100mm high SS kick plate, including P/F of Door frame made out of CP Teak / Ash wood or equivalent with melamine polish finish. Size of the frame approximate 175mm wide X 50mm thick. Applicable hardware's such as s/s handles/ ss push plate, floor spring and any other hardware etc required to complete the related works as per design & detail. door hardware make consider Dorma / Hafele/Ozon /equilient | KITCHEN ENTRY | 1500X2400 | NOS | 1 | 42312 | 42312 | 1 | 70% | 0 | 1 | 100% | 29618.4 | 12693.6 | 42312
[9 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
2 | Live Kitchen Door | Providing & fixing in position Single Leaf Door made up of 38mm thick commercial flush door shutter of approved make & thickness, Inner side finished with laminate and outer side with veneer finish including providing & fixing 750mm X 200mm glass Vision panel and 12mm thk Wooden lipping all around, including of 750mm X 200mm SS push plate and 100mm high SS kick plate, including P/F of Door frame made out of CP Teak / Ash wood or equivalent with melamine polish finish. Size of the frame approximate 175mm wide X 50mm thick. Applicable hardware's such as s/s handles, conceal door closer and any other hardware etc required to complete the related works as per design & detail. door hardware make consider Dorma / Hafele/Ozon /equilient | LIVE KITCHEN ENTRY | 900X2400 | NOS | 1 | 32450 | 32450 | 1 | 70% | 0 | 1 | 100% | 22715 | 9735 | 32450
[9 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
[9 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
[9 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
5 | Fire Rated Metal Door | Providing and fixing of Hollow metal fire rated double leaf door. Door frame shall be double rebate profile of size 143 x 57 mm made out of 1.60mm (16gauge)minimum thick galvanized steel sheet.All doors and frames shall be finished with polyurethane aliphatic grade paint of approved colour. The door leaf and frame shall have passed minimum 250 hours of salt spray test.2Hrs Fire Rated Single leaf of size | KITCHEN BACK ENTRY | 2000X2400 | NOS | 1 | 51234 | 51234 | 1 | 80% | 0 | 1 | 100% | 40987.2 | 10246.8 | 51234
[9 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
CARPENTRY WORK |  | CARPENTRY WORK | [6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
1 | Service Station - A | P/F service counters in duco finished from outer surface & top finished in veneer. The storage under the Counter should be provided with 6" ht. drawers at top row finished with wooden ribs. top of the shutter having C section brass inlay & below openable shutters finished with duco. the drawer should have internal partiton with fabric finish for cutlary Shutters made out of 19mm thk. plywood finished with 1mm thk. laminate internally. The shutters to be provided with fittings such as hinges; handles; ball catch, locks etc. complete in all respect. The rates for the Shutters to be included. as per design and details. | NEAR ENTRANCE | 1130mm L X 450mmW X 900H | NOS | 1 | 43560 | 43560 | 1 | 100% | 0 | 1 | 100% | 43560 | 0 | 43560
|  | Plywood - branded Commercial Ply (MR Calibrated, IS 303) -- Greenply or Equivalent brand | [6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
|  | Veneer Make - Euro/Greenlam/Merino/ or equivalent (Basic Rate- 140 Sq. ft.) | [6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
|  | Laminate Make - Euro/Greenlam/Merino/ or equivalent (Basic Rate- 40 Sq. ft.) | [6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
[9 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
2 | Console with Display Unit | P/F console having 25 x 25mm MS framework with black powder coat upto ceiling height, having wooden shelf @ every 350mm c/c. the base console finished in duco from outer surface & top finished in veneer. The storage under the Counter should be provided with 6" ht. drawers at top row finished with wooden ribs. top of the shutter having C section brass inlay & below openable shutters finished with duco. Shutters made out of 19mm thk. plywood finished with 1mm thk. laminate internally. The shutters to be provided with fittings such as hinges; handles; ball catch etc. complete in all respect. The rates for the Shutters to be included. as per design and details. | NEAR KITCHEN DOOR | 1600mm L X 350mmW X 900H | no. | 1 | 76235 | 76235 | 1 | 100% | 0 | 1 | 100% | 76235 | 0 | 76235
|  | Plywood - branded Commercial Ply (MR Calibrated, IS 303) -- Greenply or Equivalent brand | [6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
|  | Veneer Make - Euro/Greenlam/Merino/ or equivalent (Basic Rate- 140 Sq. ft.) | [6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
|  | Laminate Make - Euro/Greenlam/Merino/ or equivalent (Basic Rate- 40 Sq. ft.) | [6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
| a | Console |  |  | no. | 1 | 0 | 0 | 1 | 70% | -1 |  |  | 0 | 0 | 0
| b | 25X25mm MS section finish with black powder coat |  |  | RFT | 180 | 193 | 34740 | 180 | 100% | 0 | 180 | 100% | 34740 | 0 | 34740
| c | 20mm thk sandwitched glass shelf with cane in center and with veneer finish frame |  | 375mm x 230mm | no. | 12 | 2833 | 33996 | 12 | 100% | 0 | 12 | 100% | 33996 | 0 | 33996
[9 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
[9 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
3 | Bar Counter | P/F Bar counter to be made out of 19mm thk approved make branded Commercial Ply (MR Calibrated, IS 303) -- Greenply or Equivalent brand apron to be cladded with wood & netal cane as per detail and Double level of platform in Marble finished based on ply with necessary ms barcket, Necessary opening should be made for fixing of stainless steel sink. Erecting brick wall for plumbing and Brick platform should be provided on floor below the platform of 150mm high Marble skirting from outside. The top platform to have 50mm wide Marble finish fascia horizontally. | [6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
|  | Plywood - branded Commercial Ply (MR Calibrated, IS 303) -- Greenply or Equivalent brand | [6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
|  | Marble Basic Rate 600/- per SQ.FT. | [6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
|  | Veneer Make - Euro/Greenlam/Merino/ or equivalent (Basic Rate- 140 Sq. ft.) | [6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
|  | 12 x 75mm Wood Basic Coat @ 140 Rs SFT | [6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
| a | Top service Counter Ply Base with Neccesory Support to receved marble |  | 600mm Width | RFT | 50 | 2931 | 146550 | 50 | 70% | -1 | 49 | 100% | 102585 | 41034 | 143619
| b | Front Elevation (apron) to be to be made out of 19mm thk approved make branded Commercial Ply (MR Calibrated, IS 303) -- Greenply or Equivalent brand with veneer finish frames, ply to be finished with duco and veneer frames to be finished with melamine polish. Top row finished with metal cane and 100mm skirting with veneer as per detailed Drawing & design. Provision for indirect lighting to be made |  |  | SFT | 120 | 1155 | 138600 | 120 | 100% | -70 | 50 | 100% | 138600 | -80850 | 57750
| c | 50mm thk Top service platform in Marble |  | 450mm Width | RFT | 30 | 1645 | 49350 | 30 | 100% | -14 | 16 | 100% | 49350 | -23030 | 26320
| d | 35mm Dia Foot rest real brass antique finish at the bottom. |  |  | RFT | 30 | 560 | 16800 | 30 | 100% | -14 | 16 | 100% | 16800 | -7840 | 8960
| e | 750mm Flap door for bar area entry |  | 600 x 1100mm | Nos | 1 | 6540 | 6540 | 1 | 100% | 0 | 1 | 100% | 6540 | 0 | 6540
| f | 100mm high Wooden Skirting |  |  | RFT | 30 | 232 | 6960 | 30 | 100% | -14 | 16 | 100% | 6960 | -3248 | 3712
[9 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
[9 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
4 | Bar Display unit | P/F Bar display unit to be made out of 19mm thk approved make branded Commercial Ply (MR Calibrated, IS 303) -- Greenply or Equivalent brand with veneer finish, having brass finish shelf @ every 400mm c/c. The Backdrop made out of 12mm thk approved make branded Commercial Ply (MR Calibrated, IS 303) -- Greenply or Equivalent brand with finished with bronze mirror, front panelling to be veneer finsh. The shelves to be provided with necessary fittings etc. complete in all respect. The rates for shelves to be included. as per design and details. | [6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
|  | Plywood - branded Commercial Ply (MR Calibrated, IS 303) -- Greenply or Equivalent brand | [6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
|  | Marble Basic Rate 600/- per SQ.FT. | [6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
|  | Veneer Make - Euro/Greenlam/Merino/ or equivalent (Basic Rate- 140 Sq. ft.) | [6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
|  | Laminate Make - Euro/Greenlam/Merino/ or equivalent (Basic Rate- 40 Sq. ft.) | [6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
| a | Mirror Panelling |  |  | SFT | 30 | 512 | 15360 | 30 | 100% | -12 | 18 | 100% | 15360 | -6144 | 9216
| b | brass shelves |  | 850mm X300mm | no. | 6 | 4523 | 27138 | 6 | 30% | 0 | 6 | 100% | 8141.4 | 18996.6 | 27138
| c | brass patti |  |  | Rft | 50 | 450 | 22500 | 50 | 30% | -50 | 0 | 100% | 6750 | -6750 | 0
| d | Veneer Cladding |  |  | Sqft | 75 | 500 | 37500 | 75 | 100% | -41 | 34 | 100% | 37500 | -37500 | 0
[9 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0
5 | Hostess Desk | Desk to have 2 drawers of ht 155mm, finished with duco outside and veneer maching laminate inside with inbuilt recessed handles in wood and polish. |  | 750mm L X 500mm W X 1050 H | NOS | 1 | 19562 | 19562 | 1 | 100% | 0 | 1 | 100% | 19562 | 0 | 19562
[11 empty] | 0 |  |  | 0 | 0 | 0
[11 empty] | 0 |  |  | 0 | 0 | 0
[11 empty] | 0 |  |  | 0 | 0 | 0
[11 empty] | 0 |  |  | 0 | 0 | 0
[11 empty] | 0 |  |  | 0 | 0 | 0
6 | Banquet Seating A | Providing, making and fixing sofa made out of wooden frame work and cladded with 12mm thk approved make branded Commercial Ply (MR Calibrated, IS 303) -- Greenply or Equivalent brand & approved fabric with required wooden frame, required wodden frame finishing/cleaning/cutting/required fixture & fasteners etc. as per design & drawing & as directed by Project Manager etc. complete. Sofa will have high density rubber foam.(Foam used should be approved and to be certified against poisonous and noxious fumes.) Rate includes upholstery of fabrics. | Near Live kitchen | 9880 x 650 x 900 HT | NOS | 2 | 175000 | 350000 | 2 | 70% | 0 | 2 | 100% | 245000 | 105000 | 350000
|  | Veneer on exterior finish Basic cost @ 140Rs sft | [6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
|  | Fabric Basic cost @ 600 per MTR | [6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
|  | Size : W 650 x H 900 | [6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
[9 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
7 | Banquet Seating in entrance | Providing, making and fixing sofa made out of wooden frame work and cladded with 12mm thk approved make branded Commercial Ply (MR Calibrated, IS 303) -- Greenply or Equivalent brand & approved fabric with required wooden frame, top rail having a cane box with required wodden frame finishing/cleaning/cutting/required fixture & fasteners etc. as per design & drawing & as directed by Project Manager etc. complete. Sofa will have high density rubber foam.(Foam used should be approved and to be certified against poisonous and noxious fumes.) Rate includes upholstery of fabrics. | Near Live kitchen | 4700 x 650 x 900 HT | NOS | 1 | 93450 | 93450 | 1 | 90% | 0 | 1 | 100% | 84105 | 9345 | 93450
|  | Veneer on exterior finish Basic cost @ 140Rs sft | [6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
|  | Fabric Basic cost @ 600 per MTR | [6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
|  | Size : W 650 x H 900 | [6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
[9 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
[9 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
[9 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
8 | Cane Panel | P/F 75mm thk plywood partition finished with bamboo Cane from both side, internal ply finished with laminate. structure to be made out of 40x20mm thk wooden frame with 12mm ply on both side, intermidiate member size of 40 x 20mm wooden frame/ bidding to be finished with melamine polish. to be finished with duco paint finish with necessary fittings as per design and details. |  |  | SFT | 250 | 1550 | 387500 | 250 | 70% | -67.8746 | 182.1254 | 100% | 271250 | 11044.3146 | 282294.3146
|  | Plywood - branded Commercial Ply (MR Calibrated, IS 303) -- Greenply or Equivalent brand | [6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
[9 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
9 | Wall dado - Veneer panelling | Providing, making and fixing of wall panel made of 12mm thk branded Commercial Ply (MR Calibrated, IS 303) -- Greenply or Equivalent brand with Veneer finish with melamine polish having wooden molding all necessary required wooden framing, approved make adhesive and fasteners, cutting/ chamfering/ groove/rounding wherever required, at all height with lead and lift, finishing, cleaning as per design and drawing etc. all complete. |  | upto 900mm ht | SFT | 50 | 500 | 25000 | 50 | 90% | 290.8823 | 340.8823 | 100% | 22500 | 147941.1395 | 170441.1395
|  | Basic Rate of Veneer @ 120 Rs per SFT | [6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
|  | Seating area | [6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
[9 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
10 | Wall dado - MDF panelling with duco | Providing, making and fixing of wall panel made of 12mm thk branded Commercial Ply (MR Calibrated, IS 303) -- Greenply or Equivalent brand with MDF finish with Duco paint and wooden molding as per design, all necessary required wooden framing, approved make adhesive and fasteners, cutting/ chamfering/ groove/rounding wherever required, at all height with lead and lift, finishing, cleaning as per design and drawing etc. all complete. | KITCHEN WALL | upto 1200mm ht | SFT | 120 | 468 | 56160 | 120 | 90% | 2.2662 | 122.2662 | 100% | 50544 | 6676.5732 | 57220.5732
|  | KITCHEN area | [6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
[9 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
[9 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
11 | Ply Support In Ceiling | Providing, making and fixing plywood Support,Suspended from slab or gryprog frame level with false ceiling bottom off frame work, commercial ply backing to receved fixture/ fiting including all necessary hardware, fixture/ fasteners, cutting/finishing, cleaning. Complete as per detail drawing, specification and as directed by PMC. | [6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
| a | 12mm thk Ply support for bell or heavy duty fixtures |  |  | SFT | 250 | 125 | 31250 | 250 | 70% | 11.6373 | 261.6373 | 100% | 21875 | 10829.6618 | 32704.6618
| b | 8mm thk ply template to instal Light & Speaker with Round cutout according to fixtures |  |  | Nos | 10 | 652 | 6520 | 10 | 70% | 0 | 10 | 100% | 4564 | 1956 | 6520
[9 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
[9 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
12 | Bison board/ V board panelling | Providing, making and fixing of wall panelling made of 12mm thk branded bison board/ V board paneling on wall including ALU framework finish with all necessary required framing, approved make adhesive and fasteners, cutting/ chamfering/ groove/rounding wherever required, at all height with lead and lift, finishing, cleaning as per design and drawing etc. all complete. | KITCHEN WINDOW |  | Sqft | 75 | 295 | 22125 | 75 | 90% | -75 | 0 | 100% | 19912.5 | -19912.5 | 0
|  | OR | [6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
|  | Providing and constructing Light weight blocks masonry in cement mortar 1:4 of approved make like Aerocon/Siporex etc. Job to include raking out joints, scaffolding, making openings walls, curing etc. in substructure and superstructure to its true line & level in cement mortar proportion as specified in all shapes, size, at all heights, depths, leads & locations etc. complete. The rate shall also include for cleaning of surface, hacking of RCC surface in contact with brickwork, racking of joints, providing, erecting, & dismantling steel scaffolding , curing for 10 days. | KITCHEN WINDOW |  | Sqft | 75 | 145 | 10875 | 75 | 100% | -75 |  | 0% | 10875 | -10875 | 0
|  | Using 150mm thk Walls upto 2200mm | [6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
13 | Electrical Cabinet | P/F louver shutter with wooden framework as per design & detail made in fire rated ply with openable shutters with duco finish externally laminate finish internally. Including all necessary required wooden framing, approved make adhesive and fasteners, Lock, cutting/ chamfering/ groove/rounding wherever required, at all height with lead and lift, finishing, cleaning as per design and drawing etc. all complete. |  |  | SQFT | 30 | 1500 | 45000 | 30 | 70% | 62.7117 | 92.7117 | 100% | 31500 | 107567.5698 | 139067.5698
[11 empty] | 0 |  |  | 0 | 0 | 0
METAL FURNITURE & SCREENS |  | CARPENTRY WORK | [8 empty] | 0 |  |  | 0 | 0 | 0
[11 empty] | 0 |  |  | 0 | 0 | 0
1 | Show kitchen Glass Partition | P/F 10 mm thk. toughened glass partitions with 20x 40mm MS framework with white powder coating and bottom base wooden partiton height upto 900mm with wooden molding finish with duco paint and all necessary required groove, wooden framing, including glass door with heavy duty floor spring fixing with approved make adhesive and fasteners, cutting/ chamfering/ groove/rounding wherever required, at all height with lead and lift, finishing, cleaning as per design and drawing etc. all complete. |  | N.A | SFT | 150 | 560 | 84000 | 150 | 70% | -30.9684 | 119.0316 | 100% | 58800 | 7857.7111 | 66657.7111
[9 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
2 | Spice Jar Unit | Providing and fixing M.S frame structure/ rack made out of 20mm X 20mm hollow pipe sections with 20 mm thick plywood shelves finished in laminate. finishing/supporting/cutting/required fixture & fasteners etc. as per design, drawing & as directed by Project Manager etc. complete. | [6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
|  | M.S to be finished in Asian paint Coal Mine - 8301 finish matt | [6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
|  | Size : 3500 X 200 X 3500(H) |  |  | Nos | 1 | 40000 | 40000 | 1 | 70% | 0 | 1 | 100% | 28000 | 12000 | 40000
[5 empty] | Nos |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0
[9 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
3 | Brass framework on wallpaper | Providing and fixing 20 x 20mm SS box section finished in brass pvd coating framework fixed on walls finishing/supporting/cutting/required fixture & fasteners etc. as per design, drawing & as directed by Project Manager etc complete. |  |  | RFT | 200 | 283 | 56600 | 200 | 70% | -65.3215 | 134.6785 | 100% | 39620 | -1505.9908 | 38114.0092
[9 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
4 | MS framework on walls | Providing and fixing M.S frame structure/ rack made out of 20mm X 20mm hollow pipe sections on walls finishing/supporting/cutting/required fixture & fasteners etc. as per design, drawing & as directed by Project Manager etc. complete. |  |  | RFT | 150 | 165 | 24750 | 150 | 90% | -42.7822 | 107.2178 | 100% | 22275 | -4584.0551 | 17690.9449
[9 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
5 | MS framework on ceiling | Providing and fixing M.S frame structure out of 20mm X 20mm hollow pipe sections framework supported from ceiling finished with black powder coat finishing/supporting/cutting/required fixture & fasteners etc. as per design, drawing & as directed by Project Manager etc. complete. |  |  | RFT | 150 | 180 | 27000 | 150 | 90% | -150 | 0 | 100% | 24300 | -24300 | 0
[14 empty] | 0 | 0 | 0
MISCELLANEOUS - 1 | [13 empty] | 0 | 0 | 0
[14 empty] | 0 | 0 | 0
1 | Texture wallpaper | P & F of texture wallpaper as per approval |  |  | SFT | 400 | 206 | 82400 | 400 | 0% |  | 310.386 | 100% | 0 | 63939.5094 | 63939.5094
|  | Basic rate- 155/Sq Ft | [6 empty] | 0 | 0% |  |  |  | 0 | 0 | 0
[9 empty] | 0 | 0% |  |  |  | 0 | 0 | 0
2 | Ceiling Fans | P & F of ceiling fans paper as per approval |  |  | NOS | 7 | 2650 | 18550 | 7 | 0% |  | 0 | 0% | 0 | 0 | 0
[9 empty] | 0 | 0% |  |  |  | 0 | 0 | 0 |  | 167
3 | Sheer curtain on metal frame / roller blinds | P & F of linen/ Jute manual folding curtains as per approval |  |  | SQFT | 200 | 178 | 35600 | 200 | 0% |  | 167 | 100% | 0 | 29726 | 29726
|  | Basic rate- 150/Sq Ft | [6 empty] | 0 | 0% |  |  |  | 0 | 0 | 0
4 | Air curtain | P & F of Euronics Air Curtains as per approval |  |  | NOS | 2 | 27650 | 55300 | 2 | 70% |  | 0 | 0% | 38710 | -38710 | 0
SUB TOTAL OF INTERIOR WORKS | [7 empty] | 2253467 | [5 empty] | 1663830.5 | 341339.9334 | 2005170.4334

## Int. MB
Measurement Book of Interior Work Copper Chimney Rajouri Garden
S.No. | Items | Descriptions | Unit | Measurement (mm) |  |  | Measurement (Feet)
|  |  |  | L | B | H | L | B | H | NO | TOTAL
General Site Work
1 | Kitchen Door | Kitchen Door | Nos | [6 empty] | 1 | 1
2 | Live Kitchen Door | Live Kitchen Door | Nos | [6 empty] | 1 | 1
3 | Fire Rated Metal Door | Fire Rated Metal Door | Nos | [6 empty] | 1 | 1
Carpentary Work
1 | Service Station - A | Service Station - A | Nos | [6 empty] | 1 | 1
2 | Console with Display Unit | Console with Display Unit | Nos | [6 empty] | 1 | 1
a |  | Console | Nos | [7 empty] | 0
b |  | 25X25mm MS section finish with black powder coat | Rft |  |  |  | 180 |  |  | 1 | 180
c |  | 20mm thk sandwitched glass shelf with cane in center and with veneer finish frame | Nos | [6 empty] | 12 | 12
3 | Bar Counter | Bar Counter | [8 empty] | 0
a |  | Top service Counter Ply Base with Neccesory Support to receved marble | RFT |  |  |  | 49 |  |  | 1 | 49
b |  | Front Elevation (apron) to be to be made out of 19mm thk approved make branded Commercial Ply (MR Calibrated, IS 303) -- Greenply or Equivalent brand with veneer finish frames, ply to be finished with duco and veneer frames to be finished with melamine polish. Top row finished with metal cane and 100mm skirting with veneer as per detailed Drawing & design. Provision for indirect lighting to be made | SFT |  |  |  | 50 |  |  | 1 | 50
c |  | 50mm thk Top service platform in Marble | RFT |  |  |  | 16 |  |  | 1 | 16
d |  | 35mm Dia Foot rest real brass antique finish at the bottom. | RFT |  |  |  | 16 |  |  | 1 | 16
e |  | 750mm Flap door for bar area entry | Nos | [6 empty] | 1 | 1
f |  | 100mm high Wooden Skirting | RFT |  |  |  | 16 |  |  | 1 | 16
4 | Bar Display unit | Bar Display unit
a |  | Mirror Panelling | SFT |  |  |  | 18 |  |  | 1 | 18
b |  | brass shelves | no. |  |  |  | 6 |  |  | 1 | 6
c |  | brass patti | Rft |  |  |  | 0 |  |  | 1 | 0
d |  | Veneer Cladding | Sqft |  |  |  | 34 |  |  | 1 | 34
5 | Hostess Desk | Hostess Desk | Nos | [6 empty] | 1 | 1
6 | Banquet Seating A | Banquet Seating A | Nos | [6 empty] | 2 | 2
7 | Banquet Seating in entrance | Banquet Seating in entrance | Nos | [6 empty] | 1 | 1
8 | Cane Panel | Cane Panel | Sqft
|  | Photo Frame Wall | Sqft | 3000 |  | 1800 | 9.8425 | 0 | 5.9055 | 1 | 58.1251
|  | Heritage Wall | Sqft | 4800 |  | 2400 | 15.748 | 0 | 7.874 | 1 | 124.0002
|  |  | Sqft |  |  |  | 0 | 0 |  |  | 0
|  | Total:- | Sqft | [7 empty] | 182.1254
9 | Wall dado - Veneer panelling | Providing, making and fixing of wall panel made of 12mm thk branded Commercial Ply (MR Calibrated, IS 303) -- Greenply or Equivalent brand with Veneer finish with melamine polish having wooden molding all necessary required wooden framing, approved make adhesive and fasteners, cutting/ chamfering/ groove/rounding wherever required, at all height with lead and lift, finishing, cleaning as per design and drawing etc. all complete.
|  | Photo Frame wall | Sqft | 3000 |  | 1100 | 9.8425 | 0 | 3.6089 | 1 | 35.5209
|  |  | Sqft | 250 |  | 1100 | 0.82021 | 0 | 3.6089 | 1 | 2.9601
|  |  | Sqft | 14940 |  | 1100 | 49.0157 | 0 | 3.6089 | 1 | 176.8941
|  |  | Sqft | 10600 |  | 1100 | 34.7769 | 0 | 3.6089 | 1 | 125.5072
|  | Total:- | Sqft | [7 empty] | 340.8823
10 | Wall dado - MDF panelling with duco | Providing, making and fixing of wall panel made of 12mm thk branded Commercial Ply (MR Calibrated, IS 303) -- Greenply or Equivalent brand with MDF finish with Duco paint and wooden molding as per design, all necessary required wooden framing, approved make adhesive and fasteners, cutting/ chamfering/ groove/rounding wherever required, at all height with lead and lift, finishing, cleaning as per design and drawing etc. all complete.
|  | Live Kitchen Window Partation | Sqft | 3360 |  | 3730 | 11.0236 | 0 | 12.2375 | 1 | 134.9019
|  |  | Sqft | 2650 |  | 3730 | 8.6942 | 0 | 12.2375 | 1 | 106.3959
|  | Less Window Area | Sqft | 3360 |  | 1840 | 11.0236 | 0 | 6.0367 | -1 | -66.5468
|  |  | Sqft | 2650 |  | 1840 | 8.6942 | 0 | 6.0367 | -1 | -52.4848
|  | Total:- | Sqft | [7 empty] | 122.2662
| Ply Support In Ceiling | Providing, making and fixing plywood Support,Suspended from slab or gryprog frame level with false ceiling bottom off frame work, commercial ply backing to receved fixture/ fiting including all necessary hardware, fixture/ fasteners, cutting/finishing, cleaning. Complete as per detail drawing, specification and as directed by PMC.
| a | 12mm thk Ply support for bell or heavy duty fixtures | Sqft | 10090 |  | 1410 | 33.1037 | 0 | 4.626 | 1 | 153.1371
|  | Vertical | Sqft | 10000 |  | 450 | 32.8084 | 0 | 1.4764 | 2 | 96.8752
|  |  | Sqft | 1200 |  | 450 | 3.937 | 0 | 1.4764 | 2 | 11.625
|  |  | Sqft |  |  |  | 0 | 0 | 0 |  | 0
|  |  | Sqft |  |  |  | 0 | 0 | 0 |  | 0
|  | Total:- | Sqft | [7 empty] | 261.6373
b |  | 8mm thk ply template to instal Light & Speaker with Round cutout according to fixtures | NOS | [6 empty] | 10 | 10
12 | Bison board/ V board panelling | Providing, making and fixing of wall panelling made of 12mm thk branded bison board/ V board paneling on wall including ALU framework finish with all necessary required framing, approved make adhesive and fasteners, cutting/ chamfering/ groove/rounding wherever required, at all height with lead and lift, finishing, cleaning as per design and drawing etc. all complete.
|  | Live Kitchen Window Partation | Sqft |  |  |  | 0 | 0 | 0 |  | 0
|  |  | Sqft |  |  |  | 0 | 0 | 0 |  | 0
|  | Less Window Area | Sqft |  |  |  | 0 | 0 | 0 |  | 0
|  |  | Sqft |  |  |  | 0 | 0 | 0 |  | 0
|  | Total:- | Sqft | [7 empty] | 0
13 | Electrical Cabinet | P/F louver shutter with wooden framework as per design & detail made in fire rated ply with openable shutters with duco finish externally laminate finish internally. Including all necessary required wooden framing, approved make adhesive and fasteners, Lock, cutting/ chamfering/ groove/rounding wherever required, at all height with lead and lift, finishing, cleaning as per design and drawing etc. all complete.
|  | Electrical Panel | Sqft | 3530 | 2440 |  | 11.5814 | 8.0052 |  | 1 | 92.7117
|  |  | Sqft |  |  |  | 0 | 0 |  |  | 0
|  | Total:- | Sqft | [7 empty] | 92.7117
METAL FURNITURE & SCREENS
1 | Show kitchen Glass Partition | P/F 10 mm thk. toughened glass partitions with 20x 40mm MS framework with white powder coating and bottom base wooden partiton height upto 900mm with wooden molding finish with duco paint and all necessary required groove, wooden framing, including glass door with heavy duty floor spring fixing with approved make adhesive and fasteners, cutting/ chamfering/ groove/rounding wherever required, at all height with lead and lift, finishing, cleaning as per design and drawing etc. all complete.
|  | Window | Sqft | 3360 | 1840 |  | 11.0236 | 6.0367 |  | 1 | 66.5468
|  |  | Sqft | 2650 | 1840 |  | 8.6942 | 6.0367 |  | 1 | 52.4848
|  | Total:- | Sqft | [7 empty] | 119.0316
2 | Spice Jar Unit | Providing and fixing M.S frame structure/ rack made out of 20mm X 20mm hollow pipe sections with 20 mm thick plywood shelves finished in laminate. finishing/supporting/cutting/required fixture & fasteners etc. as per design, drawing & as directed by Project Manager etc. complete.
|  | M.S to be finished in Asian paint Coal Mine - 8301 finish matt | Nos | [6 empty] | 1 | 1
Size : 3500 X 200 X 3500(H)
3 | Brass framework on wallpaper | Providing and fixing 20 x 20mm SS box section finished in brass pvd coating framework fixed on walls finishing/supporting/cutting/required fixture & fasteners etc. as per design, drawing & as directed by Project Manager etc complete. | RFT
|  | Verical | RFT | 8550 |  |  | 28.0512 |  |  | 3 | 84.1535
|  | Horizontal | RFT | 2200 |  |  | 7.2178 |  |  | 7 | 50.5249
|  | Total:- | RFT | [7 empty] | 134.6785
4 | MS framework on walls | Providing and fixing M.S frame structure/ rack made out of 20mm X 20mm hollow pipe sections on walls finishing/supporting/cutting/required fixture & fasteners etc. as per design, drawing & as directed by Project Manager etc. complete.
|  | Verical | RFT | 2440 |  |  | 8.0052 |  |  | 10 | 80.0525
|  | Horizontal | RFT | 920 |  |  | 3.0184 |  |  | 9 | 27.1654
|  | Total:- | RFT | [7 empty] | 107.2178
| MS framework on ceiling | Providing and fixing M.S frame structure out of 20mm X 20mm hollow pipe sections framework supported from ceiling finished with black powder coat finishing/supporting/cutting/required fixture & fasteners etc. as per design, drawing & as directed by Project Manager etc. complete.
|  | Bell Ceiling | RFT |  |  |  | 0 |  |  |  | 0
|  |  | RFT |  |  |  | 0 |  |  |  | 0
|  |  | RFT |  |  |  | 0 |  |  |  | 0
|  |  | RFT |  |  |  | 0 |  |  |  | 0
|  | Total:- | RFT | [7 empty] | 0
MISCELLANEOUS - 1
1 | Texture wallpaper | P & F of texture wallpaper as per approval | Sqft | 8550 | 2200 |  | 28.0512 | 7.2178 |  | 1 | 202.4692
|  | Coloum | Sqft |  |  |  | 0 | 0 |  |  | 0
|  | Coloum | Sqft |  |  |  | 0 | 0 |  |  | 0
|  | Window Wall | Sqft | 4670 | 3740 |  | 15.3215 | 12.2703 |  | 1 | 188.0003
|  | Less Window | Sqft | 3100 | 2400 |  | 10.1706 | 7.874 |  | -1 | -80.0835
|  | Coloum | Sqft |  |  |  | 0 | 0 |  |  | 0
|  | Total:- | Sqft | [7 empty] | 310.386
3 | Sheer curtain on metal frame / roller blinds | P & F of linen/ Jute manual folding curtains as per approval
|  | Decorative Wall | Sqft | 1219.2 | 2590.8 | 2590.8 | 4 |  | 8.5 | 2 | 68
|  | Window | Sqft | 914.4 | 1676.4 | 1676.4 | 3 |  | 5.5 | 6 | 99
|  | Total:- | Sqft | [7 empty] | 167

## BOQ-Electrical
Site Name :Copper Chimney Project, Vishal Cinema, Delhi
Work: Electrical Works
Contractor: Stars and Merit Interiors Private Limited
Work order No : DCPL/Vishal Cinema/CC/23-24/CP-202
Bill NO. :RA-4 Bill
SR.NO. | DESCRIPTION | UNIT | As Per Work order |  |  | As per Bill Quantity |  |  |  |  | As per Bill Amount |  |  | Remarlks
|  |  | QTY. | RATE | AMOUNT | Preious Bill | % OF Work | This Bill | Cumulative Bill | % of Works | Preious Bill | This Bill | Cumulative Bill
ELECTRICAL WORKS
1 | Electrical Panel
Design, Manufacture, Supplying, Transport to the site, Receiving, Unloading, Shifting to Sub-Station at various locations, handling, assembling, installation in correct aligned position, grouting with dash fasteners, GI nuts-bolts, testing and commissioning of the following bolted fabricated in compartmentalized (Form-3B construction) conform to IS: 8623/1993, Suitable for 415V, 3Phase, 4 Wire 50 Hz Ac supply, are housed in design from CRCA sheet steel of 2mm thick for frame work and door covers, 3mm thick for gland plate, i/c cleaning & finishing complete, having extensible type bus bars of high conductivity, SMC bus bar supports, the maunfacturer shall be certified from CPRI for short circuit withstand capacity of min. 70kA for 1 Sec., fabrication shall be done in transportable sections and all front and back doors shall be hinged type and earth with frame, Entire panel shall have a common earth bar as specified below at the rear with 2 Nos. earth stud each side, bus bars and control wiring with suitable size of FRLS PVC insulated copper conductor cable, cable alleys, cable gland plates in two half, i/c providing following switch gears :-
The Bus bars will be Copper purity 99.9% / electrolytic grade E91 Aluminium duly sleeved with Helogen Free heat shrink coloured Insulated tube confirming to IEC 60684-3-247 Standard. The powder coating (70-80micron as per IS:13871 for indoor and 100-120 micron for outdoor), include one size higher terminal block in cable alley and interconnecting wires between bus bars and terminals via MCB.
Make: Super control / Shivalic / Zonex
1.1 | MAIN MDB
INCOMER
1 Nos. 160A TP+NL MCCB with display built in thermal magnetic based release (adjustable O/L, adjustable S/C & adjustable E/F) of fault breaking capacity 25KA (Ics=Icu=100%) upto 415V manually operated with extended rotary handle with castle lock for door interlock with Phase spreader & Phase Barriers at both sides. MCCB shall conforming to IS-1397-2 1993 as amended.
METERING, INDICATOR AND RELAYs
Provide 3 Nos. Resin Filled Nylon 66 Casing CTs, Class-1.0 and MFM True RMS type digital with min. features of measurements A,V,Hz and RS-485 port for BMS with class-1.0 accuracy for all outgoing feeder.
1 Set of R,Y,B phase indication lamps with 4Nos. SP HRC fuses as per fault requirement for each Incomer.
Provide 3 Nos indicating lamps for status indication "ON","OFF" , Tripped due to earth fault on each incomer
BUS BARS
200 Amps TP+N, 25kA, 500volts grade busbar chamber of suitable length with Aluminium busbars mount on SMC supports. All interconnections shall be as follows; a). Upto 63A, FRLS PVC insulated copper flexible colour coded wires b). 64Amp to 200Amp Copper Bus-bars and c). 201Amp and above Aluminium Bus-bars , current density of bus-bars shall not be less than 1Amps/sq.mm for Aluminium and 2Amps/sq.mm for copper cross sectional area of Bus Bar.
OUTGOINGS
3 Nos. 63A 4P 'C' CURVE MCB with central overload trip mechanism and flag indication
2 Nos. 40A 4P 'C' CURVE MCB with central overload trip mechanism and flag indication
2 Nos. 32A 4P 'C' CURVE MCB with central overload trip mechanism and flag indication
3 Nos. 32A DP 'C' CURVE MCB with central overload trip mechanism and flag indication
2 Set of 20A,TP MPCB with inbuilt over load relay of 50kA breaking capacity each with 5HP DOL motor starter type ii co-ordination along with TP power contactors (AC3Duty) with inbuilt 2NO + 2NC contact and single phase Ammeter with single CT with selector switch, Red, Green & Yellow Indicating Lamps each with control SP HRC Fuses, Start/Stop Push buttons, Auto/Manual/off selector switch, 230Vac, 0-30Secondand SPP Complete as required, For 2 Nos.2500-4000 CFM Ceiling suspended AHU.
1 Set of 40A,TP MPCB with inbuilt over load relay of 50kA breaking capacity each with 10HP DOL motor starter type ii co-ordination along with TP power contactors (AC3Duty) with inbuilt 2NO + 2NC contact and single phase Ammeter with single CT with selector switch, Red, Green & Yellow Indicating Lamps each with control SP HRC Fuses, Start/Stop Push buttons, Auto/Manual/off selector switch, 230Vac, 0-30Secondand SPP Complete as required, For 1 No. 12000/14000 CFM Floor Standing Air washer.
2 Set of 63A,TP MPCB with inbuilt over load relay of 50kA breaking capacity each with 15 HP Star-Delta motor starter type ii co-ordination along with 3 Nos TP power contactors (AC3Duty) with inbuilt 2NO + 2NC contact and necessary additional potantial free auxiliary contactor, 24 VAC Auxilary transformer (Minimum 100VA upto 5HP and 200VA for above), digital Ammeter with selector switch, Red, Green & Yellow Indicating Lamps each with control SP HRC Fuses, Start/Stop Push buttons, Auto/Manual/off selector switch, Star-Delta timer and On delay Time for delayed automatic restart of air handling unit motor (0-180 Sec) and SPP Complete as required, For 1 No 12000/14000 CFM Floor Standing Wet Scrubber. Provide interlocking in such a manner, when Air-Washer fresh air unit motor make start/stop subsequently the Pump & motor Exhaust Scrubber shall start/stop vice varsa. In case any pump does not start with-in 30 second the motor of respective pump should also not start. (1 No. Dry Scrubber & 1No. Spare)
Note:- | 1. All Starters shall be High Performance Star Delta / DOL Motor Starters as specified (Type 2 Co-ordination chart shall be followed of selected OEM but contactor shall be used one rating higher for IE3 efficiency motors with MPCB/MCCB at 415 V).
Provide 1 Set of 220 VAC/ 24 VDC transformer with 5A output current and 10A Miniature Relay with 4Nos. Changeover Contacts and bridge rectifier controlled by solid state devices like SCR, MOSFET, IGBT etc. for automatically trigger On/Off the motor/ fan in case of receiving single from Fire Alarm Device/ Panel/ CO2 Sensor including necessary wiring
Note:- Fire Supression system work in panel in client scope
| MDB as described above | Set | 1 | 296534 | 296534 | 1 | 1 | 0 | 1 | 100% | 296534 | 0 | 296534
Note: GA & TDS must to be approved by Consultant
4 | LT Cables
Supplying, Laying, testing & commissioning of the following sizes of Power Cables, Solid Aluminum/copper conductor up to 10 sqmm balance stranded conductor, XLPE Insulated, cores laid up, PVC tape / Extruded Inner sheathed , Un. Armour or Armour (Aluminium wire for single core up to 70 sqmm balance Aluminium strip, Galvanized wire for cables up to 2x10 sqmm, 3x10 sqmm, 4x6 sqmm balance all galvanised steel strip), extruded PVC Type ST2 sheathed, FRLS insulation at outer sheath, 1100V grade as per IS 7098(Part 1) 1988
[8 empty] | 0 |  |  | 0 | 0 | 0
4.1 | 3.5C x 95 Sqmm Al. Arm Cable (to be verified as/actual site) | Mtr | 50 | 734 | 36700 | 50 | 0 | -50 | 0 | 0% | 0 | 0 | 0
4.2 | 4C x 25 Sq. mm Al. Arm cable | Mtr | 20 | 323 | 6460 | 20 | 0.7 | -20 | 0 | 0% | 4522 | -4522 | 0 |  | -2000%
4.3 | 4C x 16 Sq. mm Al. Arm cable | Mtr | 30 | 291 | 8730 | 30 | 0.7 | 50 | 80 | 100% | 6111 | 17169 | 23280 |  | 5100%
4.4 | 4C x 10 Sq. mm Cu. Arm cable | Mtr | 40 | 653 | 26120 | 40 | 0.7 | 20 | 60 | 100% | 18284 | 20896 | 39180 |  | 2100%
4.5 | 4C x 4 Sq. mm Cu. Arm cable | Mtr | 45 | 312 | 14040 | 45 | 0.7 | 2 | 47 | 100% | 9828 | 4836 | 14664 |  | 300%
4.6 | 3C x 6 Sq. mm Cu. Arm cable | Mtr | 30 | 363 | 10890 | 30 | 0.7 | 10 | 40 | 100% | 7623 | 6897 | 14520 |  | 1100%
[8 empty] | 0 |  |  | 0 | 0 | 0 |  | 0%
5 | Supply, laying & testing of following size circuit/submain/control wiring along with earth wire including making both end terminations with copper lugs, the following sizes of FRLS Type-D PVC insulated (RoHS compliance) class 2 copper conductor, single core cable confirming to IS:694 in surface/recessed existing ISI Mark Rigid G.I. conduit as on date as required. | [6 empty] | 0 |  |  | 0 | 0 | 0 |  | 0%
5.1 | 4 X 16 sq. mm + 2 X 6 sq. mm earth wire | Metre | 28 | 1302 | 36456 | 28 | 0.7 | -28 | 0 | 0% | 25519.2 | -25519.2 | 0 |  | -2800%
5.2 | 4 X 6 sq. mm + 2 X 6 sq. mm earth wire | Metre | 52 | 655 | 34060 | 52 | 0.7 | -52 | 0 | 0% | 23842 | -23842 | 0 |  | -5200%
5.3 | 4 X 4 sq. mm + 2 X 4 sq. mm earth wire | Metre | 48 | 456 | 21888 | 48 | 0.7 | -48 | 0 | 0% | 15321.6 | -15321.6 | 0 |  | -4800%
5.4 | 2 X 6 sq. mm + 1 X 6 sq. mm earth wire | Metre | 40 | 580 | 23200 | 40 | 0.7 | -40 | 0 | 0% | 16240 | -16240 | 0 |  | -4000%
[6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
6 | Supplying and fixing of following sizes of minimum 2.0/1.6 mm thick ISI Mark Rigid G.I. conduit as per IS:9537 Part-3 latest as on date along with accessories in surface/recess including cutting the wall and making good the same in case of recessed conduit as required. |  |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
6.1 | 20 mm internal dia 1.6 mm thick | Metre | 50 | 165 | 8250 | 50 | 1 | -50 | 0 | 0% | 8250 | -8250 | 0 |  | -5000%
6.2 | 25 mm internal dia 1.6 mm thick | Metre | 75 | 180 | 13500 | 75 | 1 | 225 | 300 | 100% | 13500 | 40500 | 54000 |  | 22600%
[6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
7 | Supplying and fixing of following sizes of Corrugated pattern (min 120gsm) Pre-Galvanized Steel (min Z120GSM) Flexible Conduit as per IS:3480 & BS:731-1 latest as on date, helical wound single lock, LFHSUV resistance against corrosion, certain water tightness, Coupler for tight spot installation at both ends. Temperature Range - 25 deg 'C' to +90 deg 'C' and IP rating: 40, complete with all required accessories in such a way wires should not be viewed and proper clamp on surface at max distance of 300mm completed as required. |  |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
7.1 | 20mm size having ID:17mm, OD:20mm sheet thickness min. 0.25mm | Meter | 70 | 98 | 6860 | 70 | 1 | -38 | 32 | 100% | 6860 | -3724 | 3136 |  | -3700%
7.2 | 25mm size having ID:21mm, OD:24mm sheet thickness min. 0.25mm | Meter | 90 | 89 | 8010 | 90 | 1 | -62 | 28 | 100% | 8010 | -5518 | 2492 |  | -6100%
[6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
8 | Cable End Temination with Gland |  |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
| Supplying and making end termination with brass compression gland and aluminium lugs for following size of PVC insulated and PVC sheathed / XLPE aluminium conductor cable of 1.1 KV grade as required. |  |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
8.1 | 3.5C x 120 Sqmm Al. Arm Cable (to be verified as/actual site) | Nos | 4 | 455 | 1820 | 4 | 0 | 0 | 4 | 100% | 0 | 1820 | 1820 |  | 100%
8.2 | 4C x 25 Sq. mm Al. Arm cable | Nos | 4 | 280 | 1120 | 4 | 0.7 | -4 | 0 | 0% | 784 | -784 | 0 |  | -400%
8.3 | 4C x 16 Sq. mm Al. Arm cable | Nos | 4 | 250 | 1000 | 4 | 0.7 | 0 | 4 | 100% | 700 | 300 | 1000 |  | 100%
8.4 | 4C x 10 Sq. mm Cu. Arm cable | Nos | 8 | 390 | 3120 | 8 | 0.7 | 0 | 8 | 100% | 2184 | 936 | 3120 |  | 100%
8.5 | 4C x 6 Sq. mm Cu. Arm cable | Nos | 4 | 350 | 1400 | 4 | 0.7 | 0 | 4 | 100% | 980 | 420 | 1400 |  | 100%
8.6 | 3C x 6 Sq. mm Cu. Arm cable | Nos | 4 | 312 | 1248 | 4 | 0.7 | 0 | 4 | 100% | 873.6 | 374.4 | 1248 |  | 100%
[6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
9 | Distribution Board - DB |  |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
| Design, fabrication, assembling, wiring, supply, installation, testing & commissioning of (IP:43) horizontal type 7-Segment Distribution boards Three pole and Neutral conforming to IS: 8623-1 & 3, made out of pre-treated and powder coated (minimum 60-80 micron), minimum 1.2mm thick sheet steel double door enclosure (IK 09), 500 V, mount on surface / recess, complete with minimum 3 x 63A tinned copper insulated prong type short links with end cap , common neutral bus bar, common earth bar, din bar, interconnections including earthing stud etc. as required. The cost shall include required minimum 10sqmm copper insulated interconnection wire set, blanking Plates, sticking saddles, cement spill protector, cable ties, circuit identification labels & laminated DB Detail chart as standard or as suggested by Architect/Consultant. (As described below) |  |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
9.1 | 12 WAY (7-SEGMENT) TPN PDB (Make ABB, Legrands, Schneider, L&T) |  |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
| Incomer |  |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
| 1 No. 63A, 4P MCB + 3x63A / 30mA DP RCCB's |  |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
| Outgoing |  |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
| 30 Nos. 6A/10A/16A/20A/32A SP MCB's |  |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
| PDB- 12WAY (7-SEGMENT) TPN DB as described above | Set | 1 | 32456 | 32456 | 1 | 0.9 | 1 | 2 | 100% | 29210.4 | 35701.6 | 64912 |  | 200%
[6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
9.2 | 12 WAY (7-SEGMENT) TPN LPDB (Make ABB, Legrands, Schneider, L&T) |  |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
| Incomer |  |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
| 1 No. 40A, 4P MCB + 3x40A/30mA DP RCCB's |  |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
| Outgoing |  |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
| 30 Nos. 6A/10A/16A/20A/32A SP MCB's |  |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
| LPDB- 12WAY (7-SEGMENT) TPN DB as described above | Set | 1 | 31234 | 31234 | 1 | 0.9 | -1 | 0 | 0% | 28110.6 | -28110.6 | 0 |  | -100%
[6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
10 | Design, fabrication, assembling, wiring, supply, installation, testing & commissioning of (IP:43) Distribution boards Single pole and Neutral conforming to IS: 8623-1 & 3, made out of pre-treated and powder coated (minimum 60-80 micron), minimum 1.2mm thick sheet steel double door enclosure (IK 09), 240 V, mount on surface / recess, complete with minimum 63A tinned copper insulated prong type short links with end cap, neutral bus bar, earth bar, din bar, interconnections including earthing stud etc. as required. The cost shall include required copper insulated wire set, blanking Plates, sticking saddles, cement spill protector, cable ties, circuit identification labels & laminated DB Detail chart as standard or as suggested by Architect/Consultant. (As described below) |  |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
10.1 | 12 WAY SPN UPS DB (Make ABB, Legrands, Schneider, L&T) |  |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
| Incomer |  |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
| 1 No. 32A, DP MCB |  |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
| Outgoing |  |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
| 10 Nos. 6A/10A/16A/20/25A SP MCB's |  |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
| 12 WAY SPN UPSDB as described above | Set | 1 | 11200 | 11200 | 1 | 0.9 | 0 | 1 | 100% | 10080 | 1120 | 11200 |  | 100%
[6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
12 | EARTHING |  |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
12.1 | 25mm x6 mm G.I. Strip for Panel on surface/ existing tray, tapped from nearest earth strip. | Mtr | 150 | 153 | 22950 | 150 | 0.7 | -60 | 90 | 100% | 16065 | -2295 | 13770 |  | -5900%
[6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
12.2 | SINGLE CORE COPPER FLEXIBLE CABLE FOR EARTHING: |  |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
| Supply, laying, connection, testing and commissioning of following sizes of 1.1kV grade Single core FR PVC insulated Single core unsheathed Industrial Flexible Cable confirming to IS:694/1990 and IS: 732 for installation with Flexible Bright annealed copper conductor for 1.1kV voltage grade. It should include both ends terminal joints providing tinned copper terminal lugs, single compression PVC cable glands up to 16 sqmm cable and double compression PVC cable glands for above, insulation tape, effecting terminal connections to the equipment complete as required. |  |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
12.2.1 | 6.0 sq.mm. Cu. Flexible cable | Mtr | 100 | 93 | 9300 | 100 | 0.7 | 120 | 220 | 100% | 6510 | 13950 | 20460 |  | 12100%
[6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
13 | POINT WIRING ( FRLS Wires) |  |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
| Make- Polycab, KEI FRLS Wires Only and Receptacles - Legrands, NorthWest- only |  |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
13.1 | Wiring for SWITCH Controlled light & Fan point with 1.5Sqm FRLS PVC insulated multistrandeded copper conductor 1100 Volt grade wires in GI surface/concealed conduit with accessories including cost of providing saddles etc for surface conduiting and/or cost of cutting and filling chases for recessed conduiting and including the cost of supplying and fixing a 6 Amp 240 Volt grid plate mounted modulr switch with moulded cover plate in zinc chromate passivated MS box, including the cost of running 1.5 sq mm green colour FRLS PVC insulated copper solid conductor wire for loop earthing complete as per specifications and as required, including providing of 2x1.5 sq.mm. +1.5 sq.mm. (E) circuit wiring from DB to switch board. (Cost of MCB not to be included in this item) |  |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
13.1.1 | Primary Point | Nos | 20 | 1935 | 38700 | 20 | 0.9 | -1 | 19 | 100% | 34830 | 1935 | 36765 |  | 0%
13.1.2 | Secondary Point | Nos | 17 | 1020 | 17340 | 17 | 0.9 | 9 | 26 | 100% | 15606 | 10914 | 26520 |  | 1000%
[6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
13.2 | Wiring for MCB Controlled light point with 1.5Sqm FRLS PVC insulated multistrandeded copper conductor 1100 Volt grade wires in GI surface/concealed conduit with accessories including cost of providing saddles etc for surface conduiting and/or cost of cutting and filling chases for recessed conduiting and including the cost of supplying and fixing a 6 Amp 240 Volt grid plate mounted modulr switch with moulded cover plate in zinc chromate passivated MS box, including the cost of running 1.5 sq mm green colour FRLS PVC insulated copper solid conductor wire for loop earthing complete as per specifications and as required, including providing of 2x1.5 sq.mm. +1.5 sq.mm. (E) circuit wiring from DB to switch board. (Cost of MCB not to be included in this item) |  |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
13.2.1 | Primary Point (upto 8 meter long) | Nos | 6 | 1956 | 11736 | 6 | 0.9 | 6 | 12 | 100% | 10562.4 | 12909.6 | 23472 |  | 700%
13.2.2 | Primary Point (above 8 meter-15 meter) | Nos | 6 | 2560 | 15360 | 6 | 0.9 | 13 | 19 | 100% | 13824 | 34816 | 48640 |  | 1400%
13.2.3 | Primary Point (above 15 meter) | Nos |  | 3120 |  | 0 | 0.9 | 6 | 6 | 100% | 0 | 18720 | 18720 |  | 700%
13.2.4 | Secondary Point | Nos | 58 | 1183 | 68614 | 58 | 0.9 | -32 | 26 | 100% | 61752.6 | -30994.6 | 30758 |  | -3100%
[6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
13.3 | Wiring for Primary Power point Wiring for 6 pin 6/ 16 A Power plug point controlled by 16A Switch with 3 x 4 Sq. mm PVC insulated FRLS multi strand copper conductor 1100 Volt grade wires in recessed/surface GI conduit with accessories including cost of providing saddles etc for surface conduiting and/or cost of cutting chases for recessed conduiting, including the cost of providing & fixing Modular 6 pin 6A/ 16 A socket outlet controlled by 16 A switch in zinc chromate passivated MS box, complete as per specification and as required. (raw +ups circuits both) | Points | 12 | 3853 | 46236 | 12 | 0.9 | 20 | 32 | 100% | 41612.4 | 81683.6 | 123296 |  | 2100%
[6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
13.4 | Secondary Looped Power point Wiring on the above circuit for 6 pin 6/ 16 A Power plug point controlled by 16A Switch with 3 x 4 Sq. mm PVC insulated FRLS multi strand copper conductor 1100 Volt grade wires in recessed/surface GI conduit with accessories including cost of providing saddles etc for surface conduiting and/or cost of cutting chases for recessed conduiting, including the cost of providing & fixing of Modular 6 pin 6A/ 16 A socket outlet controlled by 16 A switch in zinc chromate passivated PVC box, complete as per specification and as required. (Looped socket on item above in same circuit) | Points | 10 | 3865 | 38650 | 10 | 0.9 | 0 | 10 | 100% | 34785 | 3865 | 38650 |  | 100%
[6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
13.5 | Power point Wiring for a set of 6 pin 2x6/ 16 A Power plug point controlled by 1x16A Switch with 3 x 4 Sq. mm PVC insulated FRLS multi strand copper conductor 1100 Volt grade wires in recessed/surface GI conduit with accessories including cost of providing saddles etc for surface conduiting and/or cost of cutting chases for recessed conduiting, including the cost of providing & fixing Modular 6 pin 2 nos.6A/ 16 A socket outlet controlled by 1 no. 16 A switch in zinc chromate passivated PVC box, complete as per specification and as required. (raw +ups circuits both) | Points | 8 | 3655 | 29240 | 8 | 0.9 | -8 | 0 | 0% | 26316 | -26316 | 0 |  | -800%
[6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
13.6 | Wiring for 5 pin 6A Light plug point controlled by 6A Switch with 3 x 2.5 Sq. mm PVC insulated FRLS multi strand copper conductor 1100 Volt grade wires in recessed/surface GI conduit with accessories including cost of providing saddles etc for surface conduiting and/or cost of cutting chases for recessed conduiting, including the cost of providing & fixing Modular 5 pin 6A socket outlet controlled by 6 A switch in zinc chromate passivated PVC box, complete as per specification and as required. (raw +ups circuits both) | Points | 8 | 2130 | 17040 | 8 | 0.9 | 14 | 22 | 100% | 15336 | 31524 | 46860 |  | 1500%
[6 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0%
13.7 | Wiring for single phase 20A, 230 V Industrial Socket & Plug Top in Moulded Plastic Box (IP55) controlled by 20A SP MCB with 3 x 4 Sq. mm PVC insulated FRLS multi strand copper conductor 1100 Volt grade wires in recessed/surface GI conduit with accessories including cost of saddles etc for surface conduiting and/or cost of cutting chases for recessed conduiting, including providing of JB at Eqpt. Location, complete as per specification and as required. (Make ABB, Legrands, Schneider) | Each | 20 | 3455 | 69100 | 20 | 0.9 | -6 | 14 | 100% | 62190 | -13820 | 48370 |  | -500%
[6 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0%
13.8 | Wiring for single phase 32A, 230 V Industrial Socket & Plug Top in Moulded Plastic Box (IP55) controlled by 32A DP MCB with 3 x 6 Sq. mm PVC insulated FRLS multi strand copper conductor 1100 Volt grade wires in recessed/surface GI conduit with accessories including cost of saddles etc for surface conduiting and/or cost of cutting chases for recessed conduiting, including providing of JB at Eqpt. Location, complete as per specification and as required. (Make ABB, Legrands, Schneider) | Each | 5 | 3983 | 19915 | 5 | 0.9 | 1 | 6 | 100% | 17923.5 | 5974.5 | 23898 |  | 200%
[6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
13.9 | Wiring for three phase 20A, 400 V Industrial Socket & Plug Top in Moulded Plastic Box (IP55) controlled by 20A FP MCB with 4 x 4 Sq. mm PVC insulated FRLS multi strand copper conductor 1100 Volt grade wires in recessed/surface GI conduit with accessories including cost of saddles etc for surface conduiting and/or cost of cutting chases for recessed conduiting, including providing of JB at Eqpt. Location, complete as per specification and as required. (Make ABB, Legrands, Schneider) | Each | 4 | 4356 | 17424 | 4 | 0.9 | -2 | 2 | 100% | 15681.6 | -6969.6 | 8712 |  | -100%
[6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
13.1 | Wiring for three phase 32A, 400 V Industrial Socket & Plug Top in Moulded Plastic Box (IP55) controlled by 32A FP MCB with 4 x 6 Sq. mm PVC insulated FRLS multi strand copper conductor 1100 Volt grade wires in recessed/surface GI conduit with accessories including cost of saddles etc for surface conduiting and/or cost of cutting chases for recessed conduiting, including providing of JB at Eqpt. Location, complete as per specification and as required. (Make ABB, Legrands, Schneider) | Each | 4 | 4435 | 17740 | 4 | 0.9 | -3 | 1 | 100% | 15966 | -11531 | 4435 |  | -200%
[6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
13.11 | Wiring for three phase 32A, 400 V Industrial Socket & Plug Top in Moulded Plastic Box (IP55) controlled by 32A FP MCB with 4 x 10 Sq. mm PVC insulated FRLS multi strand copper conductor 1100 Volt grade wires in recessed/surface GI conduit with accessories including cost of saddles etc for surface conduiting and/or cost of cutting chases for recessed conduiting, including providing of JB at Eqpt. Location, complete as per specification and as required. (Make ABB, Legrands, Schneider) | Each | 4 | 5434 | 21736 | 4 | 0.9 | -4 | 0 | 0% | 19562.4 | -19562.4 | 0 |  | -400%
[6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
13.12 | Wiring for three phase 32A, FP Juntion Box (IP55) with 4 x 6 Sq. mm PVC insulated FRLS multi strand copper conductor 1100 Volt grade wires in recessed/surface GI conduit with accessories including cost of saddles etc for surface conduiting and/or cost of cutting chases for recessed conduiting, including providing of JB at Eqpt. Location, complete as per specification and as required. (without any MCB) | Each | 1 | 4356 | 4356 | 1 | 0.9 | -1 | 0 | 0% | 3920.4 | -3920.4 | 0 |  | -100%
| Extra for providing & fixing of 32A FP MCB (IP55) near by the above item. (Make ABB, Legrands, Schneider) | Each | 1 | 569 | 569 | 1 | 0.9 | -1 | 0 | 0% | 512.1 | -512.1 | 0 |  | -100%
[6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
13.13 | Wiring for three phase 63A, FP Juntion Box (IP55) with 4 x 10 Sq. mm PVC insulated FRLS multi strand copper conductor 1100 Volt grade wires in recessed/surface GI conduit with accessories including cost of saddles etc for surface conduiting and/or cost of cutting chases for recessed conduiting, including providing of JB at Eqpt. Location, complete as per specification and as required. (without any MCB) | Each | 1 | 6534 | 6534 | 1 | 0.9 | 4 | 5 | 100% | 5880.6 | 26789.4 | 32670 |  | 500%
13.14 | Extra for providing & fixing of 63A FP MCB (IP55) near by the above item. (Make ABB, Legrands, Schneider) | Each | 1 | 1650 | 1650 | 1 | 0.9 | -1 | 0 | 0% | 1485 | -1485 | 0 |  | -100%
[6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
13.15 | ELECTRICAL HANGING BOX - Powder Coated MS Box with Adjustable Height Provision | Points | 0 | 1923 |  | 0 | 0 | 26 | 26 | 100% | 0 | 49998 | 49998 |  | 2700%
[6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
13.16 | USB port for mobile chargeing 1 module | Points | 20 | 230 | 4600 | 20 | 0.7 | -20 | 0 | 0% | 3220 | -3220 | 0 |  | -2000%
[6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
14 | LIGHTING FIXTURES |  |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
| Installation, testing, & commissioning of following type of Lighting Fixtures including all fixing hardwares complete as required Make - Philips, Wipro, Havells, Futura |  |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
14.1 | LED Panel 2x2 RC380B LED42S-6500 G5 L60W60 or equivalent | Nos. | 0 | 439 |  | 0 | 0.7 | 13 | 13 | 100% | 0 | 5707 | 5707 |  | 1400%
[6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
14.2 | SELF CONTAINED RECHARGEABLE EMERGENCY LED LIGHT 30W (3 Hours Backup, IP 65, Weatherproof) Makes: Prolite, Philips, Futura | Nos. | 4 | 3856 | 15424 | 4 | 0.7 | -3 | 1 | 100% | 10796.8 | -6940.8 | 3856 |  | -200%
[6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
14.3 | Fixing of Bracket Light complete with all necessary hardwares for fixing as required | Nos. | 0 | 655 | 0 | 0 | 0 | 14 | 14 | 100% | 0 | 9170 | 9170 |  | 1500%
[6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
14.4 | Fixing of Ceiling Light complete on false ceiling with all necessary hardwares for fixing as required | Nos. | 0 | 455 | 0 | 0 | 0 | 66 | 66 | 100% | 0 | 30030 | 30030 |  | 6700%
[6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
14.5 | Fixing of Chandelier & Pendant Light complete on false ceiling with all necessary hardwares for fixing as required | Nos. | 0 | 2133 | 0 | 0 | 0 | 12 | 12 | 100% | 0 | 25596 | 25596 |  | 1300%
[6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
14.6 | Fixing of LED stripswith driver in Cove complete with all necessary hardwares for fixing as required | Meter | 85 | 35 | 2975 | 85 | 0.7 | -65 | 20 | 100% | 2082.5 | -1382.5 | 700 |  | -6400%
[8 empty] | 0 |  |  | 0 | 0 | 0 |  | 0%
| Note:- The Supply of light fixtures will be in client's scope. | [6 empty] | 0 |  |  | 0 | 0 | 0 |  | 0%
[8 empty] | 0 |  |  | 0 | 0 | 0 |  | 0%
15 | Tel. & Data System | [6 empty] | 0 |  |  | 0 | 0 | 0 |  | 0%
15.1 | Supplying and drawing of CAT 6A UTP wire in existing GI conduit for Tel. /Data outlets | RM | 100 | 58 | 5800 | 100 | 0.9 | 318.8 | 418.8 | 100% | 5220 | 19070.4 | 24290.4 |  | 31980%
[6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
15.2 | Supplying and laying of 20 mm dia GI conduit for Tel./ Data system | RM | 30 | 165 | 4950 | 30 | 0.9 | 388.8 | 418.8 | 100% | 4455 | 64647 | 69102 |  | 38980%
[6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
15.3 | Providing & Fixing of RJ11 Outlet complete with G.I. Box Modular base & Cover Plate | Nos. | 8 | 655 | 5240 | 8 | 0.9 | -8 | 0 | 0% | 4716 | -4716 | 0 |  | -800%
[6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
15.4 | Providing & Fixing of RJ45 Outlet complete with G.I. Box Modular base & Cover Plate | Nos. | 16 | 712 | 11392 | 16 | 0.9 | -16 | 0 | 0% | 10252.8 | -10252.8 | 0 |  | -1600%
[6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
16 | Supply, Installation, Testing & Commissioning of 6 KVA UPS complete with sealed Maintenace free 12 V Battery for 30 Minutes back-up. Make: Socemec / Labotek / APC | Set | 1 | 142356 | 142356 | 1 | 0.9 | 0 | 1 | 100% | 128120.4 | 14235.6 | 142356 |  | 100%
[6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
17 | Design, manufacture , supply and fixing in position the cable trays of the following sizes for supporting 1.1 KV grade armoured/unarmoured aluminium /copper conductor cables. Fabricate the cable trays from perforated 1.6mm thick M.S. CRCA sheet duly galvanised with expansion coupler plates duly galvanised, with bolts, washer and nuts. Knock out holes for cable connections as per approved design. The tray should comply with the specification of NEC (National Electric Codes) and NEMA (National Electric Manufacturers Association). The steel should be as per IS:226 and galvanising as per IS :2629/BS 729/ASTM 123. The rate shall also include for supporting steel , fish plates , fixing accessories , nuts bolts, supporting down rods , dash fastener, cutting the RCC etc. complete as required. (the horizontal and vertical bends, T's should be factory fabricated and the rate should include for the same) |  |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
17.1 | 100 mm wide x 40 mm x 1.6 mm thick | Mtr | 50 | 623 | 31150 | 50 | 1 | 30.5 | 80.5 | 100% | 31150 | 19001.5 | 50151.5 |  | 3150%
17.2 | 150 mm wide x 40 mm x 1.6 mm thick | Mtr | 50 | 653 | 32650 | 50 | 1 | -50 | 0 | 0% | 32650 | -32650 | 0 |  | -5000%
[8 empty] | 0 |  |  | 0 | 0 | 0 |  | 0%
| Total For Electrical System | [6 empty] | 0 |  |  | 0 | 0 | 0 |  | 0%
[8 empty] | 0 |  |  | 0 | 0 | 0 |  | 0%
| ELV System | [6 empty] | 0 |  |  | 0 | 0 | 0 |  | 0%
1 | FIRE ALARM SYSTEM | [6 empty] | 0 |  |  | 0 | 0 | 0 |  | 0%
| Make- Agni, Edwards, Revel | [6 empty] | 0 |  |  | 0 | 0 | 0 |  | 0%
1.1 | Fire Alarm Panel - 2 Zone - Addressable Type complete with 4 hrs. battery back-up as required. | Nos. | 1 | 125000 | 125000 | 1 | 1 | 0 | 1 | 100% | 125000 | 0 | 125000 |  | 100%
[6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
1.2 | Supplying & laying of 2x1.5 sqmm fire survival armoured cable, 600/1000V rated with annealed copper conductor having glass mica fire barrier tape covered by an extruded layer of Cross Linkable Ethylene Propylene Rubber (EPR) insulation and LSZH inner bedding, steel wire armouring & LSZH outer sheath complete as required. | Mtrs | 120 | 185 | 22200 | 120 | 1 | 140.7 | 260.7 | 100% | 22200 | 26029.5 | 48229.5 |  | 14170%
[6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
1.3 | Supply, Installation, Testing & Commissioning of Photo-Thermal (Multi-sensor) detector with sensing chamber , 12/24 volt DC twin visual alarm indicater blink in stand by and steady in alarm (LED) camplete in al respect with Base as required | Nos | 10 | 3183 | 31830 | 10 | 1 | 4 | 14 | 100% | 31830 | 12732 | 44562 |  | 500%
[6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
1.4 | Supply, Installation, Testing & Commissioning of Response Indicator complete with Box as required | Nos | 3 | 355 | 1065 | 3 | 1 | 2 | 5 | 100% | 1065 | 710 | 1775 |  | 300%
[6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
1.5 | Supply, installation, testing and commissioning of Siren cum Strobe mount on surface / wall / false ceiling complete as required. | Nos | 2 | 2856 | 5712 | 2 | 1 | 0 | 2 | 100% | 5712 | 0 | 5712 |  | 100%
[6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
1.6 | Supply, Installation, Testing & Commissioning of Manual Call Point Break Glass Type housed in sheet Steel/ Polymer housing surface / Recess including Making connection with wire complete in all respect as per specification The manual call should have indicator which should blink in stand by condition. | Nos | 2 | 2025 | 4050 | 2 | 1 | 0 | 2 | 100% | 4050 | 0 | 4050 |  | 100%
[8 empty] | 0 |  |  | 0 | 0 | 0 |  | 0%
2 | PA SYSTEM | [6 empty] | 0 |  |  | 0 | 0 | 0 |  | 0%
| Make- Agni, Edwards, Revel | [6 empty] | 0 |  |  | 0 | 0 | 0 |  | 0%
2.1 | installing, testing and commissioning of 6W Ceiling Speaker with max SPL1M/1W 96dB . Frequency response of 80Hz-20KHz with a dispersion angle of 160 deg. The speaker should have tappings at 6W/3W/1.5W (Supply not in our scope only labour charge ) | [6 empty] | 0 |  |  | 0 | 0 | 0 |  | 0%
| Ceiling Mounted Speakers | Nos. | 8 | 2100 | 16800 | 8 | 1 | -2 | 6 | 100% | 16800 | -4200 | 12600 |  | -100%
[6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
2.2 | Supplying and drawing of Fire Retardant PVC insulated copper conductor cable in the surface / recessed PVC conduit of following pairs, cores and size including connections and interconnections etc. as required. speaker cable Single pair, 2-core, 1.5 sqmm |  |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
2.2.1 | speaker cable Single pair, 2-core, 1.5 sqmm in existing GI conduit | RM | 80 | 57 | 4560 | 80 | 1 | -30 | 50 | 100% | 4560 | -1710 | 2850 |  | -2900%
2.2.2 | Supplying and laying of 20 mm dia GI conduit for Speaker cable | RM | 80 | 165 | 13200 | 80 | 1 | -37.5 | 42.5 | 100% | 13200 | -6187.5 | 7012.5 |  | -3650%
[6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
2.3 | installing, testing and commissioning of 1X100W Class-D Amplifier with 2 independent channels and can provide automatic re-settable overcurrent, overload, overheating, overvoltage, under-voltage and DC protection. (Supply not in our scope only labour charge ) | Nos. | 1 | 2133 | 2133 | 1 | 0 | 0 | 1 | 100% | 0 | 2133 | 2133 |  | 100%
[6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
3 | CCTV System |  |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
3.1 | Supplying and drawing of CAT 6 UTP wire in existing GI conduit | RM | 250 | 58 | 14500 | 250 | 1 | 127.2 | 377.2 | 100% | 14500 | 7377.6 | 21877.6 |  | 12820%
[6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
3.2 | Supplying and laying of 25 mm dia GI conduit for CCTV Camera | RM | 125 | 180 | 22500 | 125 | 1 | 220.04 | 345.04 | 100% | 22500 | 39607.2 | 62107.2 |  | 22104%
[6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0%
3.3 | Installation, Testing and Commissioning of 2MP x IR Fixed lens Turret Camera, 1920 X 1080 at 25/30fps,1/2.9"CMOS, Fixed lens 2.8mm,H.265, H.264 compression,Smart Compression, internal 850nm IR Range 30 meter or better,Built in Microphone, 100dB true WDR as per IEC62676, Triple streaming,Motion Detection,Camera sabotage,IP66,IK10 Housing,Camera shall support SD card 512GB or better ,ONVIF profile S,G, & T,NDAA,UL/cUL Listed, UL 60950-22, CE, FCC. Approved Makes- Axis P series/ Pelco Value Series / Avigilon H5 series/ Mobotix | Nos | 16 | 2865 | 45840 | 16 | 1 | -16 | 0 | 0% | 45840 | -45840 | 0 |  | -1600%
[6 empty] | 0 |  |  |  |  | 0 | 0 | 0
| Sub - Total ( FAS & PA System + CCTV System) | [9 empty] | 0 | 0 | 0
| TOTAL COST OF ELECTRICAL |  |  |  | 1676413 | [5 empty] | 1493608.9 | 333758.8 | 1827367.7

## Elec Mb
Measurement Book of Electrical Work Copper Chimney Rajouri Garden
S.No. | Items | Unit | Measurement (m)
|  |  | L | B | H | NO | TOTAL
1 | Electrical Panel
| Design, Manufacture, Supplying, Transport to the site, Receiving, Unloading, Shifting to Sub-Station at various locations, handling, assembling, installation in correct aligned position, grouting with dash fasteners, GI nuts-bolts, testing and commissioning of the following bolted fabricated in compartmentalized (Form-3B construction) conform to IS: 8623/1993, Suitable for 415V, 3Phase, 4 Wire 50 Hz Ac supply, are housed in design from CRCA sheet steel of 2mm thick for frame work and door covers, 3mm thick for gland plate, i/c cleaning & finishing complete, having extensible type bus bars of high conductivity, SMC bus bar supports, the maunfacturer shall be certified from CPRI for short circuit withstand capacity of min. 70kA for 1 Sec., fabrication shall be done in transportable sections and all front and back doors shall be hinged type and earth with frame, Entire panel shall have a common earth bar as specified below at the rear with 2 Nos. earth stud each side, bus bars and control wiring with suitable size of FRLS PVC insulated copper conductor cable, cable alleys, cable gland plates in two half, i/c providing following switch gears :- | Set |  |  |  | 1 | 1
4 | LT Cables
4.1 | 3.5C x 95 Sqmm Al. Arm Cable (to be verified as/actual site) | Mtr | 0 |  |  |  | 0
4.2 | 4C x 25 Sq. mm Al. Arm cable | Mtr | 0 |  |  |  | 0
4.3 | 4C x 16 Sq. mm Al. Arm cable | Mtr
| Lobby Power Db | Mtr | 22 |  |  |  | 22
| Fresh air | Mtr | 20 |  |  |  | 20
| scrubber | Mtr | 22 |  |  |  | 22
| Kitchen Power Db | Mtr | 8 |  |  |  | 8
| Kitchen Dish Washer | Mtr | 10 |  |  |  | 10
| Total:- | Rmt |  |  |  |  | 80 | 80
4.4 | 4C x 10 Sq. mm Cu. Arm cable | Mtr
| Ups For Store Room | Mtr | 60 |  |  |  | 60
0
| Total:- | Rmt |  |  |  |  | 60
4.5 | 4C x 4 Sq. mm Cu. Arm cable | Mtr
| Bar Counter Metal Clad1 | Mtr | 28 |  |  |  | 28
| Bar Counter Metal Clad2 | Mtr | 26 |  |  |  | 26
| Ahu1 | Mtr | 26.3 |  |  |  | 26.3
| Ahu2 | Mtr | 30 |  |  |  | 30
| Kitchen hood Side | Mtr | 21.5 |  |  |  | 21.5
0
| Total:- | Rmt |  |  |  |  | 47 | 47
4.6 | 3C x 6 Sq. mm Cu. Arm cable | Mtr
| Lobby UPS | Mtr | 10 |  |  |  | 10
| Fresh air Pump Looping | Mtr | 3.5 |  |  |  | 3.5
| Ups In | Mtr | 8.9 |  |  |  | 8.9
| RO | Mtr | 19.5 |  |  |  | 19.5
|  | Mtr |  |  |  |  | 0
| Total:- | [5 empty] | 40 | 40
5 | Supply, laying & testing of following size circuit/submain/control wiring along with earth wire including making both end terminations with copper lugs, the following sizes of FRLS Type-D PVC insulated (RoHS compliance) class 2 copper conductor, single core cable confirming to IS:694 in surface/recessed existing ISI Mark Rigid G.I. conduit as on date as required.
5.1 | 4 X 16 sq. mm + 2 X 6 sq. mm earth wire | Metre | 0 |  |  |  | 0
5.2 | 4 X 6 sq. mm + 2 X 6 sq. mm earth wire | Metre | 0 |  |  |  | 0
5.3 | 4 X 4 sq. mm + 2 X 4 sq. mm earth wire | Metre | 0 |  |  |  | 0
5.4 | 2 X 6 sq. mm + 1 X 6 sq. mm earth wire | Metre | 0 |  |  |  | 0
6 | Supplying and fixing of following sizes of minimum 2.0/1.6 mm thick ISI Mark Rigid G.I. conduit as per IS:9537 Part-3 latest as on date along with accessories in surface/recess including cutting the wall and making good the same in case of recessed conduit as required.
6.1 | 20 mm internal dia 1.6 mm thick | Metre | 0 |  |  |  | 0
6.2 | 25 mm internal dia 1.6 mm thick | Metre
| GI conduit | Mtr | 300 |  |  |  | 300
|  | Mtr |  |  |  |  | 0
| Total:- | [5 empty] | 300
7 | Supplying and fixing of following sizes of Corrugated pattern (min 120gsm) Pre-Galvanized Steel (min Z120GSM) Flexible Conduit as per IS:3480 & BS:731-1 latest as on date, helical wound single lock, LFHSUV resistance against corrosion, certain water tightness, Coupler for tight spot installation at both ends. Temperature Range - 25 deg 'C' to +90 deg 'C' and IP rating: 40, complete with all required accessories in such a way wires should not be viewed and proper clamp on surface at max distance of 300mm completed as required.
7.1 | 20mm size having ID:17mm, OD:20mm sheet thickness min. 0.25mm | Meter | 32 |  |  |  | 32
7.2 | 25mm size having ID:21mm, OD:24mm sheet thickness min. 0.25mm | Meter | 28 |  |  |  | 28
8 | Cable End Temination with Gland
Supplying and making end termination with brass compression gland and aluminium lugs for following size of PVC insulated and PVC sheathed / XLPE aluminium conductor cable of 1.1 KV grade as required.
8.1 | 3.5C x 120 Sqmm Al. Arm Cable (to be verified as/actual site) | Nos | 4 |  |  |  | 4
8.2 | 4C x 25 Sq. mm Al. Arm cable | Nos |  |  |  |  | 0
8.3 | 4C x 16 Sq. mm Al. Arm cable | Nos | 4 |  |  |  | 4
8.4 | 4C x 10 Sq. mm Cu. Arm cable | Nos | 8 |  |  |  | 8
8.5 | 4C x 6 Sq. mm Cu. Arm cable | Nos | 4 |  |  |  | 4
8.6 | 3C x 6 Sq. mm Cu. Arm cable | Nos | 4 |  |  |  | 4
9 | Distribution Board - DB
9.1 | 12 WAY (7-SEGMENT) TPN PDB (Make ABB, Legrands, Schneider, L&T)
Incomer
1 No. 63A, 4P MCB + 3x63A / 30mA DP RCCB's
Outgoing
30 Nos. 6A/10A/16A/20A/32A SP MCB's
| PDB- 12WAY (7-SEGMENT) TPN DB as described above | Set | 2 |  |  |  | 2
9.2 | 12 WAY (7-SEGMENT) TPN LPDB (Make ABB, Legrands, Schneider, L&T)
Incomer
1 No. 40A, 4P MCB + 3x40A/30mA DP RCCB's
Outgoing
30 Nos. 6A/10A/16A/20A/32A SP MCB's
| LPDB- 12WAY (7-SEGMENT) TPN DB as described above | Set |  |  |  |  | 0
10 | Design, fabrication, assembling, wiring, supply, installation, testing & commissioning of (IP:43) Distribution boards
10.1 | 12 WAY SPN UPS DB (Make ABB, Legrands, Schneider, L&T)
Incomer
1 No. 32A, DP MCB
Outgoing
10 Nos. 6A/10A/16A/20/25A SP MCB's
| 12 WAY SPN UPSDB as described above | Set | 1 |  |  |  | 1
12 | EARTHING
12.1 | 25mm x6 mm G.I. Strip for Panel on surface/ existing tray, tapped from nearest earth strip. | Mtr | 90 |  |  |  | 90
12.2 | SINGLE CORE COPPER FLEXIBLE CABLE FOR EARTHING:
12.2.1 | 6.0 sq.mm. Cu. Flexible cable | Mtr | 220 |  |  |  | 220
13 | POINT WIRING ( FRLS Wires)
Make- Polycab, KEI FRLS Wires Only and Receptacles - Legrands, NorthWest- only
13.1 | Wiring for SWITCH Controlled light & Fan point with 1.5Sqm FRLS PVC insulated multistrandeded copper conductor 1100 Volt grade wires in GI surface/concealed conduit with accessories including cost of providing saddles etc for surface conduiting and/or cost of cutting and filling chases for recessed conduiting and including the cost of supplying and fixing a 6 Amp 240 Volt grid plate mounted modulr switch with moulded cover plate in zinc chromate passivated MS box, including the cost of running 1.5 sq mm green colour FRLS PVC insulated copper solid conductor wire for loop earthing complete as per specifications and as required, including providing of 2x1.5 sq.mm. +1.5 sq.mm. (E) circuit wiring from DB to switch board. (Cost of MCB not to be included in this item)
13.1.1 | Primary Point | Nos | 19 |  |  |  | 19
13.1.2 | Secondary Point | Nos | 26 |  |  |  | 26
13.2 | Wiring for MCB Controlled light point with 1.5Sqm FRLS PVC insulated multistrandeded copper conductor 1100 Volt grade wires in GI surface/concealed conduit with accessories including cost of providing saddles etc for surface conduiting and/or cost of cutting and filling chases for recessed conduiting and including the cost of supplying and fixing a 6 Amp 240 Volt grid plate mounted modulr switch with moulded cover plate in zinc chromate passivated MS box, including the cost of running 1.5 sq mm green colour FRLS PVC insulated copper solid conductor wire for loop earthing complete as per specifications and as required, including providing of 2x1.5 sq.mm. +1.5 sq.mm. (E) circuit wiring from DB to switch board. (Cost of MCB not to be included in this item)
13.2.1 | Primary Point (upto 8 meter long) | Nos | 12 |  |  |  | 12
13.2.2 | Primary Point (above 8 meter-15 meter) | Nos | 19 |  |  |  | 19
13.2.3 | Primary Point (above 15 meter) | Nos | 6 |  |  |  | 6
13.2.4 | Secondary Point | Nos | 26 |  |  |  | 26
13.3 | Wiring for Primary Power point Wiring for 6 pin 6/ 16 A Power plug point controlled by 16A Switch with 3 x 4 Sq. mm PVC insulated FRLS multi strand copper conductor 1100 Volt grade wires in recessed/surface GI conduit with accessories including cost of providing saddles etc for surface conduiting and/or cost of cutting chases for recessed conduiting, including the cost of providing & fixing Modular 6 pin 6A/ 16 A socket outlet controlled by 16 A switch in zinc chromate passivated MS box, complete as per specification and as required. (raw +ups circuits both) | Points | 32 |  |  |  | 32
13.4 | Secondary Looped Power point Wiring on the above circuit for 6 pin 6/ 16 A Power plug point controlled by 16A Switch with 3 x 4 Sq. mm PVC insulated FRLS multi strand copper conductor 1100 Volt grade wires in recessed/surface GI conduit with accessories including cost of providing saddles etc for surface conduiting and/or cost of cutting chases for recessed conduiting, including the cost of providing & fixing of Modular 6 pin 6A/ 16 A socket outlet controlled by 16 A switch in zinc chromate passivated PVC box, complete as per specification and as required. (Looped socket on item above in same circuit) | Points | 10 |  |  |  | 10
13.5 | Power point Wiring for a set of 6 pin 2x6/ 16 A Power plug point controlled by 1x16A Switch with 3 x 4 Sq. mm PVC insulated FRLS multi strand copper conductor 1100 Volt grade wires in recessed/surface GI conduit with accessories including cost of providing saddles etc for surface conduiting and/or cost of cutting chases for recessed conduiting, including the cost of providing & fixing Modular 6 pin 2 nos.6A/ 16 A socket outlet controlled by 1 no. 16 A switch in zinc chromate passivated PVC box, complete as per specification and as required. (raw +ups circuits both) | Points |  |  |  |  | 0
13.6 | Wiring for 5 pin 6A Light plug point controlled by 6A Switch with 3 x 2.5 Sq. mm PVC insulated FRLS multi strand copper conductor 1100 Volt grade wires in recessed/surface GI conduit with accessories including cost of providing saddles etc for surface conduiting and/or cost of cutting chases for recessed conduiting, including the cost of providing & fixing Modular 5 pin 6A socket outlet controlled by 6 A switch in zinc chromate passivated PVC box, complete as per specification and as required. (raw +ups circuits both) | Points | 22 |  |  |  | 22
13.7 | Wiring for single phase 20A, 230 V Industrial Socket & Plug Top in Moulded Plastic Box (IP55) controlled by 20A SP MCB with 3 x 4 Sq. mm PVC insulated FRLS multi strand copper conductor 1100 Volt grade wires in recessed/surface GI conduit with accessories including cost of saddles etc for surface conduiting and/or cost of cutting chases for recessed conduiting, including providing of JB at Eqpt. Location, complete as per specification and as required. (Make ABB, Legrands, Schneider) | Each | 14 |  |  |  | 14
13.8 | Wiring for single phase 32A, 230 V Industrial Socket & Plug Top in Moulded Plastic Box (IP55) controlled by 32A DP MCB with 3 x 6 Sq. mm PVC insulated FRLS multi strand copper conductor 1100 Volt grade wires in recessed/surface GI conduit with accessories including cost of saddles etc for surface conduiting and/or cost of cutting chases for recessed conduiting, including providing of JB at Eqpt. Location, complete as per specification and as required. (Make ABB, Legrands, Schneider) | Each | 6 |  |  |  | 6
13.9 | Wiring for three phase 20A, 400 V Industrial Socket & Plug Top in Moulded Plastic Box (IP55) controlled by 20A FP MCB with 4 x 4 Sq. mm PVC insulated FRLS multi strand copper conductor 1100 Volt grade wires in recessed/surface GI conduit with accessories including cost of saddles etc for surface conduiting and/or cost of cutting chases for recessed conduiting, including providing of JB at Eqpt. Location, complete as per specification and as required. (Make ABB, Legrands, Schneider) | Each | 2 |  |  |  | 2
13.1 | Wiring for three phase 32A, 400 V Industrial Socket & Plug Top in Moulded Plastic Box (IP55) controlled by 32A FP MCB with 4 x 6 Sq. mm PVC insulated FRLS multi strand copper conductor 1100 Volt grade wires in recessed/surface GI conduit with accessories including cost of saddles etc for surface conduiting and/or cost of cutting chases for recessed conduiting, including providing of JB at Eqpt. Location, complete as per specification and as required. (Make ABB, Legrands, Schneider) | Each | 1 |  |  |  | 1
13.11 | Wiring for three phase 32A, 400 V Industrial Socket & Plug Top in Moulded Plastic Box (IP55) controlled by 32A FP MCB with 4 x 10 Sq. mm PVC insulated FRLS multi strand copper conductor 1100 Volt grade wires in recessed/surface GI conduit with accessories including cost of saddles etc for surface conduiting and/or cost of cutting chases for recessed conduiting, including providing of JB at Eqpt. Location, complete as per specification and as required. (Make ABB, Legrands, Schneider) | Each
13.12 | Wiring for three phase 32A, FP Juntion Box (IP55) with 4 x 6 Sq. mm PVC insulated FRLS multi strand copper conductor 1100 Volt grade wires in recessed/surface GI conduit with accessories including cost of saddles etc for surface conduiting and/or cost of cutting chases for recessed conduiting, including providing of JB at Eqpt. Location, complete as per specification and as required. (without any MCB) | Each
| Extra for providing & fixing of 32A FP MCB (IP55) near by the above item. (Make ABB, Legrands, Schneider) | Each
13.13 | Wiring for three phase 63A, FP Juntion Box (IP55) with 4 x 10 Sq. mm PVC insulated FRLS multi strand copper conductor 1100 Volt grade wires in recessed/surface GI conduit with accessories including cost of saddles etc for surface conduiting and/or cost of cutting chases for recessed conduiting, including providing of JB at Eqpt. Location, complete as per specification and as required. (without any MCB) | Each | 5 |  |  |  | 5
13.14 | Extra for providing & fixing of 63A FP MCB (IP55) near by the above item. (Make ABB, Legrands, Schneider) | Each | 0
13.15 | ELECTRICAL HANGING BOX - Powder Coated MS Box with Adjustable Height Provision | Points | 26 |  |  |  | 26
13.16 | USB port for mobile chargeing 1 module | Points
14 | LIGHTING FIXTURES
Installation, testing, & commissioning of following type of Lighting Fixtures including all fixing hardwares complete as required Make - Philips, Wipro, Havells, Futura
14.1 | LED Panel 2x2 RC380B LED42S-6500 G5 L60W60 or equivalent | Nos. | 13 |  |  |  | 13
14.2 | SELF CONTAINED RECHARGEABLE EMERGENCY LED LIGHT 30W (3 Hours Backup, IP 65, Weatherproof) Makes: Prolite, Philips, Futura | Nos. | 1 |  |  |  | 1
14.3 | Fixing of Bracket Light complete with all necessary hardwares for fixing as required | Nos. | 14 |  |  |  | 14
14.4 | Fixing of Ceiling Light complete on false ceiling with all necessary hardwares for fixing as required | Nos. | 66 |  |  |  | 66
14.5 | Fixing of Chandelier & Pendant Light complete on false ceiling with all necessary hardwares for fixing as required | Nos. | 12 |  |  |  | 12
14.6 | Fixing of LED stripswith driver in Cove complete with all necessary hardwares for fixing as required | Meter | 20 |  |  |  | 20
Note:- The Supply of light fixtures will be in client's scope.
15 | Tel. & Data System
15.1 | Supplying and drawing of CAT 6A UTP wire in existing GI conduit for Tel. /Data outlets | RM
| Main Gate Counter (2nos. Data/1nos. Voice) | RM | 13.1 |  |  | 3 | 39.3
| Bar Area (2nos. Data/1nos. Voice) | RM | 13.5 |  |  | 3 | 40.5
| Bar Out Area (2nos. Data) | RM | 14.5 |  |  | 2 | 29
| Counter (2nos. Data/1nos. Voice) | RM | 15 |  |  | 3 | 45
| Main Gate Outside (2nos. Data/1nos. Voice) | RM | 10 |  |  | 3 | 30
| TV 1 | RM | 16 |  |  | 1 | 16
| TV 2 | RM | 18 |  |  | 1 | 18
| WIFI 1 | RM | 13 |  |  | 1 | 13
| WIFI 2 | RM | 18 |  |  | 1 | 18
| Kitchen1 | RM | 28 |  |  | 1 | 28
| Kitchen2 | RM | 30 |  |  | 1 | 30
| Kitchen3 | RM | 30 |  |  | 1 | 30
| Baseement area | RM | 82 |  |  | 1 | 82
0
| Total:- | Rmt |  |  |  |  | 418.8
15.2 | Supplying and laying of 20 mm dia GI conduit for Tel./ Data system | RM
| Main Gate Counter (2nos. Data/1nos. Voice) | RM | 13.1 |  |  | 3 | 39.3
| Bar Area (2nos. Data/1nos. Voice) | RM | 13.5 |  |  | 3 | 40.5
| Bar Out Area (2nos. Data) | RM | 14.5 |  |  | 2 | 29
| Counter (2nos. Data/1nos. Voice) | RM | 15 |  |  | 3 | 45
| Main Gate Outside (2nos. Data/1nos. Voice) | RM | 10 |  |  | 3 | 30
| TV 1 | RM | 16 |  |  | 1 | 16
| TV 2 | RM | 18 |  |  | 1 | 18
| WIFI 1 | RM | 13 |  |  | 1 | 13
| WIFI 2 | RM | 18 |  |  | 1 | 18
| Kitchen1 | RM | 28 |  |  | 1 | 28
| Kitchen2 | RM | 30 |  |  | 1 | 30
| Kitchen3 | RM | 30 |  |  | 1 | 30
| Baseement area | RM | 82 |  |  | 1 | 82
| Total:- | Rmt |  |  |  |  | 418.8
15.3 | Providing & Fixing of RJ11 Outlet complete with G.I. Box Modular base & Cover Plate | Nos.
15.4 | Providing & Fixing of RJ45 Outlet complete with G.I. Box Modular base & Cover Plate | Nos.
16 | Supply, Installation, Testing & Commissioning of 6 KVA UPS complete with sealed Maintenace free 12 V Battery for 30 Minutes back-up. Make: Socemec / Labotek / APC | Set | 1 |  |  |  | 1
17 | Design, manufacture , supply and fixing in position the cable trays of the following sizes for supporting 1.1 KV grade armoured/unarmoured aluminium /copper conductor cables. Fabricate the cable trays from perforated 1.6mm thick M.S. CRCA sheet duly galvanised with expansion coupler plates duly galvanised, with bolts, washer and nuts. Knock out holes for cable connections as per approved design. The tray should comply with the specification of NEC (National Electric Codes) and NEMA (National Electric Manufacturers Association). The steel should be as per IS:226 and galvanising as per IS :2629/BS 729/ASTM 123. The rate shall also include for supporting steel , fish plates , fixing accessories , nuts bolts, supporting down rods , dash fastener, cutting the RCC etc. complete as required. (the horizontal and vertical bends, T's should be factory fabricated and the rate should include for the same)
17.1 | 100 mm wide x 40 mm x 1.6 mm thick | Mtr
| Boh area Tray | Mtr | 28.9 |  |  |  | 28.9
| Cabel Tray Basement B2 | Mtr | 15 |  |  |  | 15
| Cabel Tray Basement B1 | Mtr | 5.5 |  |  |  | 5.5
| Boh Area Tranking | Mtr | 31.1 |  |  |  | 31.1
0
| Total:- | Mtr |  |  |  |  | 80.5
17.2 | 150 mm wide x 40 mm x 1.6 mm thick | Mtr | 0 |  |  |  | 0
Total For Electrical System
ELV System
1 | FIRE ALARM SYSTEM
Make- Agni, Edwards, Revel
1.1 | Fire Alarm Panel - 2 Zone - Addressable Type complete with 4 hrs. battery back-up as required. | Nos. | 1 |  |  |  | 1
1.2 | Supplying & laying of 2x1.5 sqmm fire survival armoured cable, 600/1000V rated with annealed copper conductor having glass mica fire barrier tape covered by an extruded layer of Cross Linkable Ethylene Propylene Rubber (EPR) insulation and LSZH inner bedding, steel wire armouring & LSZH outer sheath complete as required. | Mtrs
| Zone Panel To SD1 | Mtrs | 11 |  |  |  | 11
| SD1 to Sd 2 | Mtrs | 7 |  |  |  | 7
| SD 2 to SD 3 | Mtrs | 10 |  |  |  | 10
| SD 3 To SD 4 | Mtrs | 10.8 |  |  |  | 10.8
| Sd 4 to SD 5 | Mtrs | 4.7 |  |  |  | 4.7
| SD 5 to HEAt 6 | Mtrs | 2 |  |  |  | 2
| Heat To RI | Mtrs | 2 |  |  |  | 2
| HEAT 6 To SD 7 | Mtrs | 6 |  |  |  | 6
| SD 7 to Heat 8 | Mtrs | 2.5 |  |  |  | 2.5
| SD 7 TO Ri | Mtrs | 2 |  |  |  | 2
| Haat 8 to MCp | Mtrs | 12.2 |  |  |  | 12.2
| MCp TO SD 9 | Mtrs | 9.5 |  |  |  | 9.5
| SD 9 to Relay Module Panle | Mtrs | 11 |  |  |  | 11
| Relay Module to Basement SD 10 | Mtrs | 60 |  |  |  | 60
| SD 10 To Ri | Mtrs | 1.5 |  |  |  | 1.5
| SD 10 to SD 11 | Mtrs | 1.5 |  |  |  | 1.5
| Sd 11 To Mcp | Mtrs | 70 |  |  |  | 70
| MCP to Panel | Mtrs | 8 |  |  |  | 8
| Hooter 1 | Mtrs | 9 |  |  |  | 9
| Hooter 2 | Mtrs | 20 |  |  |  | 20
0
| Total:- | Mtr |  |  |  |  | 260.7
1.3 | Supply, Installation, Testing & Commissioning of Photo-Thermal (Multi-sensor) detector with sensing chamber , 12/24 volt DC twin visual alarm indicater blink in stand by and steady in alarm (LED) camplete in al respect with Base as required | Nos | 14 |  |  |  | 14
0
1.4 | Supply, Installation, Testing & Commissioning of Response Indicator complete with Box as required | Nos | 5 |  |  |  | 5
0
1.5 | Supply, installation, testing and commissioning of Siren cum Strobe mount on surface / wall / false ceiling complete as required. | Nos | 2 |  |  |  | 2
0
1.6 | Supply, Installation, Testing & Commissioning of Manual Call Point Break Glass Type housed in sheet Steel/ Polymer housing surface / Recess including Making connection with wire complete in all respect as per specification The manual call should have indicator which should blink in stand by condition. | Nos | 2 |  |  |  | 2
2 | PA SYSTEM
Make- Agni, Edwards, Revel
2.1 | installing, testing and commissioning of 6W Ceiling Speaker with max SPL1M/1W 96dB . Frequency response of 80Hz-20KHz with a dispersion angle of 160 deg. The speaker should have tappings at 6W/3W/1.5W (Supply not in our scope only labour charge )
| Ceiling Mounted Speakers | Nos. | 6 |  |  |  | 6
2.2 | Supplying and drawing of Fire Retardant PVC insulated copper conductor cable in the surface / recessed PVC conduit of following pairs, cores and size including connections and interconnections etc. as required. speaker cable Single pair, 2-core, 1.5 sqmm
2.2.1 | speaker cable Single pair, 2-core, 1.5 sqmm in existing GI conduit | RM
| Sp1 | RM | 20.3 |  |  |  | 20.3
| Sp3 | RM | 13.5 |  |  |  | 13.5
| Sp 5 | RM | 10 |  |  |  | 10
|  |  | 6.2 |  |  |  | 6.2
0
| Total:- | RM |  |  |  |  | 50
2.2.2 | Supplying and laying of 20 mm dia GI conduit for Speaker cable | RM
| Sp1 | RM | 14.5 |  |  |  | 14.5
| Sp3 | RM | 12.5 |  |  |  | 12.5
| Sp 5 | RM | 15.5 |  |  |  | 15.5
0
| Total:- | RM |  |  |  |  | 42.5
2.3 | installing, testing and commissioning of 1X100W Class-D Amplifier with 2 independent channels and can provide automatic re-settable overcurrent, overload, overheating, overvoltage, under-voltage and DC protection. (Supply not in our scope only labour charge ) | Nos. | 1 |  |  |  | 1
3 | CCTV System
3.1 | Supplying and drawing of CAT 6 UTP wire in existing GI conduit | RM
| Main Gate | RM | 11 |  |  |  | 11
| Bar | RM | 15.7 |  |  |  | 15.7
| Main Gate | RM | 10.5 |  |  |  | 10.5
| Lobby Cam 1 | RM | 14 |  |  |  | 14
| Lobby Cam 2 | RM | 22.5 |  |  |  | 22.5
| Live Kitchen | RM | 36 |  |  |  | 36
| Kitchen | RM | 40 |  |  |  | 40
| Kitchen1 | RM | 26 |  |  |  | 26
| Panel Side1 | RM | 24.5 |  |  |  | 24.5
| Store Room | RM | 75 |  |  |  | 75
| Store Room1 | RM | 72 |  |  |  | 72
| Panel Side2 | RM | 30 |  |  |  | 30
0
| Total:- | RM |  |  |  |  | 377.2
3.2 | Supplying and laying of 25 mm dia GI conduit for CCTV Camera | RM
| Main Gate | RM | 4.82 |  |  |  | 4.82
| Bar | RM | 9.52 |  |  |  | 9.52
| Main Gate | RM | 4.32 |  |  |  | 4.32
| Lobby | RM | 7.82 |  |  |  | 7.82
| Lobby | RM | 16.82 |  |  |  | 16.82
| Live Kitchen | RM | 34.82 |  |  |  | 34.82
| Kitchen | RM | 30.32 |  |  |  | 30.32
| Kitchen1 | RM | 20.32 |  |  |  | 20.32
| Panel Side | RM | 18.32 |  |  |  | 18.32
| Store Room | RM | 87.32 |  |  |  | 87.32
| Store Room1 | RM | 86.32 |  |  |  | 86.32
| Kitchen | RM | 24.32 |  |  |  | 24.32
0
| Total:- | RM |  |  |  |  | 345.04
3.3 | Installation, Testing and Commissioning of 2MP x IR Fixed lens Turret Camera, 1920 X 1080 at 25/30fps,1/2.9"CMOS, Fixed lens 2.8mm,H.265, H.264 compression,Smart Compression, internal 850nm IR Range 30 meter or better,Built in Microphone, 100dB true WDR as per IEC62676, Triple streaming,Motion Detection,Camera sabotage,IP66,IK10 Housing,Camera shall support SD card 512GB or better ,ONVIF profile S,G, & T,NDAA,UL/cUL Listed, UL 60950-22, CE, FCC. Approved Makes- Axis P series/ Pelco Value Series / Avigilon H5 series/ Mobotix | Nos

## BOQ-PHE
Site Name :Copper Chimney Project, Vishal Cinema, Delhi
Work: Plumbing Works
Contractor: Stars and Merit Interiors Private Limited
Work order No : DCPL/Vishal Cinema/CC/23-24/CP-202
Bill NO. :RA-4 Bill
SR.NO. | DESCRIPTION | UNIT | As Per Work order |  |  | As per Bill Quantity |  |  |  |  | As per Bill Amount |  |  | Remarlks
|  |  | QTY. | RATE | AMOUNT | Preious Bill | % OF Work | This Bill | Cumulative Bill | % of Works | Preious Bill | This Bill | Cumulative Bill
A | PLUMBING
DRAIINAGE SYSTEM
1 | Providing, fixing, jointing and testing in position UPVC pipes for soil, waste and vent installation conforming cut to required lengths including all necessary fittings and specials such as Bends, junctions, offsets, access pieces (plain or door) & vent cowl. Fixing at wall/ceiling level supported by clamps & hangers etc. Making proper connection with sealerl joint of required depth,making connection with existing pipes with all fittings including cutting, chases/holes in floors /walls/ slab etc and making good the same after pipe have been duly laid and testing complete. ( Including Fiittings like Nani Trap etc ) - 6 Kg Pressure Pipe Make - Prices. Aster, Himalaya or Equivalent
a) | 110 mm dia | Metre | 85 | 1021 | 86785 | 85 | 95% | -26 | 59 | 100% | 82445.75 | -22206.75 | 60239
b) | 160 mm dia | Metre | 0 | 1433 |  | 0 | 0% | 0 |  |  | 0 | 0 | 0
2 | Providing, fixing & testing uPVC pipes, conforming to IS 4985 class 3 (6 kg/cm2) including injection moulded fittings, jointing with solvent cement, cutting and making good the floors and walls and jointing to trap/waste pipe, complete of outer dia. Make - Prices. Aster, Himalaya or Equivalent |  |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0
a) | 40 mm OD | Metre | 0 | 497 |  | 0 | 0% | 0 |  |  | 0 | 0 | 0
b) | 50 mm OD | Metre | 10 | 612 | 6120 | 10 | 95% | 0 | 10 | 100% | 5814 | 306 | 6120
c) | 63 mm OD | Metre | 0 | 712 |  | 0 | 0% | 0 |  |  | 0 | 0 | 0
3 | Providing & fixing PVC clean out plug with suitable insert keys for opening in: brass cap, male threaded joint with threaded uPVC socket fixed to uPVC pipe joints as required complete in all respects. |  |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0
a) | 50 mm | Each | 1 | 1230 | 1230 | 1 | 0% | -1 |  |  | 0 | 0 | 0
b) | 110 mm | Each | 0 | 1764 |  | 0 | 0% | 1 | 1 | 100% | 0 | 1764 | 1764
4 | Providing and Fixing 110x110 mm uPVC 'P' trap with Height riser/Saddle as required size ftting with seal 50 mm of self cleansing design floor/urinal trap without vent suspended with supporting clamp or in sunken portion including cutting and making good the walls and floors wherever required complete in all respects. |  |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0
| 110 mm inlet & 110 mm outlet | Each | 15 | 980 | 14700 | 15 | 95% | -3 | 12 | 100% | 13965 | -2205 | 11760
5 | Providing and Fixing uPVC nahani trap min.-112mm of following size inlet and outlet including cutting and making good the walls and floors wherever required complete in all respects. |  |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0
| 110x90mm outlet | Each | 3 | 1121 | 3363 | 3 | 95% | 0 | 3 | 100% | 3194.85 | 168.15 | 3363
6 | Providing, fixing and testing of uPVC SWR inlet fittings with two or three saddle inlets of 40, 50 or 63 mm size, fabricated from 110 mm outer dia uPVC pipes and fixed to uPVC traps with solvent cement joint complete. | Each | 0 | 3122 | 0 | 0 | 0% | 0 | 0 |  | 0 | 0 | 0
7 | Providing and fixing 125 mm dia, 3 mm thick Stainless steel grating with frame for floor traps drains with 40mm dia hole of required pattern including cutting and making good the floors all complete. | Each | 18 | 980 | 17640 | 18 | 95% | -2 | 16 | 100% | 16758 | -1078 | 15680
8 | Providing and fixing P.V.C. waste pipe for sink or wash basin including P.V.C. waste fittings complete. |  |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0
| 40 mm dia Flexible pipe | Each | 18 | 312 | 5616 | 18 | 95% | -2 | 16 | 100% | 5335.2 | -343.2 | 4992
9 | Making Kitchen Draingae Chamber having Tiles inside all around and fixing of SS Grating plates made with 304 SS with 20x20 mm square pipe with Base plate and SS perporated mesh. |  |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0
a) | size=600x300mm | Each | 6 | 5346 | 32076 | 6 | 70% | -5 | 1 | 100% | 22453.2 | -17107.2 | 5346
b) | size=300x300mm | Each | 2 | 4560 | 9120 | 2 | 70% | 6 | 8 | 100% | 6384 | 30096 | 36480
10 | Providing & Installation of SS Grease Trap 900 x450 x500mm with all required CPVC Fiitings and pipes. | Each | 0 | 123500 |  | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0
| WATER SUPPLY | [10 empty] | 0 | 0
11 | Providing and fixing CPVC (Chlorinated Poly Vinyl Chloride) water supply pipes with pipe as per CTS SDR 11 at working pressure of 400 PSI at 23. Deg.C & 100 PSI AT 82 Deg. C & SCH 40 pipe as per ASTM F441 & fittings as per ASTM F439 shall be used for higher diameter of cPVC pipes & fittings in size 65 mm, 80 mm & 100 mm.using solvent welded CPVC fittings l.e. Tees, Elbows, Couplers, Uniouns, Reducers, brushings etc. including transition fittings connection between CPVC & metal pipe/G.l i.e. Brass Adaptors (Both male & Female threaded) with only CPVC solvent cement with fabricated and subsequently hot dip galvanised clamps / structural steel supports as required / directed at site including cutting chase and fitting the same with cement concrete cement mortar as required. All termination points for installation of faucets shall have brass termination fittings. Installation shall be to the satisfication of the Engineer-In-Charge. (for domestic and flushing water supply inside the shafts and ceiling floor) Make - Jindal, Prices. Aster, Himalaya or Equivalent | [9 empty] | 0 | 0 | 0
a) | 15 mm dia | Metre | 140 | 263 | 36820 | 140 | 95% | -140 | 0 | 0% | 34979 | -34979 | 0
b) | 20 mm dia | Metre | 40 | 290 | 11600 | 40 | 95% | 35.5 | 75.5 | 100% | 11020 | 10875 | 21895
c) | 25 mm dia | Metre | 25 | 365 | 9125 | 25 | 95% | 11 | 36 | 100% | 8668.75 | 4471.25 | 13140
d) | 32 mm dia | Metre | 10 | 432 | 4320 | 10 | 95% | 83.8 | 93.8 | 100% | 4104 | 36417.6 | 40521.6
12 | CPVC BALL Valve | [9 empty] | 0 | 0 | 0
a) | 20 MM | Each | 2 | 320 | 640 | 2 | 0% | 15 | 17 | 100% | 0 | 5440 | 5440
b) | 25 MM | Each | 2 | 320 | 640 | 2 | 0% | 0 | 2 | 100% | 0 | 640 | 640
c) | 32 MM | Each | 2 | 320 | 640 | 2 | 0% | 2 | 4 | 100% | 0 | 1280 | 1280
13 | Water Meter for Each Kitchen | [9 empty] | 0 | 0 | 0
a) | 25 MM water Meter for RO & Raw water Supply in Each Kitchen | Each | 1 | 3245 | 3245 | 1 | 0% | 0 | 1 | 100% | 0 | 3245 | 3245
14 | RO Water Tank |  |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0
| Providing and Fixing 100 Lph R.O Unit with 500 ltr Water tank for RO Make - Sintex or Equivalent - Color - White ( Food Grade) | Each | 1 | 8863 | 8863 | 1 | 85% | -1 | 0 | 0% | 7533.55 | -7533.55 | 0
15 | Providing & Fixing Hot water geyser (make venus & equvlent) |  |  |  |  | 0 |  | 0 | 0 |  | 0 | 0 | 0
| capacity 25 ltr | Each | 2 | 15234 | 30468 | 2 | 70% | 0 | 2 | 100% | 21327.6 | 9140.4 | 30468
0
16 | Providing and fixing of 15 mm dia brass angle valve complete with wall flange of approved make. (For Sink & Geyser) | Each | 20 | 856 | 17120 | 20 | 0% | 5 | 25 | 100% | 0 | 21400 | 21400
0
17 | Providing and fixing of 15 mm dia, 600 mm length stainless steel braided flexible connection pipes with C.P nuts, of approved make. (For Sink & Geyser) | Each | 20 | 562 | 11240 | 20 | 0% | 4 | 24 | 100% | 0 | 13488 | 13488
| Sub - Total (Plumbing) |  |  |  | 311371 |  |  | -16.7 |  |  | 243982.9 | 53278.7 | 297261.6

## Phe Mb
Measurement Book of Plumbing Work Copper Chimney Rajouri Garden
S.No. | Items | Unit | Measurement (m)
|  |  | L | B | H | NO | TOTAL
A | PLUMBING
DRAIINAGE SYSTEM
1 | Providing, fixing, jointing and testing in position UPVC pipes for soil, waste and vent installation conforming cut to required lengths including all necessary fittings and specials such as Bends, junctions, offsets, access pieces (plain or door) & vent cowl. Fixing at wall/ceiling level supported by clamps & hangers etc. Making proper connection with sealerl joint of required depth,making connection with existing pipes with all fittings including cutting, chases/holes in floors /walls/ slab etc and making good the same after pipe have been duly laid and testing complete. ( Including Fiittings like Nani Trap etc ) - 6 Kg Pressure Pipe Make - Prices. Aster, Himalaya or Equivalent
a) | 110 mm dia | Metre
| Drain Line | Metre |  |  |  | 1 | 1
| Bar area | Metre | 4 |  |  | 1 | 4
| Kitchen | Metre | 27 |  |  | 1 | 27
| Kitchen to live kitchen | Metre | 2 |  |  | 1 | 2
| Basement main connection | Metre | 25 |  |  | 1 | 25
0
| Total Qty | Metre |  |  |  |  | 59
b) | 160 mm dia | Metre
2 | Providing, fixing & testing UPVC pipes, conforming to IS 4985 class 3 (6 kg/cm2) including injection moulded fittings, jointing with solvent cement, cutting and making good the floors and walls and jointing to trap/waste pipe, complete of outer dia. Make - Prices. Aster, Himalaya or Equivalent
a) | 40 mm OD | Metre
b) | 50 mm OD Wate pipe | Metre | 10 |  |  | 1 | 10
c) | 63 mm OD | Metre
3 | Providing & fixing PVC clean out plug with suitable insert keys for opening in: brass cap, male threaded joint with threaded uPVC socket fixed to uPVC pipe joints as required complete in all respects.
a) | 50 mm | Each |  |  |  | 0
b) | 110 mm | Each |  |  |  | 1 | 1
4 | Providing and Fixing 110x110 mm uPVC 'P' trap with Height riser/Saddle as required size ftting with seal 50 mm of self cleansing design floor/urinal trap without vent suspended with supporting clamp or in sunken portion including cutting and making good the walls and floors wherever required complete in all respects.
| 110 mm inlet & 110 mm outlet | Each |  |  |  | 12 | 12
5 | Providing and Fixing uPVC nahani trap min.-112mm of following size inlet and outlet including cutting and making good the walls and floors wherever required complete in all respects.
| 110x90mm outlet | Each |  |  |  | 3 | 3
6 | Providing, fixing and testing of uPVC SWR inlet fittings with two or three saddle inlets of 40, 50 or 63 mm size, fabricated from 110 mm outer dia uPVC pipes and fixed to uPVC traps with solvent cement joint complete. | Each
7 | Providing and fixing 125 mm dia, 3 mm thick Stainless steel grating with frame for floor traps drains with 40mm dia hole of required pattern including cutting and making good the floors all complete. | Each |  |  |  | 16 | 16
8 | Providing and fixing P.V.C. waste pipe for sink or wash basin including P.V.C. waste fittings complete.
| 40 mm dia Flexible pipe | Each |  |  |  | 16 | 16
9 | Making Kitchen Draingae Chamber having Tiles inside all around and fixing of SS Grating plates made with 304 SS with 20x20 mm square pipe with Base plate and SS perporated mesh.
a) | size=600x300mm | Each |  |  |  | 1 | 1
b) | size=300x300mm | Each |  |  |  | 8 | 8
10 | Providing & Installation of SS Grease Trap 900 x450 x500mm with all required CPVC Fiitings and pipes. | Each
WATER SUPPLY
11 | Providing and fixing CPVC (Chlorinated Poly Vinyl Chloride) water supply pipes with pipe as per CTS SDR 11 at working pressure of 400 PSI at 23. Deg.C & 100 PSI AT 82 Deg. C & SCH 40 pipe as per ASTM F441 & fittings as per ASTM F439 shall be used for higher diameter of cPVC pipes & fittings in size 65 mm, 80 mm & 100 mm.using solvent welded CPVC fittings l.e. Tees, Elbows, Couplers, Uniouns, Reducers, brushings etc. including transition fittings connection between CPVC & metal pipe/G.l i.e. Brass Adaptors (Both male & Female threaded) with only CPVC solvent cement with fabricated and subsequently hot dip galvanised clamps / structural steel supports as required / directed at site including cutting chase and fitting the same with cement concrete cement mortar as required. All termination points for installation of faucets shall have brass termination fittings. Installation shall be to the satisfication of the Engineer-In-Charge. (for domestic and flushing water supply inside the shafts and ceiling floor) Make - Jindal, Prices. Aster, Himalaya or Equivalent
a) | 15 mm dia | Metre
b) | 20 mm dia | Metre
| Bar back wall to counter wall | Metre
| RO Water Line | Metre | 2.5 |  |  | 1 | 2.5
| Chilled Water Supply | Metre | 2.5 |  |  | 1 | 2.5
| Bar back wall point | Metre | 0.5 |  |  | 1 | 0.5
| Kitchen Entry wall | Metre | 6.5 |  |  | 2 | 13
| Kitchen Back wall | Metre | 6.5 |  |  | 1 | 6.5
| Kitchen RHS Wall | Metre | 6 |  |  | 2 | 12
| Kitchen LHS Wall | Metre | 6 |  |  | 2 | 12
| Down pipe | Metre |  |  |  |  | 0
| Ro Water Supply Line | Metre | 3 |  |  | 1 | 3
| Chilled Water Supply | Metre | 3 |  |  | 1 | 3
| Gyser point | Metre | 2 |  |  | 1 | 2
| Sink Point | Metre | 3 |  |  | 1 | 3
| Ro Water Point | Metre | 2 |  |  | 1 | 2
| Right Side wall to Partition Wall | Metre |  |  |  |  | 0
| Ro | Metre | 3.5 |  |  | 1 | 3.5
| CWS | Metre | 3.5 |  |  | 1 | 3.5
| HOT point | Metre | 3.5 |  |  | 1 | 3.5
| For fresh air Supply and drain | Metre | 3 |  |  | 1 | 3
| Total Qty | Metre |  |  |  |  | 75.5
c) | 25 mm dia | Metre
| Bar to Kitchen Entry | Metre |  |  |  |  | 0
| RO Water Line | Metre | 10.5 |  |  | 1 | 10.5
| Chilled Water Supply | Metre | 10.5 |  |  | 1 | 10.5
| Main entry to kitchn Beam Height | Metre |  |  |  |  | 0
| Ro Water Supply Line | Metre | 3.5 |  |  | 1 | 3.5
| Chilled Water Supply | Metre | 3.5 |  |  | 1 | 3.5
| Drain Pipe | Metre | 4 |  |  | 1 | 4
| drain RO Line | Metre | 4 |  |  | 1 | 4
0
| Total Qty | Metre |  |  |  |  | 36
d) | 32 mm dia | Metre
| Kitchen Back wall 32 dia | Metre | 6.5 |  |  | 1 | 6.5
| Down pipe Line | Metre |  |  |  |  | 0
| Main Line Ceiling to Raw slab | Metre | 3.5 |  |  | 1 | 3.5
| Main line GF to Basement | Metre | 3.5 |  |  | 1 | 3.5
| Basement to Main Connection | Metre | 12 |  |  | 1 | 12
| AHU Drain Line | Metre |  |  |  |  | 0
| 1st Ahu | Metre | 8 |  |  | 1 | 8
| 2nd AHU | Metre | 10.5 |  |  | 1 | 10.5
| For Tank Connections | Metre | 4 |  |  | 1 | 4
| Extra For Basement Area Connections as per mall requirement | Metre | 45.8 |  |  | 1 | 45.8
| Total Qty | Metre |  |  |  |  | 93.8
12 | CPVC BALL Valve
a) | 20 MM | Each |  |  |  | 17 | 17
b) | 25 MM | Each |  |  |  | 2 | 2
c) | 32 MM | Each |  |  |  | 4 | 4
13 | Water Meter for Each Kitchen
a) | 25 MM water Meter for RO & Raw water Supply in Each Kitchen | Each |  |  |  | 1 | 1
14 | RO Water Tank
| Providing and Fixing 100 Lph R.O Unit with 500 ltr Water tank for RO Make - Sintex or Equivalent - Color - White ( Food Grade) | Each |  |  |  |  | 0
15 | Providing & Fixing Hot water geyser (make venus & equvlent)
| capacity 25 ltr | Each |  |  |  | 2 | 2
16 | Providing and fixing of 15 mm dia brass angle valve complete with wall flange of approved make. (For Sink & Geyser) | Each |  |  |  | 25 | 25
17 | Providing and fixing of 15 mm dia, 600 mm length stainless steel braided flexible connection pipes with C.P nuts, of approved make. (For Sink & Geyser) | Each |  |  |  | 24 | 24

## HVAC
Site Name :Copper Chimney Project, Vishal Cinema, Delhi
Work: Plumbing Works
Contractor: Stars and Merit Interiors Private Limited
Work order No : DCPL/Vishal Cinema/CC/23-24/CP-202
Bill NO. :RA-4 Bill
SR.NO. | DESCRIPTION | UNIT | As Per Work order |  |  | As per Bill Quantity |  |  |  |  | As per Bill Amount |  |  | Remarlks
|  |  | QTY. | RATE | AMOUNT | Preious Bill | % OF Work | This Bill | Cumulative Bill | % of Works | Preious Bill | This Bill | Cumulative Bill
HIGH SIDE EQUIPMENTS
1 | CEILING SUSPENDED AHU
| Supply, Installation , testing and commissioning of "Eurovent certified Class- A efficiency", factory built ceiling suspended Double Skinned Chilled water air-handling unit with thermal break profile fabricated out of extruded aluminium section with 0.8mm pre-plasticized GI sheet outside & 0.8mm plain 275GSM GI Sheet inside, blower section with AMCA certified Plug fans with VFD having airfoil blade (Suitable static pressure as required , minimum 2 bend GSS/ PVC eliminators ) and blower motor TEFC type with IE-3 Class rating suitable for operation on 415 volts ± 10% , 50 Hz ± 5% AC supply , 6RD (3RD+3RD With 400mm gap between the two coils ) cooling coil selected for off coil temperature of 11.5 °C of Aluminium finned Copper tube( Tube thickness not less than 0.5 mm) and with coil section , thermostat ,pre-filter with non wovensynthetic media down to 10 micron particle size with an efficiency of 90% & space for Electrostatic filter section air purification system that improves the indoor air quality through reducing harmful pollutants like particulate matter (PMx), PM 2.5, allergens, pollen, smoke, bacteria, pathogens based on Electrostatic precipitation technology,polished stainless steel drain pan made out of 18 G sheet duly insulated complete with motor and belt drive package.It should be a monobloc structured unit specifically designed for integration in Return Air path of the AHU, to centrally capture the pollutants. The AHU shall be complete in all respect and drain piping as per the specification to be provided to the closest floor drain. The unit shall be BMS compatible. Note: all hanging support GRIPPLE / HIRA WALRAVEN guide line (SMACNA) | [12 empty] | No VFD
Note:- complete all accessories, fittings, MS pipes 10 mtr.,PICV Valve, Drain with insulation as required. Make:- Zonex, Zeco, VTS
1.1 | TAG-CS AHU : 3000 CFM/ 12 TR - ESP-55mm - 40mm Dia. | Nos | 2 | 195600 | 391200 | 2 | 1 | 0 | 2 | 100% | 391200 | 0 | 391200
[8 empty] | 0 |  |  | 0 | 0 | 0
| Note: GA Drawings to be approved by Consultant | [6 empty] | 0 |  |  | 0 | 0 | 0
[8 empty] | 0 |  |  | 0 | 0 | 0
2 | Air Washer Unit | [6 empty] | 0 |  |  | 0 | 0 | 0
| Receiving, Installation, testing and commissioning of Double Skin (Forward Curved DIDW Fan) Air Washer Unit will be comprising as per Follow : - | [6 empty] | 0 |  |  | 0 | 0 | 0
| Double skin Modular Extracted Aluminum Profile frame construction with 25 mm thk. Insulated Panel Fan section with Fan canvass connection, drive package with taper lock pullies ,electric motor ,Base frame for Fan motor assembly , Vibration isolator, Access door for maintenance and Angle base frame for unit in 50x5 mm. TEFC foot mounted induction motor suitable for 415V +10% Hz , 3 phase supply , 1440 rpm , Insulation class F and Eff - 2, Degree of protection IP 55 ,conforms to IS : 325. Humidification section with 200 & 50 mm thick cell pad, SS-304 sump ( 18 G ), single phase pump & PVC Internal piping with spray headers. Filter section with 50 mm thk. Wire mesh metallic Pre filter, giving minimum 90% efficiency, makeup, quickfill and drain connections, butterfly valves for quickfill, pumps (2 Nos, 1W+1S), Y strainers and necessary fittings. Note : It is contractor responsibilty to provide secure structural framework for ceiling suspended units duly vetted ,certified & verified by site incharge, engineer & structural engineer appointed by client & approval taken from MEP Consultant prior to ordering / execution at site. Make:- Zonex, Zeco, Blowtech | [6 empty] | 0 |  |  | 0 | 0 | 0
2.1 | 9800 CFM Static- 60-65 MMWG | Nos | 1 | 230000 | 230000 | 1 | 1 | 0 | 1 | 100% | 230000 | 0 | 230000
[8 empty] | 0 |  |  | 0 | 0 | 0
| Note: GA Drawings to be approved by Consultant | [6 empty] | 0 |  |  | 0 | 0 | 0
[8 empty] | 0 |  |  | 0 | 0 | 0
3 | EXHAUST AIR SCRUBBER (DRY TYPE) | [6 empty] | 0 |  |  | 0 | 0 | 0
| Supplying, installing, testing and commissioning of Double skin DRY SCRUBBER UNIT for Kitchen exhaust. The Scrubber shall be Electrostatic precipitation technology based dry type air cleaner to remove oil, smoke & fumes from the Kitchen exhaust air. It shall be made of 16 gauge galvanized sheet, high bake epoxy powder coated. having prefilter, post filters, ionizers & collector plates and having a average effeciency of 90% to 95%. | [6 empty] | 0 |  |  | 0 | 0 | 0
| Make: Zonex, Rydair, Trion | [6 empty] | 0 |  |  | 0 | 0 | 0
3.1 | 11500 CFM | Nos | 1 | 321345 | 321345 | 1 | 1 | 0 | 1 | 100% | 321345 | 0 | 321345
[6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
4 | EXHAUST AIR UNIT |  |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0
| Supply of the following SISW fans with Backward curved inclined type heavy duty class I SISW centrifugal fan with 3 phase TEFC with IP55 protection & class F insulation, Double skin construction complete with Filters,adjusting brackets, 'V' drive belt & belt guard, vibration spring isolators, canvas connection and epoxy painted all as per specs. Motor : BB/Havells/ABB |  |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0
4.1 | 11500 CFM Static- 80 MMWG | Nos | 1 | 219400 | 219400 | 1 | 1 | 0 | 1 | 100% | 219400 | 0 | 219400
[6 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
| Note: GA Drawings to be approved by Consultant |  |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0
[8 empty] | 0 |  |  | 0 | 0 | 0
| LOW SIDE AIR DISTRIBUTION | [6 empty] | 0 |  |  | 0 | 0 | 0
[8 empty] | 0 |  |  | 0 | 0 | 0
1 | SITE/ FACTORY FABRICATED DUCTING | [6 empty] | 0 |  |  | 0 | 0 | 0
| Supply, Fabrication, Installation and Testing of sheet metal rectangular ducts complete with vanes, splitter damper hanging arrangement including check nuts in accordance with the approved shop drawings and specifications | [6 empty] | 0 |  |  | 0 | 0 | 0
1.1 | 0.63mm (24 gauge) GSS | Sqmtr | 80 | 1500 | 120000 | 80 | 0.85 | -28.48 | 51.52 | 100% | 102000 | -24720 | 77280
1.2 | 0.8 mm (22 gauge) GSS | Sqmtr | 80 | 1587 | 126960 | 80 | 0.85 | 0.23 | 80.23 | 100% | 107916 | 19409.01 | 127325.01
1.3 | 1.0mm (20 gauge) GSS | Sqmtr | 20 | 1685 | 33700 | 20 | 0.85 | -20 | 0 | 0% | 28645 | -28645 | 0
| Make: ADS / Ductofab/ GP Spira / Projtech | [6 empty] | 0 |  |  | 0 | 0 | 0
[8 empty] | 0 |  |  | 0 | 0 | 0
2 | FACTORY FABRICATED DUCTING | [6 empty] | 0 |  |  | 0 | 0 | 0
| Supply, fabrication, Installation, testing and commissioning of factory fabricated single walled round/elliptical ducts using G.I Sheets (120GSM coating) as per IS 655 or SMACNA standard in accordance with the approved shop drawings. The price shall include factory fabricated TDF flanges, insulation 19 mm, turning vanes, splitter dampers, supports (factory fabricated, full threaded GI rod/hangers & G.I slotted channel), sealant, neoprene gasket, access door etc. The joints shall be with least leak and shall be tested with pressure testing machine. | [6 empty] | 0 |  |  | 0 | 0 | 0
2.1 | 0.63mm (24 gauge) GSS | Sqmtr | 40 | 1585 | 63400 | 40 | 0.9 | -21.8 | 18.2 | 100% | 57060 | -28213 | 28847
2.2 | 0.8 mm (22 gauge) GSS | Sqmtr | 40 | 1683 | 67320 | 40 | 0.9 | -11 | 29 | 100% | 60588 | -11781 | 48807
| Make: ADS / Ductofab/ GP Spira / Projtech | [6 empty] | 0 |  |  | 0 | 0 | 0
[8 empty] | 0 |  |  | 0 | 0 | 0
3 | Collar Damper | [6 empty] | 0 |  |  | 0 | 0 | 0
3.1 | Supply, installation, testing and commissioning of 50 micron powder coated "Aluminium" collar volume control dampers with key operated of black painted in supply air registers / terminals. | sqmtr | 6 | 6122 | 36732 | 6 | 0 | -4.08 | 1.92 | 100% | 0 | 11754.24 | 11754.24
[8 empty] | 0 | 0 |  | 0 | 0 | 0
4 | FIRE DAMPER | [6 empty] | 0 | 0 |  | 0 | 0 | 0
| Supplying, Fixing,testing and commissioning of fire damper in supply air duct/main branch and return air path as and where required of required sizes i/c control wiring, the damper shall be motorized and spring return so as to close the damper in the event of power failure automatically and open the same in case of power being restored. The spring return action shall be inbuilt mechanism and not externally mounted. the damper shall also be closed in the event of fire signal complete as required adn as per specifications. | [6 empty] | 0 | 0 |  | 0 | 0 | 0
4.1 | Fire damper | Sqm | 10 | 7560 | 75600 | 10 | 0 | -8.995 | 1.005 | 100% | 0 | 7597.8 | 7597.8
4.2 | Actuator | No. | 4 | 8670 | 34680 | 4 | 0 | -2 | 2 | 100% | 0 | 17340 | 17340
[8 empty] | 0 | 0 |  | 0 | 0 | 0
5 | Grille/ Diffuser | [6 empty] | 0 | 0 |  | 0 | 0 | 0
| Supply, installation, testing and commissioning of 50 micron powder coated Linear Grill/Diffuser, Note: color as per Interior Designer | Sqmtr | 10 | 5800 | 58000 | 10 | 0 | -5.805 | 4.195 | 100% | 0 | 24331 | 24331
[8 empty] | 0 | 0 |  | 0 | 0 | 0
6 | VCD - Volume Control Damper | [6 empty] | 0 | 0 |  | 0 | 0 | 0
| Supplying, installing, testing & commissioning of GI volume control damper with minimum 1.6 mm flange and 1.8 mm blade thickness within ducts to be provided with suitable links, levers and quadrants for manual control of volume of air flow and for proper balancing of the air distribution system as per schedules & drawings. | sqmtr | 4 | 6122 | 24488 | 4 | 1 | -2.08 | 1.92 | 100% | 24488 | -12733.76 | 11754.24
[8 empty] | 0 |  |  | 0 | 0 | 0
7 | FRESH/EXHAUST AIR LOUVER | [6 empty] | 0 |  |  | 0 | 0 | 0
| Supplying, installing, testing and commissioning of GI construction fresh/exhaust air louvers with min. 60 % free area, bird screen and painted in baked enamel shade as per clients or architect approval with metallic frame work complete as per specification approved drawings and schedules. | Nos | 5 | 2344 | 11720 | 5 | 0 | -3 | 2 | 100% | 0 | 4688 | 4688
[8 empty] | 0 |  |  | 0 | 0 | 0
8 | DUCT ACOUSTIC LINING | [6 empty] | 0 |  |  | 0 | 0 | 0
| Supply ,Installation,testing and commissioning of duct acoustic lining of supply air duct and plenum with 15 mm thick Open Cell engineered Nitrile Rubber foam of density 140-180 kg/cu.m with in built Microban and tested as per ISO 354:2003 complete as required and as per specifications. | [6 empty] | 0 |  |  | 0 | 0 | 0
| 15 mm thick | Sqmt | 20 | 653 | 13060 | 20 | 0.5 | -20 | 0 | 0% | 6530 | -6530 | 0
[8 empty] | 0 | 0 |  | 0 | 0 | 0
9 | DUCT INSULATION | [6 empty] | 0 | 0 |  | 0 | 0 | 0
| Make: Hira / Armacell / Vidoflex | [6 empty] | 0 | 0 |  | 0 | 0 | 0
| Supplying and fixing of following thickness duly laminated aluminium foil of mat fininshed closed cell Nitrile rubber (class ''O'') insulation on duct after applying two coats of cold setting adhesive (The joints shall sealed with 50mm wide and 3 mm thick self adhesive nitrile rubber tape insulaton complete as per specifications and as required. | [6 empty] | 0 | 0 |  | 0 | 0 | 0
9.2 | Thermal Duct Insulation with 25 mm nitrile rubber (air washer) | sqmtr | 50 | 655 | 32750 | 50 | 0.7 | 33.187 | 83.187 | 100% | 22925 | 31562.485 | 54487.485
[8 empty] | 0 |  |  | 0 | 0 | 0
10 | DOUBLE LAYER CANVAS CONNECTION | [6 empty] | 0 |  |  | 0 | 0 | 0
| Supply,Installation,testing and commissioning of double Layer canvas connection fire retardant cloth for the end connection of AHU / CSU / AIR WASHER / SCRUBBER / TFA and Ventilation fan to reduce the vibration.It shall be fire rated for atleat 2 hrs.Refer tender specification for detail description | Sqmt | 10 | 1865 | 18650 | 10 | 0 | -8.175 | 1.825 | 100% | 0 | 3403.625 | 3403.625
[8 empty] | 0 |  |  | 0 | 0 | 0
11 | Transportation,Unloading,Shifting, Erection and Commissioning Charges of Exhaust Machine ,Airwasher& Air Handling Unit. | Job | 1 | 72345 | 72345 | 1 | 1 | 0 | 1 | 100% | 72345 | 0 | 72345
[8 empty] | 0 |  |  | 0 | 0 | 0
12 | FRAME WORK | [6 empty] | 0 |  |  | 0 | 0 | 0
| Supply & Fixing of structural support fabricated from ISA50/ ISA75/ ISMC50/ ISMC75 for Supporting AHU, Airwasher & Scrubber suspended from ceiling including fabrication, alll necessary hardwares like Anchor fastners, G.I. hangers, G.I. nuts & bolts complete with painting as required. | RO / KG |  | 150 |  | 0 | 0 | 3860 | 3860 | 100% | 0 | 579000 | 579000
[11 empty] | 0 | 0 | 0
| GRAND TOTAL |  |  |  | 1951350 | [5 empty] | 1644442 | 586463.4 | 2230905.4

## HvacMb
Measurement Book of HVAC Work Copper Chimney Rajouri Garden
S.No. | Items | Unit | Measurement (m)
|  |  | L | B | H | NO | TOTAL | Remarks
HIGH SIDE EQUIPMENTS
1 | CEILING SUSPENDED AHU | [6 empty] | No VFD
1.1 | TAG-CS AHU : 3000 CFM/ 12 TR - ESP-55mm - 40mm Dia. | Nos |  |  |  | 2 | 2
2 | Air Washer Unit
2.1 | 9800 CFM Static- 60-65 MMWG | Nos |  |  |  | 1 | 1
3 | EXHAUST AIR SCRUBBER (DRY TYPE)
3.1 | 11500 CFM | Nos |  |  |  | 1 | 1
4 | EXHAUST AIR UNIT
4.1 | 11500 CFM Static- 80 MMWG | Nos |  |  |  | 1 | 1
LOW SIDE AIR DISTRIBUTION
1 | SITE/ FACTORY FABRICATED DUCTING
1.1 | 0.63mm (24 gauge) GSS
| Exhaust Blank OFF | Sqmtr | 0.7 | 0.3 |  | 1 | 0.21
| Piece | Sqmtr | 8 |  |  | 1 | 8
| Bend | Sqmtr | 1.584 |  |  | 1 | 1.584
| Connection Coller | Sqmtr | 0.16 |  |  | 1 | 0.16
| Hoods Coller | Sqmtr | 3.36 |  |  | 1 | 3.36
| Fresh Air Balnk Off | Sqmtr | 0.4 |  |  | 1 | 0.4
| Piece | Sqmtr | 5.83 |  |  | 1 | 5.83
| Piece | Sqmtr | 2.86 |  |  | 1 | 2.86
| Bend | Sqmtr | 2.75 |  |  | 1 | 2.75
| piece | Sqmtr | 2.112 |  |  | 1 | 2.112
| Blankoff | Sqmtr | 0.4 |  |  | 1 | 0.4
| Piece | Sqmtr | 5.83 |  |  | 1 | 5.83
| Offset | Sqmtr | 2.86 |  |  | 1 | 2.86
| Barnch Coller | Sqmtr | 0.72 |  |  | 1 | 0.72
| Offset | Sqmtr | 0.88 |  |  | 1 | 0.88
| bend | Sqmtr | 1.64 |  |  | 1 | 1.64
| Piece | Sqmtr | 2.48 |  |  | 1 | 2.48
| Piece | Sqmtr | 1.28 |  |  | 1 | 1.28
| Piece | Sqmtr | 1.12 |  |  | 1 | 1.12
| Bend | Sqmtr | 1.584 |  |  | 1 | 1.584
| Blankoff | Sqmtr | 0.21 |  |  | 1 | 0.21
| Blankoff | Sqmtr | 0.14 |  |  | 1 | 0.14
| Blankoff | Sqmtr | 0.32 |  |  | 1 | 0.32
| Bend | Sqmtr | 0.84 |  |  | 1 | 0.84
| Grill Coller | Sqmtr | 0.96 |  |  | 1 | 0.96
|  |  | 3.24 |  |  | 1 | 3.24
0
| Total:- | Sqm |  |  |  |  | 51.52 | 51.52
| 0.8 mm (22 gauge) | Sqmtr
| GSS Ahu Planium | Sqmtr | 3 |  |  | 1 | 3
| blank off | Sqmtr | 4.32 |  |  | 1 | 4.32
| Connection Coller | Sqmtr | 1.54 |  |  | 1 | 1.54
| fresh air | Sqmtr | 2.842 |  |  | 1 | 2.842
| Offset | Sqmtr | 2.32 |  |  | 1 | 2.32
| Planium Fresh air | Sqmtr | 4.125 |  |  | 1 | 4.125
| Balnk off Fresh air | Sqmtr | 1.7 |  |  | 1 | 1.7
| Balnk off Exhaust | Sqmtr | 0.5 |  |  | 1 | 0.5
| Exhaust peace | Sqmtr | 6.89 |  |  | 1 | 6.89
| Bend | Sqmtr | 3.796 |  |  | 1 | 3.796
| piece | Sqmtr | 6.89 |  |  | 1 | 6.89
| band | Sqmtr | 5.382 |  |  | 1 | 5.382
| piece | Sqmtr | 1.04 |  |  | 1 | 1.04
| piece | Sqmtr | 1.43 |  |  | 1 | 1.43
| bend | Sqmtr | 3.341 |  |  | 1 | 3.341
| bend | Sqmtr | 2.21 |  |  | 1 | 2.21
| Connection coller | Sqmtr | 1 |  |  | 1 | 1
| piece | Sqmtr | 1.56 |  |  | 1 | 1.56
| piece | Sqmtr | 6.89 |  |  | 1 | 6.89
| Blank off | Sqmtr | 0.5 |  |  | 1 | 0.5
| Plainium Exhaust | Sqmtr | 7.56 |  |  | 1 | 7.56
| Blank off | Sqmtr | 2.6 |  |  | 1 | 2.6
| basement | Sqmtr | 12.19 |  |  | 1 | 12.19
| piece | Sqmtr | 2.99 |  |  | 1 | 2.99
| Connection Coller | Sqmtr | 1.15 |  |  | 1 | 1.15
0
0
| Total:- | Sqm |  |  |  |  | 80.23 | 80.23
1.3 | 1.0mm (20 gauge) GSS | Sqmtr
Make: ADS / Ductofab/ GP Spira / Projtech
2 | FACTORY FABRICATED DUCTING
2.1 | 0.63mm (24 gauge) GSS | Sqmtr | 20.02 |  |  | 1 | 18.2
2.2 | 0.8 mm (22 gauge) GSS | Sqmtr | 29.7 |  |  | 1 | 29
Make: ADS / Ductofab/ GP Spira / Projtech
3 | Collar Damper
3.1 | Supply, installation, testing and commissioning of 50 micron powder coated "Aluminium" collar volume control dampers with key operated of black painted in supply air registers / terminals. | sqmtr | 0.48 |  |  | 1 | 0.48
|  | sqmtr | 0.78 |  |  | 1 | 0.78
|  | sqmtr | 0.66 |  |  | 1 | 0.66
0
| Total:- | Sqm |  |  |  |  | 1.92
4 | FIRE DAMPER
Supplying, Fixing,testing and commissioning of fire damper in supply air duct/main branch and return air path as and where required of required sizes i/c control wiring, the damper shall be motorized and spring return so as to close the damper in the event of power failure automatically and open the same in case of power being restored. The spring return action shall be inbuilt mechanism and not externally mounted. the damper shall also be closed in the event of fire signal complete as required adn as per specifications.
4.1 | Fire damper | Sqm | 1.005 |  |  |  | 1.005
4.2 | Actuator | No. | 2 |  |  |  | 2
5 | Grille/ Diffuser
| Supply, installation, testing and commissioning of 50 micron powder coated Linear Grill/Diffuser, Note: color as per Interior Designer | Sqmtr | 0.675 |  |  | 1 | 0.675
|  | Sqmtr | 0.32 |  |  | 1 | 0.32
|  | Sqmtr | 1.68 |  |  | 1 | 1.68
|  | Sqmtr | 2.52 |  |  | 1 | 2.52
0
| Total:- | Sqm |  |  |  |  | 4.195 | 4.195
6 | VCD - Volume Control Damper
| Supplying, installing, testing & commissioning of GI volume control damper with minimum 1.6 mm flange and 1.8 mm blade thickness within ducts to be provided with suitable links, levers and quadrants for manual control of volume of air flow and for proper balancing of the air distribution system as per schedules & drawings. | sqmtr | 0.675 |  |  | 1 | 0.675
|  |  | 2.52 |  |  | 1 | 2.52
|  |  | 0 |  |  |  | 0
| Total:- | Sqm |  |  |  |  | 1.92 | 1.92
7 | FRESH/EXHAUST AIR LOUVER
| Supplying, installing, testing and commissioning of GI construction fresh/exhaust air louvers with min. 60 % free area, bird screen and painted in baked enamel shade as per clients or architect approval with metallic frame work complete as per specification approved drawings and schedules. | Nos | 2 |  |  |  | 2
8 | DUCT ACOUSTIC LINING
Supply ,Installation,testing and commissioning of duct acoustic lining of supply air duct and plenum with 15 mm thick Open Cell engineered Nitrile Rubber foam of density 140-180 kg/cu.m with in built Microban and tested as per ISO 354:2003 complete as required and as per specifications.
| 15 mm thick | Sqmt | 0 |  |  |  | 0
9 | DUCT INSULATION
Make: Hira / Armacell / Vidoflex
Supplying and fixing of following thickness duly laminated aluminium foil of mat fininshed closed cell Nitrile rubber (class ''O'') insulation on duct after applying two coats of cold setting adhesive (The joints shall sealed with 50mm wide and 3 mm thick self adhesive nitrile rubber tape insulaton complete as per specifications and as required.
9.2 | Thermal Duct Insulation with 25 mm nitrile rubber (air washer) | sqmtr | 78.9 |  |  |  | 83.187
10 | DOUBLE LAYER CANVAS CONNECTION
| Supply,Installation,testing and commissioning of double Layer canvas connection fire retardant cloth for the end connection of AHU / CSU / AIR WASHER / SCRUBBER / TFA and Ventilation fan to reduce the vibration.It shall be fire rated for atleat 2 hrs.Refer tender specification for detail description | Sqmt | 1.1 |  |  | 1 | 1.1
|  | Sqmt | 0.725 |  |  | 1 | 0.725
0
| Total:- | Sqm |  |  |  |  | 1.825
11 | Transportation,Unloading,Shifting, Erection and Commissioning Charges of Exhaust Machine ,Airwasher& Air Handling Unit. | Job | 1 |  |  |  | 1
12 | FRAME WORK
| Supply & Fixing of structural support fabricated from ISA50/ ISA75/ ISMC50/ ISMC75 for Supporting AHU, Airwasher & Scrubber suspended from ceiling including fabrication, alll necessary hardwares like Anchor fastners, G.I. hangers, G.I. nuts & bolts complete with painting as required. | RO / KG
| M.s Structure As per Approved Drawing, Base for air washer and scrubber,Ro and water tank | KG |  |  |  | 3860 | 3860

## Fire Fighting
Site Name :Copper Chimney Project, Vishal Cinema, Delhi
Work: Fire-Fighting Works
Contractor: Stars and Merit Interiors Private Limited
Work order No : DCPL/Vishal Cinema/CC/23-24/CP-202
Bill NO. :RA-4 Bill
SR.NO. | DESCRIPTION | UNIT | As Per Work order |  |  | As per Bill Quantity |  |  |  |  | As per Bill Amount |  |  | Remarlks
|  |  | QTY. | RATE | AMOUNT | Preious Bill | % OF Work | This Bill | Cumulative Bill | % of Works | Preious Bill | This Bill | Cumulative Bill
B | FIRE FIGHTING SYSTEM
1 | Providing, laying, testing & commissioning of 'C' class heavy duty MS pipe conforming to IS 3589/IS 1239 including Welding, fittings like elbows, tees, flanges, tapers, nuts bolts, gaskets etc. and fixing the pipe on the wall/ceiling with suitable clamp/support frame and painting with two or more coats of synthetic enamel paint of required shade complete as required : Make-SURYA PIPES/ JINDAL HISSAR (Note: Qty. as per drg and may vary depending upon the use of existing pipe lines)
a) | 25 mm dia. | Metre | 85 | 614 | 52190 | 85 | 85% | 0.6 | 85.6 | 100% | 44361.5 | 8196.9 | 52558.4
b) | 32 mm dia. | Metre | 0 | 712 |  | 0 | 0% | 9.2 | 9.2 | 100% | 0 | 6550.4 | 6550.4
c) | 40 mm dia. | Metre | 25 | 723 | 18075 | 25 | 85% | -5.2 | 19.8 | 100% | 15363.75 | -1048.35 | 14315.4
d) | 50 mm dia. | Metre | 10 | 985 | 9850 | 10 | 85% | 2.6 | 12.6 | 100% | 8372.5 | 4038.5 | 12411
e) | 65 mm dia. | Metre | 10 | 1030 | 10300 | 10 | 0% | 6 | 16 | 100% | 0 | 16480 | 16480
f) | 80 mm dia. | Metre | 20 | 1189 | 23780 | 20 | 0% | -20 | 0 | 0% | 0 | 0 | 0
g) | 100 mm dia. | Metre | 0 | 1456 |  |  | 0% | 0 | 0 | 0% | 0 | 0 | 0
[8 empty] | 0 |  |  | 0 | 0 | 0
2 | Providing, fixing, testing and commissioning brass quartzoid sprinklers K-80 (UL-Underwriters Laboratories Listed) suitable for 175 psi(12 Bars) maximum working pressure and 7 psi(0.5 Bars) minimum operating pressure with 15 mm dia BSPT threaded opening complete in all respects. The type & temperature rating shall be as follows. Make-SAFEX/NEWAGE/HD FIRE | [6 empty] | 0 |  |  | 0 | 0 | 0
a) | Pendent Concealed Sprinklers (68°)- Quick response type | Each | 19 | 455 | 8645 | 19 | 70% | -2 | 17 | 100% | 6051.5 | 1683.5 | 7735
b) | Pendent Concealed Sprinklers (79°)- Quick response type | Each | 10 | 495 | 4950 | 10 | 70% | -3 | 7 | 100% | 3465 | 0 | 3465
c) | Upright Sprinkler (68°)- Quick response type | Each | 19 | 432 | 8208 | 19 | 70% | -18 | 1 | 100% | 5745.6 | -5313.6 | 432
d) | Upright Sprinkler (79°)- Quick response type | Each | 10 | 448 | 4480 | 10 | 70% | -9 | 1 | 100% | 3136 | -2688 | 448
[8 empty] | 0 |  |  | 0 | 0 | 0
3 | Supplying, installation, testing & commissioning of sprinkler flexible pipe (UL Listed) of stainless steel complete with 15 NPT on reducer thread with maximum working pressure of 175 PSI test pressure of 875 PSI (Burst) with branch line (Inlet) 25mm NPT male thread to sprinkler head (Outlet) 15mm NPT female thread with reducer, nipple, 2 side brackets, center bracket, stockbar of following sizes complete as required. Make-SAFEX/NEWAGE/HD FIRE | [6 empty] | 0 |  |  | 0 | 0 | 0
a) | 1500mm | Each | 29 | 1820 | 52780 | 29 | 0% | -16 | 13 | 100% | 0 | 23660 | 23660
b) | 2000mm | Each |  | 2350 |  |  | 0% | 0 | 0 | 0% | 0 | 0 | 0
[8 empty] | 0 |  |  | 0 | 0 | 0
4 | Provding & Fixing Powder coated double plate rosette plate for pendent / side wall sprinkler where ever required. | Each |  | 155 | 0 |  | 0% | 22 | 22 | 100% | 0 | 3410 | 3410
[8 empty] | 0 |  |  | 0 | 0 | 0
5 | Providing and fixing following size Pressure gauge (0-15 Kg/Cm2) complete with shut off valve duly calibrated before installation complete as required & as per enclosed specification. 150mm dia. | Each | 1 | 1983 | 1983 | 1 | 70% | 0 | 1 | 100% | 1388.1 | 594.9 | 1983
[8 empty] | 0 | 0 |  | 0 | 0 | 0
6 | Providing & fixing flow switch in following sizes M.S. pipe including connection etc as required. 150mm dia. | Each | 1 | 5230 | 5230 | 1 | 0% | 0 | 1 | 100% | 0 | 5230 | 5230
[8 empty] | 0 | 0 |  | 0 | 0 | 0
7 | Supplying, fixing, testing and commissioning of butterfly valve of PN 1.6 rating with bronze/gunmetal seat duly ISI marked complete with nuts, bolts, washers, gaskets conforming to IS 13095 of following sizes as required : | [6 empty] | 0 | 0 |  | 0 | 0 | 0
a) | 50mm dia | Each | 1 | 3233 | 3233 | 1 | 0% | -1 | 0 | 0% | 0 | 0 | 0
b) | 65mm dia | Each | 1 | 3546 | 3546 | 1 | 0% | 0 | 1 | 100% | 0 | 3546 | 3546
[8 empty] | 0 |  |  | 0 | 0 | 0
8 | Fire Extinguisher | [6 empty] | 0 |  |  | 0 | 0 | 0
a) | Supply, installation, testing and commissioning ISI marked (IS:15683) Fire Extinguisher, Carbon-di-oxide type capacity 4.5 Kg. Flat base including valve, discharge hose of not less than 10 mm dia, 1M long and complete in all respects including initial fill with CO2 gas conforming to IS:307-1966 and walll suspension braket as required as per specifications. (Make-MINIMAX/SAFEX/KALPEX, PADMINI) | Each | 0 | 6843 | 0 | 3 | 0% | 0 | 3 | 100% | 0 | - | -
b) | Supply, installation, testing and commissioning of 6kg ABC (Powder Type) Fire Extinguisher. Mild Steel Cylinders ISI marked fitted with pressure indicating gauge, internal tube, squeeze lever type valve fully charged with ABC 90 powder (Mono Ammonium Phosphate) pressured by Nitrogen complete in all respects including wall suspension bracket and conforming to IS:15683 as required as per specifications. (Make-MINIMAX/SAFEX/KALPEX/PADMINI) | Each | 0 | 2344 | 0 | 3 | 0% | 0 | 3 | 100% | 0 | - | -
C | Fire Supression system | [6 empty] | 0 |  |  | 0 | 0 | 0
| Make: Ansul / Radiant / Firetrace | [6 empty] | 0 |  |  | 0 | 0 | 0
| The Fire suppression system shall be Complete UL - 300 approved system in all respect and shall comply with ANSI/UL-300, ANSI/UL-1254, UL-Ex.6885, UL (Underwriters Laboratories). | [6 empty] | 0 |  |  | 0 | 0 | 0
| Suppression unit:-The Fire suppression system shall include DOT approved Cylinder with Fire Suppressant, Automatic release module, Nozzles based on Appliances as per UL recommendation, Nitrogen Cartridge, Remote Pull Station for manual release, Corner Pulleys, SS piping and its Network. | [6 empty] | 0 |  |  | 0 | 0 | 0
| Detection unit:-The system shall only comprise of fusible link type of detection unit . All fusible links should be installed with the help of shielded cable & Fusible link holder to eliminate cut and crimp. The whole detection line shall be continuous. | [6 empty] | 0 |  |  | 0 | 0 | 0
| Source & Signal :-System shall include mechanical gas shut off valve. So that incase of fire, the source for ignition (fuel) can be cut off. This should be in automatic mode. Similarly NO/NC contact should be generated so that the system can have interfacing with fire alarm. And electrical power to the electrical kitchen appliances can be cut off. | [6 empty] | 0 |  |  | 0 | 0 | 0
| The wet chemical shall be a liquid fire suppressant like Aqueous Potassium Carbonate or Potassium Acetate based solution that suppresses cooking grease fires both through saponification and cooling. The agent stored in a cylinder shall be working at 195 psig (1344 kpa) @70oF (21oC). The unit shall be self-contained and shall be self-equipped with its own non-electric automatic detection system to detect the fire and release wet chemical into the hood, suppressing the fire. | [6 empty] | 0 |  |  | 0 | 0 | 0
| The Fire supression system to be of Ansul ( Tyco) make or equivalent which must be UL approved & specifications to be as per certification of Calicut Airport Authority. It need to be properlly integrated with exhaust system & electrical main panel. All electrical terminations must be made to UL listed junction boxes only. And must be complete with minimum 2 SPDT micro switches inbuilt interface. | [6 empty] | 0 |  |  | 0 | 0 | 0
(i) | SIZE:900MM X 900MM X 500MM (EX HOOD) | Set | 1 |  | 0 | 1 | 0% | -1 |  |  | 0 | 0 | 0
(ii) | SIZE:1200MM X 11500MM X 500MM (EX HOOD) | Set | 1 |  | 0 | 1 | 0% | -1 |  |  | 0 | 0 | 0
(iii) | SIZE:2150MM X 1150MM X 500MM (EX HOOD) | Set | 1 |  | 0 | 1 | 0% | -1 |  |  | 0 | 0 | 0
(iv) | SIZE:3050MM X 1150MM X 500MM (EX HOOD) | Set | 1 |  | 0 | 1 | 0% | -1 |  |  | 0 | 0 | 0
| TOTAL COST OF FIRE FIGHTING |  |  |  | 207250 |  |  | -37.8 |  |  | 87883.95 | 64340.25 | 152224.2

## Firemb
Measurement Book of Fire - Work Copper Chimney Rajouri Garden
S.No. | Items | Unit | Measurement (m)
|  |  | L | B | H | NO | TOTAL
B | FIRE FIGHTING SYSTEM
1 | Providing, laying, testing & commissioning of 'C' class heavy duty MS pipe conforming to IS 3589/IS 1239 including Welding, fittings like elbows, tees, flanges, tapers, nuts bolts, gaskets etc. and fixing the pipe on the wall/ceiling with suitable clamp/support frame and painting with two or more coats of synthetic enamel paint of required shade complete as required : Make-SURYA PIPES/ JINDAL HISSAR (Note: Qty. as per drg and may vary depending upon the use of existing pipe lines)
a) | 25 mm dia. | Metre
| FOH area | Metre
| Branch-1 | Metre | 1.3 |  |  | 1 | 1.3
| Branch-2 | Metre | 4.5 |  |  | 1 | 4.5
| Branch-3 | Metre | 4.5 |  |  | 1 | 4.5
| Branch-4 | Metre | 4.5 |  |  | 1 | 4.5
| Branch-5 | Metre | 4.5 |  |  | 1 | 4.5
| BOH area | Metre |  |  |  |  | 0
| Main Header Branch-1 | Metre | 0.5 |  |  | 1 | 0.5
| Branch-2 | Metre | 5.2 |  |  | 1 | 5.2
| Branch-3 | Metre | 1 |  |  | 1 | 1
| Branch-4 | Metre | 3 |  |  | 1 | 3
| Branch-5 | Metre | 2.1 |  |  | 1 | 2.1
| Branch-6 | Metre | 0.5 |  |  | 1 | 0.5
| Rework | Metre | 54 |  |  | 1 | 54
0
| Total Qty | Meter |  |  |  |  | 85.6
b) | 32 mm dia. | Metre
| FOH area | Metre
| Branch-1 | Metre | 4.5 |  |  | 1 | 4.5
| BOH area | Metre |  |  |  |  | 0
| Main Header Branch-1 | Metre | 4.7 |  |  | 1 | 4.7
0
| Total Qty | Meter |  |  |  |  | 9.2
c) | 40 mm dia. | Metre
| FOH area | Metre
| Main Header | Metre | 6 |  |  | 1 | 6
| Branch-1,2,3,4 | Metre | 2.2 |  |  | 4 | 8.8
| Rework | Metre | 5 |  |  | 1 | 5
0
| Total Qty | Meter |  |  |  |  | 19.8
d) | 50 mm dia. | Metre
| FOH area | Metre
| Main Header | Metre | 7.6 |  |  | 1 | 7.6
| Rework | Metre | 5 |  |  | 1 | 5
0
| Total Qty | Meter |  |  |  |  | 12.6
e) | 65 mm dia. | Metre
| Main Header | Metre | 4 |  |  | 1 | 4
| Rework | Metre | 12 |  |  | 1 | 12
0
| Total Qty | Meter |  |  |  |  | 16
f) | 80 mm dia. | Metre
g) | 100 mm dia. | Metre
2 | Providing, fixing, testing and commissioning brass quartzoid sprinklers K-80 (UL-Underwriters Laboratories Listed) suitable for 175 psi(12 Bars) maximum working pressure and 7 psi(0.5 Bars) minimum operating pressure with 15 mm dia BSPT threaded opening complete in all respects. The type & temperature rating shall be as follows. Make-SAFEX/NEWAGE/HD FIRE
a) | Pendent Concealed Sprinklers (68°)- Quick response type | Each |  |  |  | 17 | 17
b) | Pendent Concealed Sprinklers (79°)- Quick response type | Each |  |  |  | 7 | 7
c) | Upright Sprinkler (68°)- Quick response type | Each |  |  |  | 1 | 1
d) | Upright Sprinkler (79°)- Quick response type | Each |  |  |  | 1 | 1
3 | Supplying, installation, testing & commissioning of sprinkler flexible pipe (UL Listed) of stainless steel complete with 15 NPT on reducer thread with maximum working pressure of 175 PSI test pressure of 875 PSI (Burst) with branch line (Inlet) 25mm NPT male thread to sprinkler head (Outlet) 15mm NPT female thread with reducer, nipple, 2 side brackets, center bracket, stockbar of following sizes complete as required. Make-SAFEX/NEWAGE/HD FIRE
a) | 1500mm | Each |  |  |  | 13 | 13
b) | 2000mm | Each
4 | Provding & Fixing Powder coated double plate rosette plate for pendent / side wall sprinkler where ever required. | Each |  |  |  | 22 | 22
5 | Providing and fixing following size Pressure gauge (0-15 Kg/Cm2) complete with shut off valve duly calibrated before installation complete as required & as per enclosed specification. 150mm dia. | Each |  |  |  | 1 | 1
6 | Providing & fixing flow switch in following sizes M.S. pipe including connection etc as required. 150mm dia. | Each |  |  |  | 1 | 1
7 | Supplying, fixing, testing and commissioning of butterfly valve of PN 1.6 rating with bronze/gunmetal seat duly ISI marked complete with nuts, bolts, washers, gaskets conforming to IS 13095 of following sizes as required :
a) | 50mm dia | Each
b) | 50mm dia- 65 mm dia | Each |  |  |  | 1 | 1
8 | Fire Extinguisher
a) | Supply, installation, testing and commissioning ISI marked (IS:15683) Fire Extinguisher, Carbon-di-oxide type capacity 4.5 Kg. Flat base including valve, discharge hose of not less than 10 mm dia, 1M long and complete in all respects including initial fill with CO2 gas conforming to IS:307-1966 and walll suspension braket as required as per specifications. (Make-MINIMAX/SAFEX/KALPEX, PADMINI) | Each |  |  |  | 3 | 3
b) | Supply, installation, testing and commissioning of 6kg ABC (Powder Type) Fire Extinguisher. Mild Steel Cylinders ISI marked fitted with pressure indicating gauge, internal tube, squeeze lever type valve fully charged with ABC 90 powder (Mono Ammonium Phosphate) pressured by Nitrogen complete in all respects including wall suspension bracket and conforming to IS:15683 as required as per specifications. (Make-MINIMAX/SAFEX/KALPEX/PADMINI) | Each |  |  |  | 3 | 3
C | Fire Supression system
Make: Ansul / Radiant / Firetrace
The Fire suppression system shall be Complete UL - 300 approved system in all respect and shall comply with ANSI/UL-300, ANSI/UL-1254, UL-Ex.6885, UL (Underwriters Laboratories).
Suppression unit:-The Fire suppression system shall include DOT approved Cylinder with Fire Suppressant, Automatic release module, Nozzles based on Appliances as per UL recommendation, Nitrogen Cartridge, Remote Pull Station for manual release, Corner Pulleys, SS piping and its Network.
Detection unit:-The system shall only comprise of fusible link type of detection unit . All fusible links should be installed with the help of shielded cable & Fusible link holder to eliminate cut and crimp. The whole detection line shall be continuous.
Source & Signal :-System shall include mechanical gas shut off valve. So that incase of fire, the source for ignition (fuel) can be cut off. This should be in automatic mode. Similarly NO/NC contact should be generated so that the system can have interfacing with fire alarm. And electrical power to the electrical kitchen appliances can be cut off.
The wet chemical shall be a liquid fire suppressant like Aqueous Potassium Carbonate or Potassium Acetate based solution that suppresses cooking grease fires both through saponification and cooling. The agent stored in a cylinder shall be working at 195 psig (1344 kpa) @70oF (21oC). The unit shall be self-contained and shall be self-equipped with its own non-electric automatic detection system to detect the fire and release wet chemical into the hood, suppressing the fire.
The Fire supression system to be of Ansul ( Tyco) make or equivalent which must be UL approved & specifications to be as per certification of Calicut Airport Authority. It need to be properlly integrated with exhaust system & electrical main panel. All electrical terminations must be made to UL listed junction boxes only. And must be complete with minimum 2 SPDT micro switches inbuilt interface.
(i) | SIZE:900MM X 900MM X 500MM (EX HOOD) | Set |  |  |  |  | 0
(ii) | SIZE:1200MM X 11500MM X 500MM (EX HOOD) | Set |  |  |  |  | 0
(iii) | SIZE:2150MM X 1150MM X 500MM (EX HOOD) | Set |  |  |  |  | 0
(iv) | SIZE:3050MM X 1150MM X 500MM (EX HOOD) | Set |  |  |  |  | 0

## FACADE
Site Name :Copper Chimney Project, Vishal Cinema, Delhi
Work: Façade Finishing Works
Contractor: Stars and Merit Interiors Private Limited
Work order No : DCPL/Vishal Cinema/CC/23-24/CP-202
Bill NO. :RA-4 Bill
SR.NO. | ITEM | DESCRIPTION | DRAWING NO | DIMENSION | UNIT | As Per Work order |  |  | As per Bill Quantity |  |  |  |  | As per Bill Amount |  |  | Remarlks
[6 empty] | QTY. | RATE | AMOUNT | Preious Bill | % OF Work | This Bill | Cumulative Bill | % of Works | Preious Bill | This Bill | Cumulative Bill
FAÇADE |  | CARPENTRY WORK
1 | Entry Glass Partition | P/F 10 mm thk. toughened glass partitions with 20 x 40mm MS framework with white/ black powder coating and all necessary required groove, wooden framing, including glass door with heavy duty floor spring fixing with approved make adhesive and fasteners, cutting/ chamfering/ groove/rounding wherever required, at all height with lead and lift, finishing, cleaning as per design and drawing etc. all complete. |  | N.A | SFT | 140 | 890 | 124600 |  | 0% | 64.7449 | 64.7449 | 100% | 0 | 57622.9798 | 57622.9798
2 | FAÇADE GLASS BOTTOM - MDF panelling with duco | Providing, making and fixing of wall panel made of 12mm thk branded Commercial Ply (MR Calibrated, IS 303) -- Greenply or Equivalent brand with MDF finish with Duco paint and wooden molding as per design, all necessary required wooden framing, approved make adhesive and fasteners, cutting/ chamfering/ groove/rounding wherever required, at all height with lead and lift, finishing, cleaning as per design and drawing etc. all complete. |  | upto 900mm ht | SFT | 55 | 723 | 39765 |  | 0% | 48.5991 | 48.5991 | 100% | 0 | 35137.1171 | 35137.1171
[11 empty] | 0 |  |  | 0 | 0 | 0
3 | ACP Cladding for signages | Providing, fabricating & fixing of ACP as per approval Make 3mm thick PVDF coated, exterior quality Aluminum Composite Panel with required framing, DC 789 Weather sealant including all necessary hardware etc. complete as directed. |  | N.A | SFT | 100 | 392 | 39200 |  | 0% | 0 |  | 0% | 0 | 0 | 0
| OR | [8 empty] | 0% | 0 |  | 0% | 0 | 0 | 0
| Granite cladding | P&F of 12 mm thick full body granite finish tile cladding walls / column's surface with cement sand mortar bed in 1:4 proportions, finishing of joints in white cement with added colour pigments, including cutting of random sizes , finishing of top edges up to the mark, making cut out provision for all related services such as electrical switch board, plumbing fittings, etc as require. Complete laying in proper line & level as per architectural detail drawing & site engineer's instruction. Basic rate 180/- Sq Ft |  |  | SFT | 100 | 413 | 41300 |  | 0% | 41.9793 | 41.9793 | 100% | 0 | 17337.4305 | 17337.4305
4 | Entry main glass door | P/F 10 mm thk. toughened glass partitions with 20 x 40mm MS framework with white powder coating and all necessary required groove, wooden framing, including glass door with heavy duty floor spring fixing with approved make adhesive and fasteners, cutting/ chamfering/ groove/rounding wherever required, at all height with lead and lift, finishing, cleaning as per design and drawing etc. all complete. |  | 2000 x 2400 | Nos | 1 | 56345 | 56345 |  | 0% | 1 | 1 | 100% | 0 | 56345 | 56345
5 | MAIN DOOR HANDLE | Providing, Supplying & fixing Single sided Sign metal handle with brass finsih. |  |  | Nos | 1 | 5532 | 5532 |  | 0% | 1 | 1 | 100% | 0 | 5532 | 5532
|  | Grand Total of façade | [5 empty] | 306742 | [5 empty] | 0 | 171974.5275 | 171974.5275

## facademb
Measurement Book of Façade Work Copper Chimney Rajouri Garden
S.No. | Items | Descriptions | Unit | Measurement (mm) |  |  | Measurement (Feet)
|  |  |  | L | B | H | L | B | H | NO | TOTAL
1 | Entry Glass Partition | P/F 10 mm thk. toughened glass partitions with 20 x 40mm MS framework with white/ black powder coating and all necessary required groove, wooden framing, including glass door with heavy duty floor spring fixing with approved make adhesive and fasteners, cutting/ chamfering/ groove/rounding wherever required, at all height with lead and lift, finishing, cleaning as per design and drawing etc. all complete.
|  |  | Sqft | 2550 |  | 1500 | 8.3661 |  | 4.9213 | 1 | 41.172
|  |  | Sqft | 1460 |  | 1500 | 4.79 |  | 4.9213 | 1 | 23.573
|  | Total:- | Sqft | [7 empty] | 64.7449
2 | FAÇADE GLASS BOTTOM - MDF panelling with duco | Providing, making and fixing of wall panel made of 12mm thk branded Commercial Ply (MR Calibrated, IS 303) -- Greenply or Equivalent brand with MDF finish with Duco paint and wooden molding as per design, all necessary required wooden framing, approved make adhesive and fasteners, cutting/ chamfering/ groove/rounding wherever required, at all height with lead and lift, finishing, cleaning as per design and drawing etc. all complete. | Nos
|  | Façade | Sqft | 1150 | 900 |  | 3.773 | 2.9528 |  | 1 | 11.1406
|  | Façade | Sqft | 2500 | 900 |  | 8.2021 | 2.9528 |  | 1 | 24.2188
|  | Led Panel | Sqft | 820 | 1500 |  | 2.6903 | 4.9213 |  | 1 | 13.2396
|  | Total:- | Sqft | [7 empty] | 48.5991
3 | ACP Cladding for signages | Providing, fabricating & fixing of ACP as per approval Make 3mm thick PVDF coated, exterior quality Aluminum Composite Panel with required framing, DC 789 Weather sealant including all necessary hardware etc. complete as directed. | Nos
| OR |  | Nos
| Granite cladding | P&F of 12 mm thick full body granite finish tile cladding walls / column's surface with cement sand mortar bed in 1:4 proportions, finishing of joints in white cement with added colour pigments, including cutting of random sizes , finishing of top edges up to the mark, making cut out provision for all related services such as electrical switch board, plumbing fittings, etc as require. Complete laying in proper line & level as per architectural detail drawing & site engineer's instruction. Basic rate 180/- Sq Ft
|  |  | Sqft | 6000 | 650 |  | 19.685 | 2.1325 |  | 1 | 41.9793
|  | Total:- | Sqft | [7 empty] | 41.9793
4 | Entry main glass door | P/F 10 mm thk. toughened glass partitions with 20 x 40mm MS framework with white powder coating and all necessary required groove, wooden framing, including glass door with heavy duty floor spring fixing with approved make adhesive and fasteners, cutting/ chamfering/ groove/rounding wherever required, at all height with lead and lift, finishing, cleaning as per design and drawing etc. all complete. | [7 empty] | 1 | 1
5 | MAIN DOOR HANDLE | Providing, Supplying & fixing Single sided Sign metal handle with brass finsih. | [7 empty] | 1 | 1

## FACADE SIGNAGE
Site Name :Copper Chimney Project, Vishal Cinema, Delhi
Work: Façade Signage Works
Contractor: Stars and Merit Interiors Private Limited
Work order No : DCPL/Vishal Cinema/CC/23-24/CP-202
Bill NO. :RA-4 Bill
SR.NO. | ITEM | DESCRIPTION | REFERENCE IMAGE | DIMENSION | UNIT | As Per Work order |  |  | As per Bill Quantity |  |  |  |  | As per Bill Amount |  |  | Remarlks
[6 empty] | QTY. | RATE | AMOUNT | Preious Bill | % OF Work | This Bill | Cumulative Bill | % of Works | Preious Bill | This Bill | Cumulative Bill
FAÇADE SIGNAGE
1 | COPPER CHIMNEY | FRONT LIT SIGNAGE - Providing, Supplying & fixing Single sided Sign Board of size with suitable inner frame and proper support, with sign substrate of suitable size of 4mm front glow acrylic sheet with side facia of SS PVD coated in approved color and symbols accordingly, fixed to inner frame with the help of Very High Bond tape of 24mm wide and 2.3mm thick. The board is to be fixed on RCC wall/pillar/ ACP sheet with dash fasteners of SS pipe of S-304 grade. All stainless steel items shall be of S-304 Grade ( EXTERNAL SIGNAGES) (Material should be in compliance with Code of practise for Road signs, Indian Road Congress 2010)
A | Copper Chimney logo - Main signage | SAME AS ABOVE |  | 525mm X 300MM |  | 1 | 25340 | 25340 |  | 0% | 1 | 1 | 100% | 0 | 25340 | 25340
B | Copper Chimney Logo - hostess desk | SAME AS ABOVE |  | 520mm X 350mm |  | 1 | 25340 | 25340 |  | 0% | 1 | 1 | 100% | 0 | 25340 | 25340
C | Copper Chimney Lettering - English | SAME AS ABOVE |  | 3900mm X 300mm |  | 1 | 123000 | 123000 |  | 0% | 1 | 1 | 100% | 0 | 123000 | 123000
E | Copper Chimney Slogan | SAME AS ABOVE |  | 500mm x 80mm |  | 1 | 32450 | 32450 |  | 0% | 1 | 1 | 100% | 0 | 32450 | 32450
TOTAL FAÇADE SIGNAGE | [7 empty] | 206130 | [5 empty] | 0 | 206130 | 206130

## MISCELLANEOUS (hidden)
BOQ of Civil work for Copper Chimney Project, Vishal Cinema, Delhi | [6 empty] | 2023-03-24 |  | R1
|  | GROUND FLOOR |  |  |  |  | FT
SR.NO. | ITEM | DESCRIPTION | DRAWING NO | DIMENSION | UNIT | QTY. | RATE | AMOUNT | REMARK
MISCELLANEOUS -2
1 | Story Wall Images | High Resolution Digital printing on HP Canvas STRETCHED on 1 inch wooden frame (stapling on sides)
Back: 3 mm sun board with leather finish vinyl pasted on it.
Size :
|  | Size : 440 x 600mm |  | 440 x 600mm | NOS |  |  | 0
|  | Size : 440 x 340mm |  | 440 x 340mm | NOS |  |  | 0
2 | Chef Photos | Size : 775 x 1050mm |  |  | NOS |  |  | 0
3 | Artifact | P & F of decorative artifact (approx cost - 250000) |  |  | LS |  |  | 0
4 | Natural & Artificial | P & F of planters (approx cost - 200000) |  |  | LS |  |  | 0
TOTAL MISCELLANEOUS - 2 | [7 empty] | 0

## BELLS
Site Name :Copper Chimney Project, Vishal Cinema, Delhi
Work: Bells Works
Contractor: Stars and Merit Interiors Private Limited
Work order No : DCPL/Vishal Cinema/CC/23-24/CP-202
Bill NO. :RA-4 Bill
SR.NO. | ITEM | DESCRIPTION | LOCATION | DIMENSION | UNIT | As Per Work order |  |  | As per Bill Quantity |  |  |  |  | As per Bill Amount |  |  | Remarlks
[6 empty] | QTY. | RATE | AMOUNT | Preious Bill | % OF Work | This Bill | Cumulative Bill | % of Works | Preious Bill | This Bill | Cumulative Bill
| Bells | Height | Diameter | Design no.
A |  | (160mm+30mm) | (120mm) | 12 | nos | 30 | 1120 | 33600 | 30 | 70% | 0 | 30 | 100% | 23520 | 10080 | 33600
B |  | 7" (135mm+30mm) | 4" (100mm) | 11 | nos | 50 | 983 | 49150 | 50 | 70% | 0 | 50 | 100% | 34405 | 14745 | 49150
C |  | 6 ¾" (115mm+30mm) | 3.5" (90mm) | 10 | nos | 60 | 890 | 53400 | 60 | 70% | 0 | 60 | 100% | 37380 | 16020 | 53400
D |  | 5" (100mm+20mm) | 3" (80mm) | 9 | nos | 80 | 815 | 65200 | 80 | 70% | 0 | 80 | 100% | 45640 | 19560 | 65200
| TOTAL OF BELLS | [6 empty] | 201350 | [5 empty] | 140945 | 60405 | 201350

## Bells MB
Measurement Book of Bells Work Copper Chimney Rajouri Garden
S.No. | Height | Diameter | Unit | Measurement (Feet)
|  |  |  | L | B | H | NO | TOTAL
A | (160mm+30mm) | (120mm) | Nos |  |  |  | 30 | 30
B | 7" (135mm+30mm) | 4" (100mm) | Nos |  |  |  | 50 | 50
C | 6 ¾" (115mm+30mm) | 3.5" (90mm) | Nos |  |  |  | 60 | 60
D | 5" (100mm+20mm) | 3" (80mm) | Nos |  |  |  | 80 | 80

## NON BOQ
Project : Charcoal Concept
Site Name :Copper Chimney Project, Vishal Cinema, Delhi
Work: Interior Finishing and MEP Work
Contractor: Stars and Merit Interiors Private Limited
Work order No : DCPL/Vishal Cinema/CC/23-24/CP-202
RA Bill No : 4
SR.NO. | ITEM | DESCRIPTION | UNIT | As Amendment |  |  |  | As per Bill Quantity |  |  |  |  | As per Bill Amount |  |  | Remarks | Final Doscounted Amount |  | S&M Remarks
|  |  |  | QTY. | RATE |  | AMOUNT | Preious Bill | % OF Work | This Bill | Cumulative Bill | % of Works | Preious Bill | This Bill | Cumulative Bill |  | Rate | Amount
1 | Fire Rated Metal Door | Providing and fixing of Hollow metal fire rated door. Door frame shall be double rebate profile of Suitable szie made out of 1.60mm (16gauge)minimum thick galvanized steel sheet.All doors and frames shall be finished with polyurethane aliphatic grade paint of approved colour. The door leaf and frame shall have passed minimum 250 hours of salt spray test.2Hrs Fire Rated Single leaf of size | NOS | 1 | 36200 | 36200 | 36200 |  |  | 1 | 1 | 100% | 0 | 36200 | 36200 | Noted | 36200 | 36200
2 | Ceiling Fans | P & F of ceiling fans paper as per approval | NOS | 6 | 29000 | 174000 | 174000 |  |  | 6 | 6 | 100% | 0 | 174000 | 174000 | Noted | 27432 | 164592 | Basis cost of Rs 21600/ plus Rs 15000/ freight from Bangalore to Delhi
3 | Stucco Paint | Stucko paint As Per Approval makes and approved drawings | Sqft | 320.1015 | 360 | 115236.5305 | 115236.5305 |  |  | 320.1015 | 320.1015 | 100% | 0 | 115236.5305 | 115236.5305 | Noted | 312 | 99871.6597
4 | Removal | Existing Exhaust fan removal | Each | 2 | 4700 | 9400 | 9400 |  |  | 2 | 2 | 100% | 0 | 9400 | 9400 | Noted | 4700 | 9400
5 | Ms Plateform | Electrical Panel Platform | Each | 1 | 8200 | 8200 | 8200 |  |  | 1 | 1 | 100% | 0 | 8200 | 8200 | Noted | 8200 | 8200
6 | Sccafolding | Scaffolding For Outside Area for exhaust and fresh air duct. | Each | 1 | 45000 | 45000 | 45000 |  |  | 1 | 1 | 100% | 0 | 45000 | 45000 | Noted | 45000 | 45000 | This will further increase due to the delays from Mall team and working time from 1 AM midnight till 6 AM
7 | Storage Rack | Providing and Fixing Of Storage made out of 18mm thick ply With Mica Finish as Per the approval of Project Incharge.Having Size of 900*900*2400 | Each | 1 | 62000 | 62000 | 62000 |  |  | 1 | 1 | 100% | 0 | 62000 | 62000 | Noted | 51230 | 51230
8 | Ahu Boxing | Providing and Fixing of Gypsum Laying on Exisiting Ply Boxing For Boxing Ahu With Appvoved finish,as Per the approval of Project Incharge. | Sqft | 694.2023 | 52 | 36098.5173 | 36098.5173 |  |  | 694.2023 | 694.2023 | 100% | 0 | 36098.5173 | 36098.5173 | Noted | 46 | 31933.3038
9 | Frosted Film | Frosted Film | Sqft | 94.5502 | 220 | 20801.0416 | 20801.0416 |  |  | 94.5502 | 94.5502 | 100% | 0 | 20801.0416 | 20801.0416 | Noted | 165 | 15600.7812
10 | Equipment Shifting | Providing labourers for unloading and shifting of Kitchen equipments as per instruction given by Site in charge | Lot | 6 | 15500 | 93000 | 93000 |  |  | 6 | 6 | 100% | 0 | 93000 | 93000 | Noted | 14000 | 84000 | This will further increase.
11 | SS Gratings | Providing and fixing of Chamber SS cover grating upto size 300 mm 300 mm. | Each | 8 | 3500 | 28000 | 28000 |  |  | 8 | 8 | 100% | 0 | 28000 | 28000 | Noted; removed from Kitchen fabricator scope | 3500 | 28000 | It is not there in any other items nor in the Initial BOQ.
12 | SS Gratings | Providing and fixing of Chamber SS cover grating upto size 300 mm 600 mm. | Each | 1 | 7250 | 7250 | 7250 |  |  | 1 | 1 | 100% | 0 | 7250 | 7250 | Noted; removed from Kitchen fabricator scope | 6234 | 6234 | It is not there in any other items nor in the Initial BOQ.
13 | Sprinkler | Providing, fixing, testing and commissioning brass quartzoid sprinklers K-80 (UL-Underwriters Laboratories Listed) suitable for 175 psi(12 Bars) maximum working pressure and 7 psi(0.5 Bars) minimum operating pressure with 15 mm dia BSPT threaded opening complete in all respects. The type & temperature rating shall be as follows. Make-SAFEX/NEWAGE/HD FIRE |  | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 |  |  | 0
| a) | Pendent Concealed Sprinklers (141°)- Quick response type | Nos | 8 | 815 | 6520 | 6520 |  |  | 8 | 8 | 100% | 0 | 6520 | 6520 | Noted | 815 | 6520
|  |  |  | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 |  |  | 0
14 | Site Deep Cleaning | Deep Cleaning | Nos | 1 | 35000 | 35000 | 35000 |  |  | 1 | 1 | 100% | 0 | 35000 | 35000 | Noted | 35000 | 35000 | This will furtehr increase.
15 | WPC of Main Wall. | Extra for 12 mm WPC of Main Wall. | Nos | 700.004 | 108 | 75600.4325 | 75600.4325 |  |  | 700.004 | 700.004 | 100% | 0 | 75600.4325 | 75600.4325 | Noted | 108 | 75600.4325 | Basic Rate of Rs 78 PSF plus Rs 27 as the installation cost.
16 | SS Front For Bar | SS Front Elevations For Bar Area Including Glass Hangings Unit | LS | 1 | 78000 | 78000 | 78000 |  |  | 1 | 1 | 100% | 0 | 78000 | 78000 | Noted | 66230 | 66230 | It is the complete arrangement of SS with Brass Color Coating for the Baar. Cost from the supplier for us is Rs 46000/ Plus the Coating cost is 14000/
17 | Buster Pump | P/F and Fixing Pressure Buster Pump For Kitchen water supply Lines | Each | 1 | 22500 | 22500 | 22500 |  |  | 1 | 1 | 100% | 0 | 22500 | 22500 | Noted | 20345 | 20345
18 | Metal Ceiling | Supply of Metal false ceiling consisting 600mmx600mmX0.7 mm tilesalong with necessary supports , hangers etc. Make-Armstrong | Sqm | 44.1088 | 2588 | 114153.7038 | 114153.7038 |  |  | 44.1088 | 44.1088 | 100% | 0 | 114153.7038 | 114153.7038 | Noted | 1600 | 70574.16
19 | 6-Way TPN Db | Supply and Installation of TPN DB including Switchgear as per site requirement. | NOS | 1 | 21300 | 21300 | 21300 |  |  | 1 | 1 | 100% | 0 | 21300 | 21300 | Noted | 21300 | 21300
20 | LED Glass | Supply and Fixing of Glass for LED TV Protection including With SS Profiles as per design and site requirement | NOS | 1 | 18700 | 18700 | 18700 |  |  | 1 | 1 | 100% | 0 | 18700 | 18700 | Noted | 18700 | 18700
21 | HI-Wall Split AC | Supply and Installation HI-Wall Split AC 2 tonnes as per requirement | NOS | 1 | 62000 | 62000 | 62000 |  |  | 1 | 1 | 100% | 0 | 62000 | 62000 | Noted | 62000 | 62000 | 2 Tr Ac installed in palce of 1.5 Tr.
22 | Gas Piping Work | Supply and laying of Gas Piping Work as per recommend by Projects incharge | Lumsum | 0 | 85000 | 0 | 0 |  |  | 0 |  |  | 0 |  |  |  | 85000 | 0
23 | LT Cabels |  |  | 0 |  | 0 | 0 |  |  | 0 | 0 | 100% | 0 | 0 | 0 |  |  | 0
a | 4C X2.5 Sqmm Copper CaBLE | Supply and Laying,Testing and Comissioning of 4C X2.5 Sqmm Copper Cable for GLD Panel along with | Rmt | 120 | 165 | 19800 | 19800 |  |  | 120 | 120 | 100% | 0 | - | - | part of initial scope | 165 | 19800 | These are not part of Initial BOQ.
b | 2C X1.5 Sqmm Copper CaBLE | Supply and Laying,Testing and Comissioning of 2C X1.5 Sqmm Copper Cable for GLD Panel along with | Rmt | 52 | 123 | 6396 | 6396 |  |  | 52 | 52 | 100% | 0 | - | - | part of initial scope | 123 | 6396
c | 3C X2.5 Sqmm Copper CaBLE | Supply and Laying,Testing and Comissioning of 3C X2.5 Sqmm Copper Cable for Pump Controller | Rmt | 46 | 135 | 6210 | 6210 |  |  | 46 | 46 | 100% | 0 | - | - | part of initial scope | 135 | 6210
d | 4C X1.5 Sqmm Copper CaBLE | Supply and Laying,Testing and Comissioning of 4C X1.5 Sqmm Copper Cable for Ahu control cable | Rmt | 40 | 131 | 5240 | 5240 |  |  | 40 | 40 | 100% | 0 | - | - | part of initial scope | 131 | 5240
24 | Supply of Lights | Supply and installation of Lights as per Site requirement and approved by Project incharge |  | 0 |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0
a | Luxxor-LED 36 Watt | Luxxor-LED 36 Watt- Recessed Light | Nos | 3 | 2967.5 | 8902.5 | 8902.5 |  |  | 3 | 3 | 100% | 0 | 8902.5 | 8902.5 | Noted | 1450 | 4350
c | Luxxor-LED 12 Watt | Luxxor-LED 12 Watt- Spot light four way movement with phase cut drivers | Nos | 4 | 3030 | 12120 | 12120 |  |  | 4 | 4 | 100% | 0 | 12120 | 12120 | Noted | 2312 | 9248
25 | Ceiling Mounted CO2 Fire Cylinder | Supply and installation of Ceiling Mounted CO2 Fire Cylinder as per site requirement | Nos | 1 | 2100 | 2100 | 2100 |  |  | 1 | 1 | 100% | 0 | - | - | Not approved | 0 | 0
26 | Rework at Entrance MS Framing Work | Rework at Entrance MS Framing Work | Nos | 1 | 15000 | 15000 | 15000 |  |  | 1 | 1 | 100% | 0 | - | - | Not approved | 12000 | 12000 | What we have taken very less Amount There have been few changes due to which lot of labour and material was wasted. Reducing to 12 K
27 | SS Taps for Sink | SS Taps for Sink | Nos | 6 | 2100 | 12600 | 12600 |  |  | 0 | 0 | 100% | 0 | 0 | 0 | Noted | 2100 | 0
28 | Civil Work changes due to Layout | Civil Work changes due to Layout | Nos | 1 | 25000 | 25000 | 25000 |  |  | 1 | 1 | 100% | 0 | - | - | Not approved | 20000 | 20000 | What we have quoted is less. There have been Several Changes due to which lot of labour and overheads Reducing it to 20 K
29 | Drawer units | Storage Drawer units for sofas as per revised Drawings ( Units are made in 18mm ply and both side laminate finishing, Sliding Channels, Handles etc using barnded harware hetich etc. Approx Size (500X600) | Nos | 32 | 3350 | 107200 | 107200 |  |  | 32 | 32 | 100% | 0 | 107200 | 107200 | Noted | 3023 | 96736 | Storage Drawer units for sofas as per revised Drawings ( Units are made in 18mm ply and both side laminate finishing, Sliding Channels, Handles etc using barnded harware hetich etc. Approx Size (500X600)
30 | Rework of Fire-Fighting Works | Extra Labour used for rework of Fire-Fighting Works as per Mall and Client Instructions. | Nos | 2 | 7500 | 15000 | 15000 |  |  | 2 | 2 | 100% | 0 | 15000 | 15000 | Noted | 7500 | 15000
31 | Rework of Electrical Works | Extra Labour used for rework of Electrical Works as per client Instructions and further changes in drawings as per mall and as per client | Nos | 4 | 3800 | 15200 | 15200 |  |  | 4 | 4 | 100% | 0 | 15200 | 15200 | Noted | 3800 | 15200
32 | Extra Switchgear as per Instructed by mall management. | Extra Switchgear as per Instructed by mall management. | Nos | 0 |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0
a | RCCB 40/4/30 ma | RCCB 40/4/30 ma | Nos | 3 | 2522.0333 | 7566.1 | 7566.1 |  |  | 3 | 3 | 100% | 0 | 7566.1 | 7566.1 | Noted | 2522.0333 | 7566.1
b | ELCB 63/2/30 ma | ELCB 63/2/30 ma | Nos | 1 | 2862.3 | 2862.3 | 2862.3 |  |  | 1 | 1 | 100% | 0 | 2862.3 | 2862.3 | Noted | 2862.3 | 2862.3
c | RCCB 63/4/30 ma | RCCB 63/4/30 ma | Nos | 1 | 3127.65 | 3127.65 | 3127.65 |  |  | 1 | 1 | 100% | 0 | 3127.65 | 3127.65 | Noted | 3127.65 | 3127.65
d | 1200 mm Alfa Breeze | 1200 mm Alfa Breeze | Nos | 1 | 1776.25 | 1776.25 | 1776.25 |  |  | 1 | 1 | 100% | 0 | 1776.25 | 1776.25 | Noted | 1776.25 | 1776.25
33 | Hood Installation | Installation of Hood inside Kitchen area and Live kitchen area rates are including of all the consumables. | Nos | 3 | 7100 | 21300 | 21300 |  |  | 3 | 3 | 100% | 0 | 21300 | 21300 | Noted | 7100 | 21300
34 | Anti-Vibration pads | Supply and Installation of Anti-vibration pads as per requirement | Nos | 12 | 1820 | 21840 | 21840 |  |  | 12 | 12 | 100% | 0 | 21840 | 21840 | Noted | 1820 | 21840
0
|  | Grand Total |  |  |  |  | 1378201.0257 | [5 empty] | 0 | 1285855.0257 | 1285855.0257 |  |  | 1225183.6372

## NON BOQ (2)
Project : Charcoal Concept
Site Name :Copper Chimney Project, Vishal Cinema, Delhi
Work: Interior Finishing and MEP Work
Contractor: Stars and Merit Interiors Private Limited
Work order No : DCPL/Vishal Cinema/CC/23-24/CP-202
RA Bill No : 4
SR.NO. | ITEM | DESCRIPTION | UNIT | As Amendment |  |  | As per Bill Quantity |  |  |  |  | As per Bill Amount |  |  | Remarks
|  |  |  | QTY. | RATE | AMOUNT | Preious Bill | % OF Work | This Bill | Cumulative Bill | % of Works | Preious Bill | This Bill | Cumulative Bill
35 | Providing Additional Ms Rods 900mm for Fans Fixing As per the Instruction of Project incharge. |  | Nos | 6 | 2300 | 13800 |  |  | 6 | 6 | 100% | 0 | 13800 | 13800 | Noted
36 | Wiring for single phase 20A, 230 V Industrial Socket & Plug Top in Moulded Plastic Box (IP55) controlled by 20A SP MCB with 3 x 4 Sq. mm PVC insulated FRLS multi strand copper conductor 1100 Volt grade wires in recessed/surface GI conduit with accessories including cost of saddles etc for surface conduiting and/or cost of cutting chases for recessed conduiting, including providing of JB at Eqpt. Location, complete as per specification and as required. (Make ABB, Legrands, Schneider) |  | Each | 6 | 4370 | 26220 |  |  | 3 | 3 | 100% | 0 | 13110 | 13110 | Noted. Reduce qty to 3 as we added 3 additional only
37 | Three phase 20A, 400 V Industrial Socket & Plug Top Changed With Single Phase Modular Swith Socket |  | Each | 2 | 1400 | 2800 |  |  | 2 | 2 | 100% | 0 | 2800 | 2800 | Noted
38 | Removal of Live Kitchen Area Glazing And Refixing of the same for tandoor Placement, as per the instruction of the Project Manager |  | L.S | 1 | 15000 | 15000 |  |  | 1 | 1 | 100% | 0 | 15000 | 15000 | Noted
39 | Two Additional Point For Ceiling Fans, As per The site Condition. As per the Instruction Of Project Manager. |  | L.S | 2 | 2100 | 4200 |  |  | 2 | 2 | 100% | 0 | 0 |  | Not Approved
40 | Additional Switch Sockets And Site Condition. As approved by Project Manager |  | L.S | 1 | 12000 | 12000 |  |  | 1 | 1 | 100% | 0 | 0 |  | Not Approved, location not mentioned
41 | Providing And Fixing Of 1000w Helogen For Tandoor |  | L.S | 2 | 800 | 1600 |  |  | 2 | 2 | 100% | 0 | 1600 | 1600 | Noted
42 | Proving LPG Cylinder and required fittings For Kitchen Use, As per the instruction of Project Incharge |  | LS | 1 | 2600 | 2600 |  |  | 1 | 1 | 100% | 0 | 2600 | 2600 | Noted
43 | Silicon Work Done As Per The Instructions |  | Ls | 1 | 28000 | 28000 |  |  | 1 | 1 | 100% | 0 | 28000 | 28000 | Noted
44 | Faucets For Dish Wash Area |  | Each | 4 | 6500 | 26000 |  |  | 4 | 4 | 100% | 0 | 26000 | 26000 | Noted
45 | Additinoal Plumbing Point as per the Site Condition |  | Each | 1 | 3500 | 3500 |  |  | 1 | 1 | 100% | 0 | 3500 | 3500 | Noted
46 | Equipment Drain work With Mislanious Fittings |  | LS | 1 | 21000 | 21000 |  |  | 1 | 1 | 100% | 0 | 21000 | 21000 | Noted
47 | Proving Tip Wooden Box and per instructions of project manager |  | LS | 1 | 3100 | 3100 |  |  | 1 | 1 | 100% | 0 | 3100 | 3100 | Noted
48 | Fixing of Pesto flash |  | Ls | 1 | 800 | 800 |  |  | 1 | 1 | 100% | 0 | 800 | 800 | Noted
49 | Supply, installation, testing and commissioning of 50 micron powder coated Linear Grill/Diffuser, Note: color as per Interior Designer |  | Sqmt | 0.675 | 7800 | 5265 |  |  | 0.675 | 0.675 | 100% | 0 | 5265 | 5265 | Noted
50 | Supplying, installing, testing & commissioning of GI volume control damper with minimum 1.6 mm flange and 1.8 mm blade thickness within ducts to be provided with suitable links, levers and quadrants for manual control of volume of air flow and for proper balancing of the air distribution system as per schedules & drawings. |  | Sqmt | 0.675 | 8000 | 5400 |  |  | 0.675 | 0.675 | 100% | 0 | 5400 | 5400 | Noted
51 | Entrance gate duco paint |  | Each | 1 | 12000 | 12000 |  |  | 1 | 1 | 80% |  | 0 |  | Not Approved
52 | Kitchen Equepment Installatiin |  | Each | 1 | 8000 | 8000 |  |  | 1 | 1 | 100% |  | 8000 | 8000 | Noted
53 | Cat 6 wire for additional |  | Each | 1 | 3500 | 3500 |  |  | 1 | 1 | 100% |  | 3500 | 3500 | Noted
54 | Panel integration |  | Each | 1 | 7000 | 7000 |  |  | 1 | 1 | 100% |  | 0 |  | Not Approved
55 | Labour |  | Each | 1 | 14000 | 14000 |  |  | 1 | 1 | 100% |  | 14000 | 14000
56 | Pcc For Basement area |  | Each | 1 | 5000 | 5000 |  |  | 1 | 1 | 100% |  | 5000 | 5000 | Noted
57 | Jar Unit Which was waste due Drawing Changes |  | Each | 1 | 20000 | 20000 |  |  | 1 | 1 | 0% |  | 0 | 0
|  | Grand Total |  |  |  | 240785 | [5 empty] | 0 | 172475 | 172475

## Non BOQ MB
Measurement Book of Interior Work Copper Chimney Rajouri Garden
S.No. | Items | Descriptions | Unit | Measurement (mm) |  |  | Measurement (Feet)
|  |  |  | L | B | H | L | B | H | NO | TOTAL
General Site Work
1 | Fire Rated Metal Door | Providing and fixing of Hollow metal fire rated double leaf door. Door frame shall be double rebate profile of size 143 x 57 mm made out of 1.60mm (16gauge)minimum thick galvanized steel sheet.All doors and frames shall be finished with polyurethane aliphatic grade paint of approved colour. The door leaf and frame shall have passed minimum 250 hours of salt spray test.2Hrs Fire Rated Single leaf of size | NOS | [6 empty] | 1 | 1
2 | Ceiling Fans | P & F of ceiling fans paper as per approval | NOS | [6 empty] | 6 | 6
3 | Stucko Paint | Stucko paint As Per Approval makes and approved drawings | Sqft
|  | Curtain Wall LHS | Sqft | 8284 | 2600 |  | 27.1785 | 8.5302 |  | 1 | 231.8374
|  | Near Bar Area | Sqft | 2000 | 2600 |  | 6.5617 | 8.5302 |  | 1 | 55.9723
|  | Inside facede | Sqft | 6000 | 500 |  | 19.685 | 1.6404 |  | 1 | 32.2917
|  |  | Sqft |  |  |  | 0 | 0 |  |  | 0
|  |  | Sqft |  |  |  | 0 | 0 |  |  | 0
|  | Total:- | Sqft | [7 empty] | 320.1015
4 | Removal | Existing Exhaust fan removal | Each | [6 empty] | 2 | 2
5 | Ms Plateform | Electrical Panel Platform | Each | [6 empty] | 1 | 1
6 | Sccafolding | Scaffolding For Outside Area for exhaust and fresh air duct. | Each | [6 empty] | 1 | 1
7 | Storage Rack | Providing and Fixing Of Storage made out of 18mm thick ply With Mica Finish as Per the approval of Project Incharge.Having Size of 900*900*2400 | Each | [6 empty] | 1 | 1
8 | Ahu Boxing | Providing and Fixing of Gypsum Laying on Exisiting Ply Boxing For Boxing Ahu With Appvoved finish,as Per the approval of Project Incharge. | Sqft
|  | Vertical | Sqft | 6850 | 4510 |  | 22.4738 | 14.7966 |  | 1 | 332.5349
|  | Less Opening | Sqft | 1500 | 1900 |  | 4.9213 | 6.2336 |  | -1 | -30.6771
|  | Horizontal | Sqft | 5350 | 1600 |  | 17.5525 | 5.2493 |  | 1 | 92.1391
|  |  | Sqft | 1900 | 1600 |  | 6.2336 | 5.2493 |  | 2 | 65.4446
|  |  | Sqft | 1500 | 1600 |  | 4.9213 | 5.2493 |  | 1 | 25.8334
|  | Extended area Covering of Ahu Planeum | Sqft | 6850 | 2000 |  | 22.4738 | 6.5617 |  | 1 | 147.4656
|  | Less Opening | Sqft | 1500 | 1900 |  | 4.9213 | 6.2336 |  | -1 | -30.6771
|  | Horizontal | Sqft | 5350 | 1600 |  | 17.5525 | 5.2493 |  | 1 | 92.1391
Sqft
|  | Total:- | Sqft | [7 empty] | 694.2023
9 | Frosted Film | Frosted Film | Sqft
|  | Façade | Sqft | 3600 | 2440 |  | 11.811 | 8.0052 |  | 1 | 94.5502
10 | Equipment Shifting | Providing labourers for unloading and shifting of Kitchen equipments as per instruction given by Site in charge | Lot | [6 empty] | 6 | 6
11 | SS Gratings | Providing and fixing of Chamber SS cover grating upto size 300 mm 300 mm. | Each | [6 empty] | 8 | 8
12 | SS Gratings | Providing and fixing of Chamber SS cover grating upto size 300 mm 600 mm. | Each | [6 empty] | 1 | 1
13 | Sprinkler | Providing, fixing, testing and commissioning brass quartzoid sprinklers K-80 (UL-Underwriters Laboratories Listed) suitable for 175 psi(12 Bars) maximum working pressure and 7 psi(0.5 Bars) minimum operating pressure with 15 mm dia BSPT threaded opening complete in all respects. The type & temperature rating shall be as follows. Make-SAFEX/NEWAGE/HD FIRE
| a) | Pendent Concealed Sprinklers (141°)- Quick response type | Nos | [6 empty] | 8 | 8
14 | Site Deep Cleaning | Final/Deep Cleaning of the Site for final Handover as directed by Project Incahrge. Vendor need to take Prior Approval from Projcet incharge to carried out this activity. | L.S | [6 empty] | 1 | 1
15 | WPC of Main Wall. | Extra for 19 mm WPC of Main Wall. | Sqft
|  | Main Wall 1 | Sqft | 17940 | 3625 |  | 58.8583 | 11.893 |  | 1 | 700.004
|  | Main Wall 2 | Sqft |  |  |  | 0 | 0 |  | 1 | 0
|  | Total:- | [8 empty] | 700.004
16 | SS Front For Bar | SS Front Elevations For Bar Area Including Glass Hangings Unit | LS | [6 empty] | 1 | 1
17 | Buster Pump | P/F and Fixing Pressure Buster Pump For Kitchen water supply Lines | Each | [6 empty] | 1 | 1
18 | Supply of Metal Ceiling | Supply of Metal false ceiling consisting 600mmx600mmX0.7 mm tilesalong with necessary supports , hangers etc. Make-Armstrong
|  | live Kitchen | Sqft | 3.675 | 1.38 |  |  |  |  | 1 | 5.0715
0
|  | Main Kitchen | Sqft | 6.015 | 6.49 |  |  |  |  | 1 | 39.0373
0
|  | Total Qty | [8 empty] | 44.1088
19 | 6-Way TPN Db | Supply and Installation of TPN DB including Switchgear as per site requirement. | NOS | [6 empty] | 1 | 1
20 | LED Glass | Supply and Fixing of Glass for LED TV Protection including With SS Profiles as per design and site requirement | NOS | [6 empty] | 1 | 1
21 | HI-Wall Split AC | Supply and Installation HI-Wall Split AC 1.5 tonnes as per requirement | NOS | [6 empty] | 1 | 1
22 | Gas Piping Work | Supply and laying of Gas Piping Work as per recommend by Projects incharge | NOS | [6 empty] | 1 | 1
23 | LT Cabels | [9 empty] | 0
a | 4C X2.5 Sqmm Copper CaBLE | Supply and Laying,Testing and Comissioning of 4C X2.5 Sqmm Copper Cable for GLD Panel along with | Rmt | 120 | [5 empty] | 1 | 120
b | 2C X1.5 Sqmm Copper CaBLE | Supply and Laying,Testing and Comissioning of 2C X1.5 Sqmm Copper Cable for GLD Panel along with | Rmt | 52 | [5 empty] | 1 | 52
c | 3C X2.5 Sqmm Copper CaBLE | Supply and Laying,Testing and Comissioning of 3C X2.5 Sqmm Copper Cable for Pump Controller | Rmt | 46 | [5 empty] | 1 | 46
d | 4C X1.5 Sqmm Copper CaBLE | Supply and Laying,Testing and Comissioning of 4C X1.5 Sqmm Copper Cable for Ahu control cable | Rmt | 40 | [5 empty] | 1 | 40
24 | Supply of Lights | Supply and installation of Lights as per Site requirement and approved by Project incharge | [8 empty] | 0
a | Luxxor-LED 36 Watt | Luxxor-LED 36 Watt- Recessed Light | Nos | [6 empty] | 3 | 3
c | Luxxor-LED 12 Watt | Luxxor-LED 12 Watt- Spot light four way movement | Nos | [6 empty] | 4 | 4
25 | Ceiling Mounted CO2 Fire Cylinder | Supply and installation of Ceiling Mounted CO2 Fire Cylinder as per site requirement | Nos | [6 empty] | 1 | 1
26 | Rework at Entrance MS Framing Work | Rework at Entrance MS Framing Work | Nos | [6 empty] | 1 | 1
27 | SS Taps for Sink | SS Taps for Sink | Nos | [6 empty] | 6 | 6
28 | Civil Work changes due to Layout | Civil Work changes due to Layout | Nos | [6 empty] | 1 | 1
29 | Drawer units | Drawer units for sofas as per revised Drawings | Nos | [6 empty] | 32 | 32
30 | Rework of Fire-Fighting Works | Extra Labour used for rework of Fire-Fighting Works as per Mall and Client Instructions. | Nos | [6 empty] | 2 | 2
31 | Rework of Electrical Works | Extra Labour used for rework of Electrical Works as per client Instructions and further changes in drawings as per mall and as per client | Nos | [6 empty] | 4 | 4
32 | Extra Switchgear as per Instructed by mall management. | Extra Switchgear as per Instructed by mall management. | Nos | [7 empty] | 0
a | RCCB 40/4/30 ma | RCCB 40/4/30 ma | Nos | [6 empty] | 3 | 3
b | ELCB 63/2/30 ma | ELCB 63/2/30 ma | Nos | [6 empty] | 1 | 1
c | RCCB 63/4/30 ma | RCCB 63/4/30 ma | Nos | [6 empty] | 1 | 1
d | 1200 mm Alfa Breeze | 1200 mm Alfa Breeze | Nos | [6 empty] | 1 | 1
33 | Hood Installation | Installation of Hood inside Kitchen area and Live kitchen area rates are including of all the consumables. | Nos | [6 empty] | 3 | 3
34 | Anti-Vibration pads | Supply and Installation of Anti-vibration pads as per requirement | Nos | [6 empty] | 12 | 12
0