## SUMMARY
DATE:20-04-2024
BOQ of Total C&I works for Copper Chimney
Location- | OBEROI MALL - GOREGAON
SUMMARY OF BOQ ITEMS BILL
Sr. No. | Item Description | BOQ Amount in INR. | Audited Amount as per Site | DIFFERENCE (AS PER ACTUAL-ORDER VALUE)
1 | Civil Works. | 2116565 | 2567252.464 | -450687.464
2 | Interior Work | 4528750 | 4401297.071 | 127452.929
3 | Bells /Extra Items | 83375 | 36720 | 46655
5 | Miscellaneous | 86700 | 64575 | 22125
6 | NT Items |  | 382551.3375 | -382551.3375
| Subtotal amount INR. (without taxes) | 6815390 | 7452395.8725 | -637005.8725
| GST @ 18% | 1226770.2 | 1341431.257
| GRAND TOTAL | 8042160.2 | 8793827.1296 | -751666.9296
AMOUNT IN WORDS:

## CIVIL WORK
BOQ of Civil work for Copper Chimney Project, Goregaon-Oberoi mall
[5 empty] | AS PER BOQ |  |  | AS PER SITE(Audited) |  | Deviation
SR.NO. | ITEM | DESCRIPTION | DIMENSION | UNIT | QTY. | RATE | AMOUNT | QTY. | AMOUNT | QTY | Amount
GENERAL SITE WORKS
1 | Pest control at site | Providing Pest Control & Anti-termite treatment by appointing a specialized agency as per the specifications mentioned by the Bureau of Indian Standard & Agencies specification ( Whichever is higher ) for General Civil , Plumbing / Drainage & timber / Carpentry works , Gypsum related work including 5 Years guarantee under suitable undertaking on stamp paper etc complete as directed . (Mode of Measurement to be on carpet area of floor & not the area of surface treated.) | N.A | SFT | 2100 | 10 | 21000 | 1946.5212 | 19465.212 | 153.4788 | 1534.788
DEMOLITION WORKS
1 | Wall Puncture | Removing of POP punning and making wall puncture size of 200-600mm wide on existing wall, including cleaning the surface and proper plaster in line and level ready to paint & dump the debris's at ground floor debris point. | N.A | NO's | 5 | 600 | 3000 | 3 | 1800 | 2 | 1200
2 | Debris | Removing Debris out of site included loading, unloading & shifting as per statutory rules and regulations. | N.A | NO's | 1 | 4000 | 4000 | 23 | 92000 | -22 | -88000
INTERIOR CIVIL WORK
1 | Membrane Waterproofing | P&A Waterproofing on mother slabs & wall till 450mm height, with membrane water proofing treatment on the mother slab, before doing the treatment mother slab needs to clean properly up to the mark & dust free surface needs to achieve to apply the chemical (proof bond /BASF, Dr. Fixit / Equivalent make) & chemical needs to dry properly, After all there should be a water pond testing to be done for water tightness & rectifications of defects if any. Complete with 10 years performance guarantee with client's satisfaction. Entire process to be done under guideline & supervision of appointed engineering team.
| a | Kitchen -floor | N.A | SFT | 575 | 100 | 57500 | 489.5 | 48950 | 85.5 | 8550
| b | Kitchen -wall up to 1000 mm | N.A | SFT | 350 | 100 | 35000 | 515.88 | 51588 | -165.88 | -16588
| c | Live kitchen -floor | N.A | SFT | 140 | 100 | 14000 | 130.4478 | 13044.78 | 9.5522 | 955.22
| d | Live kitchen -wall up to 1000 mm | N.A | SFT | 100 | 100 | 10000 | 179.28 | 17928 | -79.28 | -7928
| e | Bar -floor | N.A | SFT | 160 | 100 | 16000 | 109.8531 | 10985.31 | 50.1469 | 5014.69
| f | Bar -wall up to 1000 mm | N.A | SFT | 235 | 100 | 23500 | 232.64 | 23264 | 2.36 | 236
2 | Block Work | Providing and constructing Light weight blocks masonry in cement mortar 1:4 of approved make like Aerocon/Siporex etc. Job to include raking out joints, scaffolding, making openings walls, curing etc. in substructure and superstructure to its true line & level in cement mortar proportion as specified in all shapes, size, at all heights, depths, leads & locations etc. complete. The rate shall also include for cleaning of surface, hacking of RCC surface in contact with brickwork, racking of joints, providing, erecting, & dismantling steel scaffolding , curing for 10 days, including 75 mm thk. R.C.C. stiffener at approximately every 1000 mm ht. with required M.S. reinforcement bars and Lintels for Doors and wall openings etc. compete as per the drgs., details & specifications.
| a | Using 150mm thk Walls upto 1050 mm | N.A | SFT | 100 | 160 | 16000 | 213.8555 | 34216.88 | -113.8555 | -18216.88
| b | Using 150mm thk Walls upto 4200mm | N.A | SFT | 925 | 160 | 148000 | 1895.0777 | 303212.432 | -970.0777 | -155212.432
3 | Internal Plaster | P&A of single coat backing plaster of 15-18 mm thick in CM 1:4 proportion to the walls & others surface including scaffolding, curing the joints, etc. The rates are inclusive of providing chicken mesh of 18mm gauge & 150mm width at junction of brick & RCC etc. at the walls, columns, beams etc., seven days water treatment as anti crack of plaster. Complete as per site engineer's instruction. | N.A
| a | Bar Area & Live Kitchen (low height wall 1050mm) |  | SFT | 200 | 55 | 11000 | 602.2084 | 33121.462 | -402.2084 | -22121.462
| b | Wall height (4200mm) consider |  | SFT | 1850 | 60 | 111000 | 3883.3954 | 233003.724 | -2033.3954 | -122003.724
0
4 | PCC Work | Providing and laying up to 50-75 mm thick cement concrete flooring with 1:2:4 cement concrete laid to proper level and slope in alternate bays including compactions, filling joints, or as directed, finishing smooth with cement Mortar 1:1 of sufficient minimum thickness to give a smooth & even surface and curing etc. complete as per architects instructions. | N.A | SFT | 875 | 85 | 74375 | 1207.3703 | 102626.4755 | -332.3703 | -28251.4755
5 | COBA Work (Modiform) | Modiform of Avg. thickness mentioned below; After laying of soil pipes, floor traps is completed the floor of the sunken portion shall be covered with Modiform manually with 15-20 mm wide joints in 20 mm thk. Waterproofing mortar 1:4 ( 1 cement : 4 coarse sand )in layers upto the full ht. of sunken portion, having top layer of 50 mm thk waterproof mortar 1:4 ( 1 cement : 4 coarse sand ) using specialized W.P. chemical, finished smooth / rough with floating coat of neat cement all complete and as per specification.
| a | Kitchen (300mm) appox | N.A | SFT | 550 | 210 | 115500 | 489.5 | 102795 | 60.5 | 12705
| b | Live kitchen (300mm) appox | N.A | SFT | 140 | 210 | 29400 | 130.4478 | 27394.038 | 9.5522 | 2005.962
| c | Bar (150mm) appox | N.A | SFT | 160 | 145 | 23200 | 108.9531 | 15798.1995 | 51.0469 | 7401.8005
STONE & TILE WORKS
1 | KOTA Flooring | Providing and Laying KOTA stone of 19mm thk. on avg 40 mm thk bed of 1:4 cement mortar in proper line and level including neat cement float, filling joints with neat cement slurry of appropriate colour, cleaning, curing, rubbing, complete. Scope includes laying of floor protective cover on the floor and removing of the same when directed along with supply of all necessary materials, labour, tools and tackles complete in line with the Technical Specification, Drawings and as per the direction of the Architect & PMC. Including Polishing.
Size : 550x550 Basic Rate : 55 Per SFT
| a | Kitchen | N.A | SFT | 550 | 160 | 88000 | 513.5 | 82160 | 36.5 | 5840
| b | Live kitchen |  | SFT | 135 | 160 | 21600 | 130.4478 | 20871.648 | 4.5522 | 728.352
| c | Bar |  | SFT | 95 | 160 | 15200 | 77.1156 | 12338.496 | 17.8844 | 2861.504
| d | Liquor Store Room |  | SFT | 50 | 160 | 8000 | 31.8375 | 5094 | 18.1625 | 2906
2 | Wooden finish herringbone pattern Tile Flooring | Fixing & laying of tiles for flooring which includes --bedding of appropriate thickness with mortar of 1:6 ratio (1cement:6sand), spreading of grey cement slurry with minimum of 2kg/ Sq.mt. ratio over bedding mortar, including 3mm spacer with epoxy grout of approved colour, adhesive of bal Endura or approved equivalent, making of hole where ever required, in proper line and level in all direction, at all height with lead and lift, polishing/finishing/cleaning etc. as per design and drawing and directed by PMC etc. complete. | N.A | SFT | 750 | 275 | 206250 | 706.8003 | 194370.0825 | 43.1997 | 11879.9175
size - 200x1200. Basic Rate : 150 Per SFT (make kajaria)
3 | Pattern Tile Flooring | Fixing & laying of tiles for flooring which includes --bedding of appropriate thickness with mortar of 1:6 ratio (1cement:6sand), spreading of grey cement slurry with minimum of 2kg/ Sq.mt. ratio over bedding mortar, including 3mm spacer with epoxy grout of approved colour, adhesive of bal Endura or approved equivalent, making of hole where ever required, in proper line and level in all direction, at all height with lead and lift, polishing/finishing/cleaning etc. as per design and drawing and directed by PMC etc. complete. | N.A | SFT | 500 | 390 | 195000 | 509.38 | 198658.2 | -9.38 | -3658.2
size - 300x300. Basic Rate : 220 Per SFT
4 | Wooden finish Tile skirting | Fixing & laying of 100mm high tiles for skirting with bedding of appropriate approved make adhesive & colour joint filler inclusive of making all groove/chamfering/rounding/hole where ever required, in proper line and level in all direction, polishing/finishing/cleaning etc. Complete as per detail drawing, specification and as directed by PMC. | N.A | RFT | 165 | 130 | 21450 | 104.07 | 13529.1 | 60.93 | 7920.9
size - 100x1200. Basic Rate : 120 Per SFT
5 | Decorative Wall Tiles | Providing and fixing Glazed Decorative wall tiles which includes-approved make of adhesive like bal Endura or equivalent, grey cement paste with backing coat of 1:3 cement mortar not less than 12mm thick as & where ever required, joint filler of approved make and colour, as and where ever required, in proper line and level in all direction, at all height with lead and lift, polishing/finishing/cleaning etc as per design, drawing and directed by PMC etc. all complete.
Size : 75x300 Rate : 275per SFT
| a | Live kitchen Wall tiles upto 2400mm ht |  | SFT | 270 | 465 | 125550 | 233.28 | 108475.2 | 36.72 | 17074.8
| b | Bar Wall tiles upto 2400mm ht |  | SFT | 0 | 465
6 | Sada Wall Tiles for kitchen | Providing and fixing Ceramic wall tiles which includes-approved make of adhesive like bal Endura or equivalent, dry cladding on bison board panelling, joint filler of approved make and colour, as and where ever required, in proper line and level in all direction, at all height with lead and lift, polishing/finishing/cleaning etc as per design, drawing and directed by PMC etc. all complete. (Color - white/ ivory)
Size : 300x600. Rate : 45per SFT
| a | Main kitchen and under counter wall tiles upto 2400mm ht |  | SFT | 1025 | 160 | 164000 | 1045.04 | 167206.4 | -20.04 | -3206.4
| b | Live Kitchen |  | SFT | 130 | 160 | 20800 | 51.8814 | 8301.024 | 78.1186 | 12498.976
| c | Bar Area |  | SFT | 100 | 160 | 16000 | 104.22 | 16675.2 | -4.22 | -675.2
| d | Liquor Store Room |  | SFT | 250 | 160 | 40000 | 214.56 | 34329.6 | 35.44 | 5670.4
7 | SS Corner Guard | P&F of 304 grade 3mm thick SS Corner guard (30mm x 30mm, mat finished as per approved sample) fixing with conceal tile on each corner of the kitchen's wall before cladding of tiles, so that the corner may be protected from the damages. Complete in proper line & level and site engineer's instruction. | N.A | RFT | 56 | 290 | 16240 | 72 | 20880 | -16 | -4640
8 | Brass Inlay in Flooring | P&F ofe3mm thick antique brass floor inlay fixing with thread screws on each corner of the kitchen's wall before cladding of tiles, so that the corner may be protected from the damages. Complete in proper line & level and site engineer's instruction. | N.A | RFT | 80 | 350 | 28000 | 70.64 | 24724 | 9.36 | 3276
|  | TOTAL OF CIVIL WORK |  |  |  |  | 1678565 |  | 2038806.4635 |  | -360241.4635
POP & PAINTING WORK
1 | POP Punning | Providing and applying Plaster of Paris punning of average thickness 20-25mm to existing wall surfaces/ on existing tiles including chicken mesh in true level and plumb complete as per design and drawing Cleaning the surface properly with sand paper, filling cracks/holes with plaster of Paris. Applying lambi / putty (lambi/putty will be of good quality) sand papering the putty work on chamfers, etc.at any / all heights. Rate include cost for making grooves up to 12mm thick if required in horizontal or vertical direction near doors, windows, skirting, floor covering, masking tape and cleaning the area all complete as per drawing, design & manufactures specification.
| a | block work walls | N.A | SFT | 250 | 40 | 10000 |  | 0 | 250 | 10000
| b | Exposed ceiling | N.A | SFT | 650 | 45 | 29250 | 537.45 | 24185.25 | 112.55 | 5064.75
0
2 | Gypsum Ceiling | Providing, making and fixing of POP false ceiling as per manufacturer design and drawing including cut-outs for hvac grille, lights etc.at any / all heights. Rate quoted should be including of vertical drop of any heights, mouldings and size mentioned in drawings with necessary required framing in 450x 900 ultra Gyproc sections, fittings, and fixtures, scaffolding, floor covering, masking tape and cleaning the area all complete as per drawing, design & manufactures specification all complete. Rates do not include painting work. | N.A | SFT | 550 | 160 | 88000 | 892.5425 | 142806.8 | -342.5425 | -54806.8
0
3 | Metal Ceiling | Fitting of false ceiling consisting of 20g Aluminium planks made of pre-coated ( Top & Bottom ) & Size : 600mmx600mm tiles . False Ceiling with necessary supports , hangers etc. provided to install light fitting , fresh air grill etc. ( from Hunter Douglas or Armstrong ) | N.A | SFT | 675 | 260 | 175500 | 599.6375 | 155905.75 | 75.3625 | 19594.25
0
4 | Textured Wall Paint | Providing & applying three (03) coats of approved Plastic paint on walls including scraping, primer , filling with putty etc. complete with final coat no brush mark to be visible after painting colour shade as specified. | N.A | SFT | 475 | 170 | 80750 | 753.6564 | 128121.588 | -278.6564 | -47371.588
0
5 | Ceiling Paint ON Gypsum (Firated) | Providing & applying three (03) coats of approved Plastic paint on exposed surface on ceiling including scraping, primer , filling with putty etc. complete with final coat no brush mark to be visible after painting colour shade as specified. | N.A | SFT | 550 | 35 | 19250 | 892.5425 | 31238.9875 | -342.5425 | -11988.9875
0
6 | Expose Ceiling Paint including all beams | Providing & applying Three (03) coats of approved Plastic paint on exposed surface on ceiling including HVAC ducts, Sprinkler Pipes etc. complete with final coat no brush mark to be visible after painting colour shade as specified. | N.A | SFT | 675 | 30 | 20250 | 537.45 | 16123.5 | 137.55 | 4126.5
0
7 | Duct painting | Providing & applying Three (03) coats of powder coat (as per approved shade) on exposed surface on metal duct including removing of old paint, required zink oxide paint etc. complete with final coat no brush mark to be visible after painting colour shade as specified. |  | SFT | 500 | 30 | 15000 | 1002.1375 | 30064.125 | -502.1375 | -15064.125
0
8 | Fire Sprinkler paint | Providing & applying Three (03) coats of fire rated paint as per standard on exposed surface on metal including removing of old paint etc. complete with final coat no brush mark to be visible after painting colour shade as specified. |  | SFT | 100 | 0 | 0 |  | 0 | 100 | 0
|  | TOTAL of POP & PAINTING WORK |  |  |  |  | 438000 |  | 528446.0005 |  | -90446.0005
|  | GRAND TOTAL |  |  |  |  | 2116565 |  | 2567252.464 |  | -450687.464
Note on I85: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Duct & Kitchen ceiling paint

## INTERIOR WORK
BOQ of Civil work for Copper Chimney Project, Goregaon-Oberoi mall
[7 empty] | AS PER BOQ |  |  | AS PER SITE |  | Deviation
SR.NO. | ITEM | DESCRIPTION | LOCATION | DIMENSION | Executed Dimension | UNIT | QTY. | RATE | AMOUNT | QTY. | AMOUNT | Qty | Difference Rate as per prorata | Amount | REMARK
DOORS
1 | Kitchen Door | Providing & fixing in position of wooden FRD Double Leaf Door made up of 45mm thick fire rated flush door shutter of approved make & thickness, Inner side finished with wooden laminate and outer side with veneer finish including providing & fixing 750mm X 200mm fire rated glass Vision panel and 12mm thk Wooden lipping all around, including of 2100mm X 300mm SS push plate and 300mm high SS kick plate, including P/F of Door frame made out of CP Teak / Ash wood or equivalent with melamine polish finish. Size of the frame approximate 175mm wide X 50mm thick. Applicable hardware's such as s/s handles/ ss push plate, floor spring and any other hardware etc required to complete the related works as per design & detail. door hardware make consider Dorma / Hafele/Ozon /equilient Need heavy duty floor spring & both sides openable. | KITCHEN ENTRY | 1200 X 2100 MM |  | NOS. | 1 | 47500 | 47500 | 1 | 47500 | 0 |  | 0
2 | Kitchen Door (Besides Fire Passage) | Providing & fixing in position of wooden FRD single Leaf Door made up of 45mm thick fire rated flush door shutter of approved make & thickness, Inner side finished with wooden laminate and outer side with veneer finish including providing & fixing 750mm X 200mm fire rated glass Vision panel and 12mm thk Wooden lipping all around, including of 2100mm X 300mm SS push plate and 300mm high SS kick plate, including P/F of Door frame made out of CP Teak / Ash wood or equivalent with melamine polish finish. Size of the frame approximate 175mm wide X 50mm thick. Applicable hardware's such as s/s handles/ ss push plate, floor spring and any other hardware etc required to complete the related works as per design & detail. door hardware make consider Dorma / Hafele/Ozon /equilient Need heavy duty floor spring & both sides openable. | KITCHEN (FIRE EXIT) | 1200 X 2100 MM |  | NOS. | 1 | 47500 | 47500 |  | 0 |  |  |  | Not Executed
3 | Live Kitchen sliding Door | Providing & fixing in position of wooden FRD sliding door made up of 38mm thick fire rated flush door shutter of approved make & thickness, both side to be finished with wooden laminate including providing & fixing 750mm X 200mm fire rated glass Vision panel and 12mm thk Wooden lipping all around, including conceal handle a and 300mm high SS kick plate, including P/F of Door frame made out of CP Teak / Ash wood or equivalent with melamine polish finish. Size of the frame approximate 175mm wide X 50mm thick. Applicable hardware's such as sliding channel, s/s handles/ ss push plate, lock, tower bolt and any other hardware etc required to complete the related works as per design & detail. door hardware make consider Dorma / Hafele/Ozon /equilient Need heavy duty floor spring & both sides openable. | LIVE KITCHEN ENTRY | 900X 2100 MM |  | NOS. | 1 | 36000 | 36000 | 1 | 36000 | 0 |  | 0
4 | Main Door | P/F 10 mm thk. toughened glass double leaf openable door with 20x 40mm MS framework with white/ black powder coating and bottom base wooden partiton height upto 600mm with wooden molding finish with duco paint and all necessary required groove, wooden framing, including glass door with heavy duty floor spring fixing with approved make adhesive and fasteners, cutting/ chamfering/ groove/rounding wherever required, at all height with lead and lift, finishing, cleaning as per design and drawing etc. all complete. including door lock. | MAIN ENTRY | 1800X 2400MM |  | NOS. | 1 | 69400 | 69400 | 1 | 69400 | 0 |  | 0
5 | Trap Door | Providing and fixing trap doors for access to the service areas. The trap door shall have an external frame made of 50mm x 50mm in good quality seasoned wood scantling on which the shutter is hinged. Shutter shall be made of 19 mm. fire rated Plywood. The exposed side & Internal side shall be laminate finish. Concealed heavy duty hinges shall be used to mount the shutters and locking shall be provided with Allen key and panel locks. Sufficient number of hinges and locks shall be provided to avoid sagging of the shutter. Key also shall be supplied | NEAR LIVE KITCHEN | 2400X 1200 MM | 1500x2700 mm | NOS. | 2 | 19200 | 38400 | 2 | 38400
|  |  | Deviation Amount |  |  | NOS. | 0 | 7800 | 0 | 2 | 15600 | -2 | 7800 | -15600 | AS per prorata
6 | Liquor Store Room Door | Providing & fixing in position of FRD Glass Single Leaf Door made up of 45mm thick commercial flush door shutter of approved make & thickness, Inner side finished with laminate and outer side with veneer finish including providing & fixing 750mm X 200mm glass Vision panel and 12mm thk Wooden lipping all around, including of 750mm X 200mm SS push plate and 200mm high SS kick plate, including P/F of Door frame made out of CP Teak / Ash wood or equivalent with melamine polish finish. Size of the frame approximate 175mm wide X 50mm thick. Applicable hardware's such as s/s handles, conceal door closer and any other hardware etc required to complete the related works as per design & detail. door hardware make consider Dorma / Hafele/Ozon /equivalent | LIQUOR STORE ROOM ENTRY | 600X 2100 MM |  | NOS. | 1 | 27600 | 27600 | 1 | 27600 | 0 |  | 0
|  | TOTAL DOORS | [6 empty] | 266400 |  | 234500 |  |  | -15600
CARPENTRY WORK
1 | Service Station | P/F service counters in duco finished from outer surface & top finished in veneer. The storage under the Counter should be provided with 6" ht. drawers at top row finished with wooden ribs. top of the shutter having C section brass inlay & below openable shutters finished with duco. the drawer should have internal partiton with fabric finish for cutlary Shutters made out of 19mm thk. fire rated plywood finished with 1mm thk. laminate internally. The shutters to be provided with fittings such as hinges; handles; ball catch, locks etc. complete in all respect. The rates for the Shutters to be included. as per design and details. any 1drawer (in each service station) should have 3compartment made in ply finished with fabric for cutlery and bottom storage should have 1shelf for crockery, shelf in ply finished with white laminate | NEAR KITCHEN MAIN DOOR | 1200mm L X 550mmW X 900H |  | NOS. | 1 | 42000 | 42000 | 2 | 84000 | -1 | 42000 | -42000
|  | Plywood - branded fire rated -- Greenply or Equivalent brand | [7 empty] | 0
|  | Veneer Make - Euro/Greenlam/Merino/ or equivalent (Basic Rate- 140 Sq. ft.) | [7 empty] | 0
|  | Laminate Make - Euro/Greenlam/Merino/ or equivalent (Basic Rate- 40 Sq. ft.) | [7 empty] | 0
|  |  | Near Display Kitchen |  | 2100x550x900 mm | [6 empty] | -1 | 73500 | -73500 | AS per prorata basis
2 | Console | P/F service counters in duco finished from outer surface & top finished in veneer. The storage under the Counter should be provided with 6" ht. drawers at top row finished with wooden ribs. top of the shutter having C section brass inlay & below openable shutters finished with duco. the drawer should have internal partiton with fabric finish for cutlary Shutters made out of 19mm thk. fire rated plywood finished with 1mm thk. laminate internally. The shutters to be provided with fittings such as hinges; handles; ball catch, locks etc. complete in all respect. The rates for the Shutters to be included. as per design and details. any 1drawer (in each service station) should have 3compartment made in ply finished with fabric for cutlery and bottom storage should have 1shelf for crockery, shelf in ply finished with white laminate | BEHIND BANQUETTE SEATING | 1200mm L X 600mmW X 900H |  | NOS. | 1 | 41000 | 41000 | 1 | 41000 | 0 | 0 | 0
|  | Plywood - branded fire rated Ply (MR Calibrated, IS 303) -- Greenply or Equivalent brand | [7 empty] | 0
|  | Veneer Make - Euro/Greenlam/Merino/ or equivalent (Basic Rate- 140 Sq. ft.) | [7 empty] | 0
|  | Laminate Make - Euro/Greenlam/Merino/ or equivalent (Basic Rate- 40 Sq. ft.) | [7 empty] | 0
3 | MS Display Unit_01 | P/F Display unit having 20 x 20mm MS framework with black powder coat upto ceiling height, having wooden shelf @ every 350mm c/c including all necessary hardware etc. complete. 20mm thk sandwitched glass shelf with cane in center and with veneer finish frame | BEHIND BANQUETE SEATING | 1580mm L X 200mm W X 5000H |  | NOS. | 1 | 54000 | 54000 | 2 | 108000 | -1 | 54000 | -54000
|  | Plywood - branded fire rated Ply (MR Calibrated, IS 303) -- Greenply or Equivalent brand | [7 empty] | 0
|  | Veneer Make - Euro/Greenlam/Merino/ or equivalent (Basic Rate- 140 Sq. ft.) | [7 empty] | 0
|  | Laminate Make - Euro/Greenlam/Merino/ or equivalent (Basic Rate- 40 Sq. ft.) | [7 empty] | 0
20X20mm MS section finish with black powder coat
|  | 20mm thk sandwiched glass shelf with cane in center and with veneer finish frame |  | 500mm x 200mm |  |  | 18 | 2550 | 45900 | 33 | 84150 | -15 | 2550 | -38250
4 | Hostess Desk | Providing and fixing Hostess desk made out of approved make branded fire rated ply -- Greenply or Equivalent brand and finished with veneer as approved with veneer groves as per design with melamine matt polish 20X20mm MS section finish with black powder coated legs. with ss 3mm thick pvd coated 'CC' Logo |  | 1000mm L X 500mm W X 1050 H |  | NOS. | 1 | 34500 | 34500 | 1 | 34500 | 0 | 0 | 0
|  | Desk to have 2 drawers of ht 155mm, finished with duco outside and veneer maching laminate inside with inbuilt recessed handles in wood and polish. | [7 empty] | 0
|  | Basic cost of Veneer : 140/- SFT | [7 empty] | 0
5 | Banquet back planter Box | Providing and fixing of 19mm thk fire rated Ply-- Greenply or Equivalent brand apron to be cladded with Veneer/Solid Wood all necessary required groove, wooden framing, approved make adhesive and cutting/ chamfering/ groove/rounding wherever required, at all height with lead and lift, finishing, cleaning as per design and drawing etc. all complete. |  | 8450x 300 x 900 HT |  | NOS. | 1 | 72000 | 72000 | 1 | 72000 | 0 | 0 | 0
6 | Banquet Seating | Providing, making and fixing sofa made out of wooden frame work and cladded with 12mm thk approved make branded fire rated Ply -- Greenply or Equivalent brand & approved fabric with required wooden frame, top rail having 38mm dia brass metal rail height upto 150mm and side to have a cane paneling with required wooden frame with incline backrest. the bottom to have storage under seat with heavy duty sliding trolly to keep crockey. finishing/cleaning/cutting/required fixture & fasteners etc. as per design & drawing & as directed by Project Manager etc. complete. Sofa will have high density rubber foam in angle.(Foam used should be approved and to be certified against poisonous and noxious fumes.) Rate includes upholstery of fabrics. Under seating Drawers with heavy duty trolley for storage. |  | 8450x 650 x 900 HT |  | NOS. | 2 | 185000 | 370000 | 2 | 370000 | 0 | 0 | 0
Veneer on exterior finish Basic cost @ 140Rs sft
Fabric Basic cost @ 600 per MTR
Size : W 650 x H 900
38mm dia brass top rail
Heavy duty sliding trolly for storage
7 | Cane Panelling | P/F 75mm thk fire rated plywood paneling finished with bamboo Cane from Single side, internal ply finished with laminate. structure to be made out of 40x20mm thk wooden frame with 12mm ply on both side, intermidiate member size of 40 x 20mm wooden frame/ bidding to be finished with melamine polish. to be finished with duco paint finish with necessary fittings as per design and details. | ABOVE BUFFET COUNTER, KITCHEN DOOR, ABOVE SHAFT DOOR, CURTAIN WALL, WALLPAPER WALL |  |  | SQFT | 350 | 1075 | 376250 | 366.4314 | 393913.755 | -16.4314 | 1075 | -17663.755
|  | Plywood - branded fire rated Ply (MR Calibrated, IS 303) -- Greenply or Equivalent brand | [8 empty] | 72000
8 | Wall dado - Veneer panelling | Providing, making and fixing of wall panel made of 12mm thk branded fire rated Ply -- Greenply or Equivalent brand with Veneer finish with melamine polish having wooden molding all necessary required wooden framing, approved make adhesive and fasteners, cutting/ chamfering/ groove/rounding wherever required, at all height with lead and lift, finishing, cleaning as per design and drawing etc. all complete. | ALL WALLS | Upto 900mm (H) |  | SFT | 475 | 970 | 460750 | 364.4768 | 353542.496 | 110.5232 | 970 | 107207.504
Basic Rate of Veneer @ 120 Rs per SFT
9 | Moulding | Providing, making and fixing of \wooden mouldings as per detail drawing with grooves to be added with all necessary required wooden framing, approved make adhesive and fasteners, cutting/ chamfering/ groove/rounding wherever required, at all height with lead and lift, finishing, cleaning as per design and drawing etc. all complete. |  |  |  | RFT | 600 | 275 | 165000 | 677.94 | 186433.5 | -77.94 | 275 | -21433.5
10 | Storage Cabinet - with bamboo cane shutter | P/F louver shutter with fire rated plywood framework finished with veneer as per design & detail made in wood with openable shutters with bamboo cane paneling back side of the cane to be finished with laminate. Including all necessary required wooden framing, approved make adhesive and fasteners, Lock, cutting/ chamfering/ groove/rounding wherever required, at all height with lead and lift, finishing, cleaning as per design and drawing etc. all complete. | ELECTRICAL PANEL | 1000 x 2000mm (H) |  | NO. | 1 | 82500 | 82500 | 0 |  | 1 | 82500 | 82500 | As per Prorata Basis
Basic rate of Veneer @ 120 Rs per SFT
Basic rate of laminate @ 50 Rs per SFT
|  |  | Electrical Panel |  | 1500 x 3220 mm |  | 0 | 198000 |  | 1 | 198000 | -1 | 198000 | -198000
|  |  | Server Panel |  | 2400 x 3220 mm |  | 0 | 318780 |  | 1 | 318780 | -1 | 318780 | -318780
11 | Signage bulkhead Ply boxing with leather finish granite panelling on façade | Providing, making and fixing fire rated ply boxing made out of wooden/ aluminium frame work and cladded with 12mm thk approved make branded fire rated Ply (MR Calibrated, IS 303) -- Greenply or Equivalent brand finished with 18mm thk leather finish granite. all with required frame finishing/cleaning/cutting/required fixture & fasteners etc. as per design & drawing & as directed by Project Manager etc. complete. |  |  |  | SFT | 60 | 1200 | 72000 | 108.867 | 130640.4 | -48.867 | 1200 | -58640.4
12 | Planter Box above Banquete | Providing and fixing M.S frame stand made out of 20mm x 20mm hollow box sections with 19mm thk approved make branded fire rated Ply-- Greenply or Equivalent brand apron to be cladded with Veneer/Solid Wood all necessary required groove, wooden framing, approved make adhesive and cutting/ chamfering/ groove/rounding wherever required, at all height with lead and lift, finishing, cleaning as per design and drawing etc. all complete. |  | 8450x 3100 x 300mm HT |  | NOS. | 1 | 87000 | 87000 | 1 | 87000 | 0 | 0 | 0
13 | Bar Counter | P/F Bar counter to be made out of 19mm thk approved make branded fire rated ply-- Greenply or Equivalent brand apron to be cladded with wood & bamboo cane as per detail and platform in white Marble finished based on ply with necessary ms barcket, Necessary opening should be made for fixing of stainless steel sink. Erecting brick wall for plumbing and Brick platform should be provided on floor below the platform of 100mm high brass skirting from outside. The top platform to have 50mm wide Marble finish fascia horizontally. |  | 3000x 200mm
Plywood - branded fire rated Ply-- Greenply or Equivalent brand
Marble Basic Rate 800/- per SQ.FT.
Veneer Make - Euro/Greenlam/Merino/ or equivalent (Basic Rate- 140 Sq. ft.)
| a | Top service Counter Ply Base with Neccesory Support to receved marble |  | 200mm Width |  | RFT | 10 | 550 | 5500 | 9.25 | 5087.5 | 0.75 | 550 | 412.5
| b | Front Elevation (apron) to be to be made out of 19mm thk approved make branded fire rated Ply) -- Greenply or Equivalent brand with veneer finish frames, ply to be finished with duco and veneer frames to be finished with melamine polish. Top row finished with metal cane and 100mm skirting with veneer as per detailed Drawing & design. Provision for indirect lighting to be made |  |  |  | SFT | 20 | 1500 | 30000 | 24.605 | 36907.5 | -4.605 | 1500 | -6907.5
| c | 50mm thk Top service platform in Marble |  | 450mm Width |  | RFT | 10 | 950 | 9500 | 27.75 | 26362.5 | -17.75 | 950 | -16862.5
| d | 38mm Dia Foot rest real brass antique finish at the bottom. |  |  |  | RFT | 10 | 2200 | 22000 | 9.25 | 20350 | 0.75 | 2200 | 1650
| e | 600mm Flap door for bar area entry finished same as counter appron |  | 600x 1100mm |  | Nos | 1 | 7000 | 7000 | 1 | 7000 | 0 | 7000 | 0
| f | 100mm high brass plate Skirting |  |  |  | RFT | 12 | 975 | 11700 | 78.3 | 76342.5 | -66.3 | 975 | -64642.5
| g | P/F 75mm thk fire rated plywood partition finished with bamboo closed cane matting , internal ply finished with laminate. structure to be made out of 40x20mm thk wooden frame with 12mm ply on both side, intermidiate member size of 40 x 20mm wooden frame/ bidding to be finished with melamine polish. to be finished with duco paint finish with necessary fittings as per design and details. |  |  |  | SFT | 15 | 1100 | 16500 | 7.9625 | 8758.75 | 7.0375 | 1100 | 7741.25
| h | Plywood - branded fire rated Ply-- Greenply or Equivalent brand
14 | Bar Display unit | P/F 350mm deep Bar display unit to be made out of 19mm thk approved make branded fire rated Ply -- Greenply or Equivalent brand with veneer finish, having brass shelf @ every 400mm c/c. The Backdrop made out of 12mm thk approved make branded fire rated Ply -- Greenply or Equivalent brand with finished with bronze mirror, front panelling to be veneer finsh. The shelves to be provided with necessary fittings etc. complete in all respect. The rates for shelves to be included. as per design and details. |  | 3000x 2000mm |  | SFT | 0 | 2050 | 0 |  | 0
Plywood - branded fire rated Ply (MR Calibrated, IS 303) -- Greenply or Equivalent brand
Marble Basic Rate 600/- per SQ.FT.
Veneer Make - Euro/Greenlam/Merino/ or equivalent (Basic Rate- 140 Sq. ft.)
Laminate Make - Euro/Greenlam/Merino/ or equivalent (Basic Rate- 40 Sq. ft.)
| a | Mirror Panelling |  |  |  | SFT | 25 | 600 | 15000 | 65 | 39000 | -40 | 600 | -24000
| b | Brass shelves |  | 1500mm X300mm |  | no. | 3 | 8500 | 25500 | 0 | 0 | 3 | 8500 | 25500 | Not executed as per Boq, shifted to Item 3 MS Display Unit Shelves
| c | brass patti |  |  |  | Rft | 32 | 750 | 24000 | 32 | 24000 | 0 | 750 | 0
| d | Veneer Cladding |  |  |  | Sqft | 25 | 1100 | 27500 |  | 0 | 25 | 1100 | 27500
15 | Bar Counter Back | P&F of back counter of 600mm wide granite top working back counter, with 19mm thick fire rated plywood structure & 12mm plywood back, counter having 4 nos. of open able shutters (in 19mm thick plywood) on front side of the unit. Counter top to be finished with 19mm thick black galaxy granite with 38mm dual nose finished, counter front part, & all the visible part to be finished with 1mm thick wooden laminate, counter's internal part to be finished with 1mm thick light walnut laminate (selected make, basic cost INR. 1200.00/ sheet). Rate inclusive of all necessary hardware fittings - like hinges, draw telescopic channels, cup board lock, decorative antique bolt handle, wire managers, etc. (approved & branded make) & necessary cut out for services requirements. Counter having 50mm ht. 18 mm thick flamed granite skirting on front side on existing 150mm ht. kobah. Complete as per architectural detail drawing & site engineer's instruction. |  | 3000x 600mm |  | Rft | 10 | 7000 | 70000 | 9.25 | 64750 | 0.75 | 7000 | 5250
[12 empty] | 0 | 0 | 0
16 | Bar Bulkhead | P&F of 350mm wide Bar Bulkhead/ glass hanger having 25mm X 25MM brass metal/ SS PVD COATING box section in 2 layers having vertical and horizontal member @every 450mm c/c with 10mm thk toughthned glass shelf having provision for led profile light. brass metal to be brushed finish. the base including 8-10mm solid rods band in curve shape to hang the wine glass. the top portion to have 6-8mm thk flutted glass palnelling. Rate including all necessary hardware fittings to install the shelves, anchor fastner, ceiling support, scaffolding, etc. as required on site. Complete as per architectural detail drawing & site engineer's instruction. |  | 3600x 350mm |  | Rft | 12 | 8200 | 98400 | 11.16 | 91512 | 0.84 | 8200 | 6888
[12 empty] | 0 | 0 | 0
17 | Entry Glass Partition | P/F 10 mm thk. toughened glass partitions with 20 x 40mm MS framework with white/ black powder coating and all necessary required groove, wooden framing, with approved make adhesive and fasteners, cutting/ chamfering/ groove/rounding wherever required, at all height with lead and lift, finishing, cleaning as per design and drawing etc. all complete. Providing, making and fixing of wall panel made of 12mm thk fire rated ply -- Greenply or Equivalent brand with MDF finish with Duco paint and wooden molding as per design, all necessary required wooden framing, approved make adhesive and fasteners, cutting/ chamfering/ groove/rounding wherever required, at all height with lead and lift, finishing, cleaning as per design and drawing etc. all complete. skirting in metal, brass finish (same as main door handle) | ENTRANCE | 6950x 3300mm |  | SFT | 270 | 950 | 256500 | 136 | 129200 | 134 | 950 | 127300
0
18 | Main Door Handle | Providing, Supplying & fixing of double sided 3mm thk Sign handle in brass | ENTRANCE | 450mm x 450mm |  | NOS | 2 | 15000 | 30000 | 2 | 30000 | 0 | 15000 | 0
19 | Bison board/ v- board Panelling | Providing, making and fixing of wall paneling made of 12mm thk branded bison board/ V board paneling on wall including MS framework from slab to slab height of 5000mm. framework to be finished with zink oxide and enamel finish with all necessary required framing, approved make adhesive and fasteners, cutting/ chamfering/ groove/rounding wherever required, at all height with lead and lift, finishing, cleaning as per design and drawing etc. all complete. | All walls | 100mm (thick) 4200mm (height) |  | SFT | 2900 | 510 | 1479000 | 1591.627 | 811729.77 | 1308.373 | 510 | 667270.23
20 | MS framework for curtain wall | P/F of 20 x 20mm MS framework with black powder coat upto ceiling height, having intermediate memebr @ every 900mm c/c including all necessary hardware etc. complete. |  |  |  | RFT | 30 | 120 | 3600 | 621.97 | 74636.4 | -591.97 | 120 | -71036.4
21 | SS PVD COATING framework for wallpaper | P/F of 20 x 20mm ss brass pvd coating framework upto ceiling height, having intermediate memebr @ every 900mm c/c including all necessary hardware etc. complete. |  |  |  | SFT | 0 | 120 | 0 |  | 0 | 0 | 120 | 0
22 | FAÇADE granite bulkhead | Providing, making and fixing of bulkhead 600mm box paneling made of 12mm thk branded bison board/ V board paneling on wall including MS framework from slab. framework to be finished with zink oxide and enamel finish. the boxing to be finished with black leather finish granite with granite molding in levels as per detail drawing. having required holes to fix the signage letter. cost inlcudes all necessary required framing, approved make adhesive and fasteners, cutting/ chamfering/ groove/rounding wherever required, at all height with lead and lift, finishing, cleaning as per design and drawing etc. all complete. |  |  |  | SFT | 65 | 1150 | 74750 |  | 0 | 65 | 1150 | 74750 | Not Executed
[12 empty] | 0 | 0 | 0
23 | Glass PARTITION on live kitchen | P/F 10 mm thk.fire rated glass partitions with 20 x 40mm MS framework with white/ black powder coating and all necessary required groove, wooden framing, with approved make adhesive and fasteners, cutting/ chamfering/ groove/rounding wherever required, at all height with lead and lift, finishing, cleaning as per design and drawing etc. all complete. | Live kitchen |  |  | SFT | 55 | 1800 | 99000 | 64 | 115200 | -9 | 1800 | -16200
24 | Flutted Glass PARTITION on live kitchen | P/F 8 mm thk. flutted glass partitions with 20 x 40mm MS framework with white/ black powder coating and all necessary required groove, wooden framing, with approved make adhesive and fasteners, cutting/ chamfering/ groove/rounding wherever required, at all height with lead and lift, finishing, cleaning as per design and drawing etc. all complete. | Live kitchen |  |  | SFT | 30 | 1800 | 54000 | 40 | 72000 | -10 | 1800 | -18000
|  | TOTAL DOORS | [6 empty] | 4262350 |  | 4166797.071 |  |  | 62852.929
|  | GRAND TOTAL INTERIOR | [6 empty] | 4528750 |  | 4401297.071 |  |  | 47252.929

## Extra Items
EXTRA ITEMS | [8 empty] | 2024-04-20
S.No. | Item | Description | Unit | Qty | Rate | Amount | Executed | Amount | Remarks
1 | Hanging Bells | Installation of Hanging Bells in FOH as directed by Architect/EIC with necessary hardwares | Nos | 560 | 85 | 47600 | 232 | 19720
2 | Material Shifting | Civil and Interior Material Shifting | L/S | 1 | 18775 | 18775 | 0 | 0
3 | Lifting & Shifting | Unloading, Lifting and Shifting of all the equipments to the CC premises | L/S | 1 | 17000 | 17000 | 1 | 17000 | Furniture and equipments placement as per drawing
[6 empty] | 83375 |  | 36720

## MISCELLANEOUS
MISCELLANEOUS WORK, COPPER CHIMNEY, OBEROI MALL, GOREGAON
[5 empty] | AS PER BOQ |  | AS PER SITE
SR.NO. | ITEM | DESCRIPTION | UNIT | QTY. | RATE | AMOUNT | QTY. | AMOUNT | REMARK
MISCELLANEOUS
1 | Texture wallpaper | P & F of texture wallpaper as per approval | SFT | 250 | 210 | 52500 | 187.5 | 39375
Basic rate- 155/Sq Ft
2 | Ceiling Fans | P & F of ceiling fans paper as per approval | NOS | 0 | 700 | 0 | 0 | 0
3 | Bamboo blind curtain on S.S PVD black coating framework / roller blinds | P & F of bamboo blind manual folding curtains as per approval | SFT | 150 | 200 | 30000 | 108 | 21600
4 | Story Wall Images | High Resolution Digital printing on HP Canvas STRETCHED on 1 inch wooden frame (stapling on sides)
Back: 3 mm sun board with leather finish vinyl pasted on it.
Size :
|  | Size : 440 x 600mm | NOS | 0 | 1500 | 0
|  | Size : 440 x 340mm | NOS | 0 | 1000 | 0
5 | Chef Photos | Size : 775 x 1050mm | NOS | 0 | 1200 | 0 | 3 | 3600
6 | Artifact | P & F of decorative artifact (approx cost - 250000) | LS | 0 | 250000 | 0
7 | Natural & Artificial | P & F of planters (approx cost - 200000) | LS | 0 | 200000 | 0
|  | TOTAL MISCELLANEOUS |  |  |  | 82500 |  | 64575

## NT Items
BOQ of Extra work for Copper Chimney Project, Goregaon-Oberoi mall
EXTRA ITEMS | [6 empty] | 2024-04-20
S.No. | Item | Description | Unit | Qty | Rate | Amount | Remarks
1 | GRANITE CLADDING & STEPS | GRANITE CLADDING - PROVIDING AND LAYING IN POSITION 19 MM THK GRANITE OF APPROVED SIZE AND SHADE OF STANDARD THICKNESS FOR CLADDING TO TRUE LINE AND LEVEL INCLUDING 1:4 MIX CEMENT SAND MORTAR FLOATED WITH NEAT CEMENT SLURRY / ARALDITE & FILLING THE JOINTS WITH NEAT WHITE / COLOR CEMENT INCLUDING SCAFOLDING, CLEANING, WATERING, CURING ETC. COMPLETE AS PER DETAIL DRAWING, AS SPECIFIED AND AS DIRECTED BY ARCHITECT OR EI. | SFT | 21.485 | 330 | 7090.05
2 | GRANITE DOOR FRAME | PROVIDING AND FIXING IN POSITION 6" - 12" WIDE DOOR FRAME WITH 3/4" THICK APPROVED GRANITE OF APPROVED SIZE, COLOUR AND SHADE OF STANDARD THICKNESS IN APPROVED TO TRUE LINE AND LEVEL WITH 1:1 CEMENT GROUT, FILLING THE JOINTS WITH WHITE / COLOUR CEMENT INCLUDING CLEANING, WATERING, CURING ETC. COMPLETE AS PER DETAIL DRAWING, AS SPECIFIED AND AS DIRECTED BY ARCHITECT. | RFT | 14 | 395 | 5530 | LIVE KITCHEN DOOR FRAME
3 | KOTA STONE BUND WALL/LEDGE | KOTA STONE LEDGE WALL 4'' TO 9" HT. FIXED AT 2 SIDES AND TOP WITH BLACK GRANITE BOTH SIDE CHAMFERING FOR POTWASH, DISHWASH OR ANY OTHER SPACE AS REQUIRED | RFT | 9 | 260 | 2340
4 | LIVE KITCHEN LEDGE | PROVIDING AND FIXING IN POSITION 6" - 8" WIDE AUSTRALIAN WHITE STONE LEDGE WITH 3/4" THICK APPROVED STONE OF APPROVED SIZE, COLOUR AND SHADE OF STANDARD THICKNESS IN APPROVED TO TRUE LINE AND LEVEL WITH 1:1 CEMENT GROUT, FILLING THE JOINTS WITH WHITE / COLOUR CEMENT INCLUDING CLEANING, WATERING, CURING ETC. COMPLETE AS PER DETAIL DRAWING, AS SPECIFIED AND AS DIRECTED BY ARCHITECT. | RFT | 15.5 | 850 | 13175 | AUSTRALIAN WHITE STONE LEDGE ON LIVE KITCHEN
5 | KOTA SKIRTING | PROVIDING AND FIXING IN POSITION 3'' HIGH KOTA SKIRTING OF APPROVED SIZE AND 19 MM THICKNESS FOR SKIRTING TO TRUE LINE AND LEVEL WITH 1:1 CEMENT GROUT / ARALDITE/ GLUE & FILLING THE JOINTS WITH NEAT WHITE / COLOR CEMENT INCLUDING, CLEANING, WATERING, CURING ETC. COMPLETE AS PER DETAIL DRAWING, AS SPECIFIED AND AS DIRECTED BY ARCHITECT. | RFT | 239.68 | 110 | 26364.8
6
7 | MS WORK- TRAP DOOR | P/Fixing 50x50mmx 3mm thk MS Tubes on Trap doors | NOS | 2 | 8971.61 | 17943.22
8 | FABRIC BASIC RATE VARIATION | P/fixng Fabric on Banquete Sofa | MTR | 23 | 975 | 22425 | Basic rate as per order is 600/SQM. While purchaded at Rs1575/Sqm after project team approval
9 | BAMBOO BLINDS BASIC RATE VARIATION | BAMBOO BLINDS | SFT | 108 | 100 | 10800 | Material+ Labour +20% OH & C.P (Qty as per site)
10 | REWORK ON PLANTER ABOVE BANQUETE SOFA | Rework on Planter above banquete sofa due to change in drawings & desings as required by the design team. | NOS | 2 | 15000 | 30000
11 | CASH PAYMENT | PAYMENT TO ELECTRICAL CERTIFICATION ON BEHALF OF COPPER CHIMNEY | INR | 1 | 17250 | 17250
12 | MS STORAGES | P/fixing MS SHELVES finished with perforated Jali and GI sheet on the Shelves top as directed by the site incharge. | NOS | 2 | 9500 | 19000
13 | BRASS T PROFILE | P/fixing Brass PVD coated T profile on wall & Veneer Joint on BAR | RFT | 11.49 | 135 | 1551.15
14 | 19MM PLY+4MM MDF , DUCO | P/APPLYING APPROVED SHADE OF DUCO PAINT ON 19MM PLY & 4MM MDF PANELLING | SFT | 104.3 | 510 | 53193
15 | GRANITE THRESHOLD | GRANITE DOORSILL | RFT | 20.08 | 260 | 5220.8
16 | SINK COCK CHANGED | P/fixing wall mounted sink cock while replacing with the approved one. | NOS | 1 | 4500 | 4500
17 | ANGLE COCK CHANGED | ANGLE COCK ON DISHWASHER REPLACED | NOS | 1 | 1050 | 1050
18 | TWO COAT OF WATERPROOFING ON PCC BEFORE KOTA FLOORING | PROVIDING WATERPROOFING TREATMENT IN KITCHEN, BAR AND DRAINAGE LINES AND CHAMBERS AREA OVER THE SLAB BY APPLYING 2 COAT OF WATERPROOFING PRODUCT AS PER MANUFACTURER SPECIFICATIONS. INCLUDING SURFACE PREPRATION AS PER MANUFACURE'S SPECIFICATIONS, ALL LEAD, LIFTS,CURING, TESTING ETC . COMPLETE AS SPECIFIED BY EI. | SFT | 1136.0615 | 45 | 51122.7675
19 | Entry Glass Partition | P/F 10 mm thk. toughened glass partitions with 20 x 40mm MS framework with white/ black powder coating and all necessary required groove, wooden framing, with approved make adhesive and fasteners, cutting/ chamfering/ groove/rounding wherever required, at all height with lead and lift, finishing, cleaning as per design and drawing etc. all complete. Providing, making and fixing of wall panel made of 12mm thk fire rated ply -- Greenply or Equivalent brand with MDF finish with Duco paint and wooden molding as per design, all necessary required wooden framing, approved make adhesive and fasteners, cutting/ chamfering/ groove/rounding wherever required, at all height with lead and lift, finishing, cleaning as per design and drawing etc. all complete. skirting in metal, brass finish (same as main door handle) | SFT | 136 | 550 | 74800 | RATE VARIATION DUE TO CHANGE IN DESIGN. IT WAS STRAIGHT GLASS LATER CHANGED TO BEND GLASS
20 | REWORK ON MOLDING | P/APPLYING DUCO PAINT ON MOLDING | RFT | 111.23 | 85 | 9454.55
21 | SERVICE STATION TOP- ITALIAN RATE DIFFERENCE | P/fixing 19mm thk Italian (GREY WILLIAMS) stone on service stations Top | SFT | 28.65 | 340 | 9741 | Rate Difference B/w Veneer & Italian stone. As it is Veneer in Boq and Executed Italian as per dwg. The Basic rate of veneer is Rs 140/SFT while the Italian purchased at Rs 500/Sft. (Rs 500-140 I.e Rate difference of Rs 340/SFT)
|  | TOTAL |  |  |  | 382551.3375