## Budweiser
Project: |  | Budweiser
Package Details:
Previous SO No.:
Document Date:
SR NO | SERVICE NO | ITEM DESCRIPTION | UNIT | RATE | Previous BOQ |  | Variation |  |  | Revised BOQ |  | % Variation | Remarks
[5 empty] | QTY | AMOUNT | QTY | RATE | AMOUNT | QTY | AMOUNT
NOTE |  | CVCP EXTRA WORK
| 1 | Providing & laying of 20-25mm Thickness. 560mmX560mm Kota Stone flooring over a bed of 30mm thk. Cement mortar (1:4) jointed with cement slurry mixed with pigment to match the colour of kota stone including hole cutting for traps etc. necessary cutting, rubbing, grinding and mirror polishing completed as per the details are provided in drawings or as directed by Architect/Site Engineer. | Sqft |  | 0 |  | 200 | 320 | 64000 | 200 | 64000
| 2 | P/F 12.5 mm Gypsum board(Fire rated ) on wall/ partition with the help of Nylon sleeves and (Note – Surface area to be measured for payment ) Make -India Gypsum/ Gyproc/Saint gobain or equivalent make | Sqft |  |  |  | 1000 | 145 | 145000 | 1000 | 145000
| 3 | Providing and fixing of uPVC Waste pipes 6 kg/cm2 (IS: 4985:2000) including with all fittings e.g. couplings, tees, bends, reducers and screwed adoptors jointing with solvent cement as per Manufacturer's specifications complete including cutting holes or chases in wall and making good the same wherever required. (Waste pipe from fixtures).[Make:ASHIRWAD / PRINCE/ JAIN IRRIGATION]. | Ls |  |  |  | 1 | 8500 | 8500 | 1 | 8500
75 MM dia ( 19 feet )
| 4 | Providing, fixing testing, and commissioning of CPVC) pipe as per CTS SDR-11 - pipe material as per ASTM D 1784 and pipe dimension and specs as per ASTM D 2846 & fittings such as tees, elbows, reducers, male/female connector, clamps etc. , jointing with CPVC solvent cement as per manufacturer recommendations conforming to ASTM-F493 complete. [Make: HINDWARE TRUFLO / PRINCE]
|  | 20mm CPVC pipe ( 60 rft ) | Ls |  |  |  | 1 | 35000 | 35000 | 1 | 35000
| 5 | P/F 12.5 Gypsum board(Fire rated ) including providing and fixing G.I. angle of thick fixed to brick wall/ partition with the help of Nylon sleeves and (Note – Surface area to be measured for payment ) Make -India Gypsum/ Gyproc/Saint gobain or equivalent make | rft |  |  |  | 40 | 165 | 6600 | 40 | 6600
| 6 | Providing and laying of Anti-skid VITRIFIED Commercial floor tile of size 600 x 600 mm and wall tile ( 15 Nos ) | Ls |  |  |  | 1 | 15600 | 15600 | 1 | 15600
| 7 | P / F Single Leaf BLOCK Board Flush Door : (Size: as mentioned below) fabricated in 35mm thk.flush door Panel finished 1mm thick laminate (as/sample approved make) on both faces. . All the laminate grains to be vertical (Seasoned Meranti wood) margin match to laminate shade on exposed edges as per design, all door hardwares including L Key lock S.S butt hinges approved makes as per hardware schedule etc & all seasoned ghana teakwood frames, mdf / ply & timber substrate (All visible & concealed surfaces) etc complete in all respects. | Nos |  |  |  | 1 | 41033 | 41033 | 1 | 41033
1050 mm X 2100 MM
| 8 | Rework of Bar area electrical points ( 5 Nos ) | Nos |  |  |  | 5 | 1500 | 7500 | 5 | 7500
|  | TOTAL AMOUNT |  |  |  | 0 |  |  | 323233 |  | 323233
|  | GST 18% | [6 empty] | 58181.94 |  | 58181.94
|  | TOTAL AMOUNT WITH GST | [6 empty] | 381414.94 |  | 381414.94

## RA
SR NO. | DISCRIPTION | Unit | No. | L | B | H | QUANTITY | Rate | Amount | Remark
1 | Providing & laying of 20-25mm Thickness. 560mmX560mm Kota Stone flooring over a bed of 30mm thk. Cement mortar (1:4) jointed with cement slurry mixed with pigment to match the colour of kota stone including hole cutting for traps etc. necessary cutting, rubbing, grinding and mirror polishing completed as per the details are provided in drawings or as directed by Architect/Site Engineer.
| Kota Stone | sqft |  |  |  |  | 1 | 75 | 70
| Cement | sqft |  |  |  |  | 0.09 | 450 | 40.5
| Sand | sqft |  |  |  |  | 1 | 15 | 15
| Chemical/ polish | sqft |  |  |  |  | 1 | 30 | 30
155.5
| watage 14% | [7 empty] | 21.77
177.27
| cartage 5% | [7 empty] | 8.8635
186.1335
| Labour 45% | [7 empty] | 65.1467
251.2802
| esic pf 5% | [7 empty] | 12.564
263.8442
263.8442
| tools and tackals 3% | [7 empty] | 7.9153
271.7596
| Supervision 5% | [7 empty] | 13.588
285.3475
| Profit 10% | [7 empty] | 28.5348
313.8823
| shafty house keeping electric cityand water 2% | [7 empty] | 6.2776
[9 empty] | 320.1599 | Per Sqft
2 | P/F Gypsum board(Fire rated ) including providing and fixing G.I. angle of thick fixed to brick wall/ partition with the help of Nylon sleeves and (Note – Surface area to be measured for payment ) Make -India Gypsum/ Gyproc/Saint gobain or equivalent make
| Gypsum | sqft |  |  |  |  | 1 | 45 | 45
| Gyproc joint tape | rft |  |  |  |  | 1 | 15 | 15
60
| watage 5% | [7 empty] | 3
63
| cartage 5% | [7 empty] | 3.15
66.15
| Labour | [7 empty] | 43
109.15
| esic pf 5% | [7 empty] | 5.4575
114.6075
114.6075
| tools and tackals 3% | [7 empty] | 3.4382
118.0457
| Supervision 5% | [7 empty] | 5.9023
123.948
| Profit 15% | [7 empty] | 18.5922
142.5402
| shafty house keeping electric cityand water 2% | [7 empty] | 2.8508
[9 empty] | 145.391 | Per Sqft
5 | P/F 12.5 mm Gypsum board(Fire rated ) on wall/ partition with the help of Nylon sleeves and (Note – Surface area to be measured for payment ) Make -India Gypsum/ Gyproc/Saint gobain or equivalent make
| Gypsum | sqft |  |  |  |  | 1 | 45 | 45
| Gyproc joint tape | rft |  |  |  |  | 1 | 15 | 15
60
| watage 10% | [7 empty] | 6
66
| cartage 5% | [7 empty] | 3.3
69.3
| Labour | [7 empty] | 55
124.3
| esic pf 5% | [7 empty] | 6.215
130.515
130.515
| tools and tackals 3% | [7 empty] | 3.9154
134.4304
| Supervision 5% | [7 empty] | 6.7215
141.152
| Profit 15% | [7 empty] | 21.1728
162.3248
| shafty house keeping electric cityand water 2% | [7 empty] | 3.2465
[9 empty] | 165.5713 | Per Sqft
7 | P / F Single Leaf BLOCK Board Flush Door : (Size: as mentioned below) fabricated in 35mm thk.flush door Panel finished 1mm thick laminate (as/sample approved make) on both faces. . All the laminate grains to be vertical (Seasoned Meranti wood) margin match to laminate shade on exposed edges as per design, all door hardwares including L Key lock S.S butt hinges approved makes as per hardware schedule etc & all seasoned ghana teakwood frames, mdf / ply & timber substrate (All visible & concealed surfaces) etc complete in all respects.
1050 mm X 2100 MM
| 35 mm block board | sqft |  |  |  |  | 1 | 145 | 145
| wooden frame teak wood 75 x 50 mm | Rft |  |  |  |  | 1 | 850 | 850
| Laminate both side | sqft |  |  |  |  | 2 | 95 | 190
1185
| door closer concealed tpe | Nos |  |  |  |  | 1 | 7500 | 7500
| Pull handle both side | Nos |  |  |  |  | 2 | 2250 | 9870
18555
| watage 14% | [7 empty] | 2597.7
21152.7
| cartage 5% | [7 empty] | 1057.635
22210.335
| Labour 45% | [7 empty] | 9994.6508
32204.9857
| esic pf 5% | [7 empty] | 1610.2493
33815.235
33815.235
| tools and tackals 3% | [7 empty] | 1014.4571
34829.6921
| Supervision 5% | [7 empty] | 1741.4846
36571.1767
| Profit 10% | [7 empty] | 3657.1177
40228.2944
| shafty house keeping electric cityand water 2% | [7 empty] | 804.5659
[9 empty] | 41032.8602 | Per Nos