## NFA-SO (hidden)
Adani Airport Holdings Ltd
[8 empty] | Plant Code | 112A
Note for Approval
For Amendment of Service Order
Ref. No. |  | GAU/Soil Inv. Consultant |  |  |  | Date: |  | 2022-11-02
Project Name & Location: |  | Lokpriya Gopinath Bordoloi International Airport, Guwahati |  |  |  | Project WBS |  | D-2026-01-P1-AL-CM-PC-SY-
Work/Package |  | Appointment of Consultant for Soil Investigation Work for CSD land parcels (Land Areas: 18.53 Acre)
A. | Requisition | 1. | Name of Project Manager |  |  |  | to be appointed
|  | 2. | SO Requisition no. & date |  |  |  | 2022-08-16
|  | 3. | Date of Last release
|  | 4. | Target date for placement of SO |  |  |  | 2022-09-06
|  | 5. | Justify delay, if any |  |  |  | -
|  | 6. | Target date for Mobilization of Consultant
|  | 7. | Explain & justify if any delays are likely |  |  |  | -
|  | 8. | Any other significant information about PR |  |  |  | -
B. | Bidding | RFP issued on |  |  |  |  | 2022-08-16
|  | Proposals received on |  |  |  |  | 2022-08-23 | 2022-08-31
C. | Proposal Details | Parties to Whom Enquiry Issued. |  |  |  |  | R0 offer (Rs. Lakhs) | R1 offer (Rs. Lakhs) | Position
|  | 1 | Geotest Engineers |  |  |  | 16.5 | 8.232 | L1
|  | 2 | Gaveshana Geosciences |  |  |  | 11.07 | 8.76 | L2
|  | 3 | SS Solution |  |  |  | 11.44 | 11.04 | L3
|  | 4 | Bose Engineers |  |  |  | 14.25 | 12.516 | L4
D. | Basis & Justification | 1. Basis and justification for the recommendation:
|  | a. | Lowest offer |  |  |  | Yes
|  | b. | Repeat order |  |  |  | -
|  | c. | Prices as per pervious SO |  |  |  | -
|  | d. | Based on SO approved SOR |  |  |  | -
|  | e. | Based on the internal cost estimate
|  | f. | Others (specify in details) - (in case of other than lowest, indicate the financial impact)
2. Supporting enclosures (please specify):
|  | a. | Schedule of Approximate Quantities and Unit Rates |  |  |  | Yes
|  | b. | Comparatives statement of quoted & revised prices and internal estimates |  |  |  | Yes
|  | c. | Quotations of the parties |  |  |  | Yes
|  | d. | Last Order Price details
3. Emergency PR
|  | a. | Was it an Emergency PR? |  |  |  | No
|  | b. | If Yes, Was there any implication (Incase of implication specify amount and provide justification in the General Remarks). |  |  |  | -
E. | Consultant | Consultant ’s name (and place) |  |  |  |  | M/s. Geotest Engineers Pvt. Ltd
|  | Whether the Consultant is pre-qualified: |  |  |  |  | No
|  | If no, has the prequalification been carried out satisfactorily: |  |  |  |  | Yes
|  | Consultant’s PF Registration No. |  |  |  |  | -
|  | Any other details: |  |  |  |  | -
F. | Price | Part A : |  |  |  |  | Recommended Price Rs. |  | Budget
|  | Basic Order Value: |  |  |  |  | 823200 |  | 2800000
|  | Provision for travel expenses |  |  |  |  | 0 |  | 0
|  | GST : 18 % |  |  |  |  | 148176 |  | 504000
|  | Total Implication including Basic Order value, travel expenses , GST : |  |  |  |  | 971376 |  | 3304000
|  | Price Basis : |  |  |  |  | Firm Price till completion of services
|  | Provision for Quantity Variation: |  |  |  |  | Nil
G. | SEZ Benefit | Whether eligible for SEZ benefit. |  |  |  |  | No.
|  | If yes then LOP No. |  |  |  |  | -
| Other Major Terms & Conditions | Schedule of Completion: |  |  | SO Commencement Date. |  | From the date of the Service Order or Notice to proceed whichever is later
[5 empty] | SO Completion Date. |  | 30 days from effective date
|  | Payment Terms: |  |  | Mobilization Advance: |  | Nil
[5 empty] | R/A Bills: |  | 1.Max. 2 bills can be raised , one on completion of field work and other at completion and submission of final report. 2. Billing on item rate basis for actual work done. Quantities mentioned in the Price Schedule are tentative and may vary to any extent. 3. Payment shall be made within 30 days from submission of bill
|  | Securities applicable and their validity: |  |  | Advance BG: |  | Nil
[5 empty] | Contract Performance BG: |  | Nil
[5 empty] | Retention Money: |  | Nil
[5 empty] | Any other guarantees: |  | -
|  | Insurance: |  |  | CAR Policy |  | NA
Third party insurance
Workmen compensation
Contractor’s P&M
[5 empty] | Professional Indemnity |  | NA
[5 empty] | Any other |  | Staff of their company and of sub consultants engaged are fully covered under the insurance policy including COVID-19 epidemic
|  | Liquidated damages |  |  |  |  | One percent (1%) of the SO Price (along with applicable GST), for each completed week of delay or part thereof, subject to a maximum of Five percent (5 %) of the SO Price.
|  | Defect Liability Period |  |  |  |  | NA
|  | Any other significant terms and conditions: |  |  |  |  | a) Employer shall retain the right to close the assignment at any stage, as per the needs of the overall development Program. In such an event the breakup of Fees as agreed in Price Schedule shall form the basis for finalization of payment of consultancy fees, after successful completion of the work for respective stage. b) Consultant shall arrange water and electricity for the use in its work/services at its own cost. c) Safety and security of the equipment and personnel of the Consultant deployed at the site shall be its own responsibility. The Consultant shall indemnify the Employer of all the related liabilities.
|  | Mention and justify significant deviations, if any: |  |  |  |  | -
I. | General Remarks | 1. Scope of Works & Plot Layout document was received from Design team consisting of BOQ
J. | Approvers’ Notes, if any
K. | Post Approval Notes | 1. Service Order No. _________________________ dated ____________.
2. Unconditional acceptance of Service Order received on ______________.
| Proposed by |  |  | Recommended by |  | Recommended by |  | Verified by
| Manish Mulchandani |  |  | Avadhesh Kr Singh |  | Parag Thakurdesai |  | Dushyant Kumar
| Manager - Contracts & Procurement (CSD) |  |  | AGM- Contracts & Procurement (CSD) |  | Head- Contracts & Procurement (CSD) |  | GM- Finance Controller (CSD)
| Approved by |  |  |  |  | Approved by
| Vishal Mirchandani |  |  |  |  | Dr. Malay Mahadevia
| CEO (CSD) |  |  |  |  | CEO (AAHL)

## Variation Statement
VARIATION STATEMENT -01
Project: |  | The Lucknow Seating, LUCKNOW AIRPORT - TERMINAL-T3
Package Details:
Previous SO No.:
SR NO | SERVICE NO | ITEM DESCRIPTION | UNIT | RATE | Previous BOQ |  | Variation |  | Revised BOQ |  | % Variation | Remarks
[5 empty] | QTY | AMOUNT | QTY | AMOUNT | QTY | AMOUNT
CIVIL AND INTERIOR
| Boq Item no- | b
EXTRA ITEM
1 |  | Providing & fixing paneling made of 50x50mm MS framework @ 600mm c/c bothways fixed to the floor and soffit of slab/beam with MS cleats bolted as required, as base to receive tile cladding and different finishes over it as per design & details given in drawing/Architect instruction. Rate is inclusive of all necessary hardware & fixtures. | Sft. | 250 |  | 0 |  | 0 | 200.2427 | 50060.673
2 |  | Providing and fixing of hollow metal fire rated doors SIZE 2000 X 2400 as per IS 3614 part-1 & part-2 for stability and integrity. Pressed Galvanized steel confirming to IS 277 with the following specification. Recommended fire door shall have doors tested at CBRI or ARAI for maximum rating of 2hrs. Test certificates should be available for vision lites /panels as part of the fire door assembly. Door frame shall be double rebate profile of size 143 x 57 mm made out of 1.60mm (16 gauge) minimum thick galvanized steel sheet. Frames shall be Mitered and field assembled with self tabs. All provision should be mortised, drilled and tapped for receiving appropriate hardware. Rubber door silencers should be provided on the striking jamb. Frames should be provided with back plate bracket and anchor fasteners for installation on a finished plastered masonry wall opening. Once frame installed should be grouted with cement & sand slurry necessary for fire doors on the clear masonry opening. Door leaf shall be 46mm thick fully flush double skin door with or without vision lite. Door leaf shall be manufactured from 1.2mm (18guage) minimum thick galvanised steel sheet. The internal construction of the door should be rigid reinforcement pads for receiving appropriate hardware. The infill material shall be resin bonded honeycomb core. All doors shall be factory prepped for receiving appropriate hardware and provided with necessary reinforcement for hinges, locks, and door closers. The edges should be interlocked with a bending radius of 1.4mm. For pair of doors astragals has to be provided on the meeting stile for both active and inactive leaf. Vision lite wherever applicable should be provided as per manufacturers recommendation with a beeding and screws from inside. All doors and frames shall be finished with polyurethane aliphatic grade paint of approved colour. With Iron Pull Handle and Double lock. | Sft. | 75000 |  | 0 |  | 0 | 1 | 75000
3 |  | Providing and Applying kerakoll chemical Super Flex OR LATICRETE'S adhesive (as per manufacturer’s specification)or equivalent, inclusive of cleaning of site , and as per engineer in charge . | Sft. | 279.9331 |  | 0 |  | 0 | 405 | 113372.9097
4 |  | Providing & fixing testing and commissioning of braided UL Rated SS Flexible pipe With all necessery Fitting 1 Mtr. Length | Nos | 2150 |  |  |  |  | 8 | 17200
|  | TOTAL AMOUNT |  |  |  | 0 |  |  |  | 255633.5827

## MB
MB Sheet
Project the Lucknow Seating, LUCKNOW AIRPORT - TERMINAL-T3
SR. NO. | ITEM DESCRIPTION | Unit | No. | Length | Width | Height | Total | Remarks
1 | Providing & fixing paneling made of 50x50mm MS framework @ 600mm c/c bothways fixed to the floor and soffit of slab/beam with MS cleats bolted as required, as base to receive tile cladding and different finishes over it as per design & details given in drawing/Architect instruction. Rate is inclusive of all necessary hardware & fixtures.
| Mirror wall | Sqm | 1 | 3.51 |  | 3.1 | 10.881
| Elevation AA Wall | Sqm | 1 | 2.6 |  | 2.97 | 7.722
| Total Qty in Sqm | Sqm |  |  |  |  | 18.603
| Total Qty in Sft | Sft |  |  |  | 10.764 | 200.2427
2 | Providing and fixing of hollow metal fire rated doors SIZE 2000 X 2400 as per IS 3614 part-1 & part-2 for stability and integrity. Pressed Galvanized steel confirming to IS 277 with the following specification. Recommended fire door shall have doors tested at CBRI or ARAI for maximum rating of 2hrs. Test certificates should be available for vision lites /panels as part of the fire door assembly. Door frame shall be double rebate profile of size 143 x 57 mm made out of 1.60mm (16 gauge) minimum thick galvanized steel sheet. Frames shall be Mitered and field assembled with self tabs. All provision should be mortised, drilled and tapped for receiving appropriate hardware. Rubber door silencers should be provided on the striking jamb. Frames should be provided with back plate bracket and anchor fasteners for installation on a finished plastered masonry wall opening. Once frame installed should be grouted with cement & sand slurry necessary for fire doors on the clear masonry opening. Door leaf shall be 46mm thick fully flush double skin door with or without vision lite. Door leaf shall be manufactured from 1.2mm (18guage) minimum thick galvanised steel sheet. The internal construction of the door should be rigid reinforcement pads for receiving appropriate hardware. The infill material shall be resin bonded honeycomb core. All doors shall be factory prepped for receiving appropriate hardware and provided with necessary reinforcement for hinges, locks, and door closers. The edges should be interlocked with a bending radius of 1.4mm. For pair of doors astragals has to be provided on the meeting stile for both active and inactive leaf. Vision lite wherever applicable should be provided as per manufacturers recommendation with a beeding and screws from inside. All doors and frames shall be finished with polyurethane aliphatic grade paint of approved colour. With Iron Pull Handle and Double lock.
| Fire Door | Nos | 1 |  |  |  | 1
| Total Qty in Sqm | Nos |  |  |  |  | 1
3 | Providing and Applying kerakoll chemical Super Flex OR LATICRETE'S adhesive (as per manufacturer’s specification)or equivalent, inclusive of cleaning of site , and as per engineer in charge . | Sft
| Ledge Wall Both side | Sqm | 2 | 8.5 |  | 1.2 | 20.4
| Seating Sides | Sqm | 2 | 0.6 |  | 0.45 | 0.54
| Elevation AA | Sqm | 2 | 2.6 |  | 3.1 | 16.12
| Seating Sides | Sqm | 2 | 0.6 |  | 0.45 | 0.54
| Total Qty in Sqm | Sqm |  |  |  |  | 37.6
| Total Qty in Sft | Sft |  |  |  | 10.76 | 405

## Rate analysis
Rate Analysis
1 | Providing & fixing paneling made of 50x50mm MS framework @ 600mm c/c bothways fixed to the floor and soffit of slab/beam with MS cleats bolted as required, as base to receive tile cladding and different finishes over it as per design & details given in drawing/Architect instruction. Rate is inclusive of all necessary hardware & fixtures.
Rate Anaylsis for 10 Sqm Area
| MS Tubes Framing With MS cleat and Fastner @ 1.32 Kg / Sqft with Primer | Sqm | 130 | 105 | 13650
| Wastage 5% | Sqm | 6.5 | 105 | 682.5
| scaffolding | LS | 1 | 3000 | 3000
Labours
| Labour for Installation & Fixing @ 40/- Sqft | Nos | 10 | 430.56 | 4305.6
| Total |  |  |  | 21638.1
| Add CPOH @ 20% | 20% |  |  | 4327.62
| Add P.F. & ESI for Labours @ 4.25% as per CPWD |  |  |  | 919.6192
| Rate Analysis / Cost for 10 Sqm |  |  |  | 26885.3393
| Per Sqm Cost |  |  |  | 2689
| Per Sqft Cost |  |  |  | 250
4 | Providing and Applying kerakoll chemical Super Flex OR LATICRETE'S adhesive (as per manufacturer’s specification)or equivalent, inclusive of cleaning of site , and as per engineer in charge .
Chemical or adhesive
| Kerakoll super flex PU adhesive (covrage 1.5kg /m2 per mm thik (Minimum Consider 3mm Thik Chemical ) | sqm | 1 | 2325 | 2325
| wastage 5% | Sqm | 0.05 | 2325 | 116.25
Labours
| Tools & Plant Accessories @ 3% |  |  |  | 69.75
| Total |  |  |  | 2511
Water & Electricity Charges @ 2%
| Total |  |  |  | 2511
| Add CPOH @ 15% | 20% |  |  | 502.2
| Rate Analysis / Cost for 1 Sqm |  |  |  | 3013.2
| Per Sft Cost |  |  |  | 279.9331