## Sheet1
VARIATION STATEMENT
Project: |  | Cafeccino, LUCKNOW AIRPORT - TERMINAL-T3
Package Details:
Previous SO No.:
Document Date:
SR NO | SERVICE NO | ITEM DESCRIPTION | UNIT | Counter Offer | Previous BOQ |  | Variation |  | Revised BOQ |  | % Variation | Remarks
[5 empty] | QTY | AMOUNT | QTY | AMOUNT | QTY | AMOUNT
CIVIL AND INTERIOR
Boq Item no-
1 |  | P&F of single leaf service trap door, with wooden framework out of vertical members Support at 400 mm c/c & with horizontal members at 550 mm c/c with both side 18mm thick FR Grade plywood (selected & approved make) backing both side of the framing,. Rate inclusive of all necessary supporting from existing slab, necessary scaffolding & hardware fittings, etc. Complete as per architectural detail drawing. Size: 600 mm X 750mm. | Nos | 4645.1562 | (reference Irish House Door Rate) |  |  | 0 | 1 | 4645.1562
2 |  | Providing and fixing SS304 grade sink | nos | 4000 |  |  |  |  | 1 | 4000
3 |  | Providing and fixing electric metre Make- Secure | nos | 12600 |  |  |  |  | 1 | 12600
4 |  | Providing and fixing ss foot rail grade-304 16 gauge | Rmt | 1767.3384 |  |  |  |  | 11 | 19440.7224
[6 empty] | 0 |  | 0 |  | 0
|  | TOTAL AMOUNT |  |  |  | 0 |  | 0 |  | 40685.8786

## Adani RA
4 | Providing and fixing 50 MM ss foot rail grade-304 16 gauge with 25mm vertical support grout with chemical on floor or as per drawing and Engineer project-in-charge
Rate Analysis for 1 Rmt
| 50 mm SS Tube 16 Gauge weight per metre | kg | 2.537 | 260 | 659.62
| Vertical Bollard With chemical grouting | nos | 2 | 260 | 520
| Wastage @ 10% |  |  |  | 117.962
| Cartage @10 / rmt |  |  |  | 10
Labours
| Labour for fixing 120/ Rmt | Rmt | 1 | 110 | 110
| Buffing and polishing | Rmt | 1 | 50 | 50
| Tools & Plant Accessories @ 2% | Rmt | 1 | 5.2 | 5.2
| Total |  |  |  | 1472.782
Water & Electricity Charges @ 2%
| Total |  |  |  | 1472.782
| Add CPOH @ 20% |  |  |  | 294.5564
Add P.F. & ESI for Labours @ 4.25% as per CPWD
| Total cost of 1 Rmt |  |  |  | 1767.3384