## Variation sheet-03
VARIATION STATEMENT -3
Project: |  | IRISH HOUSE, LUCKNOW AIRPORT - TERMINAL-T3
Package Details:
Previous SO No.:
Document Date: |  | 2024-05-04
SR NO | SERVICE NO | ITEM DESCRIPTION | UNIT | RATE | Previous BOQ |  | Variation |  | Revised BOQ |  | % Variation | Remarks
[5 empty] | QTY | AMOUNT | QTY | AMOUNT | QTY | AMOUNT
EXTRA ITEM
1 |  | Providing Waterproof and flexible Led strips Lights for planters and Bar counter cove as per approved make and specification or as per project in-charge. | Rmt | 212.137 |  |  |  | 0 | 44.95 | 9535.5604
2 |  | Providing Spike lights in 6 watt for a planters as per approved make and specification or as per project in-charge. | Nos | 723.741 |  |  |  |  | 12 | 8684.892
3 |  | Proving and fixing 20mm SS (304) T- profile Finished in Brass PVD coating between Two diffrrent flooring,Fixed with Adhesive super glue or complete as per approved drawing and make and as directed by Engineer - In- Charge | Rmt | 1507.4809 |  |  |  |  | 44.29 | 66766.3313
4 |  | Providing and applying Enamal black paint on Existing Cable Tray Height 3.75 m Height or per desire and as per project -in - charge.(Quantity will be change after measurment,so far taken a close approximate) | Sft | 22 |  |  |  |  | 189.6897 | 4173.1727
5 |  | Providing and fixing exsting ceiling gypsum board to inseated FR grade fire board as per project in charge | Sft | 18.9056 |  |  |  |  | 1812.227 | 34261.26
6 |  | Supplying, installation, Testing and commissioning flush mounting floor metallic boxes(POP-UP BOX) IP 66 3 module of 6/16A International switch & socket outlet + 1 set complete with all installation kits, accessories, required to finish the installation Make- Legrand | nos | 4955.925 |  |  |  |  | 13 | 64427.025
7 |  | Installation and testing of TV both side all nessery hardware required for fixing or as per project engineer. | nos | 1173 |  |  |  |  | 2 | 2346
|  | Providing and fixing electric metre Make- Secure | nos | 12600 |  |  |  |  | 1 | 12600 |  | Kinldy check if this is installed or not. Payment shall be against executed quantity.
|  | TOTAL AMOUNT | [7 empty] | 202794.2413

## MB
MB Sheet
PROJECT: IRISH HOUSE, LUCKNOW AIRPORT - TERMINAL-T3
SR. NO. | ITEM DESCRIPTION | Unit | No. | Length | Width | Height | Total | Remarks
1 | Providing Waterproof and flexible Led strips Lights for planters and Bar counter cove as per approved make and specification or as per project in-charge.
| Flexible Led strips for planters-01 | rmt. | 1 | 22.8 |  |  | 22.8
| Flexible Led strips for planters-02 | rmt. | 1 | 12 |  |  | 12
| Bar counter front | Rmt | 1 | 3.85 |  |  | 3.85
| Side | Rmt | 1 | 3.15 |  |  | 3.15
| Side | Rmt | 1 | 3.15 |  |  | 3.15
| Total Qty in Rmt | Rmt. |  |  |  |  | 44.95
2 | Providing Spike lights in 6 watt for a planters as per approved make and specification or as per project in-charge.
| Spike Light for Planters | Nos | 12 |  |  |  | 12
| Total Qty in nos | [5 empty] | 12
3 | Proving and fixing 20mm SS (304) T- profile Finished in Brass PVD coating between Two diffrrent flooring,Fixed with Adhesive super glue or complete as per approved drawing and make and as directed by Engineer - In- Charge
| T profile | Rmt | 2 | 19.2 |  |  | 38.4
| Front of Bar counter | Rmt | 1 | 5.89 |  |  | 5.89
| Total Qty in | Rmt |  |  |  |  | 44.29
4 | Providing and applying Enamal black paint on Existing Cable Tray Height 3.75 m Height or per desire and as per project -in - charge.(Quantity will be change after measurment,so far taken a close approximate)
| Cable tray | Sqm | 2 | 19.155 | 0.46 |  | 17.6226
| Total Qty in | sqm |  |  |  |  | 17.6226
| Total Qty in | Sft |  |  |  | 10.764 | 189.6897
5 | Providing and fixing exsting ceiling gypsum board to inseated FR grade fire board as per project in charge
| Flat area | Sqm | 1 | 18.3 | 9.2 |  | 168.36
| Total Qty in | sqm |  |  |  |  | 168.36
| Total Qty in | Sft |  |  |  | 10.764 | 1812.227
6 | Supplying, installation, Testing and commissioning flush mounting floor metallic boxes(POP-UP BOX) IP 66 3 module of 6/16A International switch & socket outlet + 1 set complete with all installation kits, accessories, required to finish the installation Make- Legrand
| Floor Pop up box | Nos | 13 |  |  |  | 13
| Total Qty in | Nos |  |  |  |  | 13
7 | Installation and testing of TV both side all nessery hardware required for fixing or as per project engineer.
| TV Both side | Nos | 2 |  |  |  | 2
| Total Qty in | Nos |  |  |  |  | 2

## Analysis (hidden)
Rate Analysis
1 | Providing Waterproof and flexible Led strips Lights for planters and Bar counter cove as per approved make and specification or as per project in-charge.
Rate Anaylsis for 1 Rmt Area
| Purchase Rate | Rmt | 1 | 155 | 155
| Wastage 5% | Rmt | 0.05 | 155 | 7.75
| Freight Charge 2% | Rmt | 0.02 | 120 | 2.4
Labours
| Labour for Installation & Fixing @ 20/- Rmt | Rmt | 1 | 20 | 20
| Tools & Plant Accessories @ 2% |  |  |  | 3.703
| Total |  |  |  | 188.853
| Add CPOH @ 15% | 15% |  |  | 28.328
| Add P.F. & ESI for Labours @ 4.25% as per CPWD |  |  |  | 8.0263
| Rate Analysis / Cost for 1 Rmt |  |  |  | 225.2072
2 | Providing Spike lights in 6 watt for a planters as per approved make and specification or as per project in-charge.
Rate Anaylsis for 1 nos
| Purchase Rate | Nos | 1 | 500 | 500
| Freight Charge 2% | Nos | 0.02 | 500 | 10
Labours
| Labour for Installation & Fixing @ 110/- Rmt |  | 1 | 107 | 107
| Tools & Plant Accessories @ 2% |  |  |  | 12.34
| Total |  |  |  | 629.34
| Add CPOH @ 15% | 15% |  |  | 94.401
| Add P.F. & ESI for Labours @ 4.25% as per CPWD |  |  |  | 26.747
| Rate Analysis / Cost for 1 Nos |  |  |  | 750.4879
3 | Proving and fixing 20mm SS (304) T- profile Finished in Brass PVD coating between Two diffrrent flooring,Fixed with Adhesive super glue or complete as per approved drawing and make and as directed by Engineer - In- Charge
Rate Anaylsis for 1 rmt
| Purchase Rate | Rmt | 1 | 1130 | 1130
| Wastage 5% | Rmt | 0.05 | 1130 | 56.5
| Freight Charge 2% | Rmt | 0.02 | 1130 | 22.6
| Chemical / super glue | Rmt | 1 | 64 | 64
| Wastage Chemical 5% | Rmt | 0.05 | 64 | 3.2
Labours
| Labour for Installation & Fixing @ 40/- Rmt |  | 1 | 40 | 40
| Tools & Plant Accessories @ 2% |  |  |  | 26.326
| Total |  |  |  | 1342.626
| Add CPOH @ 15% | 15% |  |  | 201.3939
| Add P.F. & ESI for Labours @ 4.25% as per CPWD |  |  |  | 57.0616
| Rate Analysis / Cost for 1 Rmt |  |  |  | 1601.0815
4 | Providing and applying Enamal black paint on Existing Cable Tray Height 3.75 m Height or per desire and as per project -in - charge.(Quantity will be change after measurment,so far taken a close approximate)
Rate Analysis / Cost for 20 Sqm
Consumption Single Coat 5 Sqm / Per Kg
Materials
| Enamel paint paint | Litre | 4 | 350 | 1400
| Wastage @ 5% | Sqm | 0.2 | 350 | 70
| Sand Paper | Sqm | 20 | 20 | 400
| Mixing preparation of thinner or tarpin oil | Litre | 4 | 50 | 200
Labours
| Labour Rate for Painting @ 15/- Sqft | Sqft | 20 | 161.481 | 3229.62
| Helper for Cleaning | Nos | 1 | 550 | 550
| Scaffolding,Blend Machine, Tools & Plant Accessories @ 10% | Sqm | 20 | 35 | 700
| Total |  |  |  | 6549.62
Water & Electricity Charges @ 2%
| Total |  |  |  | 6549.62
| Add CPOH @ 20% |  |  |  | 1309.924
| Add P.F. & ESI for Labours @ 4.25% as per CPWD |  |  |  | 278.3589
| Rate Analysis / Cost for 20 Sqm |  |  |  | 8137.9028
| Per Sqm Cost |  |  |  | 407
| Per Sqft Cost |  |  |  | 38
5 | Providing and fixing exsting ceiling gypsum board to inseated FR grade fire board as per project in charge
Rate Anaylsis for 1 Sqm
| Normal Gypsum board | sqm | 1 | 185 | 185
| Total Cost normal gypsum board |  |  |  | 185
| Fire Rate Gypsum Board | Sqm | 1 | 393 | 393
| Freight Charge 2% | Rmt | 0.02 | 393 | 7.86
| Wastage 5% | Rmt | 0.05 | 393 | 19.65
| Total Cost fire rated board |  |  |  | 420.51
| Price varation of normal and fire rated board Sqm |  |  |  | 235.51
| Price varation of sft |  |  | 10.764 | 21.8794
6 | Supplying, installation, Testing and commissioning flush mounting floor metallic boxes(POP-UP BOX) IP 66 3 module of 6/16A International switch & socket outlet + 1 set complete with all installation kits, accessories, required to finish the installation Make- Legrand
Rate Anaylsis for 1 nos
| Purchase Rate | Nos | 1 | 4050 | 4050
| Freight Charge 2% | Nos | 0.02 | 4050 | 81
Labours
| Labour for Installation & Fixing @ 350/- nos |  | 1 | 350 | 350
| Tools & Plant Accessories @ 2% |  |  |  | 89.62
| Total |  |  |  | 4570.62
| Add CPOH @ 15% | 15% |  |  | 685.593
| Add P.F. & ESI for Labours @ 4.25% as per CPWD |  |  |  | 194.2514
| Rate Analysis / Cost for 1 Nos |  |  |  | 5450.4644
7 | Installation and testing of TV both side all nessery hardware required for fixing or as per project engineer.
Rate Anaylsis for 1 nos
| Purchase Rate | Nos |  |  | 0
| Freight Charge 2% | Nos |  |  | 0
Labours
| Labour for Installation & Fixing @ 2000/- nos |  | 1 | 2150 | 2150
| Tools & Plant Accessories @ 2% |  |  |  | 43
| Total |  |  |  | 2193
| Add CPOH @ 15% | 15% |  |  | 328.95
| Add P.F. & ESI for Labours @ 4.25% as per CPWD |  |  |  | 93.2025
| Rate Analysis / Cost for 1 Nos |  |  |  | 2615.1525

## Adani Analysis
Rate Analysis
1 | Providing Waterproof and flexible Led strips Lights for planters and Bar counter cove as per approved make and specification or as per project in-charge.
Rate Anaylsis for 1 Rmt Area
| Purchase Rate | Rmt | 1 | 155 | 155
| Wastage 5% | Rmt | 0.05 | 155 | 7.75
| Freight Charge 2% | Rmt | 0.02 | 155 | 3.1
Labours
| Labour for Installation & Fixing @ 20/- Rmt | Rmt | 1 | 15 | 15
| Tools & Plant Accessories @ 2% |  |  |  | 3.617
| Total |  |  |  | 184.467
| Add CPOH @ 15% | 15% |  |  | 27.67
Add P.F. & ESI for Labours @ 4.25% as per CPWD
| Rate Analysis / Cost for 1 Rmt |  |  |  | 212.137
2 | Providing Spike lights in 6 watt for a planters as per approved make and specification or as per project in-charge.
Rate Anaylsis for 1 nos
| Purchase Rate | Nos | 1 | 500 | 500
| Freight Charge 2% | Nos | 0.02 | 500 | 10
Labours
| Labour for Installation & Fixing @ 110/- Rmt |  | 1 | 107 | 107
| Tools & Plant Accessories @ 2% |  |  |  | 12.34
| Total |  |  |  | 629.34
| Add CPOH @ 15% | 15% |  |  | 94.401
Add P.F. & ESI for Labours @ 4.25% as per CPWD
| Rate Analysis / Cost for 1 Nos |  |  |  | 723.741
3 | Proving and fixing 20mm SS (304) T- profile Finished in Brass PVD coating between Two diffrrent flooring,Fixed with Adhesive super glue or complete as per approved drawing and make and as directed by Engineer - In- Charge
Rate Anaylsis for 1 rmt
| Purchase Rate | Rmt | 1 | 1130 | 1130
| Wastage 5% | Rmt | 0.05 | 1130 | 56.5
| Freight Charge 2% | Rmt | 0.02 | 1130 | 22.6
| Chemical / super glue | Rmt | 1 | 35 | 35
| Wastage Chemical 3% | Rmt | 0.03 | 35 | 1.05
Labours
| Labour for Installation & Fixing @ 40/- Rmt |  | 1 | 40 | 40
| Tools & Plant Accessories @ 2% |  |  |  | 25.703
| Total |  |  |  | 1310.853
| Add CPOH @ 15% | 15% |  |  | 196.6279
Add P.F. & ESI for Labours @ 4.25% as per CPWD
| Rate Analysis / Cost for 1 Rmt |  |  |  | 1507.4809
4 | Providing and applying Enamal black paint on Existing Cable Tray Height 3.75 m Height or per desire and as per project -in - charge.(Quantity will be change after measurment,so far taken a close approximate)
Rate Analysis / Cost for 20 Sqm
Consumption Single Coat 5 Sqm / Per Kg
Materials
| Enamel paint paint | Litre | 4 | 300 | 1200
| Wastage @ 5% | Sqm | 0.2 | 300 | 60
| Sand Paper | Sqm | 20 |  | 0
| Mixing preparation of thinner or tarpin oil | Litre | 4 | 10 | 40
Labours
| Labour Rate for Painting @ 10/- Sqft | Sqft | 20 | 107.654 | 2153.08
| Helper for Cleaning | Nos | 1 | 550
| Scaffolding,Blend Machine, Tools & Plant Accessories @ 10% | Sqm | 20 | 30 | 600
| Total |  |  |  | 4053.08
Water & Electricity Charges @ 2%
| Total |  |  |  | 4053.08
| Add CPOH @ 15% |  |  |  | 607.962
Add P.F. & ESI for Labours @ 4.25% as per CPWD
| Rate Analysis / Cost for 20 Sqm |  |  |  | 4661.042
| Per Sqm Cost |  |  |  | 233
| Per Sqft Cost |  |  |  | 22
5 | Providing and fixing exsting ceiling gypsum board to inseated FR grade fire board as per project in charge
Rate Anaylsis for 1 Sqm
| Normal Gypsum board | sqm | 1 | 185 | 185
| Total Cost normal gypsum board |  |  |  | 185
| Fire Rate Gypsum Board | Sqm | 1 | 370 | 370
| Freight Charge 2% | Rmt | 0.02 | 370
| Wastage 5% | Rmt | 0.05 | 370 | 18.5
| Total Cost fire rated board |  |  |  | 388.5
| Price varation of normal and fire rated board Sqm |  |  |  | 203.5
| Price varation of sft |  |  | 10.764 | 18.9056
6 | Supplying, installation, Testing and commissioning flush mounting floor metallic boxes(POP-UP BOX) IP 66 3 module of 6/16A International switch & socket outlet + 1 set complete with all installation kits, accessories, required to finish the installation Make- Legrand
Rate Anaylsis for 1 nos
| Purchase Rate | Nos | 1 | 4050 | 4050
| Freight Charge 2% | Nos | 0.02 | 4050
Labours
| Labour for Installation & Fixing @ 350/- nos |  | 1 | 175 | 175
| Tools & Plant Accessories @ 2% |  |  |  | 84.5
| Total |  |  |  | 4309.5
| Add CPOH @ 15% | 15% |  |  | 646.425
Add P.F. & ESI for Labours @ 4.25% as per CPWD
| Rate Analysis / Cost for 1 Nos |  |  |  | 4955.925
7 | Installation and testing of TV both side all nessery hardware required for fixing or as per project engineer.
Rate Anaylsis for 1 nos
| Purchase Rate | Nos |  |  | 0
| Freight Charge 2% | Nos |  |  | 0
Labours
| Labour for Installation & Fixing @ 2000/- nos |  | 1 | 1000 | 1000
| Tools & Plant Accessories @ 2% |  |  |  | 20
| Total |  |  |  | 1020
| Add CPOH @ 15% | 15% |  |  | 153
Add P.F. & ESI for Labours @ 4.25% as per CPWD
| Rate Analysis / Cost for 1 Nos |  |  |  | 1173