## CAfeccino
BILL OF QUANTITIES- INTERIOR Additional WORKS
B03 & B04-Cafeccino, T3, Lucknow Airport
[5 empty] | FDT Proposal |  | Adani CO |  | FDT Final Proposal' |  | Adani Final
S. No. | Location | Description | Unit | Qty. | Rate | Amount | Rate | Amount | Rate | Amount | Rate | Amount
Preamble
| a | Base Rate shall mean the landed cost of material at site excluding all taxes and duties (Net of GST). Base rate also includes loading, transport, packing, forwarding, unloading and handling charges (FOR site) required for the works to be executed but exclude contractor’s profit and overheads.
| b | The item rate shall include cost of equipments and machineries, all leads and lifts, loading and unloading charges, transportation cost and conveyance of all material and all other incidental charges etc., complete for successful completion of work and as directed by the project manager.
| c | The BOQ shall be read in conjunction with the available drawings, technical specifications and FFE.
| g | All flooring items shall be inclusive of protection with adhesive sheet/ cello bubble roll on the flooring till final handover to avoid breakage. Any breakage till final handover to Operations Team shall be the responsibility of the contractor.
| h | All flooring items shall be of minimum thickness specified in the item and no extra cost shall be paid for any thickness over and above the minimum specified thickness. Nothing extra to be paid for wastage.
| i | All paints shall have low VOC / zero VOC. For all types of paint, Contractor shall provide product warranty of minimum 7 years.
| j | The Contractor has to do the housekeeping on daily basis without claiming any additional cost.
| k | Storage and safety of materials shall be the responsibility of the Contractor.
| l | Barricading material for the safety and work progress to be arranged by the concern contractor
| l | Shift working in operational areas to be considered by the vendor. Prior approval of the logistic and shift working to be taken by the contractor.
1 | Location | Flooring PCC And Tile
PCC And Tile
1.1 | PCC F.O.H Area | Preparing of 50-38mm PPC bed for floor Leveling at FOH | Sqm. | 14 | 1250 | 17500 | 500 | 7000 | 750 | 10500 | 750 | 10500
1.2 | PCC BOH | Preparing of 90mm PPC floor Leveling Store Back Side Area | Sqm. | 6 | 1650 | 9900 | 900 | 5400 | 1250 | 7500 | 1170 | 7020
1.3 | TILE WORK -FLOORING | Supply and fixing of floor tile Belgium Grey Tile 600 X 600MM Vetrified - FULL BODY, | Sqm. | 6 | 2250 | 13500 | 2250 | 13500 | 2250 | 13500 | 2250 | 13500
2 |  | FALSE CEILING WORKS
FALSE CEILING
2.1 | GRID CEILING Store Area | "Metal Grid ceiling -Alminium Perameter of size 0.55 mm thick having one flange of 20mm and another flange of 30mm and a web of 27mm along with perimeter of ceiling, The suspending Aluminium T channels of size 25mm 0.9mm thick with two flanges of 15mm each from the soffit at 600mm centers with ceiling angle of width 25X25 mm thick fixed to soffit with GI cleat and steel expansion fasteners. Ceiling section of 0.55mm thickness having knurled web of 51.5mm and two flanges of 26mm each with lips of 10.5mm" | Sqm. | 6 | 3850 | 23100 | 2400 | 14400 | 2850 | 17100 | 2850 | 17100
3 |  | PAINTING WORKS
PAINT FINISH
3.1 | Srore Room Walls Paint | Providing and applying three (minimum) coats of White - Emlsion, Make - Asian Paint, as specified in drawing, with a coat of approved primer including the cost of scraping, levelling & preparing the surfaces with filling materials (putty) required primer, along with sand papering wherever required, scaffolding etc. complete as per specs with giving necessary drying period for each coat of approved colours and shade with roller. Contractor must get sample approved by the Architect before executing. All complete to the entire satisfaction of Project Manager. Refer finishing schedule for the Paint code. | Sqm. | 23 | 650 | 14950 | 650 | 14950 | 650 | 14950 | 650 | 14950
4 |  | Electrical & Lighting Work
SURFACE CEILING LIGHT
4.1 | BOH | 600mmX600mm Surface Ceiling light (Make Philips Osram wipro- 18 watt. ) | Nos. | 2 | 3200 | 6400 | 2200 | 4400 | 2850 | 5700 | 2500 | 5000
5 |  | Furniture
5.1 | Front Count | Supply & Installation of Fill Unit of available space, make of 18mm & 12mm FR Plywood, 1mm Laminate finish inside, exterior finish with existing matching c12mm Solic Acrylic Surfance. | Nos. | 1 | 48000 | 48000 | Pls share the rate analysis |  | 48000 | 48000 | 46000 | 46000 | Annexure attached
5.2 | Corian L-Corner | Providing & Fixing Corian CR-02 in L-shape of size 82x225mm at left the side edges of the outlet as shown in detail civil draing over existing HDHMR board panelling. | RM | 1.86 | 4800 | 8928 | 4800 | 8928 | 4800 | 8928 | 4800 | 8928
|  | TOTAL |  |  |  | 142278 |  | 68578 |  | 126178 |  | 122998
GST EXTRA

## Counter Rate Analysis
Refabrication
Filler Counter
S.N | Item | Unit Location | Spec. | L | B | Pcs | UOM | Qty | Rate | Amount(Rs.)
1 | 19mm FR Plywood | Shutter | Century FR |  |  |  | Sqft. | 24 | 127 | 3048
2 | 1mm Laminate | shutter , Floor, Side Partition & Back with Door | Merino |  |  |  | Sqft. | 24 | 45.31 | 1087.44
2 | 12mm Corian Cladding | Front Corian |  | 750 | 1800 | 1 | Sqft. | 14.5314 | 880 | 12787.632
2 | Corian Fabrication | Re fixing of Front artwork |  |  |  |  | Sqft. | 14.5314 | 450 | 6539.13
3 | Adhesive Corian & Silicon | [5 empty] | No | 3 | 850 | 2550
4 | Overhead & Wastages |  | Screw, Adhesive, Machine hours, Wastages |  |  |  | No | 1 | 1300.6101 | 1300.6101
5 | Re Fabrication |  | Labour Carpentry , Finishing, SS fixing, Local Transport, Material loading, bits tools etc. |  |  |  | EA | 1 | 5100 | 5100
6 | Transportation, & Traveling, Accomodation, Allowances |  | 3 Manpower & To & Fro |  |  |  | EA | 1 | 6000 | 6000
A | Sub Total | [8 empty] | 38412.8121
B | Contractor Markup | [8 empty] | 9603.203
C | COST | [8 empty] | 48016.0151
| RATE | [8 empty] | 48000

## Counter Rate Analysis - Adani
Refabrication
Filler Counter
S.N | Item | Unit Location | Spec. | L | B | Pcs | UOM | Qty | Rate | Amount(Rs.)
1 | 19mm FR Plywood | Shutter | Century FR |  |  |  | Sqft. | 24 | 127 | 3048
2 | 1mm Laminate | shutter , Floor, Side Partition & Back with Door | Merino |  |  |  | Sqft. | 24 | 45.31 | 1087.44
2 | 12mm Corian Cladding | Front Corian |  | 750 | 1800 | 1 | Sqft. | 14.5314 | 880 | 12787.632
2 | Corian Fabrication | Re fixing of Front artwork |  |  |  |  | Sqft. | 14.5314 | 450 | 6539.13
3 | Adhesive Corian & Silicon | [5 empty] | No | 3 | 850 | 2550
4 | Overhead & Wastages |  | Screw, Adhesive, Machine hours, Wastages |  |  |  | No | 1 | 1300.6101 | 1300.6101
5 | Re Fabrication |  | Labour Carpentry , Finishing, SS fixing, Local Transport, Material loading, bits tools etc. |  |  |  | EA | 1 | 5100 | 5100
6 | Transportation, & Traveling, Accomodation, Allowances |  | 3 Manpower & To & Fro |  |  |  | EA | 1 | 2000 | 2000
A | Sub Total | [8 empty] | 34412.8121
B | Contractor Markup | [8 empty] | 5161.9218
C | COST | [8 empty] | 39574.7339
| RATE | [8 empty] | 40000

## Bills
Secure Energy Meter
Rate Analysis
Particular | Amount(INR)
Material Rate | 18280
Electrician | 1800
Overheads | 401.6
Total | 20481.6
Mark up | 2048.16
Total Cost | 22529.76
Round off | 22500
SS Sink :
Rate Analysis
Particular | Amount(INR) | Amount(INR)
Material Rate | 3813.56 | 3813.56
Accessories | 500 | 500
Plumber/Fitting | 1200
Overheads | 110.2712
Total | 5623.8312 | 4313.56
Mark up | 843.5747 | 647.034
Total Cost | 6467.4059 | 4960.594
Round off | 6500 | 5000

## Manpower (hidden)
Detail of Manpower Losses due to Changes & Delay in Takeover the Site.
S.No | Manpower Type | Per Day Wages | Accomodation | Footing | Local Conveyance | Total | No. of Manpower Deployed | Days | Total
1 | Supervisor | 1333.3333 | 350 | 500 | 200 | 2383.3333 | 1 | 7 | 16683.3333
2 | Carpenter | 933.3333 | 200 | 350 | 100 | 1583.3333 | 1 | 5 | 7916.6667
3 | Electrician | 1000 | 200 | 350 | 100 | 1650 | 1 | 5 | 8250
4 | Painter | 833.3333 | 200 | 350 | 100 | 1483.3333 | 0 | 0 | 0
5 | Tile Meson | 833.3333 | 200 | 350 | 100 | 1483.3333 | 0 | 0 | 0
6 | Ceiling | 833.3333 | 200 | 350 | 100 | 1483.3333 | 0 | 0 | 0
7 | MS Welder | 1000 | 200 | 350 | 100 | 1650 | 2 | 7 | 23100
8 | Labour Hel0er | 600 | 200 | 350 | 100 | 1250 | 1 | 5 | 6250
| TOTAL MANPOWER | [7 empty] | 62200