## Summary Sheet
Summary of KFC
SL NO. | Description | As Per PO | Executed Amount | NT Items | Deviation
1 | Civil & Interior | 4369849 | 4459129.655 |  | 89280.655
2 | Plumbing | 790080 | 659585 |  | -130495
3 | NT Items |  |  | 203725 | 203725
Total |  | 5159929 | 5118714.655 | 203725 | 162510.655

## BOQ Price Bid
Sr No. | Item Code | Item Name | Item Description | UOM | PO Qty | Minimum Amount | Unit Price | Amount | Executed Qty | Executed Amount
1 |  | Civil work | Civil work | NOS | 1.000 |  |  | 4369849 |  | 4459129.655
1 | 1 | ANTI TERMITE TREATMENT | ANTI TERMITE TREATMENT
2 | 1 | PEST CONTROL Providing doing anti termite treatment with IMIDACLOPRID (OZIER) for entire area (Pest control) Diluting and injecting chemical emulsion 3 in floor for pre constructional Anti Termite treatment and creating a continuous chemical @ 4 center to center barrier all over as per manufacturer specification and ISI standards. | PEST CONTROL Providing doing anti termite treatment with IMIDACLOPRID (OZIER) for entire area (Pest control) Diluting and injecting chemical emulsion 3 in floor for pre constructional Anti Termite treatment and creating a continuous chemical @ 4 center to center barrier all over as per manufacturer specification and ISI standards. | Sft | 960.000 |  | 15 | 14400 | 1096.5 | 16447.5
3 | 2 | DISMANTLING WORKS | DISMANTLING WORKS
4 | 1 | DISMANTLING WORKS Pre-approval of Amount for any dismantling works required | DISMANTLING WORKS Pre-approval of Amount for any dismantling works required | Job | 1.000 | 5,000.00 | 10000 | 10000 | 1 | 10000
5 | 3 | CIVIL WORKS | CIVIL WORKS
6 | 3.01 | 100MM THK SIPOREX WALL P C light wt. Block masonry of 100mm thk with CM 1 4 in proper line, level plumb (Siporex or Aerocon block of size 600 x 200 x 100 mm) At every 1 tm ht. interval stiffener should be provided. Rate to include the cost of stiffener lintel. | 100MM THK SIPOREX WALL P C light wt. Block masonry of 100mm thk with CM 1 4 in proper line, level plumb (Siporex or Aerocon block of size 600 x 200 x 100 mm) At every 1 tm ht. interval stiffener should be provided. Rate to include the cost of stiffener lintel. | Sft | 2600.000 |  | 165 | 429000 | 2546.105 | 420107.325
7 | 3.02 | INTERNAL PLASTER P A 12-15mm thick plaster in cement mortar 1 4 (1 cement 4coarse sand) to ceiling, all types of RCC. work, brick work surfaces at all levels in line, level and plumb including smooth cement finish or roughning of surface to hold tiles and providing necessary grooves at junctions of walls and ceiling, door window frames incl. racking the joints of roughing the RCC. surface, necessary curing scaffolding etc. complete as directed. Note Allow for providing and fixing galvanized chicken mesh 300mm wide (24 gauge, 12mm size) at junction of brick masonry and concrete members to be plastered or clapped or other locations as called for, properly stretched and nailed ensuring equal thickness of plaster on both sides of mesh. Provision for chemical bonding with a layer of Plaster Master from Roff for RCC surfaces and use of REUROn fibres to avoid superficial cracks.No extra payment shall be made for p f chicken mesh, Plaster Master and REUROn. | INTERNAL PLASTER P A 12-15mm thick plaster in cement mortar 1 4 (1 cement 4coarse sand) to ceiling, all types of RCC. work, brick work surfaces at all levels in line, level and plumb including smooth cement finish or roughning of surface to hold tiles and providing necessary grooves at junctions of walls and ceiling, door window frames incl. racking the joints of roughing the RCC. surface, necessary curing scaffolding etc. complete as directed. Note Allow for providing and fixing galvanized chicken mesh 300mm wide (24 gauge, 12mm size) at junction of brick masonry and concrete members to be plastered or clapped or other locations as called for, properly stretched and nailed ensuring equal thickness of plaster on both sides of mesh. Provision for chemical bonding with a layer of Plaster Master from Roff for RCC surfaces and use of REUROn fibres to avoid superficial cracks.No extra payment shall be made for p f chicken mesh, Plaster Master and REUROn. | Sft | 4900.000 | 318,500.00 | 70 | 343000 | 4896.025 | 342721.75
8 | 4 | BRICK BAT COBA WATERPROOFING WORKS | BRICK BAT COBA WATERPROOFING WORKS
9 | 4.01 | SIPOREX BAT COBA- upto 100MM P L light wt. Solid Block (siporex or Aerocon) bat coba to conceal drainage plumbing lines for Grease trap of average thk of 100 mm with CM 1 4 top layer should be finished properly to receive flooring layer on it [ DISH WASH AREA] | SIPOREX BAT COBA- upto 100MM P L light wt. Solid Block (siporex or Aerocon) bat coba to conceal drainage plumbing lines for Grease trap of average thk of 100 mm with CM 1 4 top layer should be finished properly to receive flooring layer on it [ DISH WASH AREA] | Sft | 25.000 | 3,000.00 | 125 | 3125 | 87.285 | 10910.625
10 | 4.02 | SIPOREX BAT COBA- upto 150MM P L light wt. Solid Block (siporex or Aerocon) bat coba to conceal drainage plumbing lines for Grease trap of average thk of 150 mm with CM 1 4 top layer should be finished properly to receive flooring layer on it [ DISH WASH AREA] | SIPOREX BAT COBA- upto 150MM P L light wt. Solid Block (siporex or Aerocon) bat coba to conceal drainage plumbing lines for Grease trap of average thk of 150 mm with CM 1 4 top layer should be finished properly to receive flooring layer on it [ DISH WASH AREA] | Sft | 30.000 | 4,350.00 | 165 | 4950 | 0 | 0
11 | 4.03 | SIPOREX BAT COBA- upto 305MM P L light wt. Solid Block (siporex or Aerocon) bat coba to conceal drainage plumbing lines for Grease trap of average thk of 200 mm with CM 1 4 top layer should be finished properly to receive flooring layer on it [ DISH WASH AREA] | SIPOREX BAT COBA- upto 305MM P L light wt. Solid Block (siporex or Aerocon) bat coba to conceal drainage plumbing lines for Grease trap of average thk of 200 mm with CM 1 4 top layer should be finished properly to receive flooring layer on it [ DISH WASH AREA] | Sft | 870.000 | 182,700.00 | 225 | 195750 | 1096.5 | 246712.5
12 | 4.04 | WATER PROOFING- MEMBRANE Providing and laying water- proofing treatment to hand wash, BOH area consisting of 4mm Thk Apex Apcon Sheild Dr Fixit Torchsheild or equivalent polyster reinforced APP modified bitumen membrane sheet(Basic Rate Rs.2000 Roll of 10mX1m) as approved, cleaning and smoothing of entire surface, smooth plaster upto 600mm from raw floor lvl, 12mmx12mm groove at 150mm from floor rising lvl, one coat of Bitcote Dr Fixit Apex equivalent (as approved)-heavy body bitumen primer (Basic Rate Rs.82 Kg) coating as a primer on surface and till 450mm from floor rising lvl, application of membrane sheet as per application detail and packing the hole cuts for pipe line and checking the area which is water proofed. Rate includes of laying the protective layer of Plaster. Measurement to be done of floor area, wall area not to be paid, if ht. is < 600 mm, difference of 600mm will be paid. | WATER PROOFING- MEMBRANE Providing and laying water- proofing treatment to hand wash, BOH area consisting of 4mm Thk Apex Apcon Sheild Dr Fixit Torchsheild or equivalent polyster reinforced APP modified bitumen membrane sheet(Basic Rate Rs.2000 Roll of 10mX1m) as approved, cleaning and smoothing of entire surface, smooth plaster upto 600mm from raw floor lvl, 12mmx12mm groove at 150mm from floor rising lvl, one coat of Bitcote Dr Fixit Apex equivalent (as approved)-heavy body bitumen primer (Basic Rate Rs.82 Kg) coating as a primer on surface and till 450mm from floor rising lvl, application of membrane sheet as per application detail and packing the hole cuts for pipe line and checking the area which is water proofed. Rate includes of laying the protective layer of Plaster. Measurement to be done of floor area, wall area not to be paid, if ht. is < 600 mm, difference of 600mm will be paid. | Sft | 1750.000 | 192,500.00 | 175 | 306250 | 2215.32 | 387681
13 | 5 | PCC WORKS | PCC WORKS
14 | 5.01 | 50mm PCC Providing Laying PCC 1 3 6 of average thk 50mm of M 10 grade of concrete ( 1 cement 3 coarse sand 6graded stone aggregate 10 mm nominal size) BOH AREA | 50mm PCC Providing Laying PCC 1 3 6 of average thk 50mm of M 10 grade of concrete ( 1 cement 3 coarse sand 6graded stone aggregate 10 mm nominal size) BOH AREA | Sft | 870.000 |  | 75 | 65250 | 1096.5 | 82237.5
15 | 6 | CUT OUT WORKS | CUT OUT WORKS
16 | 6.01 | CUT OUT IN THE WALLS FOR AC DUCT ROUTING Making Cut out for AC ducts finishing the edges or filling the gaps after the duct installation; incl of water weather proofing walls from exterior side. | CUT OUT IN THE WALLS FOR AC DUCT ROUTING Making Cut out for AC ducts finishing the edges or filling the gaps after the duct installation; incl of water weather proofing walls from exterior side. | Nos | 6.000 |  | 1000 | 6000 | 6 | 6000
17 |  | Note No holes to be made in any beams, columns, slabs, etc by Sapphire or Sapphire s vendors. If any core cutting is required, same to be done by respective LL mall management. As per case, if core cutting is to be reimbursed, Sapphire or Sapphire s vendors will reimburse the LL mall management as per project managers corresspondence with LL Mall management. | Note No holes to be made in any beams, columns, slabs, etc by Sapphire or Sapphire s vendors. If any core cutting is required, same to be done by respective LL mall management. As per case, if core cutting is to be reimbursed, Sapphire or Sapphire s vendors will reimburse the LL mall management as per project managers corresspondence with LL Mall management.
18 | 7 | GRANITE WORKS | GRANITE WORKS
19 | 7.01 | GRANITE PARTITION DOUBLE THICKNESS P F 36mm thk Granite Partition by sandwiching two 18mm thk granite (3 -6 height) with Araldite adhesive including cutting, fixing, grinding, half round moulding at the edge polishing complete. Base Rate of granite is Rs. 150 - sq.ft. Product- Jet black granite | GRANITE PARTITION DOUBLE THICKNESS P F 36mm thk Granite Partition by sandwiching two 18mm thk granite (3 -6 height) with Araldite adhesive including cutting, fixing, grinding, half round moulding at the edge polishing complete. Base Rate of granite is Rs. 150 - sq.ft. Product- Jet black granite | Sft | 10.000 | 7,500.00 | 850 | 8500 | 0 | 0
20 | 7.02 | GRANITE FLOORING STAIRCASE P F 18mm thk Granite on flooring laid over a properly prepared bed of cement mortar in line and level. All joints to be hairline, to be cleaned and filled with approved color Laticrete, to the required line level at all heights and leads, as per detailed designs and drawings, including all labour, edge polish, champhering, moulding, material, curing, cleaning. Base Rate of granite is Rs. 150 - sq.ft. Product- Jet black granite | GRANITE FLOORING STAIRCASE P F 18mm thk Granite on flooring laid over a properly prepared bed of cement mortar in line and level. All joints to be hairline, to be cleaned and filled with approved color Laticrete, to the required line level at all heights and leads, as per detailed designs and drawings, including all labour, edge polish, champhering, moulding, material, curing, cleaning. Base Rate of granite is Rs. 150 - sq.ft. Product- Jet black granite | Sft | 12.000 |  | 650 | 7800 | 11.25 | 7312.5
21 | 7.03 | GRANITE THRESHOLD IN FLOORING AND JAMB LINING P F upto 9 wide 18mm Granite threshold on flooring laid over a properly prepared bed of cement mortar in line and level. All joints to be hairline, to be cleaned and filled with approved color Laticrete, to the required line level at all heights and leads, as per detailed designs and drawings, including all labour, edge polish, champhering, moulding, material, curing, cleaning. Base Rate of granite is Rs. 150 - sq.ft. Product- Jet black granite | GRANITE THRESHOLD IN FLOORING AND JAMB LINING P F upto 9 wide 18mm Granite threshold on flooring laid over a properly prepared bed of cement mortar in line and level. All joints to be hairline, to be cleaned and filled with approved color Laticrete, to the required line level at all heights and leads, as per detailed designs and drawings, including all labour, edge polish, champhering, moulding, material, curing, cleaning. Base Rate of granite is Rs. 150 - sq.ft. Product- Jet black granite | Rft | 10.000 |  | 480 | 4800 | 190.5 | 91440
22 | 8 | FLOORING WORKS | FLOORING WORKS
23 | 8.01 | KOTA STONE FLOORING P L Kota stone flooring of size 22 x 22 (25 mm thk) with 40 mm avg thk of cement sand bedding of CM 1 6 neat cement slurry paste with polish KOTA PRE-POLISH KOTA | KOTA STONE FLOORING P L Kota stone flooring of size 22 x 22 (25 mm thk) with 40 mm avg thk of cement sand bedding of CM 1 6 neat cement slurry paste with polish KOTA PRE-POLISH KOTA | Sft | 1100.000 | 231,000.00 | 250 | 275000 | 1129.3 | 282325
24 | 9 | DADO WORKS | DADO WORKS
25 | 9.01 | DADO TILES (8 -0” HT) FOR KFC P L BLACK BEVELED TILES, JOHNSON MAKE (200mmX100mm) Dado TILE with neat cement paste with avg thk of 6mm in proper line, level plumb. Make color will be approved by architect. Base Rate of tile is Rs. 80 - sq.ft. | DADO TILES (8 -0” HT) FOR KFC P L BLACK BEVELED TILES, JOHNSON MAKE (200mmX100mm) Dado TILE with neat cement paste with avg thk of 6mm in proper line, level plumb. Make color will be approved by architect. Base Rate of tile is Rs. 80 - sq.ft. | Sft | 245.000 |  | 290 | 71050 | 283.5872 | 82240.288
26 | 9.02 | DADO TILES (8 -0 HT) P LGLAZE CERAMIC WALL TILE of size 600 x 300 mm on 40 mm thk of cement sand bedding with CM 1 4 (fixing to be done with cement slurry paste) for toilet area. Base Rate of tile is Rs. 60 - sq.ft. NO ACCEPTANCE FOR ANY RATE VARIATION ON BASIC RATE. | DADO TILES (8 -0 HT) P LGLAZE CERAMIC WALL TILE of size 600 x 300 mm on 40 mm thk of cement sand bedding with CM 1 4 (fixing to be done with cement slurry paste) for toilet area. Base Rate of tile is Rs. 60 - sq.ft. NO ACCEPTANCE FOR ANY RATE VARIATION ON BASIC RATE. | Sft | 1550.000 | 325,500.00 | 225 | 348750 | 1710.8364 | 384938.19
27 | 9.03 | WALL TILE BOXES HANDED OVER TO OPERATIONS Handing over sealed boxes of wall tiles to maintenance operations team on completion of the project at time of handover- to be preserved used by maintenance operations team for any future repair work at same outlet | WALL TILE BOXES HANDED OVER TO OPERATIONS Handing over sealed boxes of wall tiles to maintenance operations team on completion of the project at time of handover- to be preserved used by maintenance operations team for any future repair work at same outlet
28 |  | GREY TILE - GLOSSY- Johnson - maximum one box WILL BE PAID ADDITIONAL BASIS ON SUPPORTING | GREY TILE - GLOSSY- Johnson - maximum one box WILL BE PAID ADDITIONAL BASIS ON SUPPORTING | Box | 2.000 |  | 1250 | 2500 | 0 | 0
29 |  | Toronto Blanco- maximum two boxes WILL BE PAID ADDITIONAL BASIS ON SUPPORTING | Toronto Blanco- maximum two boxes WILL BE PAID ADDITIONAL BASIS ON SUPPORTING | Box | 2.000 |  | 1250 | 2500 | 0 | 0
30 | 10 | SKIRTING WORKS | SKIRTING WORKS
31 | 10.01 | KOTA SKIRTING P F upto 100 mm high kota tile STONE skirting | KOTA SKIRTING P F upto 100 mm high kota tile STONE skirting | Rft | 240.000 | 30,000.00 | 140 | 33600 | 265 | 37100
32 | 10.02 | SS 304 GRADE SKIRTING P F upto 100 mm high tile skirting | SS 304 GRADE SKIRTING P F upto 100 mm high tile skirting | Rft | 100.000 | 11,000.00 | 195 | 19500 | 114.75 | 22376.25
33 | 11 | PARTITIONS AND PANELINGS | PARTITIONS AND PANELINGS
34 | 11.01 | 8 MM PLYWOOD PANELING BOXING P F 8mm 12mm plywood as paneling as per following specs incl of all hardware, labour; in perfect line and plumb, incl of grooves as desired or specified in drawing, complete in all respects. Frame sections of upto 2 x 1.5 size can be of seasoned termite- treated Sal wood, or aluminium sections of same size. | 8 MM PLYWOOD PANELING BOXING P F 8mm 12mm plywood as paneling as per following specs incl of all hardware, labour; in perfect line and plumb, incl of grooves as desired or specified in drawing, complete in all respects. Frame sections of upto 2 x 1.5 size can be of seasoned termite- treated Sal wood, or aluminium sections of same size.
35 |  | P F 8mm plywood plain paneling without frame or laminate | P F 8mm plywood plain paneling without frame or laminate | Sft | 295.000 | 53,100.00 | 205 | 60475 | 455.5 | 93377.5
36 |  | P F 8mm plywood plain paneling with frame or without laminate | P F 8mm plywood plain paneling with frame or without laminate | Sft | 20.000 | 4,900.00 | 320 | 6400 | 844.93 | 270377.6
37 |  | P F 12mm plywood plain paneling with frame, with laminate | P F 12mm plywood plain paneling with frame, with laminate | Sft | 15.000 | 5,400.00 | 450 | 6750 | 0 | 0
38 |  | P F 12mm plywood plain paneling with frame, without laminate | P F 12mm plywood plain paneling with frame, without laminate | Sft | 35.000 | 8,575.00 | 395 | 13825 | 35.0625 | 13849.6875
39 | 11.02 | 12MM BISON BOARD PANELING BOXING P F 12mm bison panel as paneling as per following specs incl of all hardware, labour; in perfect line and plumb, incl of grooves as desired or specified in drawing, complete in all respects. | 12MM BISON BOARD PANELING BOXING P F 12mm bison panel as paneling as per following specs incl of all hardware, labour; in perfect line and plumb, incl of grooves as desired or specified in drawing, complete in all respects.
40 |  | P F 12mm Bison panel paneling with MS frame of upto 1.25 x 1.25 pipe sections | P F 12mm Bison panel paneling with MS frame of upto 1.25 x 1.25 pipe sections | Sft | 280.000 | 64,400.00 | 430 | 120400 | 0 | 0
41 | 11.03 | 12MM SHERA BOARD PANELING BOXING P F 12MM shear board as paneling as per following specs incl of all hardware, labour; in perfect line and plumb, incl of grooves as desired or specified in drawing, complete in all respects. Inclusive of polish paint- Asian Paints cement primer followed by two coats of Apex Ultima of approved shade followed by top coat of Asian Reemers. | 12MM SHERA BOARD PANELING BOXING P F 12MM shear board as paneling as per following specs incl of all hardware, labour; in perfect line and plumb, incl of grooves as desired or specified in drawing, complete in all respects. Inclusive of polish paint- Asian Paints cement primer followed by two coats of Apex Ultima of approved shade followed by top coat of Asian Reemers.
42 |  | P F 12MM Shera board paneling without frame on existing surface | P F 12MM Shera board paneling without frame on existing surface | Sft | 335.000 |  | 350 | 117250 | 331.9975 | 116199.125
43 | 11.04 | SUSPENDED PANELING FOR DMB P F plywood partition made as per detailed drawing with MS frame work of 50 x 50 sections and MS base plate supported from upper slab to support DMB structure. M.S. FRAMEWORK COVERED WITH M S SHEET TO BE FINISHED WITH BLACK PAINT . Rate is inclusive of all necessary hardware and MS fabrication dropped down from true slab as per drawing. Only front of MS sheet finish area to be considered for measurements, rear and edges not to be measured | SUSPENDED PANELING FOR DMB P F plywood partition made as per detailed drawing with MS frame work of 50 x 50 sections and MS base plate supported from upper slab to support DMB structure. M.S. FRAMEWORK COVERED WITH M S SHEET TO BE FINISHED WITH BLACK PAINT . Rate is inclusive of all necessary hardware and MS fabrication dropped down from true slab as per drawing. Only front of MS sheet finish area to be considered for measurements, rear and edges not to be measured | Sft | 25.000 | 10,750.00 | 475 | 11875 | 31.25 | 14843.75
44 | 11.05 | GYPSUM PANELING P F 12.5mm thick gypsum board as seamless paneling in complete plumb, line and level, with tapered joints finished with tape and gypsum | GYPSUM PANELING P F 12.5mm thick gypsum board as seamless paneling in complete plumb, line and level, with tapered joints finished with tape and gypsum
45 |  | P F gypsum board as paneling without any framework on existing surface | P F gypsum board as paneling without any framework on existing surface | Sft | 35.000 |  | 120 | 4200 | 0 | 0
46 | 11.06 | FULL LOW HEIGHT PARTITION P F Partition made on aluminium sal wood frame of 2 x 1.5 sections fixed at 600 x 600, properly clamped to walls, ceiling and floor. Rate is inclusive all necessary hardware, labour, etc. | FULL LOW HEIGHT PARTITION P F Partition made on aluminium sal wood frame of 2 x 1.5 sections fixed at 600 x 600, properly clamped to walls, ceiling and floor. Rate is inclusive all necessary hardware, labour, etc.
47 |  | P F 12mm plywood on both sides of frame mentioned above with laminate | P F 12mm plywood on both sides of frame mentioned above with laminate | Sft | 50.000 | 22,500.00 | 550 | 27500 | 50.625 | 27843.75
48 |  | P F 12mm bison panel on both sides of frame mentioned above | P F 12mm bison panel on both sides of frame mentioned above | Sft | 15.000 | 3,450.00 | 450 | 6750 | 25 | 11250
49 | 11.07 | BACK PAINTED GLASS P F fixed 12mm back painted glass with all edges crystal edge polished | BACK PAINTED GLASS P F fixed 12mm back painted glass with all edges crystal edge polished | Sft | 175.000 | 131,250.00 | 750 | 131250 | 284.0425 | 213031.875
50 | 12 | COUNTERS AND STORAGES | COUNTERS AND STORAGES
51 | 12.01 | OVERHEAD CABINETS STORAGE CABINETS P F Overhead Cabinet storage cabinet Takeaway counter made out of 19mm marine ply for sides, top, bottom, shelves and shutters. Back of cabinet to be made out of 6mm marine ply. All external surfaces to be finished with approved laminate of 1.0mm thickness. All internal surfaces to be finished in balancing laminate of 0.8mm thickness. All edges of ply to be finished with beading patti finished in paint polish. Costs to include for all hardware and fittings like handles, locks, powder coated M.S wire managers, sliding channels, lipping, nylon bushing for legs, making grooves etc complete as per drawing and details. Open area for data rack shelves (if open area is part of one single complete overhead storage structure will be measured in same heading) | OVERHEAD CABINETS STORAGE CABINETS P F Overhead Cabinet storage cabinet Takeaway counter made out of 19mm marine ply for sides, top, bottom, shelves and shutters. Back of cabinet to be made out of 6mm marine ply. All external surfaces to be finished with approved laminate of 1.0mm thickness. All internal surfaces to be finished in balancing laminate of 0.8mm thickness. All edges of ply to be finished with beading patti finished in paint polish. Costs to include for all hardware and fittings like handles, locks, powder coated M.S wire managers, sliding channels, lipping, nylon bushing for legs, making grooves etc complete as per drawing and details. Open area for data rack shelves (if open area is part of one single complete overhead storage structure will be measured in same heading)
52 |  | Upto 18 depth (extra will not be paid if storage depth is 18 + shutters thickness) | Upto 18 depth (extra will not be paid if storage depth is 18 + shutters thickness) | Sft | 60.000 |  | 2450 | 147000 | 65.9178 | 161498.61
53 | 12.02 | DISPENSING COUNTER (KFC) P F dispensing counter (ORDER PICKUP) made out of 19mm thk. Marine Ply finished with 1mm THK. laminate FOR ALL INTERNAL SURFACES with provision OF NICHE for KDS (as per detail dwg). complete with TELESCOPIC drawer channels, VERTICAL PARTITIONS SHELVES with neccessary hardware , raceways, SS BASKETS 304 GRADE wire manager,below the counter top to route the electrical wiring for POS machine. All CUTOUTS, hardwares and fixtures to be included in rate. Mode of measurement will be from BOH elevation height. 30 depth, 30 height. Rate to be inclusive of ledge finished in plywood. Rate is INclusive OF Solid Surface (10MM Corian FOR FRONT FACIA TOP front) | DISPENSING COUNTER (KFC) P F dispensing counter (ORDER PICKUP) made out of 19mm thk. Marine Ply finished with 1mm THK. laminate FOR ALL INTERNAL SURFACES with provision OF NICHE for KDS (as per detail dwg). complete with TELESCOPIC drawer channels, VERTICAL PARTITIONS SHELVES with neccessary hardware , raceways, SS BASKETS 304 GRADE wire manager,below the counter top to route the electrical wiring for POS machine. All CUTOUTS, hardwares and fixtures to be included in rate. Mode of measurement will be from BOH elevation height. 30 depth, 30 height. Rate to be inclusive of ledge finished in plywood. Rate is INclusive OF Solid Surface (10MM Corian FOR FRONT FACIA TOP front) | Sft | 50.000 | 210,000.00 | 4400 | 220000 | 47.8125 | 210375
54 | 13 | MISCELLANEOUS CARPENTRY | MISCELLANEOUS CARPENTRY
55 | 13.01 | SOFT BOARD P F 12mm thk. Soft board fixed onto to existing surface finished approved colour fabric as per detailed drawing. Backing plywood if required to be billed in paneling heading above. | SOFT BOARD P F 12mm thk. Soft board fixed onto to existing surface finished approved colour fabric as per detailed drawing. Backing plywood if required to be billed in paneling heading above. | Sft | 10.000 |  | 350 | 3500 | 0 | 0
56 | 13.02 | WORK TOP MANAGER DESK P F work top manager desk Top and verticals to be made in 19mm granite fixed on marble surface with vertical supports as per design detail, inclusive of cutout for wire manager. | WORK TOP MANAGER DESK P F work top manager desk Top and verticals to be made in 19mm granite fixed on marble surface with vertical supports as per design detail, inclusive of cutout for wire manager. | Rft | 7.000 |  | 6125 | 42875 | 6.58 | 40302.5
57 | 13.03 | KEYBOARD TRAY P F PVC Keyboard tray without mouse of earl bihari (ebco) make, with drawer channel | KEYBOARD TRAY P F PVC Keyboard tray without mouse of earl bihari (ebco) make, with drawer channel | Nos | 2.000 | 3,000.00 | 1650 | 3300 | 0 | 0
58 | 13.04 | CPU TROLLEY P F metal CPU trolley of earl bihari make | CPU TROLLEY P F metal CPU trolley of earl bihari make | Nos | 1.000 | 1,450.00 | 2550 | 2550 | 0 | 0
59 | 13.05 | PELMET Providing and Fixing of 6 high Pelmet Above Manager Table made out of 19mm thk. Ply, covered with approved laminate of 1.0mm thickness, as per detail Drawing | PELMET Providing and Fixing of 6 high Pelmet Above Manager Table made out of 19mm thk. Ply, covered with approved laminate of 1.0mm thickness, as per detail Drawing | Rft | 7.000 |  | 350 | 2450 | 6.58 | 2303
60 | 13.06 | TRAP DOOR OPENABLE P F Trap door made of 19mm marine ply finished with approved laminate of 1.0mm thickness with all necessary frame work in salwood hardware fittings complete as per the detailed drawing instruction | TRAP DOOR OPENABLE P F Trap door made of 19mm marine ply finished with approved laminate of 1.0mm thickness with all necessary frame work in salwood hardware fittings complete as per the detailed drawing instruction | Sft | 25.000 | 20,000.00 | 1050 | 26250 | 0 | 0
61 | 13.07 | TRAP DOOR MOVEABLE P F moveable trapdoor Fixing frame of 2 x 2 1.5 x 1.5 Aluminium angles along perimeter of trapdoor with intermediate 1.5 tee sections at every 24 to house 8mm pre-laminated particle board as trapdoor for air-conditioning ahu units. Each pre-laminated particle board panel size not to exceed 24 x 24 , to be housed on all 4 sides by aluminium sections. Each panel to be removable. Refer detail drawings. | TRAP DOOR MOVEABLE P F moveable trapdoor Fixing frame of 2 x 2 1.5 x 1.5 Aluminium angles along perimeter of trapdoor with intermediate 1.5 tee sections at every 24 to house 8mm pre-laminated particle board as trapdoor for air-conditioning ahu units. Each pre-laminated particle board panel size not to exceed 24 x 24 , to be housed on all 4 sides by aluminium sections. Each panel to be removable. Refer detail drawings. | Sft | 35.000 | 35,000.00 | 1050 | 36750 | 0 | 0
62 | 13.08 | KEY HIVE BOX P F Key Box with provision for mounting 50 keys. Space should be available for labeling each hook. | KEY HIVE BOX P F Key Box with provision for mounting 50 keys. Space should be available for labeling each hook.
63 |  | P F ready made Key Box in PVC powder coated MS. | P F ready made Key Box in PVC powder coated MS. | Nos | 1.000 |  | 7500 | 7500 | 0 | 0
64 | 14 | DOORS DOOR FRAMES (FRD) | DOORS DOOR FRAMES (FRD)
65 | 14.01 | VISION PANEL DOOR (FRD) P F Door with Vision Panel (35 mm thk ) Wooden Jambs finished with 1mm laminate on both side with 6 wide S.S Laminate band as per design 60 x 12 Vision Panel at eye level complete as per drawing. Rate is inclusive of all necessary hardware (I.e. S.S.Handle, Hinges, Lock, Floor Spring, Door Closer, Latch or Tower Bolt, Door Stopper, PVC Buffer, 6mm Clear Glass, Frosted Film, etc | VISION PANEL DOOR (FRD) P F Door with Vision Panel (35 mm thk ) Wooden Jambs finished with 1mm laminate on both side with 6 wide S.S Laminate band as per design 60 x 12 Vision Panel at eye level complete as per drawing. Rate is inclusive of all necessary hardware (I.e. S.S.Handle, Hinges, Lock, Floor Spring, Door Closer, Latch or Tower Bolt, Door Stopper, PVC Buffer, 6mm Clear Glass, Frosted Film, etc
66 |  | MANAGER ROOM DOOR Size of door upto 840 x 2150mm | MANAGER ROOM DOOR Size of door upto 840 x 2150mm | Nos | 1.000 | 3,800.00 | 36283 | 36283 | 1 | 36283
67 |  | DRY STORE ROOM DOOR Size of door upto 900 x 2150mm | DRY STORE ROOM DOOR Size of door upto 900 x 2150mm | Nos | 1.000 | 3,800.00 | 36283 | 36283 | 1 | 36283
68 | 14.02 | SOLID DOOR (FRD) Providing making Door with (35 mm thk marine ) Wooden Jambs finished with 1mm laminate on both as per drawing. Rate is inclusive of all necessary hardware (I.e. S.S.Handle, Lock, Floor Spring, Door Closer, Latch or Tower Bolt, Door Stopper, PVC Buffer, Frosted Film, etc | SOLID DOOR (FRD) Providing making Door with (35 mm thk marine ) Wooden Jambs finished with 1mm laminate on both as per drawing. Rate is inclusive of all necessary hardware (I.e. S.S.Handle, Lock, Floor Spring, Door Closer, Latch or Tower Bolt, Door Stopper, PVC Buffer, Frosted Film, etc
69 |  | SHAFT DOOR Size of door upto 750 x 2150 MM (RATE IS INCLUSIVE OF 2 PANELS HARWARES) | SHAFT DOOR Size of door upto 750 x 2150 MM (RATE IS INCLUSIVE OF 2 PANELS HARWARES) | Nos | 1.000 |  | 30236 | 30236 | 0 | 0
70 |  | SERVICE DOOR Size of door upto 988 x 2150 MM | SERVICE DOOR Size of door upto 988 x 2150 MM | Nos | 1.000 | 32,000.00 | 40327 | 40327 | 1 | 40327
71 | 14.03 | ALUMINUM LOUVERS SHUTTER | ALUMINUM LOUVERS SHUTTER | Sft | 220.000 | 143,000.00 | 1250 | 275000 | 113.39 | 141737.5
72 | 15 | SS WORKS | SS WORKS
73 | 15.01 | SS EDGE PROFILE P F of Stainless steel section edge profile protectors of size 19mm x 19mm x 1.5mm thick to protect all corners of the walls columns in kitchen | SS EDGE PROFILE P F of Stainless steel section edge profile protectors of size 19mm x 19mm x 1.5mm thick to protect all corners of the walls columns in kitchen | Rft | 165.000 |  | 375 | 61875 | 184 | 69000
74 | 15.02 | SS KICK PLATE P F S.S. Kick plate on door as directed same rate for all width, LENGTH, HEIGHT doors | SS KICK PLATE P F S.S. Kick plate on door as directed same rate for all width, LENGTH, HEIGHT doors | Nos | 6.000 | 8,400.00 | 2350 | 14100 | 0 | 0
75 | 16 | MS WORKS (UNIT WEIGHT MUST BE AS PER IS CODE) | MS WORKS (UNIT WEIGHT MUST BE AS PER IS CODE)
76 | 16.01 | MS STRUCTURES FOR RO, DG, WATER TANKS, ETC P F of in M.S Frame work in sections of various sizes as required and MS chequered plate with MS supports beams sections at regular intervals as per detail drawings with necessary base plate and supports from walls and slab complete as per design detail finished with approved paint. For base structure in MS for RO, DG, water tanks, etc. Detailed breakup of the weight of each section to be provided | MS STRUCTURES FOR RO, DG, WATER TANKS, ETC P F of in M.S Frame work in sections of various sizes as required and MS chequered plate with MS supports beams sections at regular intervals as per detail drawings with necessary base plate and supports from walls and slab complete as per design detail finished with approved paint. For base structure in MS for RO, DG, water tanks, etc. Detailed breakup of the weight of each section to be provided | kg | 1000.000 | 210,000.00 | 240 | 240000 | 650 | 156000
77 | 17 | POP FALSE CEILING WORK | POP FALSE CEILING WORK
78 | 17.01 | GYPSUM CEILING P F seamless Gypsum ceiling with gyp board of 12.5mm fixed to the under side of the suspended grid formed of GI perimeter channel of size 20x27x30mm fixed along the wall by using wood screws metal expansion raw plugs. The GI intermediate channel of size 45x15x0.90mm shall be fixed to the suspended strap hanger GI ceiling angle at intervals not more than 1220mm.The suspended GI ceiling angle strap hanger is to be connected with G.I soffit cleat of size 37x27x25 1.6mm it should be fixed on the roof slab beam by using metal expansion fasteners of 12.5mm dia. to the length of 35mm with screw at top ends, including all drops, coves etc and taping finishing. | GYPSUM CEILING P F seamless Gypsum ceiling with gyp board of 12.5mm fixed to the under side of the suspended grid formed of GI perimeter channel of size 20x27x30mm fixed along the wall by using wood screws metal expansion raw plugs. The GI intermediate channel of size 45x15x0.90mm shall be fixed to the suspended strap hanger GI ceiling angle at intervals not more than 1220mm.The suspended GI ceiling angle strap hanger is to be connected with G.I soffit cleat of size 37x27x25 1.6mm it should be fixed on the roof slab beam by using metal expansion fasteners of 12.5mm dia. to the length of 35mm with screw at top ends, including all drops, coves etc and taping finishing. | Sft | 300.000 |  | 155 | 46500 | 323.4986 | 50142.283
79 | 17.02 | CUTOUTS FOR LIGHTS Making cutouts for lights. Only to be paid for renovation sites as per project managers approval. | CUTOUTS FOR LIGHTS Making cutouts for lights. Only to be paid for renovation sites as per project managers approval. | Nos | 24.000 |  | 150 | 3600 | 49 | 7350
80 | 17.03 | LAY IN METAL GRID CEILING P F Modular Grid (RH-95 plain tegular edge-Armstrong) G.I. PLANE 1 2 thk , 2 x 2 panels with silhoutte grid as per approved sample in dining area as per manufacturer s specification. inclusive of original Armstrong Frame work. | LAY IN METAL GRID CEILING P F Modular Grid (RH-95 plain tegular edge-Armstrong) G.I. PLANE 1 2 thk , 2 x 2 panels with silhoutte grid as per approved sample in dining area as per manufacturer s specification. inclusive of original Armstrong Frame work. | Sft | 470.000 | 97,760.00 | 225 | 105750 | 545.58 | 122755.5
81 | 17.04 | PVC FLOORING PROTECTOR P F PVC flooring protector on floor of 4mm thk to protect floor tiles to damage during the period of execution | PVC FLOORING PROTECTOR P F PVC flooring protector on floor of 4mm thk to protect floor tiles to damage during the period of execution | Sft | 880.000 |  | 25 | 22000 | 2151.5625 | 53789.0625
82 | 18 | PAINTING POLISHING WORKS | PAINTING POLISHING WORKS
83 | 18.01 | LUSTER PAINT P A 3 coats of Luster paint of approved quality shade by sand papering the surface, applying one coat of primer, prepare the surface with two coats of full putty, sand papering again, repeating a coat of primer, applying one coat of luster paint, touching up with putty applying two final roller coats of luster paint, to internal wall ceilings masonry concrete surfaces incl. preparing the surface by cleaning scrapping, smooth filling crevices, scaffolding etc. Paint codes to be as shown in drawing. | LUSTER PAINT P A 3 coats of Luster paint of approved quality shade by sand papering the surface, applying one coat of primer, prepare the surface with two coats of full putty, sand papering again, repeating a coat of primer, applying one coat of luster paint, touching up with putty applying two final roller coats of luster paint, to internal wall ceilings masonry concrete surfaces incl. preparing the surface by cleaning scrapping, smooth filling crevices, scaffolding etc. Paint codes to be as shown in drawing. | Sft | 1000.000 | 65,000.00 | 65.00 | 65000 | 962.4536 | 62559.484
84 | 18.02 | DUCO PAINT P A Duco paint (non metallic) approved shade on base coating of water cutting putty sand papered smooth leveled surface with spray | DUCO PAINT P A Duco paint (non metallic) approved shade on base coating of water cutting putty sand papered smooth leveled surface with spray | Sft | 260.000 | 66,300.00 | 292 | 75920 | 0 | 0
85 | 19 | MISCELLANEOUS ITEMS | MISCELLANEOUS ITEMS
86 | 19.01 | HOOD ERECTION Hood Erection (to be paid in KFC ONLY NON-VEG HOOD), VEG HOOD NOT TO BE PAID, AS IT IS FLOOR MOUNTED | HOOD ERECTION Hood Erection (to be paid in KFC ONLY NON-VEG HOOD), VEG HOOD NOT TO BE PAID, AS IT IS FLOOR MOUNTED | Nos | 1.000 |  |  | 0 | 0
87 | 19.02 | HOUSEKEEPING Keeping site clean during works, deep cleaning before handing over the project. | HOUSEKEEPING Keeping site clean during works, deep cleaning before handing over the project. | Job | 1.000 |  | 15000 | 15000 | 1 | 15000
88 | 19.03 | FIXING OF WHITE GOODS Fixing of white goods for BOH AND FOH AREA like Pestoflash, TVs, DMB, KDS, LCMS, Aircurtains, shelves, hooks, maps, internal signages, PVC buffers, Fire extinguishers, Carpentry works like wire manager holes, hand towel dispenser etc. | FIXING OF WHITE GOODS Fixing of white goods for BOH AND FOH AREA like Pestoflash, TVs, DMB, KDS, LCMS, Aircurtains, shelves, hooks, maps, internal signages, PVC buffers, Fire extinguishers, Carpentry works like wire manager holes, hand towel dispenser etc. | Job | 1.000 |  | 10000 | 10000 | 1 | 10000
89 | 19.04 | ALUMINIUM LADDER P A Aluminium ladder 8 | ALUMINIUM LADDER P A Aluminium ladder 8 | Nos | 1.000 | 8,500.00 | 15500 | 15500 | 0 | 0
90 | 19.05 | COAT HOOK | COAT HOOK
91 |  | P F coat hook in wash rooms and changing rooms behind door, Jaquar make Continental Series ACN-CHR-1161N | P F coat hook in wash rooms and changing rooms behind door, Jaquar make Continental Series ACN-CHR-1161N | Nos | 4.000 | 4,800.00 | 1200.00 | 4800 | 0 | 0
92 | 19.06 | TEMPORARY FLEX P F of Temporary flex work printed with art work as specified during project to segregate renovation area as per site requirement. Cost to include temporary door with hinges and locking provision with lock. | TEMPORARY FLEX P F of Temporary flex work printed with art work as specified during project to segregate renovation area as per site requirement. Cost to include temporary door with hinges and locking provision with lock.
93 |  | P F temporary flex as per details above with backing frame of wood MS Aluminium sections as required. | P F temporary flex as per details above with backing frame of wood MS Aluminium sections as required. | Sft | 1100.000 | 126,500.00 | 0 | 0 | 1200
94 | 19.07 | LOCKS P F pad locks for RO plant cage, tank, etc. of Godrej make | LOCKS P F pad locks for RO plant cage, tank, etc. of Godrej make | Nos | 1.000 |  | 850 | 850 | 0 | 0
95 | 19.08 | SCAFFOLDING P E of scaffolding in bamboo MS as per site condition. To be paid only in extreme cases with prior approval from Project manager. Cost to be paid based on 15 days intervel WITH SUPPORTING | SCAFFOLDING P E of scaffolding in bamboo MS as per site condition. To be paid only in extreme cases with prior approval from Project manager. Cost to be paid based on 15 days intervel WITH SUPPORTING | Sft | 2500.000 |  | 35 | 87500 | 960 | 33600
96 | 19.09 | FIRST AID BOX Providing readymade first aid box on completion of the site | FIRST AID BOX Providing readymade first aid box on completion of the site | Nos | 1.000 | 1,800.00 | 3500 | 3500 | 0 | 0
97 | 19.1 | GODREJ NIGHT LATCH P F Additional lock on service door Night Latch of Godrej Make- double turn. To be fixed over and above the existing dead tubular lock as mentioned in the door details. | GODREJ NIGHT LATCH P F Additional lock on service door Night Latch of Godrej Make- double turn. To be fixed over and above the existing dead tubular lock as mentioned in the door details. | Nos | 1.000 |  | 2250 | 2250 | 0 | 0
98 | 19.11 | FIRE BLANKET | FIRE BLANKET | Nos | 1.000 |  | 8500 | 8500 | 0 | 0
99 | 19.12 | MAINTENANCE REQUIREMENT WORKS - AMOUNT PAID TO STORE MAINTENANCE Actual bill need to be produced TO BE PAID ON CONFIRMATION OF PM | MAINTENANCE REQUIREMENT WORKS - AMOUNT PAID TO STORE MAINTENANCE Actual bill need to be produced TO BE PAID ON CONFIRMATION OF PM | Nos | 1.000 |  |  | 0 | 0
100 | 19.13 | LOADING UNLOADING - Manual shifting till location as per design (Second floor) 1. RO plant till location | LOADING UNLOADING - Manual shifting till location as per design (Second floor) 1. RO plant till location | Nos | 1.000 |  |  | 0 | 1
101 |  | 2. Fresh air Exhaust units AC units AHU units till location | 2. Fresh air Exhaust units AC units AHU units till location
102 |  | 3. Electrical panel till location | 3. Electrical panel till location
103 |  | 4. UPS with battery till location | 4. UPS with battery till location
104 |  | 5. Coldroom Dry store racks till location | 5. Coldroom Dry store racks till location
105 |  | 6. Stabilizer till location | 6. Stabilizer till location
106 |  | 7. SS Dead Equipment till location (Handwash sink, 3bowl sink, hoods, tables, shelves, etc) pepsi machine | 7. SS Dead Equipment till location (Handwash sink, 3bowl sink, hoods, tables, shelves, etc) pepsi machine
107 |  | 8. IT material till location | 8. IT material till location
108 |  | 9. Misc - weighing Scale CCTV Pesto Flash Fire-Extinguisher Music System Gas-Detection System Fire-Suppression System Air-Curtains | 9. Misc - weighing Scale CCTV Pesto Flash Fire-Extinguisher Music System Gas-Detection System Fire-Suppression System Air-Curtains
109 |  | 10. All furnitures till location | 10. All furnitures till location
110 | 19.14 | DEBRIS REMOVAL FROM STORE PREMISES (UP TO 4 VEHICLES) Except Civil vendor debris (Cold room, HVAC, Kitchen Equipment, Signages, Etc) | DEBRIS REMOVAL FROM STORE PREMISES (UP TO 4 VEHICLES) Except Civil vendor debris (Cold room, HVAC, Kitchen Equipment, Signages, Etc) | L S | 1.000 |  | 18500 | 18500 | 1 | 18500
111 | 19.15 | MATHADI LABOUR UNION Actuall bill to be produced, ONLY TO BE PAID ON CONFIRMATION OF PM (no margin to be paid additional) | MATHADI LABOUR UNION Actuall bill to be produced, ONLY TO BE PAID ON CONFIRMATION OF PM (no margin to be paid additional) | L S | 1.000 | .00 | 0.00 | 0
112 | 19.16 | Installation of amplifier Installation of amplifier 120W for music system suitable to operate on 230V AC 12V DC, with low impedance microphone input two auxiliary inputs, tone control, protection circuit complete for the speakers output 4 8 16 lines | Installation of amplifier Installation of amplifier 120W for music system suitable to operate on 230V AC 12V DC, with low impedance microphone input two auxiliary inputs, tone control, protection circuit complete for the speakers output 4 8 16 lines | L S | 1.000 |  |  | 0
2 |  | Plumbing Work | Plumbing Work | NOS | 1.000 |  |  | 790080 |  | 659585
113 | A | WATER SUPPLY PIPES | WATER SUPPLY PIPES
114 | 1.00 | Supply, laying, testing commissioning of FOOD GRADE CPVC pipes conforming to CTS (Copper Tube Size) SDR-11 as per (is 15778 ASTM D 2846) with necessary fittings up to the size of 50 mm dia, jointing with CPVC solvent cement of medium body IPS brand or equivalent conform. | Supply, laying, testing commissioning of FOOD GRADE CPVC pipes conforming to CTS (Copper Tube Size) SDR-11 as per (is 15778 ASTM D 2846) with necessary fittings up to the size of 50 mm dia, jointing with CPVC solvent cement of medium body IPS brand or equivalent conform.
115 | a | 15mm dia | 15mm dia | Rmt | 0.000 | .00 | 0.00 | .00
116 | b | 20mm dia | 20mm dia | Rmt | 68.000 |  | 745 | 50660 | 73.5 | 54757.5
117 | c | 25mm dia | 25mm dia | Rmt | 27.000 |  | 860 | 23220 | 46 | 39560
118 | d | 32mm dia | 32mm dia | Rmt | 25.000 |  | 940 | 23500 | 9.25 | 8695
119 | e | 40mm dia | 40mm dia | Rmt | 0.000 | .00 | 0.00 | .00
120 | 2.00 | Supply, laying, testing commissioning of CPVC - Schedule 80 (ASTM F 441) Pipes and fittings suitable for Domestic hot water application (max. temp.85 Deg.C) rated for a working pressure of 5 kg cm2 and conforming to latest Indian International Standards. WITH Supply Covering (Thermal Insulation) hot water pipes with 6 mm thick performed closed cell nitrite rubber pipe section insulation having density not less than 60 kg cm2 and K valve not more than 0.034 w m Deg. K @ 20 Deg C mean temperature. | Supply, laying, testing commissioning of CPVC - Schedule 80 (ASTM F 441) Pipes and fittings suitable for Domestic hot water application (max. temp.85 Deg.C) rated for a working pressure of 5 kg cm2 and conforming to latest Indian International Standards. WITH Supply Covering (Thermal Insulation) hot water pipes with 6 mm thick performed closed cell nitrite rubber pipe section insulation having density not less than 60 kg cm2 and K valve not more than 0.034 w m Deg. K @ 20 Deg C mean temperature.
121 | a | 15mm dia | 15mm dia | Rmt | 0.000 | .00 | 0.00 | .00
122 | b | 20mm dia | 20mm dia | Rmt | 30.000 |  | 745 | 22350 | 34 | 25330
123 | c | 25mm dia | 25mm dia | Rmt | 0.000 | .00 | 0.00 | .00
124 | d | 32mm dia | 32mm dia | Rmt | 0.000 | .00 | 0.00 | .00
125 | e | 40mm dia | 40mm dia | Rmt | 0.000 | .00 | 0.00 | .00
126 | 4.00 | Supply, Installation, Commissioning Testing for Booster Pump WITH FLOW SWITCH GRAVITATIONAL FLOW (top to bottom flow) with both side Sensor operations- A) 3CUM PER HR. B) HEAD 25M, C) PHASE SINGLE PHASE, D) PROTECTION IP55, E) MONOBLOCK TYPE | Supply, Installation, Commissioning Testing for Booster Pump WITH FLOW SWITCH GRAVITATIONAL FLOW (top to bottom flow) with both side Sensor operations- A) 3CUM PER HR. B) HEAD 25M, C) PHASE SINGLE PHASE, D) PROTECTION IP55, E) MONOBLOCK TYPE
127 |  | 0.5 HP | 0.5 HP | Nos. | 2.000 | 29,000.00 | 22000 | 44000 | 2 | 44000
128 |  | 1.0 HP | 1.0 HP | Nos. | 0.000 | .00 | 0.00 | .00
129 |  | 1.5 HP | 1.5 HP | Nos. | 0.000 | .00 | 0.00 | .00
130 | 4.00 | Supply, Installation, Commissioning Testing for HYDROPNEUMATIC Booster Pump WITH FLOW SWITCH with pressure vessel (AGINST GRAVITY bottom to top flow) with both side Sensor operations (60ltr vessel) with both side Sensor operations- A) 3CUM PER HR. B) HEAD 40M, C) PHASE SINGLE PHASE, D) PROTECTION IP55, E) MONOBLOCK TYPE F) WITH VALVE STATION | Supply, Installation, Commissioning Testing for HYDROPNEUMATIC Booster Pump WITH FLOW SWITCH with pressure vessel (AGINST GRAVITY bottom to top flow) with both side Sensor operations (60ltr vessel) with both side Sensor operations- A) 3CUM PER HR. B) HEAD 40M, C) PHASE SINGLE PHASE, D) PROTECTION IP55, E) MONOBLOCK TYPE F) WITH VALVE STATION
131 |  | 1.5HP | 1.5HP | Nos. | 0.000 | .00 | 0.00 | .00
132 | B | WATER DRAIN PIPES | WATER DRAIN PIPES
133 | 1.00 | Supply, Laying , Testing Commissioning of CI (Cast Iron) CLASS Pipes Conforming to IS 3114 1994 and Fittings Conforming to IS 1538 (1993), Cutting the Pipes to required Lengths, Laying in position to required Grade Level , Jointing , Making holes , Pockets , chases in. | Supply, Laying , Testing Commissioning of CI (Cast Iron) CLASS Pipes Conforming to IS 3114 1994 and Fittings Conforming to IS 1538 (1993), Cutting the Pipes to required Lengths, Laying in position to required Grade Level , Jointing , Making holes , Pockets , chases in.
134 | a | 150mm dia | 150mm dia | Rmt | 0.000 | .00 | 0.00 | .00
135 | b | 100mm dia | 100mm dia | Rmt | 25.000 |  | 1450.00 | 36250 | 23.5 | 34075
136 | c | 75mm dia | 75mm dia | Rmt | 18.000 |  | 1250.00 | 22500 | 15.75 | 19687.5
137 | 2.00 | PVC Plastic Pipe , Schedule 40,80,120 ( ASTM D1785 ) | PVC Plastic Pipe , Schedule 40,80,120 ( ASTM D1785 )
138 | a | Drain for ac line | Drain for ac line | Rmt | 0.000 | .00 | 0.00 | .00
139 | b | Company Make - Prince , Finolex | Company Make - Prince , Finolex | Rmt | 0.000 | .00 | 0.00 | .00
140 | c | Company Make - Prince , Finolex | Company Make - Prince , Finolex | Rmt | 0.000 | .00 | 0.00 | .00
141 | d | Company Make - Prince , Finolex | Company Make - Prince , Finolex | Rmt | 0.000 | .00 | 0.00 | .00
142 | e | Company Make - Prince, Finolex (Basement Suspended Pipe) | Company Make - Prince, Finolex (Basement Suspended Pipe) | Rmt | 0.000 | .00 | 0.00 | .00
143 | f | Drainage Exacavation SITC of 150mm (Underground) PVC Waste Pipe Make Prince Finolex | Drainage Exacavation SITC of 150mm (Underground) PVC Waste Pipe Make Prince Finolex | Rmt | 0.000 | .00 | 0.00 | .00
144 | 3.00 | UPVC Plastic Pipe , Schedule 40,80,120 (ASTM D1785 ) | UPVC Plastic Pipe , Schedule 40,80,120 (ASTM D1785 )
145 | a | Company Make - Prince , Finolex | Company Make - Prince , Finolex | Rmt | 0.000 | .00 | 0.00 | .00
146 | b | Company Make - Prince , Finolex | Company Make - Prince , Finolex | Rmt | 0.000 | .00 | 0.00 | .00
147 | c | Company Make - Prince , Finolex | Company Make - Prince , Finolex | Rmt | 0.000 | .00 | 0.00 | .00
148 | d | Company Make - Prince , Finolex | Company Make - Prince , Finolex | Rmt | 0.000 | .00 | 0.00 | .00
149 | C | CHAMBER GRATING | CHAMBER GRATING
150 | 1.00 | Constructing Inspection chamber in 100mm thick Brick Wall, WATER PROOFING with Plaster. TILE EXTRA TO BE PAID | Constructing Inspection chamber in 100mm thick Brick Wall, WATER PROOFING with Plaster. TILE EXTRA TO BE PAID
151 | a | 300mm x 300mm | 300mm x 300mm | Nos. | 0.000 | .00 | 0.00 | .00
152 | b | 450mm x 450mm | 450mm x 450mm | Nos. | 0.000 | .00 | 0.00 | .00
153 | c | 450mm x 900mm (with Excavation, C.I. Cover frame) | 450mm x 900mm (with Excavation, C.I. Cover frame) | Nos. | 0.000 | .00 | 0.00 | .00
154 | 2.00 | Constructing Gully trap in 100mm thick Brick Wall with Plaster wih top cover. | Constructing Gully trap in 100mm thick Brick Wall with Plaster wih top cover.
155 | a | 300mm x 300mm | 300mm x 300mm | Nos. | 0.000 | .00 | 0.00 | .00
156 | 3.00 | Providing Fixing 20mm heavy quality SS Grating along with Perforated Mesh Angle Frame as per Size , Drawings. Weight not more than 60kg. Rate inclusive of chamber construction | Providing Fixing 20mm heavy quality SS Grating along with Perforated Mesh Angle Frame as per Size , Drawings. Weight not more than 60kg. Rate inclusive of chamber construction
157 | 3.01 | 200mm width | 200mm width
158 | a | 900mm X 200mm with SS Perforated Jali. (Grating Set) | 900mm X 200mm with SS Perforated Jali. (Grating Set) | Nos. | 0.000 | .00 | 0.00 | .00
159 | b | 600mm X 200mm with SS Perforated Jali. (Grating Set) | 600mm X 200mm with SS Perforated Jali. (Grating Set) | Nos. | 0.000 | .00 | 0.00 | .00
160 | c | 300mm X 200mm with SS Perforated Jali. (Grating Set) | 300mm X 200mm with SS Perforated Jali. (Grating Set) | Nos. | 0.000 | .00 | 0.00 | .00
161 | d | 200mm X 200mm with SS Perforated Jali. (Grating Set) | 200mm X 200mm with SS Perforated Jali. (Grating Set) | Nos. | 9.000 | 49,500.00 | 9500 | 85500 | 9 | 85500
162 | 3.02 | 300mm width | 300mm width
163 | a | 900mm X 300mm with SS Perforated Jali. (Grating Set) | 900mm X 300mm with SS Perforated Jali. (Grating Set) | Nos. | 0.000 | .00 | 0.00 | .00
164 | b | 600mm X 300mm with SS Perforated Jali. (Grating Set) | 600mm X 300mm with SS Perforated Jali. (Grating Set) | Nos. | 0.000 | .00 | 0.00 | .00
165 | c | 300mm X 300mm with SS Perforated Jali. (Grating Set) | 300mm X 300mm with SS Perforated Jali. (Grating Set) | Nos. | 6.000 |  | 10500 | 63000 | 6 | 63000
166 | d | 200mm X 300mm with SS Perforated Jali. (Grating Set) | 200mm X 300mm with SS Perforated Jali. (Grating Set) | Nos. | 0.000 | .00 | 0.00 | .00
167 | 3.03 | 450mm width | 450mm width
168 | a | 600mm X 450mm with SS Perforated Jali. (Grating Set) | 600mm X 450mm with SS Perforated Jali. (Grating Set) | Nos. | 0.000 | .00 | 0.00 | .00
169 | b | 450mm X 450mm with SS Perforated Jali. (Grating Set) | 450mm X 450mm with SS Perforated Jali. (Grating Set) | Nos. | 1.000 | 8,500.00 | 16500 | 16500 | 1 | 16500
170 | c | 300mm X 450mm with SS Perforated Jali. (Grating Set) | 300mm X 450mm with SS Perforated Jali. (Grating Set) | Nos. | 0.000 | .00 | 0.00 | .00
171 | d | 200mm X 450mm with SS Perforated Jali. (Grating Set) | 200mm X 450mm with SS Perforated Jali. (Grating Set) | Nos. | 0.000 | .00 | 0.00 | .00
172 | 3.04 | 1200mm X 200mm with SS Perforated Jali. (Grating Set) | 1200mm X 200mm with SS Perforated Jali. (Grating Set) | Nos. | 1.000 | 16,500.00 | 23500 | 23500 | 1 | 23500
173 | 4.00 | Providing Fixing 25 x 25 x 3mm thick SS Angle Frame for open drains. As per Size , Drawings. Ready to receive kota. | Providing Fixing 25 x 25 x 3mm thick SS Angle Frame for open drains. As per Size , Drawings. Ready to receive kota.
174 | 4.01 | 560mm X upto 125mm | 560mm X upto 125mm | Nos. | 0.000 | .00 | 0.00 | .00
175 | 4.02 | 560mm X from 130mm upto 200mm | 560mm X from 130mm upto 200mm | Nos. | 0.000 | .00 | 0.00 | .00
176 | 4.03 | 560mm X from 205mm upto 300mm | 560mm X from 205mm upto 300mm | Nos. | 0.000 | .00 | 0.00 | .00
177 | 4.04 | 200mm X 200mm | 200mm X 200mm | Nos. | 0.000 | .00 | 0.00 | .00
178 | 5.00 | Fixing of Portable SS grease trap 3 bowl sink as per drg. | Fixing of Portable SS grease trap 3 bowl sink as per drg. | Nos. | 1.000 |  | 9500 | 9500 | 1 | 9500
179 | 5.01 | Bush for portable grease trap | Bush for portable grease trap | Nos. | 2.000 |  | 4500.00 | 9000 | 2 | 9000
180 | 6.00 | Construction of grease trap with SS cover (2 -6 x 3 -6 x upto 3 -0 deep) - inside the store as per drawing. Rate includes SS angles of 50 x 50 x 6mm as frame; SS cover on frame made by 50 x 50 SS Pipes @ maximum 15 c c, covered with SS Sheet. Inclusive of fabricated SS T sections made as per detailed drawings (3mm thick) for mounting grease trap partitions. Internal tiling plaster to be paid seperately. | Construction of grease trap with SS cover (2 -6 x 3 -6 x upto 3 -0 deep) - inside the store as per drawing. Rate includes SS angles of 50 x 50 x 6mm as frame; SS cover on frame made by 50 x 50 SS Pipes @ maximum 15 c c, covered with SS Sheet. Inclusive of fabricated SS T sections made as per detailed drawings (3mm thick) for mounting grease trap partitions. Internal tiling plaster to be paid seperately. | Nos. | 0.000 | .00 | 0.00 | .00
181 | 7.00 | Construction of grease trap with SS cover (2 -6 x 3 -6 x upto 3 -0 deep) - outside the store as per drawing. Rate includes MS angles of 50 x 50 x 6mm as frame; MS cover on frame made by 50 x 50 MS Pipes @ maximum 15 c c, covered with MS chequered plate. Inclusive of fabricated MS T sections made as per detailed drawings (3mm thick) for mounting grease trap partitions. Internal tiling plaster to be paid seperately. | Construction of grease trap with SS cover (2 -6 x 3 -6 x upto 3 -0 deep) - outside the store as per drawing. Rate includes MS angles of 50 x 50 x 6mm as frame; MS cover on frame made by 50 x 50 MS Pipes @ maximum 15 c c, covered with MS chequered plate. Inclusive of fabricated MS T sections made as per detailed drawings (3mm thick) for mounting grease trap partitions. Internal tiling plaster to be paid seperately. | Nos. | 0.000 | .00 | 0.00 | .00
182 | D | NAHNI TRAP | NAHNI TRAP
183 | 1.00 | Supply, Laying, Testing Commissioning of Approved CI (Cast Iron) CLASS pipes Nahani - Floor Trap with Approved Make leavy Duty round or Square SS Grating etc. Complete. | Supply, Laying, Testing Commissioning of Approved CI (Cast Iron) CLASS pipes Nahani - Floor Trap with Approved Make leavy Duty round or Square SS Grating etc. Complete. | Nos. | 0.000 | .00 | 0.00 | .00
184 | 2.00 | Supply, Laying, Testing Commissioning of Approved SS Nahani TRAP WITH Floor Trap COCKROACH JAALI with Approved Make heavy duty round or Square Grating etc. Complete. | Supply, Laying, Testing Commissioning of Approved SS Nahani TRAP WITH Floor Trap COCKROACH JAALI with Approved Make heavy duty round or Square Grating etc. Complete. | Nos. | 0.000 | .00 | 0.00 | .00
185 | E | CP FIXTURES BRASS VALVES -Jaquar (only continental series) | CP FIXTURES BRASS VALVES -Jaquar (only continental series)
186 | 1.00 | P F Angle Cock. | P F Angle Cock. | Nos. | 20.000 |  | 1850 | 37000 | 18 | 33300
187 | 2.00 | P F Sink Mixer, Swinging Casted Spout. | P F Sink Mixer, Swinging Casted Spout. | Nos. | 4.000 |  | 7500 | 30000 | 2 | 15000
188 | 3.00 | P F Sink Mixer, Swinging Casted Spout. | P F Sink Mixer, Swinging Casted Spout. | Nos. | 3.000 |  | 7500 | 22500 | 1 | 7500
189 | 4.00 | P F Long Neck Bib Cock with wall Flange. Make- Jaquar | P F Long Neck Bib Cock with wall Flange. Make- Jaquar | Nos. | 5.000 |  | 5100 | 25500 | 1 | 5100
190 | 5.00 | Providing Fixing Bib Cock chrome finish with wall Flange. | Providing Fixing Bib Cock chrome finish with wall Flange. | Nos. | 4.000 | 8,800.00 | 2350 | 9400 | 2 | 4700
191 | 6.00 | P F Sink Pillar cock with swinging casted spout. | P F Sink Pillar cock with swinging casted spout. | Nos. | 4.000 | 8,000.00 | 3750 | 15000 | 9 | 33750
192 | 7.00 | P F Fixed Sink Cock. | P F Fixed Sink Cock. | Nos. | 3.000 | 7,200.00 | 3250 | 9750 | 0 | 0
193 | 8.00 | P F Tall Pillar Cock for counter flush basin. | P F Tall Pillar Cock for counter flush basin. | Nos. | 3.000 |  | 3250 | 9750 | 0 | 0
194 | 9.00 | P F Pneumatic push cock. | P F Pneumatic push cock. | Nos. | 1.000 |  | 3550 | 3550 | 0 | 0
195 | 10.00 | Foot Paddle Operated Faucet. (Below Hand Wash) | Foot Paddle Operated Faucet. (Below Hand Wash) | Nos. | 2.000 | 8,400.00 | 10500 | 21000 | 2 | 21000
196 | 11.00 | Dual press | Dual press
197 |  | P F open Flush valve. | P F open Flush valve. | Nos. | 0.000 | .00 | 0.00 | .00
198 |  | P F open Flush tank. | P F open Flush tank. | Nos. | 0.000 | .00 | 0.00 | .00
199 | 12.00 | P F CP Health Faucet with 1m long CP Flexible Tube with wall Hook. Make- Jaquar | P F CP Health Faucet with 1m long CP Flexible Tube with wall Hook. Make- Jaquar | Nos. | 0.000 | .00 | 0.00 | .00
200 | 13.00 | P F 2 in 1 bib cock in washrooms for mounting Health Faucet. Health faucet to be paid for separetly. | P F 2 in 1 bib cock in washrooms for mounting Health Faucet. Health faucet to be paid for separetly. | Nos. | 0.000 | .00 | 0.00 | .00
201 | 14.00 | Providing fixing 32mm CP finished Bottle Trap with wall flanges. | Providing fixing 32mm CP finished Bottle Trap with wall flanges. | Nos. | 10.000 |  | 2150 | 21500 | 0 | 0
202 | 15.00 | Providing Waste Coupling 32mm size full thread waste coupling to be use. | Providing Waste Coupling 32mm size full thread waste coupling to be use. | Nos. | 10.000 |  | 1050 | 10500 | 0 | 0
203 | 16.00 | Providing Fixing Ball Valve ISI mark. (For Inlet) | Providing Fixing Ball Valve ISI mark. (For Inlet)
204 | a | 15mm dia | 15mm dia | Nos. | 0.000 | .00 | 0.00 | .00
205 | b | 20mm dia | 20mm dia | Nos. | 0.000 | .00 | 0.00 | .00
206 | c | 25mm dia | 25mm dia | Nos. | 2.000 |  | 2350 | 4700 | 0 | 0
207 | d | 32mm dia | 32mm dia | Nos. | 2.000 |  | 2750 | 5500 | 4 | 11000
208 | e | 40mm dia | 40mm dia | Nos. | 0.000 | .00 | 0.00 | .00
209 | 16.02 | Providing Fixing Ball Valve ISI mark. (For Inlet) | Providing Fixing Ball Valve ISI mark. (For Inlet)
210 | a | 15mm dia | 15mm dia | Nos. | 0.000 | .00 | 0.00 | .00
211 | b | 20mm dia | 20mm dia | Nos. | 0.000 | .00 | 0.00 | .00
212 | c | 25mm dia | 25mm dia | Nos. | 0.000 | .00 | 0.00 | .00
213 | d | 32mm dia | 32mm dia | Nos. | 0.000 | .00 | 0.00 | .00
214 | e | 40mm dia | 40mm dia | Nos. | 0.000 | .00 | 0.00 | .00
215 | 17.00 | Providing Fixing Brass Non Return Vavles of ISI mark. Rates are for BRASS valves | Providing Fixing Brass Non Return Vavles of ISI mark. Rates are for BRASS valves
216 | a | 25mm | 25mm | Nos | 0.000 | .00 | 0.00 | .00
217 | b | 32mm | 32mm | Nos | 0.000 | .00 | 0.00 | .00
218 | c | 40mm | 40mm | Nos. | 0.000 | .00 | 0.00 | .00
219 | 18.00 | P F ball valve below 3 bowl sink veg pre RO sink - 75mm dia | P F ball valve below 3 bowl sink veg pre RO sink - 75mm dia | Nos. | 5.000 | 21,500.00 | 7750 | 38750 | 3 | 23250
220 | E | ACCESSORIES MISCELLANEOUS | ACCESSORIES MISCELLANEOUS
221 | 1.00 | Providing Flexible water pipe to connect Angle Valve to faucet | Providing Flexible water pipe to connect Angle Valve to faucet | Nos. | 20.000 |  | 660 | 13200 | 18 | 11880
222 | 2.00 | Pre rinse spray valve spray. | Pre rinse spray valve spray. | Nos. | 1.000 |  | 18500 | 18500 | 0 | 0
223 | 3.00 | Providing water level Indicator for In Raw tank RO water tank with gauge Glass Cock. In BOH Area. | Providing water level Indicator for In Raw tank RO water tank with gauge Glass Cock. In BOH Area. | Nos. | 1.000 |  | 0 | 0 | 0
224 | 4.00 | P F water level Indicator on terrace water tank by means of a transparent clear tube fixed along height of the water tank hence making water level visible | P F water level Indicator on terrace water tank by means of a transparent clear tube fixed along height of the water tank hence making water level visible | Nos. | 0.000 | .00 | 0.00 | .00 | 0
225 | 5.00 | P F flexible PVC waste pipe on wash basin sink drains | P F flexible PVC waste pipe on wash basin sink drains | Nos. | 10.000 |  | 450 | 4500 | 0 | 0
226 | 6.00 | Installation of plumbing fixtures kitchen equipment provided by client with new hardware as required- PLUMBING SCOPE | Installation of plumbing fixtures kitchen equipment provided by client with new hardware as required- PLUMBING SCOPE | Job | 1.000 |  | 20500 | 20500 | 1 | 20500
227 | F | BOILERS GEYSERS | BOILERS GEYSERS
228 | 1.00 | Providing Supplying boiler with Mounting Bolts etc. | Providing Supplying boiler with Mounting Bolts etc.
229 | a | 35 Liter | 35 Liter | Nos. | 1.000 |  | 24500 | 24500 | 1 | 24500
230 | b | 25 Liter | 25 Liter | Nos. | 0.000 | .00 | 0.00 | .00
231 | 2.00 | Geyser Storage | Geyser Storage
232 | b | Providing Supplying 6 Liters Geyser with Mounting Bolts etc. | Providing Supplying 6 Liters Geyser with Mounting Bolts etc. | Nos. | 2.000 |  | 7500 | 15000 | 2 | 15000
233 | G | SANITARYWARE | SANITARYWARE
234 | 1.00 | P F Wash Basin as per specs | P F Wash Basin as per specs
235 |  | P F Counter top Basin, Make Size- PARRYWARE as per drawing | P F Counter top Basin, Make Size- PARRYWARE as per drawing | Nos. | 0.000 | .00 | 0.00 | .00
236 |  | P F Under Counter Basin, Make size- PARRYWARE as per drawing | P F Under Counter Basin, Make size- PARRYWARE as per drawing | Nos. | 0.000 | .00 | 0.00 | .00
237 |  | Corner Wash Basin | Corner Wash Basin | Nos. | 0.000 | .00 | 0.00 | .00
238 | 2.0 | P F Wall hung EWC with Seat Cover Make size- PARRYWARE as per drawing | P F Wall hung EWC with Seat Cover Make size- PARRYWARE as per drawing | Nos. | 0.000 | .00 | 0.00 | .00
239 | 3.0 | P F Wall Urinal with brackets. Make size- PARRYWARE as per drawing | P F Wall Urinal with brackets. Make size- PARRYWARE as per drawing | Nos. | 0.000 | .00 | 0.00 | .00
240 | 4.0 | P F pressomatic type flush valve for urinals | P F pressomatic type flush valve for urinals | Nos. | 0.000 | .00 | 0.00 | .00

## Measurement Sheet
Sr No. | Item Code | Item Name | Item Description | UOM | PO Qty | Minimum Amount | Nos. | L | W | Executed Qty
1 |  | Civil work | Civil work | NOS | 1.000
1 | 1 | ANTI TERMITE TREATMENT | ANTI TERMITE TREATMENT
2 | 1 | PEST CONTROL Providing doing anti termite treatment with IMIDACLOPRID (OZIER) for entire area (Pest control) Diluting and injecting chemical emulsion 3 in floor for pre constructional Anti Termite treatment and creating a continuous chemical @ 4 center to center barrier all over as per manufacturer specification and ISI standards. | PEST CONTROL Providing doing anti termite treatment with IMIDACLOPRID (OZIER) for entire area (Pest control) Diluting and injecting chemical emulsion 3 in floor for pre constructional Anti Termite treatment and creating a continuous chemical @ 4 center to center barrier all over as per manufacturer specification and ISI standards. | Sft | 960.000 |  |  | 43 | 25.5 | 1096.5
3 | 2 | DISMANTLING WORKS | DISMANTLING WORKS
4 | 1 | DISMANTLING WORKS Pre-approval of Amount for any dismantling works required | DISMANTLING WORKS Pre-approval of Amount for any dismantling works required | Job | 1.000 | 5,000.00 | 1 |  |  | 1
5 | 3 | CIVIL WORKS | CIVIL WORKS
6 | 3.01 | 100MM THK SIPOREX WALL P C light wt. Block masonry of 100mm thk with CM 1 4 in proper line, level plumb (Siporex or Aerocon block of size 600 x 200 x 100 mm) At every 1 tm ht. interval stiffener should be provided. Rate to include the cost of stiffener lintel. | 100MM THK SIPOREX WALL P C light wt. Block masonry of 100mm thk with CM 1 4 in proper line, level plumb (Siporex or Aerocon block of size 600 x 200 x 100 mm) At every 1 tm ht. interval stiffener should be provided. Rate to include the cost of stiffener lintel. | Sft | 2600.000 |  |  |  |  | 2546.105
|  |  | Store Back Wall |  |  |  |  | 44.75 | 11.25 | 503.4375
|  |  | Less Door |  |  |  |  | 3.67 | 6.75 | -24.7725
|  |  | Store Left And Right Wall |  |  |  | 2 | 26.25 | 11.25 | 590.625
|  |  | Dry store |  |  |  |  | 10.58 | 11.25 | 119.025
|  |  | Less Door |  |  |  |  | 3 | 7 | -21
|  |  | Dishwash 01 |  |  |  |  | 3 | 11.25 | 33.75
|  |  | Dishwash 02 |  |  |  |  | 1.5 | 11.25 | 16.875
|  |  | Dishwash 03 |  |  |  |  | 3.17 | 11.25 | 35.6625
|  |  | Left Kitchen Wall |  |  |  |  | 12.34 | 11.25 | 138.825
|  |  | POS left Partition |  |  |  |  | 11.17 | 11.25 | 125.6625
|  |  | MCB/DB Cupboard wall |  |  |  |  | 20.92 | 11.25 | 235.35
|  |  | POS Right |  |  |  |  | 7.67 | 11.25 | 86.2875
|  |  | POS behind 01 |  |  |  |  | 3.75 | 11.25 | 42.1875
|  |  | POS behind 02 |  |  |  |  | 4.5 | 11.25 | 50.625
|  |  | Manager Cabin |  |  |  |  | 7.58 | 11.25 | 85.275
[7 empty] | 2 | 8.48 | 11.25 | 190.8
|  |  | less door |  |  |  |  | 3 | 7 | -21
[8 empty] | 3.92 | 11.25 | 44.1
|  |  | less door |  |  |  |  | 3.25 | 7 | -22.75
|  |  | Shaft |  |  |  | 2 | 3 | 10 | 60
|  |  | left Wall |  |  |  |  | 6.5 | 10 | 65
|  |  | Right Wall |  |  |  |  | 7.5 | 10 | 75
|  |  | Front Wall |  |  |  |  | 13.5 | 10 | 135
|  |  | Less |  |  |  |  | 2.42 | 7 | -16.94
|  |  | Bund Wall |  |  |  |  | 12.58 | 1 | 12.58
|  |  | Back Entry |  |  |  |  | 3.75 | 1 | 3.75
|  |  | Shaft Door |  |  |  |  | 2.75 | 1 | 2.75
7 | 3.02 | INTERNAL PLASTER P A 12-15mm thick plaster in cement mortar 1 4 (1 cement 4coarse sand) to ceiling, all types of RCC. work, brick work surfaces at all levels in line, level and plumb including smooth cement finish or roughning of surface to hold tiles and providing necessary grooves at junctions of walls and ceiling, door window frames incl. racking the joints of roughing the RCC. surface, necessary curing scaffolding etc. complete as directed. Note Allow for providing and fixing galvanized chicken mesh 300mm wide (24 gauge, 12mm size) at junction of brick masonry and concrete members to be plastered or clapped or other locations as called for, properly stretched and nailed ensuring equal thickness of plaster on both sides of mesh. Provision for chemical bonding with a layer of Plaster Master from Roff for RCC surfaces and use of REUROn fibres to avoid superficial cracks.No extra payment shall be made for p f chicken mesh, Plaster Master and REUROn. | INTERNAL PLASTER P A 12-15mm thick plaster in cement mortar 1 4 (1 cement 4coarse sand) to ceiling, all types of RCC. work, brick work surfaces at all levels in line, level and plumb including smooth cement finish or roughning of surface to hold tiles and providing necessary grooves at junctions of walls and ceiling, door window frames incl. racking the joints of roughing the RCC. surface, necessary curing scaffolding etc. complete as directed. Note Allow for providing and fixing galvanized chicken mesh 300mm wide (24 gauge, 12mm size) at junction of brick masonry and concrete members to be plastered or clapped or other locations as called for, properly stretched and nailed ensuring equal thickness of plaster on both sides of mesh. Provision for chemical bonding with a layer of Plaster Master from Roff for RCC surfaces and use of REUROn fibres to avoid superficial cracks.No extra payment shall be made for p f chicken mesh, Plaster Master and REUROn. | Sft | 4900.000 | 318,500.00 |  |  |  | 4896.025
|  |  | Store Back Wall |  |  |  | 2 | 43.75 | 11.25 | 984.375
|  |  | Less Door |  |  |  | 2 | 3.67 | 6.75 | -49.545
|  |  | Store Left And Right Wall |  |  |  | 4 | 26.75 | 11.25 | 1203.75
|  |  | Dry store |  |  |  | 2 | 10.58 | 11.25 | 238.05
|  |  | Less Door |  |  |  | 2 | 3 | 7 | -42
|  |  | Dishwash 01 |  |  |  | 2 | 3 | 11.25 | 67.5
|  |  | Dishwash 02 |  |  |  | 2 | 1.5 | 11.25 | 33.75
|  |  | Dishwash 03 |  |  |  | 2 | 3.17 | 11.25 | 71.325
|  |  | Left Kitchen Wall |  |  |  | 2 | 12.34 | 11.25 | 277.65
|  |  | POS left Partition |  |  |  | 2 | 11.17 | 11.25 | 251.325
|  |  | MCB/DB Cupboard wall |  |  |  | 2 | 20.92 | 11.25 | 470.7
|  |  | POS Right |  |  |  | 2 | 7.67 | 11.25 | 172.575
|  |  | POS behind 01 |  |  |  | 2 | 3.75 | 11.25 | 84.375
|  |  | POS behind 02 |  |  |  | 2 | 4.5 | 11.25 | 101.25
|  |  | Manager Cabin |  |  |  | 2 | 7.58 | 11.25 | 170.55
[7 empty] | 4 | 8.48 | 11.25 | 381.6
|  |  | less door |  |  |  | 2 | 3 | 7 | -42
[7 empty] | 2 | 3.92 | 11.25 | 88.2
|  |  | less door |  |  |  | 2 | 3.25 | 7 | -45.5
|  |  | Shaft |  |  |  | 4 | 3 | 10 | 120
|  |  | left Wall |  |  |  | 1 | 6.5 | 10 | 65
|  |  | Right Wall |  |  |  | 1 | 7.5 | 10 | 75
|  |  | Front Wall |  |  |  | 1 | 13.5 | 10 | 135
|  |  | Less |  |  |  | 1 | 2.42 | 7 | -16.94
|  |  | Bund Wall |  |  |  | 2 | 12.58 | 1 | 25.16
|  |  | Back Entry |  |  |  | 2 | 3.75 | 1 | 7.5
|  |  | Shaft Door |  |  |  | 2 | 2.75 | 1 | 5.5
|  |  | Wall Edges |  |  |  | 11 | 11.25 | 0.5 | 61.875
8 | 4 | BRICK BAT COBA WATERPROOFING WORKS | BRICK BAT COBA WATERPROOFING WORKS
9 | 4.01 | SIPOREX BAT COBA- upto 100MM P L light wt. Solid Block (siporex or Aerocon) bat coba to conceal drainage plumbing lines for Grease trap of average thk of 100 mm with CM 1 4 top layer should be finished properly to receive flooring layer on it [ DISH WASH AREA] | SIPOREX BAT COBA- upto 100MM P L light wt. Solid Block (siporex or Aerocon) bat coba to conceal drainage plumbing lines for Grease trap of average thk of 100 mm with CM 1 4 top layer should be finished properly to receive flooring layer on it [ DISH WASH AREA] | Sft | 25.000 | 3,000.00 |  |  |  | 87.285
[8 empty] | 6.58 | 2 | 13.16
[8 empty] | 14 | 2.75 | 38.5
[8 empty] | 6.5 | 3.75 | 24.375
[8 empty] | 3.75 | 3 | 11.25
10 | 4.02 | SIPOREX BAT COBA- upto 150MM P L light wt. Solid Block (siporex or Aerocon) bat coba to conceal drainage plumbing lines for Grease trap of average thk of 150 mm with CM 1 4 top layer should be finished properly to receive flooring layer on it [ DISH WASH AREA] | SIPOREX BAT COBA- upto 150MM P L light wt. Solid Block (siporex or Aerocon) bat coba to conceal drainage plumbing lines for Grease trap of average thk of 150 mm with CM 1 4 top layer should be finished properly to receive flooring layer on it [ DISH WASH AREA] | Sft | 30.000 | 4,350.00
11 | 4.03 | SIPOREX BAT COBA- upto 305MM P L light wt. Solid Block (siporex or Aerocon) bat coba to conceal drainage plumbing lines for Grease trap of average thk of 200 mm with CM 1 4 top layer should be finished properly to receive flooring layer on it [ DISH WASH AREA] | SIPOREX BAT COBA- upto 305MM P L light wt. Solid Block (siporex or Aerocon) bat coba to conceal drainage plumbing lines for Grease trap of average thk of 200 mm with CM 1 4 top layer should be finished properly to receive flooring layer on it [ DISH WASH AREA] | Sft | 870.000 | 182,700.00 |  | 43 | 25.5 | 1096.5
12 | 4.04 | WATER PROOFING- MEMBRANE Providing and laying water- proofing treatment to hand wash, BOH area consisting of 4mm Thk Apex Apcon Sheild Dr Fixit Torchsheild or equivalent polyster reinforced APP modified bitumen membrane sheet(Basic Rate Rs.2000 Roll of 10mX1m) as approved, cleaning and smoothing of entire surface, smooth plaster upto 600mm from raw floor lvl, 12mmx12mm groove at 150mm from floor rising lvl, one coat of Bitcote Dr Fixit Apex equivalent (as approved)-heavy body bitumen primer (Basic Rate Rs.82 Kg) coating as a primer on surface and till 450mm from floor rising lvl, application of membrane sheet as per application detail and packing the hole cuts for pipe line and checking the area which is water proofed. Rate includes of laying the protective layer of Plaster. Measurement to be done of floor area, wall area not to be paid, if ht. is < 600 mm, difference of 600mm will be paid. | WATER PROOFING- MEMBRANE Providing and laying water- proofing treatment to hand wash, BOH area consisting of 4mm Thk Apex Apcon Sheild Dr Fixit Torchsheild or equivalent polyster reinforced APP modified bitumen membrane sheet(Basic Rate Rs.2000 Roll of 10mX1m) as approved, cleaning and smoothing of entire surface, smooth plaster upto 600mm from raw floor lvl, 12mmx12mm groove at 150mm from floor rising lvl, one coat of Bitcote Dr Fixit Apex equivalent (as approved)-heavy body bitumen primer (Basic Rate Rs.82 Kg) coating as a primer on surface and till 450mm from floor rising lvl, application of membrane sheet as per application detail and packing the hole cuts for pipe line and checking the area which is water proofed. Rate includes of laying the protective layer of Plaster. Measurement to be done of floor area, wall area not to be paid, if ht. is < 600 mm, difference of 600mm will be paid. | Sft | 1750.000 | 192,500.00 |  |  |  | 2215.32
[8 empty] | 43 | 25.5 | 1096.5
[8 empty] | 43 | 3 | 129
[7 empty] | 2 | 25.5 | 3 | 153
[7 empty] | 2 | 10.58 | 3 | 63.48
[7 empty] | 2 | 3 | 3 | 18
[7 empty] | 2 | 2.08 | 3 | 12.48
[7 empty] | 2 | 3.48 | 3 | 20.88
[7 empty] | 2 | 11.58 | 3 | 69.48
[7 empty] | 2 | 12.34 | 3 | 74.04
[7 empty] | 2 | 20.92 | 3 | 125.52
[7 empty] | 2 | 7.67 | 3 | 46.02
[7 empty] | 2 | 3.75 | 3 | 22.5
[7 empty] | 2 | 4.5 | 3 | 27
[7 empty] | 2 | 3.5 | 3 | 21
[7 empty] | 2 | 7.58 | 3 | 45.48
[7 empty] | 4 | 8.48 | 3 | 101.76
[7 empty] | 2 | 3 | 3 | -18
[7 empty] | 2 | 3.92 | 3 | 23.52
[7 empty] | 2 | 3.25 | 3 | -19.5
[7 empty] | 2 | 3 | 3 | 18
[7 empty] | 2 | 3 | 3 | 18
[8 empty] | 6.5 | 3 | 19.5
[8 empty] | 8 | 3 | 24
[8 empty] | 13.75 | 3 | 41.25
[8 empty] | 14.75 | 3 | 44.25
[7 empty] | 2 | 12.58 | 1 | 25.16
[7 empty] | 2 | 3.75 | 1 | 7.5
[7 empty] | 2 | 2.75 | 1 | 5.5
13 | 5 | PCC WORKS | PCC WORKS
14 | 5.01 | 50mm PCC Providing Laying PCC 1 3 6 of average thk 50mm of M 10 grade of concrete ( 1 cement 3 coarse sand 6graded stone aggregate 10 mm nominal size) BOH AREA | 50mm PCC Providing Laying PCC 1 3 6 of average thk 50mm of M 10 grade of concrete ( 1 cement 3 coarse sand 6graded stone aggregate 10 mm nominal size) BOH AREA | Sft | 870.000 |  |  | 43 | 25.5 | 1096.5
15 | 6 | CUT OUT WORKS | CUT OUT WORKS
16 | 6.01 | CUT OUT IN THE WALLS FOR AC DUCT ROUTING Making Cut out for AC ducts finishing the edges or filling the gaps after the duct installation; incl of water weather proofing walls from exterior side. | CUT OUT IN THE WALLS FOR AC DUCT ROUTING Making Cut out for AC ducts finishing the edges or filling the gaps after the duct installation; incl of water weather proofing walls from exterior side. | Nos | 6.000 |  | 6 |  |  | 6
17 |  | Note No holes to be made in any beams, columns, slabs, etc by Sapphire or Sapphire s vendors. If any core cutting is required, same to be done by respective LL mall management. As per case, if core cutting is to be reimbursed, Sapphire or Sapphire s vendors will reimburse the LL mall management as per project managers corresspondence with LL Mall management. | Note No holes to be made in any beams, columns, slabs, etc by Sapphire or Sapphire s vendors. If any core cutting is required, same to be done by respective LL mall management. As per case, if core cutting is to be reimbursed, Sapphire or Sapphire s vendors will reimburse the LL mall management as per project managers corresspondence with LL Mall management.
18 | 7 | GRANITE WORKS | GRANITE WORKS
19 | 7.01 | GRANITE PARTITION DOUBLE THICKNESS P F 36mm thk Granite Partition by sandwiching two 18mm thk granite (3 -6 height) with Araldite adhesive including cutting, fixing, grinding, half round moulding at the edge polishing complete. Base Rate of granite is Rs. 150 - sq.ft. Product- Jet black granite | GRANITE PARTITION DOUBLE THICKNESS P F 36mm thk Granite Partition by sandwiching two 18mm thk granite (3 -6 height) with Araldite adhesive including cutting, fixing, grinding, half round moulding at the edge polishing complete. Base Rate of granite is Rs. 150 - sq.ft. Product- Jet black granite | Sft | 10.000 | 7,500.00
20 | 7.02 | GRANITE FLOORING STAIRCASE P F 18mm thk Granite on flooring laid over a properly prepared bed of cement mortar in line and level. All joints to be hairline, to be cleaned and filled with approved color Laticrete, to the required line level at all heights and leads, as per detailed designs and drawings, including all labour, edge polish, champhering, moulding, material, curing, cleaning. Base Rate of granite is Rs. 150 - sq.ft. Product- Jet black granite | GRANITE FLOORING STAIRCASE P F 18mm thk Granite on flooring laid over a properly prepared bed of cement mortar in line and level. All joints to be hairline, to be cleaned and filled with approved color Laticrete, to the required line level at all heights and leads, as per detailed designs and drawings, including all labour, edge polish, champhering, moulding, material, curing, cleaning. Base Rate of granite is Rs. 150 - sq.ft. Product- Jet black granite | Sft | 12.000 |  |  | 3.75 | 3 | 11.25
21 | 7.03 | GRANITE THRESHOLD IN FLOORING AND JAMB LINING P F upto 9 wide 18mm Granite threshold on flooring laid over a properly prepared bed of cement mortar in line and level. All joints to be hairline, to be cleaned and filled with approved color Laticrete, to the required line level at all heights and leads, as per detailed designs and drawings, including all labour, edge polish, champhering, moulding, material, curing, cleaning. Base Rate of granite is Rs. 150 - sq.ft. Product- Jet black granite | GRANITE THRESHOLD IN FLOORING AND JAMB LINING P F upto 9 wide 18mm Granite threshold on flooring laid over a properly prepared bed of cement mortar in line and level. All joints to be hairline, to be cleaned and filled with approved color Laticrete, to the required line level at all heights and leads, as per detailed designs and drawings, including all labour, edge polish, champhering, moulding, material, curing, cleaning. Base Rate of granite is Rs. 150 - sq.ft. Product- Jet black granite | Rft | 10.000 |  |  |  |  | 190.5
[8 empty] | 122 |  | 122
[8 empty] | 7 |  | 7
[8 empty] | 18 |  | 18
[8 empty] | 43.5 |  | 43.5
22 | 8 | FLOORING WORKS | FLOORING WORKS
23 | 8.01 | KOTA STONE FLOORING P L Kota stone flooring of size 22 x 22 (25 mm thk) with 40 mm avg thk of cement sand bedding of CM 1 6 neat cement slurry paste with polish KOTA PRE-POLISH KOTA | KOTA STONE FLOORING P L Kota stone flooring of size 22 x 22 (25 mm thk) with 40 mm avg thk of cement sand bedding of CM 1 6 neat cement slurry paste with polish KOTA PRE-POLISH KOTA | Sft | 1100.000 | 231,000.00 |  |  |  | 1129.3
[8 empty] | 43 | 25.5 | 1096.5
[8 empty] | 13.75 | 8 | -110
[8 empty] | 3 | 5 | 15
[8 empty] | 2.08 | 5 | 10.4
[8 empty] | 3.48 | 5 | 17.4
[8 empty] | 20 | 5 | 100
24 | 9 | DADO WORKS | DADO WORKS
25 | 9.01 | DADO TILES (8 -0” HT) FOR KFC P L BLACK BEVELED TILES, JOHNSON MAKE (200mmX100mm) Dado TILE with neat cement paste with avg thk of 6mm in proper line, level plumb. Make color will be approved by architect. Base Rate of tile is Rs. 80 - sq.ft. | DADO TILES (8 -0” HT) FOR KFC P L BLACK BEVELED TILES, JOHNSON MAKE (200mmX100mm) Dado TILE with neat cement paste with avg thk of 6mm in proper line, level plumb. Make color will be approved by architect. Base Rate of tile is Rs. 80 - sq.ft. | Sft | 245.000 |  |  |  |  | 283.5872
[8 empty] | 9.25 | 8.84 | 81.77
[8 empty] | 3.75 | 8.84 | 33.15
[8 empty] | 4.5 | 8.84 | 39.78
[8 empty] | 8.58 | 8.84 | 75.8472
[8 empty] | 6 | 8.84 | 53.04
26 | 9.02 | DADO TILES (8 -0 HT) P LGLAZE CERAMIC WALL TILE of size 600 x 300 mm on 40 mm thk of cement sand bedding with CM 1 4 (fixing to be done with cement slurry paste) for toilet area. Base Rate of tile is Rs. 60 - sq.ft. NO ACCEPTANCE FOR ANY RATE VARIATION ON BASIC RATE. | DADO TILES (8 -0 HT) P LGLAZE CERAMIC WALL TILE of size 600 x 300 mm on 40 mm thk of cement sand bedding with CM 1 4 (fixing to be done with cement slurry paste) for toilet area. Base Rate of tile is Rs. 60 - sq.ft. NO ACCEPTANCE FOR ANY RATE VARIATION ON BASIC RATE. | Sft | 1550.000 | 325,500.00 |  |  |  | 1710.8364
[8 empty] | 10.34 | 8.25 | 85.305
[8 empty] | 9.67 | 8.25 | 79.7775
[8 empty] | 7.5 | 8.25 | 61.875
[7 empty] | 2 | 7.67 | 8.25 | 126.555
[8 empty] | 5.84 | 8.25 | 48.18
[8 empty] | 0.5 | 8.25 | 4.125
[8 empty] | 4.58 | 3.25 | 14.885
[8 empty] | 9.16 | 3.25 | 29.77
[8 empty] | 5.92 | 3.25 | 19.24
[8 empty] | 3.75 | 3.25 | 12.1875
[8 empty] | 9 | 8.25 | 74.25
[8 empty] | 13.92 | 8.25 | 114.84
[8 empty] | 2.67 | 6 | -16.02
[8 empty] | 12.5 | 8.25 | 103.125
[8 empty] | 11.16 | 8.25 | 92.07
[8 empty] | 20 | 8.25 | 165
[8 empty] | 8.25 | 8.25 | 68.0625
[8 empty] | 7.75 | 8.25 | 63.9375
[8 empty] | 3.08 | 1.58 | 4.8664
[8 empty] | 6 | 8.25 | 49.5
[8 empty] | 2.75 | 7 | -19.25
[8 empty] | 4 | 8 | 32
[8 empty] | 8.25 | 8.25 | 68.0625
[8 empty] | 7 | 8.25 | 57.75
[8 empty] | 16.84 | 8.25 | 138.93
[8 empty] | 4.58 | 8.25 | 37.785
[8 empty] | 4.08 | 8.25 | 33.66
[7 empty] | 3 | 0.5 |  | 1.5
[8 empty] | 7.34 | 8.25 | 60.555
[8 empty] | 14.25 | 8.25 | 117.5625
[8 empty] | 2.75 | 7 | -19.25
27 | 9.03 | WALL TILE BOXES HANDED OVER TO OPERATIONS Handing over sealed boxes of wall tiles to maintenance operations team on completion of the project at time of handover- to be preserved used by maintenance operations team for any future repair work at same outlet | WALL TILE BOXES HANDED OVER TO OPERATIONS Handing over sealed boxes of wall tiles to maintenance operations team on completion of the project at time of handover- to be preserved used by maintenance operations team for any future repair work at same outlet
28 |  | GREY TILE - GLOSSY- Johnson - maximum one box WILL BE PAID ADDITIONAL BASIS ON SUPPORTING | GREY TILE - GLOSSY- Johnson - maximum one box WILL BE PAID ADDITIONAL BASIS ON SUPPORTING | Box | 2.000 |  | 0
29 |  | Toronto Blanco- maximum two boxes WILL BE PAID ADDITIONAL BASIS ON SUPPORTING | Toronto Blanco- maximum two boxes WILL BE PAID ADDITIONAL BASIS ON SUPPORTING | Box | 2.000 |  | 0
30 | 10 | SKIRTING WORKS | SKIRTING WORKS
31 | 10.01 | KOTA SKIRTING P F upto 100 mm high kota tile STONE skirting | KOTA SKIRTING P F upto 100 mm high kota tile STONE skirting | Rft | 240.000 | 30,000.00 | 265 |  |  | 265
32 | 10.02 | SS 304 GRADE SKIRTING P F upto 100 mm high tile skirting | SS 304 GRADE SKIRTING P F upto 100 mm high tile skirting | Rft | 100.000 | 11,000.00 |  |  |  | 114.75
[8 empty] | 43 |  | 43
[8 empty] | 71.75 |  | 71.75
33 | 11 | PARTITIONS AND PANELINGS | PARTITIONS AND PANELINGS
34 | 11.01 | 8 MM PLYWOOD PANELING BOXING P F 8mm 12mm plywood as paneling as per following specs incl of all hardware, labour; in perfect line and plumb, incl of grooves as desired or specified in drawing, complete in all respects. Frame sections of upto 2 x 1.5 size can be of seasoned termite- treated Sal wood, or aluminium sections of same size. | 8 MM PLYWOOD PANELING BOXING P F 8mm 12mm plywood as paneling as per following specs incl of all hardware, labour; in perfect line and plumb, incl of grooves as desired or specified in drawing, complete in all respects. Frame sections of upto 2 x 1.5 size can be of seasoned termite- treated Sal wood, or aluminium sections of same size.
35 |  | P F 8mm plywood plain paneling without frame or laminate | P F 8mm plywood plain paneling without frame or laminate | Sft | 295.000 | 53,100.00 |  |  |  | 455.5
[8 empty] | 7.92 | 10 | 79.2
[8 empty] | 13.5 | 10 | 135
[8 empty] | 11.25 | 10 | 112.5
[8 empty] | 3 | 10 | 30
[7 empty] | 2 | 1.34 | 10 | 26.8
[7 empty] | 4 | 3 | 6 | 72
36 |  | P F 8mm plywood plain paneling with frame or without laminate | P F 8mm plywood plain paneling with frame or without laminate | Sft | 20.000 | 4,900.00 |  |  |  | 844.93
[8 empty] | 6.83 | 10 | 68.3
[8 empty] | 8.5 | 1 | 8.5
[8 empty] | 65 | 1 | 65
[8 empty] | 9.34 | 1 | 9.34
[8 empty] | 6.58 | 1 | 6.58
[8 empty] | 7.34 | 1 | 7.34
[8 empty] | 9 | 1 | 9
[8 empty] | 13.67 | 1 | 13.67
[8 empty] | 2 | 9 | 18
[8 empty] | 63.92 | 10 | 639.2
37 |  | P F 12mm plywood plain paneling with frame, with laminate | P F 12mm plywood plain paneling with frame, with laminate | Sft | 15.000 | 5,400.00
38 |  | P F 12mm plywood plain paneling with frame, without laminate | P F 12mm plywood plain paneling with frame, without laminate | Sft | 35.000 | 8,575.00 |  | 12.75 | 2.75 | 35.0625
39 | 11.02 | 12MM BISON BOARD PANELING BOXING P F 12mm bison panel as paneling as per following specs incl of all hardware, labour; in perfect line and plumb, incl of grooves as desired or specified in drawing, complete in all respects. | 12MM BISON BOARD PANELING BOXING P F 12mm bison panel as paneling as per following specs incl of all hardware, labour; in perfect line and plumb, incl of grooves as desired or specified in drawing, complete in all respects.
40 |  | P F 12mm Bison panel paneling with MS frame of upto 1.25 x 1.25 pipe sections | P F 12mm Bison panel paneling with MS frame of upto 1.25 x 1.25 pipe sections | Sft | 280.000 | 64,400.00
41 | 11.03 | 12MM SHERA BOARD PANELING BOXING P F 12MM shear board as paneling as per following specs incl of all hardware, labour; in perfect line and plumb, incl of grooves as desired or specified in drawing, complete in all respects. Inclusive of polish paint- Asian Paints cement primer followed by two coats of Apex Ultima of approved shade followed by top coat of Asian Reemers. | 12MM SHERA BOARD PANELING BOXING P F 12MM shear board as paneling as per following specs incl of all hardware, labour; in perfect line and plumb, incl of grooves as desired or specified in drawing, complete in all respects. Inclusive of polish paint- Asian Paints cement primer followed by two coats of Apex Ultima of approved shade followed by top coat of Asian Reemers.
42 |  | P F 12MM Shera board paneling without frame on existing surface | P F 12MM Shera board paneling without frame on existing surface | Sft | 335.000 |  |  |  |  | 331.9975
[8 empty] | 6.67 | 7 | 46.69
[8 empty] | 3 | 6.75 | -20.25
[8 empty] | 19 | 8.58 | 163.02
[8 empty] | 3.67 | 6.75 | -24.7725
[8 empty] | 19.5 | 8.58 | 167.31
43 | 11.04 | SUSPENDED PANELING FOR DMB P F plywood partition made as per detailed drawing with MS frame work of 50 x 50 sections and MS base plate supported from upper slab to support DMB structure. M.S. FRAMEWORK COVERED WITH M S SHEET TO BE FINISHED WITH BLACK PAINT . Rate is inclusive of all necessary hardware and MS fabrication dropped down from true slab as per drawing. Only front of MS sheet finish area to be considered for measurements, rear and edges not to be measured | SUSPENDED PANELING FOR DMB P F plywood partition made as per detailed drawing with MS frame work of 50 x 50 sections and MS base plate supported from upper slab to support DMB structure. M.S. FRAMEWORK COVERED WITH M S SHEET TO BE FINISHED WITH BLACK PAINT . Rate is inclusive of all necessary hardware and MS fabrication dropped down from true slab as per drawing. Only front of MS sheet finish area to be considered for measurements, rear and edges not to be measured | Sft | 25.000 | 10,750.00 |  | 12.5 | 2.5 | 31.25
44 | 11.05 | GYPSUM PANELING P F 12.5mm thick gypsum board as seamless paneling in complete plumb, line and level, with tapered joints finished with tape and gypsum | GYPSUM PANELING P F 12.5mm thick gypsum board as seamless paneling in complete plumb, line and level, with tapered joints finished with tape and gypsum
45 |  | P F gypsum board as paneling without any framework on existing surface | P F gypsum board as paneling without any framework on existing surface | Sft | 35.000
46 | 11.06 | FULL LOW HEIGHT PARTITION P F Partition made on aluminium sal wood frame of 2 x 1.5 sections fixed at 600 x 600, properly clamped to walls, ceiling and floor. Rate is inclusive all necessary hardware, labour, etc. | FULL LOW HEIGHT PARTITION P F Partition made on aluminium sal wood frame of 2 x 1.5 sections fixed at 600 x 600, properly clamped to walls, ceiling and floor. Rate is inclusive all necessary hardware, labour, etc.
47 |  | P F 12mm plywood on both sides of frame mentioned above with laminate | P F 12mm plywood on both sides of frame mentioned above with laminate | Sft | 50.000 | 22,500.00 |  |  |  | 50.625
[8 empty] | 12.5 | 2.25 | 28.125
[8 empty] | 2.25 | 10 | 22.5
48 |  | P F 12mm bison panel on both sides of frame mentioned above | P F 12mm bison panel on both sides of frame mentioned above | Sft | 15.000 | 3,450.00 |  | 12.5 | 2 | 25
49 | 11.07 | BACK PAINTED GLASS P F fixed 12mm back painted glass with all edges crystal edge polished | BACK PAINTED GLASS P F fixed 12mm back painted glass with all edges crystal edge polished | Sft | 175.000 | 131,250.00 |  |  |  | 284.0425
[8 empty] | 13.5 | 8.58 | 115.83
[8 empty] | 7.75 | 9.25 | 71.6875
[8 empty] | 11.25 | 8.58 | 96.525
50 | 12 | COUNTERS AND STORAGES | COUNTERS AND STORAGES
51 | 12.01 | OVERHEAD CABINETS STORAGE CABINETS P F Overhead Cabinet storage cabinet Takeaway counter made out of 19mm marine ply for sides, top, bottom, shelves and shutters. Back of cabinet to be made out of 6mm marine ply. All external surfaces to be finished with approved laminate of 1.0mm thickness. All internal surfaces to be finished in balancing laminate of 0.8mm thickness. All edges of ply to be finished with beading patti finished in paint polish. Costs to include for all hardware and fittings like handles, locks, powder coated M.S wire managers, sliding channels, lipping, nylon bushing for legs, making grooves etc complete as per drawing and details. Open area for data rack shelves (if open area is part of one single complete overhead storage structure will be measured in same heading) | OVERHEAD CABINETS STORAGE CABINETS P F Overhead Cabinet storage cabinet Takeaway counter made out of 19mm marine ply for sides, top, bottom, shelves and shutters. Back of cabinet to be made out of 6mm marine ply. All external surfaces to be finished with approved laminate of 1.0mm thickness. All internal surfaces to be finished in balancing laminate of 0.8mm thickness. All edges of ply to be finished with beading patti finished in paint polish. Costs to include for all hardware and fittings like handles, locks, powder coated M.S wire managers, sliding channels, lipping, nylon bushing for legs, making grooves etc complete as per drawing and details. Open area for data rack shelves (if open area is part of one single complete overhead storage structure will be measured in same heading)
52 |  | Upto 18 depth (extra will not be paid if storage depth is 18 + shutters thickness) | Upto 18 depth (extra will not be paid if storage depth is 18 + shutters thickness) | Sft | 60.000 |  |  |  |  | 65.9178
[8 empty] | 6.58 | 3.16 | 20.7928
[8 empty] | 6.5 | 5.5 | 35.75
[8 empty] | 1.5 | 6.25 | 9.375
53 | 12.02 | DISPENSING COUNTER (KFC) P F dispensing counter (ORDER PICKUP) made out of 19mm thk. Marine Ply finished with 1mm THK. laminate FOR ALL INTERNAL SURFACES with provision OF NICHE for KDS (as per detail dwg). complete with TELESCOPIC drawer channels, VERTICAL PARTITIONS SHELVES with neccessary hardware , raceways, SS BASKETS 304 GRADE wire manager,below the counter top to route the electrical wiring for POS machine. All CUTOUTS, hardwares and fixtures to be included in rate. Mode of measurement will be from BOH elevation height. 30 depth, 30 height. Rate to be inclusive of ledge finished in plywood. Rate is INclusive OF Solid Surface (10MM Corian FOR FRONT FACIA TOP front) | DISPENSING COUNTER (KFC) P F dispensing counter (ORDER PICKUP) made out of 19mm thk. Marine Ply finished with 1mm THK. laminate FOR ALL INTERNAL SURFACES with provision OF NICHE for KDS (as per detail dwg). complete with TELESCOPIC drawer channels, VERTICAL PARTITIONS SHELVES with neccessary hardware , raceways, SS BASKETS 304 GRADE wire manager,below the counter top to route the electrical wiring for POS machine. All CUTOUTS, hardwares and fixtures to be included in rate. Mode of measurement will be from BOH elevation height. 30 depth, 30 height. Rate to be inclusive of ledge finished in plywood. Rate is INclusive OF Solid Surface (10MM Corian FOR FRONT FACIA TOP front) | Sft | 50.000 | 210,000.00 |  | 12.75 | 3.75 | 47.8125
54 | 13 | MISCELLANEOUS CARPENTRY | MISCELLANEOUS CARPENTRY
55 | 13.01 | SOFT BOARD P F 12mm thk. Soft board fixed onto to existing surface finished approved colour fabric as per detailed drawing. Backing plywood if required to be billed in paneling heading above. | SOFT BOARD P F 12mm thk. Soft board fixed onto to existing surface finished approved colour fabric as per detailed drawing. Backing plywood if required to be billed in paneling heading above. | Sft | 10.000
56 | 13.02 | WORK TOP MANAGER DESK P F work top manager desk Top and verticals to be made in 19mm granite fixed on marble surface with vertical supports as per design detail, inclusive of cutout for wire manager. | WORK TOP MANAGER DESK P F work top manager desk Top and verticals to be made in 19mm granite fixed on marble surface with vertical supports as per design detail, inclusive of cutout for wire manager. | Rft | 7.000 |  |  | 6.58 |  | 6.58
57 | 13.03 | KEYBOARD TRAY P F PVC Keyboard tray without mouse of earl bihari (ebco) make, with drawer channel | KEYBOARD TRAY P F PVC Keyboard tray without mouse of earl bihari (ebco) make, with drawer channel | Nos | 2.000 | 3,000.00
58 | 13.04 | CPU TROLLEY P F metal CPU trolley of earl bihari make | CPU TROLLEY P F metal CPU trolley of earl bihari make | Nos | 1.000 | 1,450.00
59 | 13.05 | PELMET Providing and Fixing of 6 high Pelmet Above Manager Table made out of 19mm thk. Ply, covered with approved laminate of 1.0mm thickness, as per detail Drawing | PELMET Providing and Fixing of 6 high Pelmet Above Manager Table made out of 19mm thk. Ply, covered with approved laminate of 1.0mm thickness, as per detail Drawing | Rft | 7.000 |  |  | 6.58 |  | 6.58
60 | 13.06 | TRAP DOOR OPENABLE P F Trap door made of 19mm marine ply finished with approved laminate of 1.0mm thickness with all necessary frame work in salwood hardware fittings complete as per the detailed drawing instruction | TRAP DOOR OPENABLE P F Trap door made of 19mm marine ply finished with approved laminate of 1.0mm thickness with all necessary frame work in salwood hardware fittings complete as per the detailed drawing instruction | Sft | 25.000 | 20,000.00
61 | 13.07 | TRAP DOOR MOVEABLE P F moveable trapdoor Fixing frame of 2 x 2 1.5 x 1.5 Aluminium angles along perimeter of trapdoor with intermediate 1.5 tee sections at every 24 to house 8mm pre-laminated particle board as trapdoor for air-conditioning ahu units. Each pre-laminated particle board panel size not to exceed 24 x 24 , to be housed on all 4 sides by aluminium sections. Each panel to be removable. Refer detail drawings. | TRAP DOOR MOVEABLE P F moveable trapdoor Fixing frame of 2 x 2 1.5 x 1.5 Aluminium angles along perimeter of trapdoor with intermediate 1.5 tee sections at every 24 to house 8mm pre-laminated particle board as trapdoor for air-conditioning ahu units. Each pre-laminated particle board panel size not to exceed 24 x 24 , to be housed on all 4 sides by aluminium sections. Each panel to be removable. Refer detail drawings. | Sft | 35.000 | 35,000.00
62 | 13.08 | KEY HIVE BOX P F Key Box with provision for mounting 50 keys. Space should be available for labeling each hook. | KEY HIVE BOX P F Key Box with provision for mounting 50 keys. Space should be available for labeling each hook.
63 |  | P F ready made Key Box in PVC powder coated MS. | P F ready made Key Box in PVC powder coated MS. | Nos | 1.000
64 | 14 | DOORS DOOR FRAMES (FRD) | DOORS DOOR FRAMES (FRD)
65 | 14.01 | VISION PANEL DOOR (FRD) P F Door with Vision Panel (35 mm thk ) Wooden Jambs finished with 1mm laminate on both side with 6 wide S.S Laminate band as per design 60 x 12 Vision Panel at eye level complete as per drawing. Rate is inclusive of all necessary hardware (I.e. S.S.Handle, Hinges, Lock, Floor Spring, Door Closer, Latch or Tower Bolt, Door Stopper, PVC Buffer, 6mm Clear Glass, Frosted Film, etc | VISION PANEL DOOR (FRD) P F Door with Vision Panel (35 mm thk ) Wooden Jambs finished with 1mm laminate on both side with 6 wide S.S Laminate band as per design 60 x 12 Vision Panel at eye level complete as per drawing. Rate is inclusive of all necessary hardware (I.e. S.S.Handle, Hinges, Lock, Floor Spring, Door Closer, Latch or Tower Bolt, Door Stopper, PVC Buffer, 6mm Clear Glass, Frosted Film, etc
66 |  | MANAGER ROOM DOOR Size of door upto 840 x 2150mm | MANAGER ROOM DOOR Size of door upto 840 x 2150mm | Nos | 1.000 | 3,800.00 | 1 |  |  | 1
67 |  | DRY STORE ROOM DOOR Size of door upto 900 x 2150mm | DRY STORE ROOM DOOR Size of door upto 900 x 2150mm | Nos | 1.000 | 3,800.00 | 1 |  |  | 1
68 | 14.02 | SOLID DOOR (FRD) Providing making Door with (35 mm thk marine ) Wooden Jambs finished with 1mm laminate on both as per drawing. Rate is inclusive of all necessary hardware (I.e. S.S.Handle, Lock, Floor Spring, Door Closer, Latch or Tower Bolt, Door Stopper, PVC Buffer, Frosted Film, etc | SOLID DOOR (FRD) Providing making Door with (35 mm thk marine ) Wooden Jambs finished with 1mm laminate on both as per drawing. Rate is inclusive of all necessary hardware (I.e. S.S.Handle, Lock, Floor Spring, Door Closer, Latch or Tower Bolt, Door Stopper, PVC Buffer, Frosted Film, etc
69 |  | SHAFT DOOR Size of door upto 750 x 2150 MM (RATE IS INCLUSIVE OF 2 PANELS HARWARES) | SHAFT DOOR Size of door upto 750 x 2150 MM (RATE IS INCLUSIVE OF 2 PANELS HARWARES) | Nos | 1.000
70 |  | SERVICE DOOR Size of door upto 988 x 2150 MM | SERVICE DOOR Size of door upto 988 x 2150 MM | Nos | 1.000 | 32,000.00 | 1 |  |  | 1
71 | 14.03 | ALUMINUM LOUVERS SHUTTER | ALUMINUM LOUVERS SHUTTER | Sft | 220.000 | 143,000.00 |  | 13.34 | 8.5 | 113.39
72 | 15 | SS WORKS | SS WORKS
73 | 15.01 | SS EDGE PROFILE P F of Stainless steel section edge profile protectors of size 19mm x 19mm x 1.5mm thick to protect all corners of the walls columns in kitchen | SS EDGE PROFILE P F of Stainless steel section edge profile protectors of size 19mm x 19mm x 1.5mm thick to protect all corners of the walls columns in kitchen | Rft | 165.000 |  | 23 | 8 |  | 184
74 | 15.02 | SS KICK PLATE P F S.S. Kick plate on door as directed same rate for all width, LENGTH, HEIGHT doors | SS KICK PLATE P F S.S. Kick plate on door as directed same rate for all width, LENGTH, HEIGHT doors | Nos | 6.000 | 8,400.00
75 | 16 | MS WORKS (UNIT WEIGHT MUST BE AS PER IS CODE) | MS WORKS (UNIT WEIGHT MUST BE AS PER IS CODE)
76 | 16.01 | MS STRUCTURES FOR RO, DG, WATER TANKS, ETC P F of in M.S Frame work in sections of various sizes as required and MS chequered plate with MS supports beams sections at regular intervals as per detail drawings with necessary base plate and supports from walls and slab complete as per design detail finished with approved paint. For base structure in MS for RO, DG, water tanks, etc. Detailed breakup of the weight of each section to be provided | MS STRUCTURES FOR RO, DG, WATER TANKS, ETC P F of in M.S Frame work in sections of various sizes as required and MS chequered plate with MS supports beams sections at regular intervals as per detail drawings with necessary base plate and supports from walls and slab complete as per design detail finished with approved paint. For base structure in MS for RO, DG, water tanks, etc. Detailed breakup of the weight of each section to be provided | kg | 1000.000 | 210,000.00 | 650 |  |  | 650
77 | 17 | POP FALSE CEILING WORK | POP FALSE CEILING WORK
78 | 17.01 | GYPSUM CEILING P F seamless Gypsum ceiling with gyp board of 12.5mm fixed to the under side of the suspended grid formed of GI perimeter channel of size 20x27x30mm fixed along the wall by using wood screws metal expansion raw plugs. The GI intermediate channel of size 45x15x0.90mm shall be fixed to the suspended strap hanger GI ceiling angle at intervals not more than 1220mm.The suspended GI ceiling angle strap hanger is to be connected with G.I soffit cleat of size 37x27x25 1.6mm it should be fixed on the roof slab beam by using metal expansion fasteners of 12.5mm dia. to the length of 35mm with screw at top ends, including all drops, coves etc and taping finishing. | GYPSUM CEILING P F seamless Gypsum ceiling with gyp board of 12.5mm fixed to the under side of the suspended grid formed of GI perimeter channel of size 20x27x30mm fixed along the wall by using wood screws metal expansion raw plugs. The GI intermediate channel of size 45x15x0.90mm shall be fixed to the suspended strap hanger GI ceiling angle at intervals not more than 1220mm.The suspended GI ceiling angle strap hanger is to be connected with G.I soffit cleat of size 37x27x25 1.6mm it should be fixed on the roof slab beam by using metal expansion fasteners of 12.5mm dia. to the length of 35mm with screw at top ends, including all drops, coves etc and taping finishing. | Sft | 300.000 |  |  |  |  | 323.4986
[8 empty] | 12.67 | 4.5 | 57.015
[8 empty] | 8.5 | 4.5 | 38.25
[8 empty] | 4 | 6.25 | 25
[8 empty] | 6.5 | 4.25 | 27.625
[8 empty] | 3.75 | 3 | 11.25
[8 empty] | 10.34 | 7.5 | 77.55
[8 empty] | 6.58 | 7.67 | 50.4686
[8 empty] | 1.84 | 2 | -3.68
[8 empty] | 13.34 | 3 | 40.02
79 | 17.02 | CUTOUTS FOR LIGHTS Making cutouts for lights. Only to be paid for renovation sites as per project managers approval. | CUTOUTS FOR LIGHTS Making cutouts for lights. Only to be paid for renovation sites as per project managers approval. | Nos | 24.000 |  | 49 |  |  | 49
80 | 17.03 | LAY IN METAL GRID CEILING P F Modular Grid (RH-95 plain tegular edge-Armstrong) G.I. PLANE 1 2 thk , 2 x 2 panels with silhoutte grid as per approved sample in dining area as per manufacturer s specification. inclusive of original Armstrong Frame work. | LAY IN METAL GRID CEILING P F Modular Grid (RH-95 plain tegular edge-Armstrong) G.I. PLANE 1 2 thk , 2 x 2 panels with silhoutte grid as per approved sample in dining area as per manufacturer s specification. inclusive of original Armstrong Frame work. | Sft | 470.000 | 97,760.00 |  |  |  | 545.58
[8 empty] | 14.5 | 19.42 | 281.59
[8 empty] | 9 | 2.75 | 24.75
[8 empty] | 10 | 2 | -20
[8 empty] | 16.5 | 8.08 | 133.32
[8 empty] | 17 | 6.5 | 110.5
[8 empty] | 6 | 4 | -24
[8 empty] | 6.16 | 5.75 | 35.42
[8 empty] | 2 | 2 | 4
81 | 17.04 | PVC FLOORING PROTECTOR P F PVC flooring protector on floor of 4mm thk to protect floor tiles to damage during the period of execution | PVC FLOORING PROTECTOR P F PVC flooring protector on floor of 4mm thk to protect floor tiles to damage during the period of execution | Sft | 880.000 |  |  | 63.75 | 33.75 | 2151.5625
82 | 18 | PAINTING POLISHING WORKS | PAINTING POLISHING WORKS
83 | 18.01 | LUSTER PAINT P A 3 coats of Luster paint of approved quality shade by sand papering the surface, applying one coat of primer, prepare the surface with two coats of full putty, sand papering again, repeating a coat of primer, applying one coat of luster paint, touching up with putty applying two final roller coats of luster paint, to internal wall ceilings masonry concrete surfaces incl. preparing the surface by cleaning scrapping, smooth filling crevices, scaffolding etc. Paint codes to be as shown in drawing. | LUSTER PAINT P A 3 coats of Luster paint of approved quality shade by sand papering the surface, applying one coat of primer, prepare the surface with two coats of full putty, sand papering again, repeating a coat of primer, applying one coat of luster paint, touching up with putty applying two final roller coats of luster paint, to internal wall ceilings masonry concrete surfaces incl. preparing the surface by cleaning scrapping, smooth filling crevices, scaffolding etc. Paint codes to be as shown in drawing. | Sft | 1000.000 | 65,000.00 |  |  |  | 962.4536
[8 empty] | 12.67 | 4.5 | 57.015
[8 empty] | 8.5 | 4.5 | 38.25
[8 empty] | 4 | 6.25 | 25
[8 empty] | 6.5 | 4.25 | 27.625
[8 empty] | 3.75 | 3 | 11.25
[8 empty] | 10.34 | 7.5 | 77.55
[8 empty] | 6.58 | 7.67 | 50.4686
[8 empty] | 1.84 | 2 | -3.68
[8 empty] | 13.34 | 3 | 40.02
[8 empty] | 13.34 | 10 | 133.4
[7 empty] | 2 | 3 | 10 | 60
[8 empty] | 6.84 | 10 | 68.4
[8 empty] | 8.5 | 1 | 8.5
[8 empty] | 65 | 1 | 65
[8 empty] | 9.34 | 1 | 9.34
[8 empty] | 6.58 | 1 | 6.58
[8 empty] | 7.34 | 1 | 7.34
[8 empty] | 9 | 1 | 9
[8 empty] | 13.67 | 1 | 13.67
[8 empty] | 12.75 | 3.5 | 44.625
[8 empty] | 148.1 |  | 148.1
[8 empty] | 65 | 1 | 65
84 | 18.02 | DUCO PAINT P A Duco paint (non metallic) approved shade on base coating of water cutting putty sand papered smooth leveled surface with spray | DUCO PAINT P A Duco paint (non metallic) approved shade on base coating of water cutting putty sand papered smooth leveled surface with spray | Sft | 260.000 | 66,300.00
85 | 19 | MISCELLANEOUS ITEMS | MISCELLANEOUS ITEMS
86 | 19.01 | HOOD ERECTION Hood Erection (to be paid in KFC ONLY NON-VEG HOOD), VEG HOOD NOT TO BE PAID, AS IT IS FLOOR MOUNTED | HOOD ERECTION Hood Erection (to be paid in KFC ONLY NON-VEG HOOD), VEG HOOD NOT TO BE PAID, AS IT IS FLOOR MOUNTED | Nos | 1.000
87 | 19.02 | HOUSEKEEPING Keeping site clean during works, deep cleaning before handing over the project. | HOUSEKEEPING Keeping site clean during works, deep cleaning before handing over the project. | Job | 1.000 |  | 1 |  |  | 1
88 | 19.03 | FIXING OF WHITE GOODS Fixing of white goods for BOH AND FOH AREA like Pestoflash, TVs, DMB, KDS, LCMS, Aircurtains, shelves, hooks, maps, internal signages, PVC buffers, Fire extinguishers, Carpentry works like wire manager holes, hand towel dispenser etc. | FIXING OF WHITE GOODS Fixing of white goods for BOH AND FOH AREA like Pestoflash, TVs, DMB, KDS, LCMS, Aircurtains, shelves, hooks, maps, internal signages, PVC buffers, Fire extinguishers, Carpentry works like wire manager holes, hand towel dispenser etc. | Job | 1.000 |  | 1 |  |  | 1
89 | 19.04 | ALUMINIUM LADDER P A Aluminium ladder 8 | ALUMINIUM LADDER P A Aluminium ladder 8 | Nos | 1.000 | 8,500.00
90 | 19.05 | COAT HOOK | COAT HOOK
91 |  | P F coat hook in wash rooms and changing rooms behind door, Jaquar make Continental Series ACN-CHR-1161N | P F coat hook in wash rooms and changing rooms behind door, Jaquar make Continental Series ACN-CHR-1161N | Nos | 4.000 | 4,800.00
92 | 19.06 | TEMPORARY FLEX P F of Temporary flex work printed with art work as specified during project to segregate renovation area as per site requirement. Cost to include temporary door with hinges and locking provision with lock. | TEMPORARY FLEX P F of Temporary flex work printed with art work as specified during project to segregate renovation area as per site requirement. Cost to include temporary door with hinges and locking provision with lock.
93 |  | P F temporary flex as per details above with backing frame of wood MS Aluminium sections as required. | P F temporary flex as per details above with backing frame of wood MS Aluminium sections as required. | Sft | 1100.000 | 126,500.00 |  | 300 | 4 | 1200
94 | 19.07 | LOCKS P F pad locks for RO plant cage, tank, etc. of Godrej make | LOCKS P F pad locks for RO plant cage, tank, etc. of Godrej make | Nos | 1.000
95 | 19.08 | SCAFFOLDING P E of scaffolding in bamboo MS as per site condition. To be paid only in extreme cases with prior approval from Project manager. Cost to be paid based on 15 days intervel WITH SUPPORTING | SCAFFOLDING P E of scaffolding in bamboo MS as per site condition. To be paid only in extreme cases with prior approval from Project manager. Cost to be paid based on 15 days intervel WITH SUPPORTING | Sft | 2500.000 |  |  |  |  | 960
[7 empty] | 2 | 8 | 20 | 320
[7 empty] | 4 | 8 | 15 | 480
[7 empty] | 4 | 4 | 10 | 160
96 | 19.09 | FIRST AID BOX Providing readymade first aid box on completion of the site | FIRST AID BOX Providing readymade first aid box on completion of the site | Nos | 1.000 | 1,800.00
97 | 19.1 | GODREJ NIGHT LATCH P F Additional lock on service door Night Latch of Godrej Make- double turn. To be fixed over and above the existing dead tubular lock as mentioned in the door details. | GODREJ NIGHT LATCH P F Additional lock on service door Night Latch of Godrej Make- double turn. To be fixed over and above the existing dead tubular lock as mentioned in the door details. | Nos | 1.000
98 | 19.11 | FIRE BLANKET | FIRE BLANKET | Nos | 1.000
99 | 19.12 | MAINTENANCE REQUIREMENT WORKS - AMOUNT PAID TO STORE MAINTENANCE Actual bill need to be produced TO BE PAID ON CONFIRMATION OF PM | MAINTENANCE REQUIREMENT WORKS - AMOUNT PAID TO STORE MAINTENANCE Actual bill need to be produced TO BE PAID ON CONFIRMATION OF PM | Nos | 1.000
100 | 19.13 | LOADING UNLOADING - Manual shifting till location as per design (Second floor) 1. RO plant till location | LOADING UNLOADING - Manual shifting till location as per design (Second floor) 1. RO plant till location | Nos | 1.000 |  | 1 |  |  | 1
101 |  | 2. Fresh air Exhaust units AC units AHU units till location | 2. Fresh air Exhaust units AC units AHU units till location
102 |  | 3. Electrical panel till location | 3. Electrical panel till location
103 |  | 4. UPS with battery till location | 4. UPS with battery till location
104 |  | 5. Coldroom Dry store racks till location | 5. Coldroom Dry store racks till location
105 |  | 6. Stabilizer till location | 6. Stabilizer till location
106 |  | 7. SS Dead Equipment till location (Handwash sink, 3bowl sink, hoods, tables, shelves, etc) pepsi machine | 7. SS Dead Equipment till location (Handwash sink, 3bowl sink, hoods, tables, shelves, etc) pepsi machine
107 |  | 8. IT material till location | 8. IT material till location
108 |  | 9. Misc - weighing Scale CCTV Pesto Flash Fire-Extinguisher Music System Gas-Detection System Fire-Suppression System Air-Curtains | 9. Misc - weighing Scale CCTV Pesto Flash Fire-Extinguisher Music System Gas-Detection System Fire-Suppression System Air-Curtains
109 |  | 10. All furnitures till location | 10. All furnitures till location
110 | 19.14 | DEBRIS REMOVAL FROM STORE PREMISES (UP TO 4 VEHICLES) Except Civil vendor debris (Cold room, HVAC, Kitchen Equipment, Signages, Etc) | DEBRIS REMOVAL FROM STORE PREMISES (UP TO 4 VEHICLES) Except Civil vendor debris (Cold room, HVAC, Kitchen Equipment, Signages, Etc) | L S | 1.000 |  | 1 |  |  | 1
111 | 19.15 | MATHADI LABOUR UNION Actuall bill to be produced, ONLY TO BE PAID ON CONFIRMATION OF PM (no margin to be paid additional) | MATHADI LABOUR UNION Actuall bill to be produced, ONLY TO BE PAID ON CONFIRMATION OF PM (no margin to be paid additional) | L S | 1.000 | .00
112 | 19.16 | Installation of amplifier Installation of amplifier 120W for music system suitable to operate on 230V AC 12V DC, with low impedance microphone input two auxiliary inputs, tone control, protection circuit complete for the speakers output 4 8 16 lines | Installation of amplifier Installation of amplifier 120W for music system suitable to operate on 230V AC 12V DC, with low impedance microphone input two auxiliary inputs, tone control, protection circuit complete for the speakers output 4 8 16 lines | L S | 1.000
2 |  | Plumbing Work | Plumbing Work | NOS | 1.000
113 | A | WATER SUPPLY PIPES | WATER SUPPLY PIPES
114 | 1.00 | Supply, laying, testing commissioning of FOOD GRADE CPVC pipes conforming to CTS (Copper Tube Size) SDR-11 as per (is 15778 ASTM D 2846) with necessary fittings up to the size of 50 mm dia, jointing with CPVC solvent cement of medium body IPS brand or equivalent conform. | Supply, laying, testing commissioning of FOOD GRADE CPVC pipes conforming to CTS (Copper Tube Size) SDR-11 as per (is 15778 ASTM D 2846) with necessary fittings up to the size of 50 mm dia, jointing with CPVC solvent cement of medium body IPS brand or equivalent conform.
115 | a | 15mm dia | 15mm dia | Rmt | 0.000 | .00
116 | b | 20mm dia | 20mm dia | Rmt | 68.000 |  |  | 73.5 |  | 73.5
117 | c | 25mm dia | 25mm dia | Rmt | 27.000 |  |  | 46 |  | 46
118 | d | 32mm dia | 32mm dia | Rmt | 25.000 |  |  | 9.25 |  | 9.25
119 | e | 40mm dia | 40mm dia | Rmt | 0.000 | .00
120 | 2.00 | Supply, laying, testing commissioning of CPVC - Schedule 80 (ASTM F 441) Pipes and fittings suitable for Domestic hot water application (max. temp.85 Deg.C) rated for a working pressure of 5 kg cm2 and conforming to latest Indian International Standards. WITH Supply Covering (Thermal Insulation) hot water pipes with 6 mm thick performed closed cell nitrite rubber pipe section insulation having density not less than 60 kg cm2 and K valve not more than 0.034 w m Deg. K @ 20 Deg C mean temperature. | Supply, laying, testing commissioning of CPVC - Schedule 80 (ASTM F 441) Pipes and fittings suitable for Domestic hot water application (max. temp.85 Deg.C) rated for a working pressure of 5 kg cm2 and conforming to latest Indian International Standards. WITH Supply Covering (Thermal Insulation) hot water pipes with 6 mm thick performed closed cell nitrite rubber pipe section insulation having density not less than 60 kg cm2 and K valve not more than 0.034 w m Deg. K @ 20 Deg C mean temperature.
121 | a | 15mm dia | 15mm dia | Rmt | 0.000 | .00
122 | b | 20mm dia | 20mm dia | Rmt | 30.000 |  |  | 34 |  | 34
123 | c | 25mm dia | 25mm dia | Rmt | 0.000 | .00
124 | d | 32mm dia | 32mm dia | Rmt | 0.000 | .00
125 | e | 40mm dia | 40mm dia | Rmt | 0.000 | .00
126 | 4.00 | Supply, Installation, Commissioning Testing for Booster Pump WITH FLOW SWITCH GRAVITATIONAL FLOW (top to bottom flow) with both side Sensor operations- A) 3CUM PER HR. B) HEAD 25M, C) PHASE SINGLE PHASE, D) PROTECTION IP55, E) MONOBLOCK TYPE | Supply, Installation, Commissioning Testing for Booster Pump WITH FLOW SWITCH GRAVITATIONAL FLOW (top to bottom flow) with both side Sensor operations- A) 3CUM PER HR. B) HEAD 25M, C) PHASE SINGLE PHASE, D) PROTECTION IP55, E) MONOBLOCK TYPE
127 |  | 0.5 HP | 0.5 HP | Nos. | 2.000 | 29,000.00 | 2 |  |  | 2
128 |  | 1.0 HP | 1.0 HP | Nos. | 0.000 | .00
129 |  | 1.5 HP | 1.5 HP | Nos. | 0.000 | .00
130 | 4.00 | Supply, Installation, Commissioning Testing for HYDROPNEUMATIC Booster Pump WITH FLOW SWITCH with pressure vessel (AGINST GRAVITY bottom to top flow) with both side Sensor operations (60ltr vessel) with both side Sensor operations- A) 3CUM PER HR. B) HEAD 40M, C) PHASE SINGLE PHASE, D) PROTECTION IP55, E) MONOBLOCK TYPE F) WITH VALVE STATION | Supply, Installation, Commissioning Testing for HYDROPNEUMATIC Booster Pump WITH FLOW SWITCH with pressure vessel (AGINST GRAVITY bottom to top flow) with both side Sensor operations (60ltr vessel) with both side Sensor operations- A) 3CUM PER HR. B) HEAD 40M, C) PHASE SINGLE PHASE, D) PROTECTION IP55, E) MONOBLOCK TYPE F) WITH VALVE STATION
131 |  | 1.5HP | 1.5HP | Nos. | 0.000 | .00
132 | B | WATER DRAIN PIPES | WATER DRAIN PIPES
133 | 1.00 | Supply, Laying , Testing Commissioning of CI (Cast Iron) CLASS Pipes Conforming to IS 3114 1994 and Fittings Conforming to IS 1538 (1993), Cutting the Pipes to required Lengths, Laying in position to required Grade Level , Jointing , Making holes , Pockets , chases in. | Supply, Laying , Testing Commissioning of CI (Cast Iron) CLASS Pipes Conforming to IS 3114 1994 and Fittings Conforming to IS 1538 (1993), Cutting the Pipes to required Lengths, Laying in position to required Grade Level , Jointing , Making holes , Pockets , chases in.
134 | a | 150mm dia | 150mm dia | Rmt | 0.000 | .00
135 | b | 100mm dia | 100mm dia | Rmt | 25.000 |  |  | 23.5 |  | 23.5
136 | c | 75mm dia | 75mm dia | Rmt | 18.000 |  |  | 15.75 |  | 15.75
137 | 2.00 | PVC Plastic Pipe , Schedule 40,80,120 ( ASTM D1785 ) | PVC Plastic Pipe , Schedule 40,80,120 ( ASTM D1785 )
138 | a | Drain for ac line | Drain for ac line | Rmt | 0.000 | .00
139 | b | Company Make - Prince , Finolex | Company Make - Prince , Finolex | Rmt | 0.000 | .00
140 | c | Company Make - Prince , Finolex | Company Make - Prince , Finolex | Rmt | 0.000 | .00
141 | d | Company Make - Prince , Finolex | Company Make - Prince , Finolex | Rmt | 0.000 | .00
142 | e | Company Make - Prince, Finolex (Basement Suspended Pipe) | Company Make - Prince, Finolex (Basement Suspended Pipe) | Rmt | 0.000 | .00
143 | f | Drainage Exacavation SITC of 150mm (Underground) PVC Waste Pipe Make Prince Finolex | Drainage Exacavation SITC of 150mm (Underground) PVC Waste Pipe Make Prince Finolex | Rmt | 0.000 | .00
144 | 3.00 | UPVC Plastic Pipe , Schedule 40,80,120 (ASTM D1785 ) | UPVC Plastic Pipe , Schedule 40,80,120 (ASTM D1785 )
145 | a | Company Make - Prince , Finolex | Company Make - Prince , Finolex | Rmt | 0.000 | .00
146 | b | Company Make - Prince , Finolex | Company Make - Prince , Finolex | Rmt | 0.000 | .00
147 | c | Company Make - Prince , Finolex | Company Make - Prince , Finolex | Rmt | 0.000 | .00
148 | d | Company Make - Prince , Finolex | Company Make - Prince , Finolex | Rmt | 0.000 | .00
149 | C | CHAMBER GRATING | CHAMBER GRATING
150 | 1.00 | Constructing Inspection chamber in 100mm thick Brick Wall, WATER PROOFING with Plaster. TILE EXTRA TO BE PAID | Constructing Inspection chamber in 100mm thick Brick Wall, WATER PROOFING with Plaster. TILE EXTRA TO BE PAID
151 | a | 300mm x 300mm | 300mm x 300mm | Nos. | 0.000 | .00
152 | b | 450mm x 450mm | 450mm x 450mm | Nos. | 0.000 | .00
153 | c | 450mm x 900mm (with Excavation, C.I. Cover frame) | 450mm x 900mm (with Excavation, C.I. Cover frame) | Nos. | 0.000 | .00
154 | 2.00 | Constructing Gully trap in 100mm thick Brick Wall with Plaster wih top cover. | Constructing Gully trap in 100mm thick Brick Wall with Plaster wih top cover.
155 | a | 300mm x 300mm | 300mm x 300mm | Nos. | 0.000 | .00
156 | 3.00 | Providing Fixing 20mm heavy quality SS Grating along with Perforated Mesh Angle Frame as per Size , Drawings. Weight not more than 60kg. Rate inclusive of chamber construction | Providing Fixing 20mm heavy quality SS Grating along with Perforated Mesh Angle Frame as per Size , Drawings. Weight not more than 60kg. Rate inclusive of chamber construction
157 | 3.01 | 200mm width | 200mm width
158 | a | 900mm X 200mm with SS Perforated Jali. (Grating Set) | 900mm X 200mm with SS Perforated Jali. (Grating Set) | Nos. | 0.000 | .00
159 | b | 600mm X 200mm with SS Perforated Jali. (Grating Set) | 600mm X 200mm with SS Perforated Jali. (Grating Set) | Nos. | 0.000 | .00
160 | c | 300mm X 200mm with SS Perforated Jali. (Grating Set) | 300mm X 200mm with SS Perforated Jali. (Grating Set) | Nos. | 0.000 | .00
161 | d | 200mm X 200mm with SS Perforated Jali. (Grating Set) | 200mm X 200mm with SS Perforated Jali. (Grating Set) | Nos. | 9.000 | 49,500.00 | 9 |  |  | 9
162 | 3.02 | 300mm width | 300mm width
163 | a | 900mm X 300mm with SS Perforated Jali. (Grating Set) | 900mm X 300mm with SS Perforated Jali. (Grating Set) | Nos. | 0.000 | .00
164 | b | 600mm X 300mm with SS Perforated Jali. (Grating Set) | 600mm X 300mm with SS Perforated Jali. (Grating Set) | Nos. | 0.000 | .00
165 | c | 300mm X 300mm with SS Perforated Jali. (Grating Set) | 300mm X 300mm with SS Perforated Jali. (Grating Set) | Nos. | 6.000 |  | 6 |  |  | 6
166 | d | 200mm X 300mm with SS Perforated Jali. (Grating Set) | 200mm X 300mm with SS Perforated Jali. (Grating Set) | Nos. | 0.000 | .00
167 | 3.03 | 450mm width | 450mm width
168 | a | 600mm X 450mm with SS Perforated Jali. (Grating Set) | 600mm X 450mm with SS Perforated Jali. (Grating Set) | Nos. | 0.000 | .00
169 | b | 450mm X 450mm with SS Perforated Jali. (Grating Set) | 450mm X 450mm with SS Perforated Jali. (Grating Set) | Nos. | 1.000 | 8,500.00 | 1 |  |  | 1
170 | c | 300mm X 450mm with SS Perforated Jali. (Grating Set) | 300mm X 450mm with SS Perforated Jali. (Grating Set) | Nos. | 0.000 | .00
171 | d | 200mm X 450mm with SS Perforated Jali. (Grating Set) | 200mm X 450mm with SS Perforated Jali. (Grating Set) | Nos. | 0.000 | .00
172 | 3.04 | 1200mm X 200mm with SS Perforated Jali. (Grating Set) | 1200mm X 200mm with SS Perforated Jali. (Grating Set) | Nos. | 1.000 | 16,500.00 | 1 |  |  | 1
173 | 4.00 | Providing Fixing 25 x 25 x 3mm thick SS Angle Frame for open drains. As per Size , Drawings. Ready to receive kota. | Providing Fixing 25 x 25 x 3mm thick SS Angle Frame for open drains. As per Size , Drawings. Ready to receive kota.
174 | 4.01 | 560mm X upto 125mm | 560mm X upto 125mm | Nos. | 0.000 | .00
175 | 4.02 | 560mm X from 130mm upto 200mm | 560mm X from 130mm upto 200mm | Nos. | 0.000 | .00
176 | 4.03 | 560mm X from 205mm upto 300mm | 560mm X from 205mm upto 300mm | Nos. | 0.000 | .00
177 | 4.04 | 200mm X 200mm | 200mm X 200mm | Nos. | 0.000 | .00
178 | 5.00 | Fixing of Portable SS grease trap 3 bowl sink as per drg. | Fixing of Portable SS grease trap 3 bowl sink as per drg. | Nos. | 1.000 |  | 1 |  |  | 1
179 | 5.01 | Bush for portable grease trap | Bush for portable grease trap | Nos. | 2.000 |  | 2 |  |  | 2
180 | 6.00 | Construction of grease trap with SS cover (2 -6 x 3 -6 x upto 3 -0 deep) - inside the store as per drawing. Rate includes SS angles of 50 x 50 x 6mm as frame; SS cover on frame made by 50 x 50 SS Pipes @ maximum 15 c c, covered with SS Sheet. Inclusive of fabricated SS T sections made as per detailed drawings (3mm thick) for mounting grease trap partitions. Internal tiling plaster to be paid seperately. | Construction of grease trap with SS cover (2 -6 x 3 -6 x upto 3 -0 deep) - inside the store as per drawing. Rate includes SS angles of 50 x 50 x 6mm as frame; SS cover on frame made by 50 x 50 SS Pipes @ maximum 15 c c, covered with SS Sheet. Inclusive of fabricated SS T sections made as per detailed drawings (3mm thick) for mounting grease trap partitions. Internal tiling plaster to be paid seperately. | Nos. | 0.000 | .00
181 | 7.00 | Construction of grease trap with SS cover (2 -6 x 3 -6 x upto 3 -0 deep) - outside the store as per drawing. Rate includes MS angles of 50 x 50 x 6mm as frame; MS cover on frame made by 50 x 50 MS Pipes @ maximum 15 c c, covered with MS chequered plate. Inclusive of fabricated MS T sections made as per detailed drawings (3mm thick) for mounting grease trap partitions. Internal tiling plaster to be paid seperately. | Construction of grease trap with SS cover (2 -6 x 3 -6 x upto 3 -0 deep) - outside the store as per drawing. Rate includes MS angles of 50 x 50 x 6mm as frame; MS cover on frame made by 50 x 50 MS Pipes @ maximum 15 c c, covered with MS chequered plate. Inclusive of fabricated MS T sections made as per detailed drawings (3mm thick) for mounting grease trap partitions. Internal tiling plaster to be paid seperately. | Nos. | 0.000 | .00
182 | D | NAHNI TRAP | NAHNI TRAP
183 | 1.00 | Supply, Laying, Testing Commissioning of Approved CI (Cast Iron) CLASS pipes Nahani - Floor Trap with Approved Make leavy Duty round or Square SS Grating etc. Complete. | Supply, Laying, Testing Commissioning of Approved CI (Cast Iron) CLASS pipes Nahani - Floor Trap with Approved Make leavy Duty round or Square SS Grating etc. Complete. | Nos. | 0.000 | .00
184 | 2.00 | Supply, Laying, Testing Commissioning of Approved SS Nahani TRAP WITH Floor Trap COCKROACH JAALI with Approved Make heavy duty round or Square Grating etc. Complete. | Supply, Laying, Testing Commissioning of Approved SS Nahani TRAP WITH Floor Trap COCKROACH JAALI with Approved Make heavy duty round or Square Grating etc. Complete. | Nos. | 0.000 | .00
185 | E | CP FIXTURES BRASS VALVES -Jaquar (only continental series) | CP FIXTURES BRASS VALVES -Jaquar (only continental series)
186 | 1.00 | P F Angle Cock. | P F Angle Cock. | Nos. | 20.000 |  | 18 |  |  | 18
187 | 2.00 | P F Sink Mixer, Swinging Casted Spout. | P F Sink Mixer, Swinging Casted Spout. | Nos. | 4.000 |  | 2 |  |  | 2
188 | 3.00 | P F Sink Mixer, Swinging Casted Spout. | P F Sink Mixer, Swinging Casted Spout. | Nos. | 3.000 |  | 1 |  |  | 1
189 | 4.00 | P F Long Neck Bib Cock with wall Flange. Make- Jaquar | P F Long Neck Bib Cock with wall Flange. Make- Jaquar | Nos. | 5.000 |  | 1 |  |  | 1
190 | 5.00 | Providing Fixing Bib Cock chrome finish with wall Flange. | Providing Fixing Bib Cock chrome finish with wall Flange. | Nos. | 4.000 | 8,800.00 | 2 |  |  | 2
191 | 6.00 | P F Sink Pillar cock with swinging casted spout. | P F Sink Pillar cock with swinging casted spout. | Nos. | 4.000 | 8,000.00 | 9 |  |  | 9
192 | 7.00 | P F Fixed Sink Cock. | P F Fixed Sink Cock. | Nos. | 3.000 | 7,200.00
193 | 8.00 | P F Tall Pillar Cock for counter flush basin. | P F Tall Pillar Cock for counter flush basin. | Nos. | 3.000
194 | 9.00 | P F Pneumatic push cock. | P F Pneumatic push cock. | Nos. | 1.000
195 | 10.00 | Foot Paddle Operated Faucet. (Below Hand Wash) | Foot Paddle Operated Faucet. (Below Hand Wash) | Nos. | 2.000 | 8,400.00 | 2 |  |  | 2
196 | 11.00 | Dual press | Dual press
197 |  | P F open Flush valve. | P F open Flush valve. | Nos. | 0.000 | .00
198 |  | P F open Flush tank. | P F open Flush tank. | Nos. | 0.000 | .00
199 | 12.00 | P F CP Health Faucet with 1m long CP Flexible Tube with wall Hook. Make- Jaquar | P F CP Health Faucet with 1m long CP Flexible Tube with wall Hook. Make- Jaquar | Nos. | 0.000 | .00
200 | 13.00 | P F 2 in 1 bib cock in washrooms for mounting Health Faucet. Health faucet to be paid for separetly. | P F 2 in 1 bib cock in washrooms for mounting Health Faucet. Health faucet to be paid for separetly. | Nos. | 0.000 | .00
201 | 14.00 | Providing fixing 32mm CP finished Bottle Trap with wall flanges. | Providing fixing 32mm CP finished Bottle Trap with wall flanges. | Nos. | 10.000
202 | 15.00 | Providing Waste Coupling 32mm size full thread waste coupling to be use. | Providing Waste Coupling 32mm size full thread waste coupling to be use. | Nos. | 10.000
203 | 16.00 | Providing Fixing Ball Valve ISI mark. (For Inlet) | Providing Fixing Ball Valve ISI mark. (For Inlet)
204 | a | 15mm dia | 15mm dia | Nos. | 0.000 | .00
205 | b | 20mm dia | 20mm dia | Nos. | 0.000 | .00
206 | c | 25mm dia | 25mm dia | Nos. | 2.000
207 | d | 32mm dia | 32mm dia | Nos. | 2.000 |  | 4 |  |  | 4
208 | e | 40mm dia | 40mm dia | Nos. | 0.000 | .00
209 | 16.02 | Providing Fixing Ball Valve ISI mark. (For Inlet) | Providing Fixing Ball Valve ISI mark. (For Inlet)
210 | a | 15mm dia | 15mm dia | Nos. | 0.000 | .00
211 | b | 20mm dia | 20mm dia | Nos. | 0.000 | .00
212 | c | 25mm dia | 25mm dia | Nos. | 0.000 | .00
213 | d | 32mm dia | 32mm dia | Nos. | 0.000 | .00
214 | e | 40mm dia | 40mm dia | Nos. | 0.000 | .00
215 | 17.00 | Providing Fixing Brass Non Return Vavles of ISI mark. Rates are for BRASS valves | Providing Fixing Brass Non Return Vavles of ISI mark. Rates are for BRASS valves
216 | a | 25mm | 25mm | Nos | 0.000 | .00
217 | b | 32mm | 32mm | Nos | 0.000 | .00
218 | c | 40mm | 40mm | Nos. | 0.000 | .00
219 | 18.00 | P F ball valve below 3 bowl sink veg pre RO sink - 75mm dia | P F ball valve below 3 bowl sink veg pre RO sink - 75mm dia | Nos. | 5.000 | 21,500.00 | 3 |  |  | 3
220 | E | ACCESSORIES MISCELLANEOUS | ACCESSORIES MISCELLANEOUS
221 | 1.00 | Providing Flexible water pipe to connect Angle Valve to faucet | Providing Flexible water pipe to connect Angle Valve to faucet | Nos. | 20.000 |  | 18 |  |  | 18
222 | 2.00 | Pre rinse spray valve spray. | Pre rinse spray valve spray. | Nos. | 1.000
223 | 3.00 | Providing water level Indicator for In Raw tank RO water tank with gauge Glass Cock. In BOH Area. | Providing water level Indicator for In Raw tank RO water tank with gauge Glass Cock. In BOH Area. | Nos. | 1.000
224 | 4.00 | P F water level Indicator on terrace water tank by means of a transparent clear tube fixed along height of the water tank hence making water level visible | P F water level Indicator on terrace water tank by means of a transparent clear tube fixed along height of the water tank hence making water level visible | Nos. | 0.000 | .00
225 | 5.00 | P F flexible PVC waste pipe on wash basin sink drains | P F flexible PVC waste pipe on wash basin sink drains | Nos. | 10.000
226 | 6.00 | Installation of plumbing fixtures kitchen equipment provided by client with new hardware as required- PLUMBING SCOPE | Installation of plumbing fixtures kitchen equipment provided by client with new hardware as required- PLUMBING SCOPE | Job | 1.000 |  | 1 |  |  | 1
227 | F | BOILERS GEYSERS | BOILERS GEYSERS
228 | 1.00 | Providing Supplying boiler with Mounting Bolts etc. | Providing Supplying boiler with Mounting Bolts etc.
229 | a | 35 Liter | 35 Liter | Nos. | 1.000 |  | 1 |  |  | 1
230 | b | 25 Liter | 25 Liter | Nos. | 0.000 | .00
231 | 2.00 | Geyser Storage | Geyser Storage
232 | b | Providing Supplying 6 Liters Geyser with Mounting Bolts etc. | Providing Supplying 6 Liters Geyser with Mounting Bolts etc. | Nos. | 2.000 |  | 2 |  |  | 2
233 | G | SANITARYWARE | SANITARYWARE
234 | 1.00 | P F Wash Basin as per specs | P F Wash Basin as per specs
235 |  | P F Counter top Basin, Make Size- PARRYWARE as per drawing | P F Counter top Basin, Make Size- PARRYWARE as per drawing | Nos. | 0.000 | .00
236 |  | P F Under Counter Basin, Make size- PARRYWARE as per drawing | P F Under Counter Basin, Make size- PARRYWARE as per drawing | Nos. | 0.000 | .00
237 |  | Corner Wash Basin | Corner Wash Basin | Nos. | 0.000 | .00
238 | 2.0 | P F Wall hung EWC with Seat Cover Make size- PARRYWARE as per drawing | P F Wall hung EWC with Seat Cover Make size- PARRYWARE as per drawing | Nos. | 0.000 | .00
239 | 3.0 | P F Wall Urinal with brackets. Make size- PARRYWARE as per drawing | P F Wall Urinal with brackets. Make size- PARRYWARE as per drawing | Nos. | 0.000 | .00
240 | 4.0 | P F pressomatic type flush valve for urinals | P F pressomatic type flush valve for urinals | Nos. | 0.000 | .00

## NT Items
Sr No. | Item Name | UOM | Qty | Rate | Amount
1 | P F temporary flex as per details above with backing frame of wood MS Aluminium sections as required. | Sq.Ft. | 1200 | 75 | 90000
2 | P&F of Corian patta on ply panelling above POS counter on both side. | Sq.Ft. | 29.5 | 1550 | 45725
3 | P&F of plywood frame for TV near POS counter | Nos. | 1 | 8500 | 8500
4 | P&F of SS hood gap covering | Nos. | 1 | 8500 | 8500
5 | Constructing Inspection chamber in 100mm thick Brick Wall, WATER PROOFING with Plaster. TILE EXTRA TO BE PAID
| 450mm x 450mm | Nos. | 1 | 6500 | 6500
| 300mm x 300mm | Nos. | 6 | 4500 | 27000
| 1200mm x 200mm | Nos. | 1 | 9500 | 9500
6 | Installation of Water Tank & Pressure Pump
| Water Tank | Nos. | 1 | 4500 | 4500
| Pressure Pump | Nos. | 1 | 3500 | 3500
| Total |  |  |  | 203725