## Designer scope (12)
Structure Consultancy
PROJECT: | Delhi T1 - Dominos
Sr No. | Description | Area | QTY
1 | Description of Work: | (Sqm) | 65.75
HVAC Equipment & False Ceiling Support
1.1 | Mounting platform above the outlets or hanging Structure
2 | Structural design work :
2.1 | Obtaining the equipment details such as dimensions and weights (Static & dynamic) from the MEP team
2.2 | Obtain the space planning for the platform from the MEP / Architect team
2.3 | Calculation of equipment loads, dead load and live loads on the platform and submission to client for approval
2.4 | Preparation of STAAD model for each of the platforms and analyse the structure, including design of the elements
2.5 | Calculation of reactions on the floor slab below and check the floor slab for its adequacy to cater for the additional loads from the platforms
2.6 | Preparation of structural GA drawings and submit for approval to client along with the staad model
2.7 | Approve the shop fabrication drawings to be submitted by the fabricator.
2.8 | Obtaining input data from HVAC Equipment supplier regarding the size and weights
2.9 | Space planning of the platform with respect to OSHA standards for safe operation and maintenance of the equipment
2.1 | Staad model of the existing mezzanine floor slab to be provided by client - TFS to coordinate with DIAL
2.11 | Preparation of As-built drawing of the mezzanine floor
2.12 | Site visits to obtain if require
2.13 | Structural Details to be approved & certificate to be submit
Prepartion of BOQ & tender dcoket