## Price Comparison
|  | RFQ No: R2114 COST COMPARISON REPORT | RFQ No: R2114 COST COMPARISON REPORT | RFQ No: R2114 COST COMPARISON REPORT | Comp. Date : 29/10/2024 | Comp. Date : 29/10/2024 | Comp. Date : 29/10/2024 | Vendor Name : FALLOW DEZIENCE TREE LLP (RV232411636)
|  | RFQ No: R2114 COST COMPARISON REPORT | RFQ No: R2114 COST COMPARISON REPORT | RFQ No: R2114 COST COMPARISON REPORT | RFQ #: R2114 | RFQ #: R2114 | RFQ #: R2114 | Contact Name : Khursheed Ahmad/Jasmine Grover
|  | RFQ No: R2114 COST COMPARISON REPORT | RFQ No: R2114 COST COMPARISON REPORT | RFQ No: R2114 COST COMPARISON REPORT | RFQ Date : 24/10/2024 11:44:55 | RFQ Date : 24/10/2024 11:44:55 | RFQ Date : 24/10/2024 11:44:55 | Vendor City :
|  | RFQ No: R2114 COST COMPARISON REPORT | RFQ No: R2114 COST COMPARISON REPORT | RFQ No: R2114 COST COMPARISON REPORT | BCD Date : 30/10/2024 23:00:00 | BCD Date : 30/10/2024 23:00:00 | BCD Date : 30/10/2024 23:00:00 | Telephone # :
|  | RFQ No: R2114 COST COMPARISON REPORT | RFQ No: R2114 COST COMPARISON REPORT | RFQ No: R2114 COST COMPARISON REPORT |  |  |  | Mobile # :
PR Number : GMR-2425-00883 | PR Number : GMR-2425-00883 | PR Number : GMR-2425-00883 | PR Number : GMR-2425-00883 | PR Number : GMR-2425-00883 | PR Number : GMR-2425-00883 | PR Number : GMR-2425-00883 | PR Number : GMR-2425-00883 | Email : accounts@fallowdezience.com
Package / RFQ Name : PR for NT itemsHYD_FF25b_Creamstone. | Package / RFQ Name : PR for NT itemsHYD_FF25b_Creamstone. | Package / RFQ Name : PR for NT itemsHYD_FF25b_Creamstone. | Package / RFQ Name : PR for NT itemsHYD_FF25b_Creamstone. | Package / RFQ Name : PR for NT itemsHYD_FF25b_Creamstone. | Package / RFQ Name : PR for NT itemsHYD_FF25b_Creamstone. | Package / RFQ Name : PR for NT itemsHYD_FF25b_Creamstone. | Package / RFQ Name : PR for NT itemsHYD_FF25b_Creamstone. | Round # : 1 (RFQ)
Buyer : Pushpak Mahesh Shewale / Technical : / Approver : | Buyer : Pushpak Mahesh Shewale / Technical : / Approver : | Buyer : Pushpak Mahesh Shewale / Technical : / Approver : | Buyer : Pushpak Mahesh Shewale / Technical : / Approver : | Buyer : Pushpak Mahesh Shewale / Technical : / Approver : | Buyer : Pushpak Mahesh Shewale / Technical : / Approver : | Buyer : Pushpak Mahesh Shewale / Technical : / Approver : | Buyer : Pushpak Mahesh Shewale / Technical : / Approver : | Quotation Date : |  |  | Quotation Validity Date :
Comp. # : 1 | Comp. # : 1 | Comp. # : 1 | Comp. # : 1 | Comp. # : 1 | Currency :INR | Currency :INR | Currency :INR | Buyer Remark :
Comp. # : 1 | Comp. # : 1 | Comp. # : 1 | Comp. # : 1 | Comp. # : 1 | BUDGET PRICE : | .00 |  | Quote Currency : INR
# | Item Code | Item Description | Unit | Qty | Last PO Details | Lowest Unit Rate | Lowest Vendor | First Bid | Disc % | GST % | Technical | Unit Price | Total
1 |  | Interior Work | NOS | 1.00 |  | 1437261.66 | FALLOW DEZIENCE TREE LLP | 1437261.66 | 0.00 | 18.00 |  | 1,437,261.66 | 1,437,261.66
Item Total | [8 empty] | .00 | 258,707.10 |  |  | 1,437,261.66
Discount Total Value | [7 empty] | Grand Dis. Amt | .00 |  |  |  | .00
GST Total Amount | [12 empty] | 258,707.10
Net Landed Cost | [11 empty] | INR | 1,695,968.76
Vendor Status | [7 empty] | Round # : 1 (RFQ) | Round # : 1 (RFQ)
Sr No. | Vendor Code | Vendor Name | [5 empty] | Status | Remarks
1 | RV232411636 | FALLOW DEZIENCE TREE LLP | [5 empty] | Participate

## BOQ Price Bid
|  | RFQ No: R2114 COST COMPARISON REPORT | RFQ No: R2114 COST COMPARISON REPORT | Comp. Date : 29/10/2024 | Comp. Date : 29/10/2024 | Comp. Date : 29/10/2024 | Vendor Name : FALLOW DEZIENCE TREE LLP | Vendor Name : FALLOW DEZIENCE TREE LLP
|  | RFQ No: R2114 COST COMPARISON REPORT | RFQ No: R2114 COST COMPARISON REPORT | RFQ #: R2114 | RFQ #: R2114 | RFQ #: R2114 | Contact Name : Khursheed Ahmad/Jasmine Grover | Contact Name : Khursheed Ahmad/Jasmine Grover
|  | RFQ No: R2114 COST COMPARISON REPORT | RFQ No: R2114 COST COMPARISON REPORT | RFQ Date : 24/10/2024 11:44:55 | RFQ Date : 24/10/2024 11:44:55 | RFQ Date : 24/10/2024 11:44:55 | Vendor City : | Vendor City :
|  | RFQ No: R2114 COST COMPARISON REPORT | RFQ No: R2114 COST COMPARISON REPORT | BCD Date : 30/10/2024 23:00:00 | BCD Date : 30/10/2024 23:00:00 | BCD Date : 30/10/2024 23:00:00 | Telephone # : | Telephone # :
|  | RFQ No: R2114 COST COMPARISON REPORT | RFQ No: R2114 COST COMPARISON REPORT |  |  |  | Mobile # : | Mobile # :
PR Number : GMR-2425-00883 | PR Number : GMR-2425-00883 | PR Number : GMR-2425-00883 | PR Number : GMR-2425-00883 | PR Number : GMR-2425-00883 | PR Number : GMR-2425-00883 | PR Number : GMR-2425-00883 | Email : accounts@fallowdezience.com | Email : accounts@fallowdezience.com
Package / RFQ Name : PR for NT itemsHYD_FF25b_Creamstone. | Package / RFQ Name : PR for NT itemsHYD_FF25b_Creamstone. | Package / RFQ Name : PR for NT itemsHYD_FF25b_Creamstone. | Package / RFQ Name : PR for NT itemsHYD_FF25b_Creamstone. | Package / RFQ Name : PR for NT itemsHYD_FF25b_Creamstone. | Package / RFQ Name : PR for NT itemsHYD_FF25b_Creamstone. | Package / RFQ Name : PR for NT itemsHYD_FF25b_Creamstone. | Round # : 1 (RFQ) | Round # : 1 (RFQ)
Buyer : Pushpak Mahesh Shewale | Buyer : Pushpak Mahesh Shewale | Buyer : Pushpak Mahesh Shewale | Buyer : Pushpak Mahesh Shewale | Buyer : Pushpak Mahesh Shewale | Buyer : Pushpak Mahesh Shewale | Buyer : Pushpak Mahesh Shewale | Techanical Score : | Techanical Score :
Comp. # : 1 | Comp. # : 1 | Comp. # : 1 | Comp. # : 1 | Currency :INR | Currency :INR | Currency :INR | Quotation Date : | Quotation Date :
Comp. # : 1 | Comp. # : 1 | Comp. # : 1 | Comp. # : 1 | BUDGET PRICE :.00 | BUDGET PRICE :.00 | BUDGET PRICE :.00 | Quotation Validity Date : | Quotation Validity Date : |  |  | Final - 11.12.2024
Sr No. | Item Code | Item Name | Item Description | UOM | Qty | Minimum Amount | Unit Price | Amount | FDT Remarks | Remarks - 21.11.2024 | Revised PR Amount
1 |  | Interior Work | Interior Work budget includes all interior work at site | NOS | 1 |  |  | 1474398.3993 |  |  | 1385994.3993
1 | 1 | Plaster Work | Plaster Work | SQFT | 884.04 | 88404 | 100 | 88404 | In BOQ ,Only Block work was considered . | Not agreed by TFS | 0
2 |  | BOH Main Wall | BOH Main Wall | [5 empty] | Plaster on block work was not considered .
3 |  | less Door | less Door | [5 empty] | Thus it was done to cover block work to make it plain surface .
4 |  | BOH Side Wall | BOH Side Wall
5 |  | less Door | less Door
6 |  | BOH Small Wall | BOH Small Wall
7 | 2 | Lintel Work | Lintel Work |  | 21.36 | 32040 | 1500 | 32040 | As per Civil work general pratcice standard thus on project team requirement , this jon had been done at site . | OK & Agreed by TFS | 32040
8 |  | BOH Main Wall | BOH Main Wall | RM | 0 | 0 | 0 | 0
9 |  | BOH Side Wall | BOH Side Wall
10 |  | BOH Small Wall | BOH Small Wall
11 | 3 | Screed upto 110mm - Floor Raised | Screed upto 110mm - Floor Raised | SQFT | 431.01 | 130134.85 | 301.93 | 130134.8493 | In BOQ , Rate was mentioned but qty was not considered . Rate was closed 3250 Sqm by puchase team . | OK & Agreed by TFS | 130134.8493
12 |  | BOH | BOH | [5 empty] | Besides it ,outlet level was 150 mm down in reference to airport level . Pic Attached .
13 |  | FOH | FOH | [5 empty] | Same information has been shared with TFS & GHIAL Team . For reference , Mail Screnshoot attached
14 | 4 | Bulhead Structure With MS Frame ( 50x50mm) With HDHMR Cladding | Bulhead Structure With MS Frame ( 50x50mm) With HDHMR Cladding | SQFT | 322.6 | 274210 | 850 | 274210 | As per architectural plan , Acrylic tube was to installed . Rates was provided to puchase as per BOQ Item ( Acrylic tube ) . These tubes require a base thus MS strcture was provided and claded with HMHMR . | OK & Agreed by TFS | 274210
15 |  | Right Side | Right Side
16 |  | Front Side | Front Side
17 |  | Left Side | Left Side
18 | 5 | Metal Ceiling (600x600) | Metal Ceiling (600x600) | SQFT | 184.42 | 95898.4 | 520 | 95898.4 | As per architectural plan ,It was mentioned in design and TFS Design team also confirm that they need metal ceiling while it was mentioned in BOQ . | OK & Agreed by TFS | 95898.4
19 |  | FOH | FOH |  | 89 | 0 | 0 | 0
20 |  | BOH | BOH |  | 95.42 | 0 | 0 | 0
21 | 6 | Providing and Cladding of approved shade and make of designer tile with the required adhasive for laying of tiles - Additional Cost as per approved By TFS - CNC Cut 3D Pattern with PU Paint - Cost Difference | Providing and Cladding of approved shade and make of designer tile with the required adhasive for laying of tiles - Additional Cost as per approved By TFS - CNC Cut 3D Pattern with PU Paint - Cost Difference | SQFT | 84.8 | 37736 | 445 | 37736 | Desingner tile was provided in 20 mm HDHMR 3D CNC Cut with PO Paint .For reference , mail attacted . | OK & Agreed by TFS | 37736
22 |  | RHS Wall Counter | RHS Wall Counter
23 |  | LHS Wall Counter | LHS Wall Counter
24 |  | Part -1 | Part -1
25 |  | Part -2 | Part -2
26 |  | Front Counter | Front Counter
27 |  | Part -1 | Part -1
28 |  | part -2 | part -2
29 |  | part -3 | part -3
30 |  | part -4 | part -4
31 | 7 | SS Skirting - 100 mm Height | SS Skirting - 100 mm Height | RM | 16.44 | 9453 | 575 | 9453 | As per site requirement . | OK & Agreed by TFS | 9453
32 |  | Left Side | Left Side
33 |  | Front Side | Front Side
34 |  | Right Side | Right Side
35 | 8 | OverHead Strorage with Shutter in ply over laminate | OverHead Strorage with Shutter in ply over laminate | SQFT | 62.64 | 115884 | 1850 | 115884 | As per design layout , It was the part of design but thus item was not considered in BOQ . | OK & Agreed by TFS | 115884
36 |  | BOH Wall | BOH Wall
37 | 9 | Black Laminate with HDHMR base | Black Laminate with HDHMR base | SQFT | 34.43 | 15493.5 | 450 | 15493.5 | As per architectural plan ,It was mentioned in design and TFS Design team also confirmed but it was not mentioned in BOQ . | OK & Agreed by TFS | 15493.5
38 |  | Front Face | Front Face
39 |  | Top Face | Top Face
40 |  | Bottom Face | Bottom Face
41 | 10 | Acrylic Rectangular Tube base cladding with PU Paint Finish | Acrylic Rectangular Tube base cladding with PU Paint Finish | SQFT | 256.61 | 166796.5 | 650 | 166796.5 | As per architectural plan ,It was mentioned in design and TFS Design team also confirmed but it was not mentioned in BOQ . Besides it , same information was provided to puchase team also . | OK & Agreed by TFS | 166796.5
42 |  | bulkhead area | bulkhead area
43 |  | left Side | left Side
44 |  | Front Side | Front Side
45 |  | Right Side | Right Side
46 | 12 | Wooden Rafter - 127x50 mm with profile light | Wooden Rafter - 127x50 mm with profile light | RM | 17.98 | 58614.8 | 3260 | 58614.8 | As per architectural plan ,It was mentioned in design and TFS Design team also confirmed but it was not mentioned in BOQ .Besides it , same information was provided to puchase team also . | OK & Agreed by TFS | 58614.8
47 |  | Rafter No -1 | Rafter No -1
48 |  | Rafter No -2 | Rafter No -2
49 |  | Rafter No -3 | Rafter No -3
50 |  | Rafter No -4 | Rafter No -4
51 |  | Rafter No -5 | Rafter No -5
52 |  | Rafter No -6 | Rafter No -6
53 |  | Rafter No -7 | Rafter No -7
54 | 13 | Door with frame and hardware | Door with frame and hardware | No | 2 | 65000 | 32500 | 65000 | As per architectural plan ,It was mentioned in design and TFS Design team also confirmed but it was not mentioned in BOQ .Besides it , same information was provided to puchase team also . | OK & Agreed by TFS | 65000
55 |  | BOH - 1000x2400 | BOH - 1000x2400
56 |  | FOH -900x2400 | FOH -900x2400
57 | 14 | Wall Tiles - FOH Wall 200X300 White Tile - Johnson | Wall Tiles - FOH Wall 200X300 White Tile - Johnson | SQFT | 446.93 | 122905.75 | 275 | 122905.75 | As per architectural plan ,It was mentioned in design and TFS Design team also confirmed but it was not mentioned in BOQ .Besides it , same information was provided to puchase team also . | OK & Agreed by TFS | 122905.75
58 |  | Wall -1 | Wall -1
59 |  | less Door | less Door
60 |  | Wall -2 | Wall -2
61 |  | less Door | less Door
62 |  | Wall -3 | Wall -3
63 |  | Wall -4 | Wall -4
64 | 15 | Guard Rail - 38 mm SS Pipe | Guard Rail - 38 mm SS Pipe | RM | 18.58 | 52953 | 2850 | 52953 | It had been done on Airport team requirment to fulfill safery noms . | OK & Agreed by TFS | 52953
65 |  | Left Side | Left Side
66 |  | Front Side | Front Side
67 |  | Right Side | Right Side
68 | 16 | MS Pillar Cladding with 12mm Sheet with Laminate | MS Pillar Cladding with 12mm Sheet with Laminate | SQFT | 29.97 | 13486.5 | 450 | 13486.5 | As per architectural plan ,It was mentioned in design and TFS Design team also confirmed but it was not mentioned in BOQ | OK & Agreed by TFS | 13486.5
69 |  | Laminate Cladding | Laminate Cladding
70 | 17 | MS Pillar Cladding with 12mm Sheet with Laminate | MS Pillar Cladding with 12mm Sheet with Laminate | SQFT | 47.53 | 16635.5 | 350 | 16635.5 |  | OK & Agreed by TFS | 16635.5
71 |  | Only cladding | Only cladding
72 | 18 | Linear Profile Light - Supply Installation | Linear Profile Light - Supply Installation | RM | 38.1 | 19050 | 500 | 19050 | As per architectural plan ,It was mentioned in design ( 12 mm Profile Light ) and TFS Design team also confirmed but it was not mentioned in BOQ | OK & Agreed by TFS | 19050
73 |  | Black Tile | Black Tile
74 |  | Counter | Counter
75 | 19 | Bottle Trap | Bottle Trap | Nos | 1 | 3600 | 3600 | 3600 |  | OK & Agreed by TFS | 3600
76 | 20 | Back Paneling - HDHMR - above MS Structure | Back Paneling - HDHMR - above MS Structure | SQM | 8.49 | 29715 | 3500 | 29715 |  | OK & Agreed by TFS | 29715
77 |  | Right Side | Right Side
78 |  | Front Side | Front Side
79 | 21 | Sprinkler Flexible Pipe - 1500mm | Sprinkler Flexible Pipe - 1500mm | Nos | 5 | 14250 | 2850 | 14250 | As per project team , it was provided , Before providing ratewas shared on mail . For reference , Mail Attached . | OK & Agreed by TFS | 14250
80 | 22 | Sink Mixture | Sink Mixture | Nos | 2 | 7000 | 3500 | 7000 | As per Site requirement | OK & Agreed by TFS | 7000
81 | 23 | Supply, Installation, Testing, and Commissioning of Addressable Type Monitor Module | Supply, Installation, Testing, and Commissioning of Addressable Type Monitor Module
82 |  | Monitor Module | Monitor Module | Nos | 1 | 9500 | 9500 | 9500 | As per Fire safety norms installed on recommnedation of project team not mentioned in BOQ | OK & Agreed by TFS | 9500
83 | 24 | Supply, Installation, Testing, and Commissioning of Addressable Type Control Module for shutting down FCU’s, and magnetic fire door holders. Elevator recall, fire damper, pressurization fan, strobes etc | Supply, Installation, Testing, and Commissioning of Addressable Type Control Module for shutting down FCU’s, and magnetic fire door holders. Elevator recall, fire damper, pressurization fan, strobes etc
84 |  | Control Module | Control Module | Nos | 1 | 7500 | 7500 | 7500 | As per Fire safety norms installed on recommnedation of project team not mentioned in BOQ | OK & Agreed by TFS | 7500
85 | 25 | Supply, Installation, Testing, and Commissioning of Addressable Type Isolation Module | Supply, Installation, Testing, and Commissioning of Addressable Type Isolation Module
86 |  | Isolation Module | Isolation Module | Nos | 1 | 7500 | 7500 | 7500 | As per Fire safety norms installed on recommnedation of project team not mentioned in BOQ | OK & Agreed by TFS | 7500
87 |  | FIRE ALARM SYSTEM - CABLING | FIRE ALARM SYSTEM - CABLING
88 | 26 | Supply and surface laying of armoured FRLS twisted pair, shielded cable. | Supply and surface laying of armoured FRLS twisted pair, shielded cable.
89 |  | 2 core 1.5 Sqmm | 2 core 1.5 Sqmm | Mtr | 220 | 33000 | 150 | 33000 | As per Fire safety norms installed on recommnedation of project team not mentioned in BOQ | OK & Agreed by TFS | 33000
90 | 27 | Paint Work | Paint Work | SFT | 412.64 | 0 | 90 | 37137.6 |  | OK & Agreed by TFS | 37137.6
91 |  | Bulkhead -FOH back side | Bulkhead -FOH back side | [5 empty] | As per architectural plan ,It was mentioned in design and TFS Design team also confirmed but it was not mentioned in BOQ
92 |  | FOH - Gypsum Ceiling | FOH - Gypsum Ceiling
93 |  | MS Pillar Cladding | MS Pillar Cladding
94 | 28 | HANGING LIGHT - Installation Only | HANGING LIGHT - Installation Only | Nos. | 5 | 3000 | 600 | 3000 | This job was not mentioned in BOQ . FDT provided manpower to install these light . ( Installation + Wiring Connection + Testing ) | OK & Agreed by TFS | 3000
95 | 29 | DOWN LIGHT COB LIGHT - Installation Only | DOWN LIGHT COB LIGHT - Installation Only | Nos. | 10 | 7500 | 750 | 7500 |  | OK & Agreed by TFS | 7500