## Summary
TFS_BEHROR
SUMMARY OF ELECTRICAL & NETWORK WORKS-INTERNAL OUTLETS
DATE: DEC.27, 2022
SR. NO. | DESCRIPTION | SUPPLY AMOUNT (RS.) | INST AMOUNT (RS.)
1 | ELECTRICAL WORKS
A | UPS | 270000 | 10000
B | DISTRIBUTION BOARDS AND SWITCHGEARS | 130500 | 22500
C | UNDERFLOOR TRUNKING, RACEWAY & JUNCTION BOXES | 8000 | 2000
D | CABLES, MAINS, SUB MAINS AND CABLE TRAYS | 308400 | 71030
E | CIRCUIT CUM POINT WIRING | 614167.5 | 160360
F | SWITCHES AND SOCKETS | 127300 | 28350
G | INSTALLATION OF LIGHTING FIXTURES |  | 21300
H | TEMPORARY LIGHTING & POWER ARRANGEMENTS | 50000 | 25000
I | MISCELLANEOUS+ SAFETY EQUIPMENT | 0 | 0
J | LIASONING WORKS |  | 0
K | EARTHING INSTALLATION | 10450 | 2090
2 | NETWORK WORKS
A. | TELEPHONE & DATA SYSTEM | 125750 | 56400
| GRAND TOTAL | 1644567.5 | 399030
| TOTAL (SUPPLY + INST) | 2043597.5
| Tax |  | 367847.55
| TOTAL WITH TAX |  | 2411445.05

## Electrical Works
TFS_BEHROR
BOQ FOR ELECTRICAL WORKS-INTERNAL OUTLETS
As Actual
Item No. | Description | PO Qty | Unit | NOODLE | CAFECCINO | GIANI'S | ROLL KING | DHABA | TEA CONCEPT | BOH | BIKANERWALA | Total executed Qty | Supply |  | Installation | Total
[13 empty] | Rate | Amount | Rate | Amount
A | UPS
1 | Supply, installation, testing and commissioning of 1 x 10 KVA/kW, Output PF at unity, rack/Floor mount (at 40 Deg Temp.), on-line UPS system with 3 phase Input and 3 phase Output with +/- 1% regulation, true sine wave, total harmonic distortion less than 5% max. DC to AC efficiency continuous duty, IGBT based PWM with instantaneous sine wave control inverter with manual by pass mode (Static Change Over Switch) and overall efficiency better than 95% with excellent voltage and battery regulation all complete as required specification. UPS Should have digital display for showing all parameters. Work to be completed as per final direction and approval of the Consultants. | 1 | Nos. | [8 empty] | 1 | 185000 | 185000 | 5000 | 5000
2 | Supply, Installation, Testing and Commissioning of 1 sets of Sealed maintenance free Valve Regulated Lead Acid batteries (SMF-VRLA) with each set having 30 minutes back up time at 9.7kW Load. The Each battery shall be of 12Volts. The rate shall also include supply and installation of suitable rating Battery Bank Isolators installed in open type Sheet Steel rack and suitable nyvin cable for connectivity between UPS and battery set. The batteries shall be open type vertical rack mounting with suitable accessories. Before supply of these batteries the detail arrangement drawing is to be prepared by the vendor and the same should be get approved from the consultants and as per final direction and approval of the Consultant. | 1 | Nos. | [8 empty] | 1 | 85000 | 85000 | 5000 | 5000
| TOTAL CARRIED TO SUMMARY | [12 empty] | 270000 |  | 10000
B | DISTRIBUTION BOARDS AND SWITCHGEARS
II | DISTRIBUTION BOARDS
Supply, installation, testing & commissioning of Distribution Boards surface / flush mounted with Double door containing MCB/ELMCB as incomer and SPMCB as outgoing. All MCBs are of 10KA breaking capacity and ELMCBs/RCCB should be of 30mA/100/300 mA sensivity. The DB shall have appropriate no. of top and bottom knock outs for outgoing circuits and shall be complete with necessary busbars, interconnection terminals and earth studs. All terminations in DB shall be complete with ferulling, dressing and all circuits shall be properly labeled with PVC strip (sticker type) having identification as per the final approval of Consultant. For UPS DB MCB shall be 'D' type and other MCBs shall be 'C' category for lighting and raw power DB.
1 | TPN UPSDB | 1
8 Way TPN DB
Incomer:
40 A FP MCB-1 NOS
32A DP RCCB 100mA-3 NOS
Outgoings : 20/32A SP MCB, 'C' Type – 24 Nos
| DHABA |  | NOS | [8 empty] | 1
| NODDLES WOK |  | NOS | [8 empty] | 1
[12 empty] | 2 | 18500 | 37000 | 3000 | 6000
2 | ETPN DB - LPDB |  | Nos. | 1 | [7 empty] | 0 | 18500 | 0 | 3000 | 0
6 Way ETPN DB
Incomer:
40A FP RCBO 100mA-1 No.
Outgoings :
32A SP MCB, 'C' Type – 9 Nos
32A TP MCB, 'C' Type – 3 Nos
3 | 6WAY TPN DB - LPDB | 1
Incomer:
40A FP MCB-1 NO
32A DP RCCB 100MA-3 NOS
Outgoings :16/20/25 SP MCB, 'C' Type – 18 Nos
| NOODLE WOK |  | NO | [8 empty] | 1
| CAFFECCINO |  | NO | [8 empty] | 0
| GAINIS |  | NOS | [8 empty] | 1
| ROLLS KING |  | NOS | [8 empty] | 0
| BIKANERWAL RETAIL |  | NOS | [8 empty] | 1
| TEA CONCEPT |  | NOS | [8 empty] | 0
[12 empty] | 3 | 18000 | 54000 | 3000 | 9000
4 | 6WAY TPN DB - LPDB |  | Nos. |  |  | 1 |  | 1 |  | 1 |  | 0 | 18500 | 0 | 3000 | 0
Incomer:
32A FP MCB-1 NO
25A DP RCCB 100MA-3 NOS
Outgoings :16/20/25 SP MCB, 'C' Type – 18 Nos
5 | 6WAY TPN DB - LPDB |  | Nos. |  |  |  | 1 |  |  |  |  | 0 | 18500 | 0 | 3000 | 0
Incomer:
63A FP MCB-1 NO
32A DP RCCB 100MA-3 NOS
Outgoings :16/20/25 SP MCB, 'C' Type – 18 Nos
6 | 8WAY TPN DB - LPDB |  | Nos. | [5 empty] | 1 |  | 1 | 0 | 18500 | 0 | 3000 | 0
Incomer:
63A FP MCB-1 NO
32A DP RCCB 100MA-3 NOS
Outgoings :16/20/25 SP MCB, 'C' Type – 24 Nos
III | SWITCHGEAR
1 | Supply,Installation,Testing and Commissioning of 40 Amps,4Pole,MCB all complete with mounting accessories (IP66) UPS I/P & O/P. | 2 | Nos. | [8 empty] | 1 | 2500 | 2500 | 500 | 500
2 | Supply,Installation,Testing and Commissioning of 100 Amps,4Pole,MCCB for kitchen equipment Isolation all complete with mounting accessories (IP66) | 0 | Nos. | [8 empty] | 0 |  |  |  | 0
3 | Supply,Installation,Testing and Commissioning of 63 Amps,4Pole,MCB for OUTLET | 3 | Nos. |  |  |  | 1 |  | 1 |  | 1 | 2 | 3500 | 7000 | 500 | 1000
4 | Supply,Installation,Testing and Commissioning of 40 Amps,4Pole,MCB for OUTLET | 2 | Nos. | 1 | 1 | [6 empty] | 6 | 2500 | 15000 | 500 | 3000
5 | Supply,Installation,Testing and Commissioning of 32 Amps,4Pole,MCB for OUTLET WATR CCOOLER/CASSETE AC / COLD ROOM | 3 | Nos. |  |  | 1 |  | 1 |  | 1 |  | 5
| CASSETE UNIT |  | Nos. | [8 empty] | 1
|  |  | Nos. | [8 empty] | 6 | 2500 | 15000 | 500 | 3000
6 | Supply,Installation,Testing and Commissioning of 63 Amps,4Pole,MCB + ELCB at 300mA for HVAC Outdoor Isolation all complete with mounting accessories. (IP66) |  | Nos. | [8 empty] | 0 |  |  |  | 0
| TOTAL CARRIED TO SUMMARY | [12 empty] | 130500 |  | 22500
C | UNDERFLOOR TRUNKING, RACEWAY & JUNCTION BOXES
1.1 | Trunking
a. | S & I of trunking same as above but of size 100mm x 38mm x1.6 mm for power/data cables. DOMINOSE | 120 | Mtr. | 10 | 15 | 10 | 10 | 20 | 10 | 20 | 25 | 20 | 400 | 8000 | 100 | 2000
b. | S & I of trunking same as above but of size 68mm x 38mm x1.6 mm thick for power/data cables. |  | Mtr. | [8 empty] | 0 |  |  |  | 0
1.2 | GI Raceway & Junction boxes
Providing and fixing of race way made from minimum 1.6 mm thick pregalvenised steel sheet, factory fabricated, with internal partition of the following sizes including providing removable double folded cover of 1.6mm thick upto 150mm wide raceway and 2mm thick above 150mm wide raceway, knock out holes and fixing accessories earthing stud for terminating 8 SWG copper earth wire complete as required including floor supports, bends, access boxes, tap off boxes and cross over, as per site requirement. (overhead / wall mounted recovery & function boxes shall be 1.6 mm thick). The pregalvenised sheet shall be as per IS 277 or BS 2989 having tensile strength of minimum 500 N/sq.m. and minimum zinc coating of 275 GSM.
a. | 300 mm wide x 40 mm deep single compartment raceway |  | RM | [8 empty] | 0 |  |  |  | 0
b. | 100 mm wide x 40 mm deep single compartment raceway |  | RM | [6 empty] | 15 |  | 0 | 350 | 0 | 150 | 0
c. | 85 mm wide x 40 mm deep single compartment raceway |  | RM | [8 empty] | 0 |  |  |  | 0
d. | 65 mm wide x 40 mm deep single compartment raceway |  | RM | [8 empty] | 0 |  |  |  | 0
1.3 | Providing and fixing of 2 mm thick pre galvanised sheet outlet junction box including providing cover with provision to adjust overall height, knock outs on four sides to accept raceways of specified sizes and cutouts to fix required outlets for following size.
a. | 450 mm x 450 mm |  | Nos | [8 empty] | 0 |  |  |  | 0
b. | 350 mm x 350 mm |  | Nos | [8 empty] | 0 |  |  |  | 0
c. | 250 mm x 250 mm |  | Nos | [8 empty] | 0 |  |  |  | 0
d. | 150 mm x 150 mm | 5 | Nos | [6 empty] | 5 |  | 0 | 500 | 0 | 100 | 0
2 | Providing trenching work for raceway at site including cutting, finishing etc. & Floor chasing for the Installation of raceway & Floor box and clearing of debris from the premises. |  | Lumsum | [8 empty] | 0 |  |  |  | 0
| TOTAL CARRIED TO SUMMARY | [12 empty] | 8000 |  | 2000
D | CABLES, MAINS, SUB MAINS AND CABLE TRAYS
1 | Supply, handling, laying effecting proper connections testing and commissioning of following sizes of 1.1 KV grade XLPE insulated FRLS Aluminium /Copper conductor cables laid over MS supports cable racks or fixing on walls including clamping the cable to supports in an approved manner as required complete with Copper earthing as specified for continuous earthing along with cable. (Earthing will be measured separately and need not be quoted under this item). All complete as required and as per final instruction as given by Owners/ Consultants. and as per Technical specifications.
1.1 | 3.5 core 300 sq. mm. Aluminium Cable Armoured |  | RM | [8 empty] | 0 |  |  |  | 0
1.2 | 3.5 core 240 sq. mm. Aluminium Cable Armoured |  | RM | [8 empty] | 0 |  |  |  | 0
1.3 | 3.5 core 185 sq. mm. Aluminium Cable Armoured |  | RM | [8 empty] | 0 |  |  |  | 0
1.4 | 3.5 core 150 sq. mm. Aluminium Cable Armoured |  | RM | [8 empty] | 0 |  |  |  | 0
1.5 | 3.5 core 120 sq. mm. Aluminium Cable Armoured |  | RM | [8 empty] | 0 |  |  |  | 0
1.6 | 3.5 core 95 sq. mm. Aluminium Cable Armoured |  | RM | [8 empty] | 0 |  |  |  | 0
1.7 | 3.5 core 70 sq. mm. Aluminium Cable Armoured |  | RM | [8 empty] | 0 |  |  |  | 0
1.8 | 3.5 core 50 sq. mm. Aluminium Cable Armoured |  | RM | [8 empty] | 0 |  |  |  | 0
1.9 | 4 core 35 sq. mm Aluminium Cable Armoured |  | RM | [8 empty] | 0 |  |  |  | 0
1.1 | 4 core 25 sq. mm Aluminium Cable Armoured |  | RM | [8 empty] | 0 |  |  |  | 0
1.11 | 4 core 16 sq.mm Aluminium Cable armoured | 35
| LT PANEL TO SERVER ROOM UPS |  | RM | [8 empty] | 50
| LT ROOM TO TERRCAE WATER COOLER |  | RM | [8 empty] | 70
| LT ROOM TO TERRCAE WATER COOLER |  | RM | [8 empty] | 55
| LT PANEL TO BIKAER FRSH AIR MACHINE 40+40 |  | RM | [8 empty] | 80
| STARTER PANEL FRESS AIR +EXHAUST BIKANERWAL |  | RM | [8 empty] | 47
| DHABA STARTER EXHAUST /FRESH AIR MACHINE STARTER TO TERRACE |  | RM | [8 empty] | 80
|  |  | RM | [8 empty] | 382 | 250 | 95500 | 50 | 19100
1.12 | 4 core 16 sq.mm Copper Cable armoured |  | RM | [8 empty] | 0 |  |  |  | 0
1.13 | 4 core 10 sq. mm. Copper cable Armoured |  | RM | [8 empty] | 0 |  |  |  | 0
1.14 | 4 core 6 sq.mm copper cable Armoured
| DOMINOSE TO TERRACE FOR COLD ROOM 40X3 | 20 | RM | [8 empty] | 40 | 450 | 18000 | 50 | 2000
1.15 | 4 core 4 sq.mm copper cable Armoured
| DOMISOE STORE TO CASSTE UNIT OUT DOOR 45X2 | 35 | RM | [8 empty] | 90
| LT PANEL TO BIKANERWALA COLD ROOM OUT DOOR |  | RM | [8 empty] | 40
| FOR TEMPORARY SUPPLY |  | RM | [8 empty] | 0
| COMMON AREA COLD ROOM OUTDOOR UNIT FROM LT PANEL |  | RM | [8 empty] | 66
| SAME AS ABOVE FOR TEMPORARU SUPPLY |  | RM | [8 empty] | 0
| FOR CENRTA AREA FAN |  | RM | [8 empty] | 71
[12 empty] | 267 | 350 | 93450 | 40 | 10680
1.16 | 3 core 6 sq.mm copper cable Armoured |  | RM | [8 empty] | 0 |  |  |  | 0
1.17 | 3 core 4 sq.mm copper cable Armoured |  | RM | [8 empty] | 0 |  |  |  | 0
1.18 | 3 core 2.5 sq.mm copper Flexible Cable | 353 | RM | 30 | 40 | 60 | 60 | 40 | 18 | 70 | 35 | 0 | 150 | 0 | 40 | 0
| LT PANEL TERRACE FOR 1.5 HP MOTOR |  | RM | [8 empty] | 72
| LT PANEL TO GAS BANK |  | RM | [8 empty] | 70
142
1.19 | 4 core 6 sq.mm copper cable Armoured UPS | 15 | RM | 15 | [7 empty] | 0 | 450 | 0 | 50 | 0
1.2 | 5R X 1 core 6 sq.mm copper cable FLEXIBLE | 30 | RM | 30 | [7 empty] | 0 | 800 | 0 | 50 | 0
2 | Supply and making terminal joints for the following sizes of 1.1KV grade XLPE Insulated armoured/Unarmoured Aluminium/Copper conductor cables including providing heavy duty tinned coper terminal lugs, crimping type, insulation tape, heavy duty single compression type brass glands effecting terminal connection to the equipment/Panel complete as required as per final direction and approval of the Owner/Consultant.Supply and making terminal joints for the following sizes of 1.1KV grade XLPE Insulated armoured/Unarmoured Aluminium/Copper conductor cables including providing heavy duty tinned coper terminal lugs, crimping type, insulation tape, heavy duty single compression type brass glands effecting terminal connection to the equipment/Panel complete as required as per final direction and approval of the Owner/Consultant. |  | STARTER PANEL
2.1 | 3.5 core 300 sq. mm. Aluminium Cable Armoured |  | Nos. | [8 empty] | 0 |  |  |  | 0
2.2 | 3.5 core 240 sq. mm. Aluminium Cable Armoured |  | Nos. | [8 empty] | 0 |  |  |  | 0
2.3 | 3.5 core 185 sq. mm. Aluminium Cable Armoured |  | Nos. | [8 empty] | 0 |  |  |  | 0
2.4 | 3.5 core 150 sq. mm. Aluminium Cable Armoured |  | Nos. | [8 empty] | 0 |  |  |  | 0
2.5 | 3.5 core 120 sq. mm. Aluminium Cable Armoured |  | Nos. | [8 empty] | 0 |  |  |  | 0
2.6 | 3.5 core 95 sq. mm. Aluminium Cable Armoured |  | Nos. | [8 empty] | 0 |  |  |  | 0
2.7 | 3.5 core 70 sq. mm. Aluminium Cable Armoured |  | Nos. | [8 empty] | 0 |  |  |  | 0
2.8 | 3.5 core 50 sq. mm. Aluminium Cable Armoured |  | Nos. | [8 empty] | 0 |  |  |  | 0
2.9 | 4 core 35 sq. mm Aluminium Cable Armoured |  | Nos. | [8 empty] | 0 |  |  |  | 0
2.1 | 4 core 25 sq. mm Aluminium Cable Armoured |  | Nos. | [8 empty] | 0 |  |  |  | 0
2.11 | 4 core 16 sq.mm Aluminium Cable armoured | 6 | Nos. |  |  |  | 2 |  | 2 |  | 2 | 12 | 350 | 4200 | 50 | 600
2.12 | 4 core 16 sq.mm Copper Cable armoured |  | Nos. | [8 empty] | 0 |  |  |  | 0
2.13 | 4 core 10 sq. mm. Copper cable Armoured |  | Nos. | [8 empty] | 0 |  |  |  | 0
2.14 | 4 core 6 sq.mm copper cable Armoured | 4 | Nos. | 2 | 2 | [6 empty] | 3 | 250 | 750 | 50 | 150
2.15 | 4 core 4 sq.mm copper cable Armoured | 6 | Nos. |  |  | 2 |  | 2 |  | 2 |  | 22 | 250 | 5500 | 50 | 1100
2.16 | 3 core 6 sq.mm copper cable Armoured |  | Nos. | [8 empty] | 0 |  |  |  | 0
2.17 | 3 core 4 sq.mm copper cable Armoured |  | Nos. | [8 empty] | 0 |  |  |  | 0
2.18 | 3 core 2.5 sq.mm copper Flexible Cable | 28 | Nos. | 2 | 2 | 2 | 2 | 2 | 2 | 14 | 2 | 28 | 250 | 7000 | 50 | 1400
2.19 | 4 core 6 sq.mm copper cable Armoured UPS | 2 | Nos. | 2 | [7 empty] | 0 | 250 | 0 | 50 | 0
3 | Supply and fixing of factory fabricated GI ladder type cable trays, with radial bends, suspenders and supports as per specification and of the following sizes.
3.1 | 1000 mm wide |  | RM | [8 empty] | 0 |  |  |  | 0
3.2 | 600 mm wide |  | RM | [8 empty] | 0 |  |  |  | 0
3.3 | 450 mm wide |  | RM | [8 empty] | 0 |  |  |  | 0
4 | Supply and fixing of perforated type factory fabricated GI cable trays of the following sizes including providing GI suspenders and supports as per specifications..
4.1 | 600mm x 40/50 x 2 mm thick |  | RM | [6 empty] | 15 |  | 0 | 850 | 0 | 150 | 0
4.2 | 450mm x 40/50 x 2 mm thick |  | RM | [8 empty] | 0 |  |  |  | 0
4.3 | 300mm x 40/50 x 2 mm thick |  | RM | [8 empty] | 0 |  |  |  | 0
4.4 | 200mm x 40/50 x 2 mm thick |  | RM | [8 empty] | 0 |  |  |  | 0
4.5 | 150mm x 40/50 x 2 mm thick | 78
| SERVER ROOM TO GIANIS |  | RM | [8 empty] | 87
| SERVER ROOM TO CAFFECCINO |  | RM | [8 empty] | 85
| LT PANEL TO TERRACE |  | RM | [8 empty] | 62
| DOMINOSE OUTLET TO TERRACE DHABA OUT LTE TO TERRACE |  | RM | [8 empty] | 3
| DHABA TO TERRACE |  | RM | [8 empty] | 3
|  |  | RM | [8 empty] | 240 | 350 | 84000 | 150 | 36000
| TOTAL CARRIED TO SUMMARY | [12 empty] | 308400 |  | 71030
E | CIRCUIT CUM POINT WIRING
Point wiring LENGTH from DB to SB or First Light point control be MCB shall be avg. of 15Mtr. of 3R x 2.5 sq mm FRLS PVC insulated stranded copper conductor wires. For SB to SB the length shall be measured in Mtr.
The secondary/Loop point length shall be 10Mtr from Light fixture to light fixture. If secondary point shall be operated from MCB then the length shall be 10 Mtr.
All sockets to be checked with a Check Plug socket tester for live-neutral reverse, no earth,neutral fault, live earth reverse, neutral earth reverse.
The Circuit No. and DB no. label shall be provided on all UPS ,RAW sockets and switchboards with label printer.
The Length shall be paid as per the actual measurements & as per following manner.
1.1 | Wiring for the Primary light points with 3R x 2.5 Sq.mm FRLS PVC insulated stranded copper conductor wires in PVC conduits in F.ceiling/walls/ceiling as direc
1.1.1 | From DB to Normal Switch Board |  | Mtrs | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 225 | 0 | 50 | 0
1.1.2 | From DB to Emergency Switch Board |  | Mtrs | 30 | 40 | 60 | 60 | 40 | 18 | 30 | 35 | 0 | 200 | 0 | 50 | 0
1.2 | Wiring for the following light points with 3R x 2.5 Sq.mm FRLS PVC insulated stranded copper conductor wires in PVC conduits in F.ceiling/walls/ceiling as direc
1.2.1 | First point controlled by one no. 6 amp switch. (upto 10Mtr.) |  | Nos. | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 4 | 0 | 700 | 0 | 200 | 0
1.2.2 | First point controlled by one no. 6 amp switch. (upto 20Mtr.) |  | Nos. | [8 empty] | 0 | 900 | 0 | 200 | 0
1.2.3 | First point controlled by one no. 6 amp switch. For Emergency Light (upto 10Mtr.) |  | Nos. | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 6 | 0 | 700 | 0 | 200 | 0
1.2.4 | First point controlled by one no. 6 amp switch. For Emergency Light (upto 20Mtr.) |  | Nos. | [8 empty] | 0 |  |  |  | 0
1.3 | Same as item No. 1.2.1 & 1.2.2 above but LOOP POINT i.e. wiring of point looped from first point with 3R x 2.5 sq. mm FRLS PVC insulated copper conductor wire in concealed/exposed PVC conduit and earthing |  | Nos. | 1 | 0 | 0 | 0 | 5 | 0 | 5 | 12 | 0 | 600 | 0 | 150 | 0
1.4 | Same as item No. 1.2.3 & 1.2.4 above but LOOP POINT i.e. wiring of point looped from first point with 3R x 2.5 sq. mm FRLS PVC insulated copper conductor wire in concealed/exposed PVC conduit and earthing For Emergency Light |  | Nos. | 0 | 0 | 0 | 0 | 2 | 0 | 1 | 3 | 0 | 600 | 0 | 150 | 0
1.5 | Wiring for the following light points controlled by MCB in DB (Cost of MCB has been taken elsewhere in the tender) with 3R x 2.5 sq. mm FRLS PVC insulated copper conductor wires in concealed/exposed PVC conduits as called for and earthing. | [10 empty] | 0 |  |  |  | 0
1.5.1 | First point controlled by existing MCB in D.B. |  | Mtr. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.5.2 | First Emergency point controlled by existing MCB in D.B. |  | Mtr. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.6 | Same as item No.1.5.1 above but LOOP POINT i.e. wiring of point looped from first point with 3R x 2.5 sq. mm FRLS. insulated copper conductor wire in concealed/exposed GI conduit and earthing |  | Nos. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.7 | Same as item No. 1.5.2 above but LOOP POINT i.e. wiring of point looped from first point with 3R x 2.5 sq. mm FRLS. insulated copper conductor wire in concealed/exposed M.S. conduit and earthing For Emergency Lighting |  | Nos. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.8 | Wiring for UPS/Raw plug outlets points with 3R x 2.5 sqmm FRLS PVC Insulated and PVC sheathed flexible cable with bright annealed electrolytic copper conductor , 1100 volt grade confirming to IS : 694-1990 with latest amendments, in existing Channels/ conduit in ceiling/walls/floor including all cable termination accessories) (including body earth for GI boxes) |  | Mtr. | 10 | 10 | 10 | 10 | 10 | 15 | 60 | 15 | 0 | 225 | 0 | 50 | 0
2 | Wiring for Exhaust fan point with 2.5 sq. mm. insulated copper conductor 1100 volts grade stranded flexible FRLS wires of approved make in embeded 25mm dia. heavy duty FRLS PVC conduit as per IS 9537 part-3 or surface mounted / Existing raceway. Providing and fixing of 6 amps flush mounted switch at the normal switch level in 1.6 mm thick GI box and 6 amps 3 pin flush mounted socket out of near exhaust fan and earthing of exhaust fan through the third pin of the socket outlet and GI box with 2.5 sq. mm. PVC insulated copper conductor flexible FRLS wire. Cost of switch socket, switch board and accessories shall be included. Average point length to be derived by Contractor, from the drawing provided AND +/- 1 Mtr Measured Radially. |  | Pt. | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 0 | 1250 | 0 | 500 | 0
3 | Supply, Installation, Testing and commissioning circuit wiring from MCB DB's to switch/socket boxes and between switch/socket boxes using 4 Runs of 4 sq.mm (One each for Phase & Neutral) and 1 Run of 2.5 sq.mm (Earth) FRLS PVC insulated stranded single core copper conductor wires to be laid in heavy class MS conduits which are to be concealed in ceiling/wall/partitions or laid in open fashion above false ceiling. The rate shall include conduits, all necessary conduit accessories, clamps, screws, saddles etc as applicable. (For kitchen Power supply-3ph equipment) | 10
| BIKANERWALA |  | MTRS | [8 empty] | 30
| CAFFECCINO |  | MTRS | [8 empty] | 30
[12 empty] | 60 | 450 | 27000 | 50 | 3000
4 | Supply, Installation, Testing and commissioning circuit wiring from MCB DB's to switch/socket boxes and between switch/socket boxes using 2 Runs of 4 sq.mm (One each for Phase & Neutral) and 1 Run of 2.5 sq.mm (Earth) FRLS PVC insulated stranded single core copper conductor wires to be laid in heavy class MS conduits which are to be concealed in ceiling/wall/partitions or laid in open fashion above false ceiling. The rate shall include conduits, all necessary conduit accessories, clamps, screws, saddles etc as applicable. (For kitchen Power supply) | 979
BIKANERWAL
| DB TO SERVICE COUNTER FDU |  | MTRS | [8 empty] | 34
| SECODN PONT BAINMERRY 2X38 |  | MTRS | [8 empty] | 76
| COLD BAIN MERRY 2X40 |  | MTRS | [8 empty] | 80
| POWER DB TO TO DEEP FREEZER |  | MTRS | [8 empty] | 21
| NEAR MICRO WAVE 2X19 |  | MTRS | [8 empty] | 38
| NEAR SINK RO |  | MTRS | [8 empty] | 22
| POWER DB TO NEAR STORE AREA |  | MTRS | [8 empty] | 26
| COLD ROOM WALL |  | MTRS | [8 empty] | 18
PROVIDING AND FIXING OF NEW POWER POINTS COMPLETES
| FOR KITCHEN POWER SUPPLY UPS DB OUTER AREA FOR CASH COUNTER 3X53 |  | MTRS | [8 empty] | 159
| FOR SIGANGE |  | MTRS | [8 empty] | 55
DHABA
| POWER DB TO NEAR SINK EXISTING WALL |  | MTRS | [8 empty] | 28
| POWER DB TO BOH POT AREA |  | MTRS | [8 empty] | 19
| POWER DB TO BOH HOT BAINMERRY |  | MTRS | [8 empty] | 22
| POWER DB TO SAME WALL |  | MTRS | [8 empty] | 20
| POWER DB TO CENTE WALL NEAR SINK |  | MTRS | [8 empty] | 14.7
| POWER DB TO COUNTER HOT BAINMERRY |  | MTRS | [8 empty] | 13.3
| POWER DB TO COCACOLA FRIZ |  | MTRS | [8 empty] | 12
| POWER DB TO NEAR COLA FRIZ |  | MTRS | [8 empty] | 7
| POWR DB TO NEAR SINK |  | MTRS | [8 empty] | 14.7
| POWER DB TO TO NEAR SINK TV POINT 2X7 |  | MTRS | [8 empty] | 14
| SIGNAGE |  | MTRS | [8 empty] | 14
NOODLE WOK
| SIGNAGE |  | MTR | [8 empty] | 12
| POWER DB TO NEAR SINK |  | MTR | [8 empty] | 16
| PWER DB TO DEEP FREEZER |  | MTR | [8 empty] | 11.8
| POWER DB TO FRYER |  | MTR | [8 empty] | 9.7
| KITCHEN DB TO POS COUNTER |  | MTR | [8 empty] | 24
CAFFECCINO
| POWER DB TO 3 PHASE POINTS |  | MTR | [8 empty] | 9
| POWER DB TO GEYSER POINTS 2*19.9 |  | MTR | [8 empty] | 39.8
| POWER DB TO NEAR 3 PHASE POINTS |  | MTR | [8 empty] | 8
| POWER DB TO NEAR 3 PHASE POINTS |  | MTR | [8 empty] | 7
| POWER DB TO NEAR 3 PHASE POINTS |  | MTR | [8 empty] | 6
| POWER DB TO NEAR 3 PHASE POINTS |  | MTR | [8 empty] | 5
| DB TO SERVICE COUNTER 2X6 |  | MTR | [8 empty] | 12
| SIGNAGE 2X23 |  | MTR | [8 empty] | 46
GIANIS
| POWER DB TO GEYSER |  | MTR | [8 empty] | 14
| NEAR SINK DB |  | MTR | [8 empty] | 9
| 2ND POINT |  | MTR | [8 empty] | 8
| 3RD POINT |  | MTR | [8 empty] | 7
| 4TH POINT |  | MTR | [8 empty] | 6.2
| FRONT COUNTER |  | MTR | [8 empty] | 5
| UPS DN TO POS CONNECT 2X17 |  | MTR | [8 empty] | 34
| SIGNAGE |  | MTR | [8 empty] | 14
BIKANER RETAILS
| SIGNAGE |  | MTR | [8 empty] | 15
| POWER SUPPLY |  | MTR | [8 empty] | 12
DOMINOS
| POWER DB TO STAFF LOCK AREA WALL 2X33 |  | MTR | [8 empty] | 42
| DB TO 3 SINK |  | MTR | [8 empty] | 35
| DB TO 3 SINK |  | MTR | [8 empty] | 24
| DB TO NEAR GEYSER 3X27.5 |  | MTR | [8 empty] | 82.5
| DB TO NEAR HEYSER SECOND WALL |  | MTR | [8 empty] | 31.1
| DB TO SPLIT AC POINT |  | MTR | [8 empty] | 14
| DB TO GLD PANEL BELOW |  | MTR | [8 empty] | 13.3
| DB TO OVEN AREA GEYSER |  | MTR | [8 empty] | 13.7
| DB TO REFRIGERATOR |  | MTR | [8 empty] | 21.8
| DB TO DOUGH MANAGEMENT AREA |  | MTR | [8 empty] | 27.2
| DB TO OVEN WALL 4X39 |  | MTR | [8 empty] | 156
| DB TO MS |  | MTR | [8 empty] | 48
| DB TO ICE MACHINE 4X 53 |  | MTR | [8 empty] | 212
| DB TO MNEAR MACHINE TV POINT 2X52.3 |  | MTR | [8 empty] | 104.6
| DB TO MS POLL |  | MTR | [8 empty] | 46
| DB TO POS COUNTER 4X42.3 |  | MTR | [8 empty] | 167.2
| DB TO STANDING COMPUTER |  | MTR | [8 empty] | 22
| DB TO STANDING COMPUTER |  | MTR | [8 empty] | 24
| DB TO DMB |  | MTR | [8 empty] | 43
| DB TO GLD PANEL |  | MTR | [8 empty] | 14
| DB TO MANAGER OVER HEAD FOR WALL FAN |  | MTR | [8 empty] | 3.5
| DB TO MANAGER TABLE 3X9 |  | MTR | [8 empty] | 27
| DB TO SERVER RACK 2X2 |  | MTR | [8 empty] | 4
| BELOW DB 2X2 |  | MTR | [8 empty] | 4
[12 empty] | 2218.1 | 225 | 499072.5 | 50 | 110905
5 | Supply, Installation, Testing and commissioning circuit wiring from MCB DB's to switch/socket boxes and between switch/socket boxes using 2 Runs of 2.5 sq.mm (One each for Phase & Neutral) and 1 Run of 2.5 sq.mm (Earth) FRLS PVC insulated stranded single core copper conductor wires to be laid in heavy class MS conduits which are to be concealed in ceiling/wall/partitions or laid in open fashion above false ceiling. The rate shall include conduits, all necessary conduit accessories, clamps, screws, saddles etc as applicable (For kitchen power supply) |  | Mtrs | 24 | 24 | 24 | 0 | 30 | 8 | 180 | 10 | 0 | 215 | 0 | 50 | 0
6 | Supplying, installation, Testing and commissioning of brushed stainless steel finish POP UP boxes of following modules for perfect integration with office furnitures complete with all installation kits, accessories, required to finish the installation - Approved by Client. (Cost of Switches, sockets, IT/ data outlets NOT to be included in this item)
6.1 | 10 modules |  | Nos. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
6.2 | 12 modules |  | Nos. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
7 | Supply and fixing of heavy duty rigid FRLS PVC conduit as per IS 9537 part-3 or surface mounted of 25mm Dia sizes including cost of junction boxes, bends, elbows, sockets, tees etc. laying in slab, cutting chasis and making good or surface mounted including all fixing hardware. | 282
| SERVER ROOM TO GIANIS |  | RMTR | [8 empty] | 87
| SERVER OOM TO ROLLS KING |  | RMTR | [8 empty] | 87
| SERVEROOM TO DOMINOSE |  | RMTR | [8 empty] | 68
| SERVER ROOM BIKNERWALA 2 X40 |  | RMTR | [8 empty] | 80
| SERVEROOM TO BIKANERWAL RETAILS |  | RMTR | [8 empty] | 38
| SERVE ROOM TO TEA CONCEPT |  | RMTR | [8 empty] | 33
| SERVER ROOM TO CAFFECCINO |  | RMTR | [8 empty] | 78
| SERVER ROOM TO NOODLES WOK |  | RMTR | [8 empty] | 58
| SERVROOM TO DHABA 2 X 30 |  | RMTR | [8 empty] | 60
| SERVER ROOM TO OFFICE CABIN |  | RMTR | [8 empty] | 18
| SERVER ROOM CABIN |  | RMTR | [8 empty] | 13
| SERVROOM TO OFFICE |  | RMTR | [8 empty] | 3
| SERVER ROOM TO STORE ROOM |  | RMTR | [8 empty] | 5
| SERVROOM TO OFFICE CABIN |  | RMTR | [8 empty] | 18
| SERVER OOM TO STAFF MES ROOM |  | RMTR | [8 empty] | 24
| DOMINOSE OULTET 4X72 |  | RMTR | [8 empty] | 288
FOR MUSIC CONDUITING
| SERVER ROOM TO GIANIS |  | RMTR | [8 empty] | 87
| SERVER ROOM TO BIKANERWALA |  | RMTR | [8 empty] | 70
| SERVER TO NOODLES |  | RMTR | [8 empty] | 58
| FOR MUSIC CONDUITING |  | RMTR | [8 empty] | 90
[12 empty] | 1263 | 65 | 82095 | 35 | 44205
8 | Supply and fixing of flexible PVC conduit as per IS 9537 part-3 or surface mounted of 25mm Dia sizes including cost of junction boxes, bends, elbows, sockets, tees etc. laying in slab, cutting chasis and making good or surface mounted including all fixing hardware. | 30 | Mtrs | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 150 | 40 | 6000 | 15 | 2250
9 | Supply and fixing of heavy duty GI conduitor surface mounted of 25mm Dia sizes including cost of junction boxes, bends, elbows, sockets, tees etc. laying in slab, cutting chasis and making good or surface mounted including all fixing hardware. |  | Mtrs | [8 empty] | 0 |  |  |  | 0
10 | Supply and fixing of flexible GI conduitor surface mounted of 25mm Dia sizes including cost of junction boxes, bends, elbows, sockets, tees etc. laying in slab, cutting chasis and making good or surface mounted including all fixing hardware. |  | Mtrs | [8 empty] | 0 |  |  |  | 0
11 | Providing Television wiring inside 25mm dia GI conduit from each TV outlet to LV Shaft by using coaxial cable of type RG 6. Tinned copper conductor with necessary accessories viz. deep junction boxes, inspection boxes bends, termination etc. making complete piping rigid by adhesive/ resin and fixed with binding wire ‘U’nails. |  | Mtrs | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 100 | 0 | 50 | 0 | pvc conduits
| TOTAL CARRIED TO SUMMARY | [12 empty] | 614167.5 |  | 160360
F | SWITCHES AND SOCKETS
I | Supply Installation testing and commission of 240V-AC, wiring devices and its accessories such as modular type switch socket outlets with modular front plate, modular box, G.I. back box and all required accessories etc. Installation scope includes all civil works related to this job such as chiselling , making good with concrete and plaster, supply of fixing screw / wall plugs and other necessary hardware, marking identification numbers of circuits & interconnections of the switch /sockets as per standard drawing, complete as per site requirement.Switches and sockets may be individual or combined with bigger lighting switchboards, contractor to refer drawings ton understand exact scope of work.
1 | 6/16A international Switch Socket | 105
| BIKANERWALA |  | Nos. | [8 empty] | 37
| DHABA |  | Nos. | [8 empty] | 35
| NOODLES WOK |  | Nos. | [8 empty] | 11
| CAFFECCINO |  | Nos. | [8 empty] | 0
| GIANIS |  | Nos. | [8 empty] | 14
| BIKANER RETAILS |  | Nos. | [8 empty] | 0
| DOMINOSE |  | Nos. | [8 empty] | 72
|  |  | Nos. | [8 empty] | 169 | 700 | 118300 | 150 | 25350
II | METAL CLAD PLUG & SOCKETS
1 | Supply, Installation, Testing and Comissioning of 230V, Ph+E following rated Industrial type metal clad plug & socket, IP 66 rated with MCBs with different enclosures to be mounted in the wall.
2 | 20A DP MCB with Plug and socket | 8 | Nos. | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1500 | 0 | 500 | 0
3 | 32A DP MCB with Plug and socket
| BIKANEWALA | 1 | Nos. | [8 empty] | 2
| DHABA |  | Nos. | [8 empty] | 1
| NOODLE WOK |  | Nos. | [8 empty] | 3
|  |  | Nos. | [8 empty] | 6 | 1500 | 9000 | 500 | 3000
III | Supply, Installation, Testing and Comissioning of 415V, Ph+E following rated Industrial type metal clad plug & socket with IP 66 rated MCBs with different enclosures to be mounted in the wall.
1 | 20A 4P MCB with Plug and socket | 0 | Nos. | [8 empty] | 0 |  |  |  | 0
2 | 25A 4P MCB with Plug and socket | 0 | Nos. | [8 empty] | 0 |  |  |  | 0
3 | 32A 4P MCB with Plug and socket | 0 | Nos. | [8 empty] | 0 |  |  |  | 0
| TOTAL CARRIED TO SUMMARY | [12 empty] | 127300 |  | 28350
G | INSTALLATION OF LIGHTING FIXTURES
Installation of the following lighting fixtures with all fixing accessories etc. as required.
1 | Spot Light | 0 | Nos. | [8 empty] | 0 |  |  |  | 0
2 | Panel Light 600 x 600mm | 66
| BIKANERWALA |  | Nos. | [8 empty] | 18
| DHABA |  | Nos. | [8 empty] | 9
| NODLES WOK |  | Nos. | [8 empty] | 3
| CAFFECCINO |  | Nos. | [8 empty] | 6
| GIANIS |  | Nos. | [8 empty] | 4
| BIKANER RETAIL |  | Nos. | [8 empty] | 4
| DOMINOSE |  | Nos. | [8 empty] | 27
|  |  | Nos. | [8 empty] | 71 |  |  | 300 | 21300
3 | Panel Light 300 x 300mm | 0 | Nos. | [8 empty] | 0 |  |  |  | 0
4 | Cove Light | 0 | Nos. | [8 empty] | 0 |  |  |  | 0
5 | Wall Support Light | 0 | Nos. | [8 empty] | 0 |  |  |  | 0
6 | 1 x 1 Grid Light | 0 | Nos. | [8 empty] | 0 |  |  |  | 0
| TOTAL CARRIED TO SUMMARY | [12 empty] | 0 |  | 21300
H | TEMPORARY LIGHTING & POWER ARRANGEMENTS
| Supply, installation of temporary lighting & power arrangement for construction purpose of with industrial type switch & sockets/MCB's/ELCB's & lighting fittings as required to finish the work for interior contractor & necessary electrical protections throughout the site for construction work till the handover of site. Contractor shall maintain the saftey rules & regulations as per safety Security Department. The material shall be taken back by the contractor. | 1 | Job | [8 empty] | 1 | 50000 | 50000 | 25000 | 25000
| TOTAL CARRIED TO SUMMARY | [12 empty] | 50000 |  | 25000
I | MISCELLANEOUS+ SAFETY EQUIPMENT
1 | Supply & laying of Rubber Mats, CPRI tested conforming to standards like BS 921, ASTM-D 178 & IEC 479 for different operatng voltage ratings as below.
1.1 | Supply of 2M x 3M Rubber mat suitable for operatng voltage upto 1.1 KV |  | Set | [8 empty] | 0 |  |  |  | 0
2 | Supply & fixing of approved shock treatment chart written in English and in local Language. The chart shall be framed in Teakwood and covered with glass. |  | Nos. | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 2000 | 0 | 200 | 0
0
3 | Supply & fixing of approved Fire Alarm evacuation plan chart written in English and in local Language approved by cleint requrements. |  | Nos | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 2000 | 0 | 200 | 0
4 | Supply & fixing of the best quality LT Danger Boards(415V) for of approved shape and size as specified by the local electrical authorities written in English, and local Language |  | Nos. | [8 empty] | 0 |  |  |  | 0
5 | Supply & handed over to client of First Aid Box |  | Set | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 2000 | 0 | 200 | 0
6 | Supply Installation Testing and comissioning of FLUSH MOUNT DUAL SIDED, Maintained 3 Watt LED, FIRE Exit luminaires, Sheet metal Body, Painted to RAL 9010, Pictogram 280 (I) X 130(W), with spring supports, Legend with clear acrylic/engraved pattern to be fully compliant with requirements of designed and installed to meet the fire and safety code of practice & the respective EN 60598-2-22 and the system designed in compliance with EN50171, EN50272-2, EN50172, and EN1838 standards EN Standards, IP 20 with NiCad 2 x 1.2V Battery Backup for 90 Minutes operation in following formats as per Layouts : Right Arrow, Left Arrow, Down Arrow, Both sides etc. Input Supply : 220 V AC ±10%. |  | Nos. | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 2000 | 0 | 200 | 0
| TOTAL CARRIED TO SUMMARY | [12 empty] | 0 |  | 0
J | LIASONING WORKS
| Preparation of necessary drawings and documents, submission & cordination with electrical inspector to get the approval, and coordination with local electricity board for the power sanction. The successful contractor to do liasoning with above authorities.” |  | Job | [8 empty] | 1 |  |  |  | 0 | NOT APPLICABLE
| TOTAL CARRIED TO SUMMARY | [14 empty] | 0
K | EARTHING INSTALLATION
Supplying, designing, installation testing and commissioning of following type earth pits. Note: The material to be used for executing the work shall be of good quality and warranty certificate in the form of indemnity bond shall be submitted offering min. 5 years warranty towards the successful working of system from the date of commissioning. Warranty implies the voltage between earth and neutral will not exceed 0 volts for earthing pits installed. The system installed shall be such that the voltage between neutral and earth shall be 0V. The system installed shall have IR value less than 1 Ohms. The purity of copper shall not be less than 99.9%. Entire system to be installed as per IS 3043. The entire works shall be executed under supervision of Original equipment manufacturer (OEM). (Makes : SI, Ashlok, Indelec, Doksun)
1 | Earthing with copper earth electrode 80mm dia including accessories, and providing masonry enclosure with cover plate having locking arrangement and watering pipe of 2.7 metre long etc. with charcoal/ coke and salt as required in accordance with IS 3043 (Dedicated Earthing for UPS) |  | Set | [8 empty] | 0 |  |  |  | 0
2 | Earthing with G.I. earth plate 600 mm X 600 mm X 6 mm thick including accessories, and providing masonry enclosure with cover plate having locking arrangement and watering pipe of 2.7 metre long etc. with charcoal/ coke and salt as required. |  | Set | [8 empty] | 0 |  |  |  | 0
3 | Supply and Installation of Maintenance Free Chemical earthing using Electrode of Size approx. 38 mm dia +/- 2mm, 3 metres long bonded with 50x6 copper internal strip complete with excavation, civil works, cast iron cover with backfill compound min. 40 KG. The system shall be CPRI tested. Warranty period of chemical earthing from the date of commissioning shall be 5 years. Warranty implies the voltage between earth and neutral will not exceed 0 volts for earthing pits installed. FOR DG SET |  | Set | [8 empty] | 0 |  |  |  | 0
4 | Providing and fixing 50 mm X 6 mm G.I. strip on surface or in recess for connections etc. as required |  | Mtr | [8 empty] | 0 |  |  |  | 0
5 | Providing and fixing 25 mm X 6 mm G.I. strip on surface or in recess for connections etc. as required |  | Mtr | [8 empty] | 0 |  |  |  | 0
6 | Providing and fixing 8 SWG GI wire on surface or in recess for loop earthing as required.
6 | PROVIDING AND FIXING THE EARTING WIRE 8 GAUZE IN THE EXISTING LAID CABLE BY LL | 144
| BIKANERWALA |  | RM |  |  |  | 18 |  |  |  |  | 18
| DOMINOSE |  | RM |  |  |  | 30 | 18 |  |  |  | 30
| ROLLS KING |  | RM |  |  |  | 30 | 30 |  |  |  | 30
| GIANIS |  | RM |  |  |  | 38 | 30 |  |  |  | 38
| DHABA |  | RM |  |  |  | 40 | 38 |  |  |  | 40
| NOODLES |  | RM |  |  |  | 60 | 40 |  |  |  | 60
| CAFFECCINO |  | RM |  |  |  | 82 | 60 |  |  |  | 82
| BIKNAEERWAL RETAIL |  | RM |  |  |  | 25 | 82 |  |  |  | 25
| TEA CONCEPT |  | RM |  |  |  | 32 | 25 |  |  |  | 32
| PFFICE AREA |  | RM |  |  |  | 28 | 32 |  |  |  | 28
| SERVER ROOM |  | RM |  |  |  | 35 | 28 |  |  |  | 35
[7 empty] | 418 | 35 |  |  |  | 418 | 25 | 10450 | 5 | 2090
418
7 | Providing and fixing single core 25 sq mm green color copper conductor Armoured cable including copper thimbles, fixing hardware as required. |  | RM | [8 empty] | 0 |  |  |  | 0
8 | Providing and fixing single core 10 sq mm green color copper conductor Armoured cable including copper thimbles, fixing hardware as required. |  | RM | [8 empty] | 0 |  |  |  | 0
9 | Providing and fixing of earthing terminal box with CU & GI strip as per site requirements. |  | Set | [8 empty] | 0 |  |  |  | 0
| TOTAL CARRIED TO SUMMARY | [12 empty] | 10450 |  | 2090

## Network Works
TFS_BEHROR
BOQ FOR NETWORK WORKS-INTERNAL OUTLETS
Item No. | Description | PO Qty | Unit | NOODLE | CAFECCINO | GIANI'S | ROLL KING | DHABA | TEA CONCEPT | BOH | BIKANERWALA | Total executed Qty | Supply | SUPPLY | Installation | INSTALLATION
[13 empty] | Rate | AMOUNT | Rate | Amount
A. | TELEPHONE & DATA SYSTEM
1 | Supply and installation of following for ethernet switches with 2 sets of 32A DP MCB A.C. distribution board (Power cord), wire manager, fan tray, lockable front tinted glass door and two pair angle to support the switch installed in the rack.
1.1 | 42 U Rack - CLOSE RACK |  | Nos. | [8 empty] | 0 |  |  |  | 0
1.2 | 45 U Rack - OPEN RACK |  | Nos. | [8 empty] | 0 |  |  |  | 0
2 | Supply & Installation of 24 Port PoE switch |  | Nos. | [8 empty] | 0 |  |  |  | 0
3 | Supply & Installation of 24 Port Patch Panel |  | Nos. | [8 empty] | 0 |  |  |  | 0
4 | Supply, installation, testing and commissioning of 4 pair Category 6 LAN cable consisting of 24 AWG solid copper conductors and as per the specification. The cable shall have flexible jacket and ripcord for easy Stripability, in the existing surface/ recessed steel/ PVC conduit /raceways required. | 1496
| SERVER ROOM TO GIAINIS -----------------------4X95 MTR |  | RM | [8 empty] | 380
| SERVER ROOM TO ROLLS KING----------------- 4X95 MT |  | RM | [8 empty] | 380
| SERVER ROOM TO DOMINOSE------------------ 2X 70 MTR |  | RM | [8 empty] | 140
| SERVER ROOM TO BIKANERWALA ---------------6 X 40 MTR |  | RM | [8 empty] | 240
| SERVER ROOM TO BIKERWALA RETAIL -------3X38 MTR |  | RM | [8 empty] | 114
| SERVER ROOM TO TEA CONCEPT ---------3X35 MTR |  | RM | [8 empty] | 105
| SERVER ROOM TO CAFFECCINO -----------3X72 MTR |  | RM | [8 empty] | 216
| SERVER ROOM TO NOODLE WOK -----------3X60 MTR |  | RM | [8 empty] | 180
| SERVER ROOM TO DHABA----------------------3X32 MTR |  | RM | [8 empty] | 96
| SERVER OOM TO DHABA------------------------5X30 MTR |  | RM | [8 empty] | 90
| SERVER ROOM TO OFFICE AREA ROOM ----1 X 18MTR |  | RM | [8 empty] | 18
| SERVROOM TO SERVER RACK ----------------2X3 MTR |  | RM | [8 empty] | 6
| SERVER ROOM TO STORE ROOM -------------2X5 MTR |  | RM | [8 empty] | 10
| SERVER ROOM TO OFFICE----------------------2X19 MTR |  | RM | [8 empty] | 38
| SERVER ROOM TO STAFF MESS ROOM 2X25 |  | RM | [8 empty] | 50
| SERVER ROOM DOMINOSE OUTLTE ----------4X22 |  | RM | [8 empty] | 88
| SERVER ROOM DOMINOSE OUTLTE ----------4X23 |  | RM | [8 empty] | 46
| SERVER ROOM DOMINOSE OUTLTE ----------6X27 |  | RM | [8 empty] | 162
| SERVER ROOM DOMINOSE OUTLTE ----------2X19 |  | RM | [8 empty] | 38
| SERVER ROOM DOMINOSE OUTLTE ----------2X15 |  | RM | [8 empty] | 30
| SERVER ROOM DOMINOSE OUTLTE ----------8X23 |  | RM | [8 empty] | 184
| SERVER ROOM DOMINOSE OUTLTE ----------4X6 |  | RM | [8 empty] | 24
[12 empty] | 2635 | 40 | 105400 | 20 | 52700
5 | Supplying, laying and termination cat 6 wiring in existing raceways/ conduits from data outlet to patch panel, with all wiring connections, accessories required to complete the work. Average point length to be derived by Contractor, from the drawing provided AND +/- 1 Mtr Measured Radially. |  | Point | [8 empty] | 0 |  |  |  | 0
6 | Supplying, fixing and testing of modular type computer Jack RJ 45 with safety shutter ISI mark approved make duly erected with face plate, G.I back box with all connections, accessories required to complete the work. | 49 | Nos. | 3 | 3 | 3 | 3 | 3 | 3 | 24 | 7 | 37 | 550 | 20350 | 100 | 3700
7 | Supplying, fixing and testing of modular type computer Jack RJ 11 with safety shutter ISI mark approved make duly erected with face plate, G.I back box with all connections, accessories required to complete the work. | 13 | Nos | 1 | 1 | 1 | 1 | 1 | 1 | 6 | 1 | 0 | 550 | 0 | 100 | 0
8 | Supply, installation, testing and commissioning of following jelly filled armoured cable of 0.5mm dia PVC insulated copper conductor telephone cabling from the telephone tag blocks to Main telephone tag block through provided raceways/Cable tray in LV shaft. | [10 empty] | 0 |  |  |  | 0
8.1 | 50 Pair |  | Rmt.
8.2 | 100 Pair |  | Rmt. | [8 empty] | 0 |  |  |  | 0
8.3 | 200 Pair |  | Rmt. | [8 empty] | 0 |  |  |  | 0
[12 empty] | 0 |  |  |  | 0
9 | Supply & ITC of G.I telephone tag block with KRONE terminal modules/ connectors as specified & compete with all interconnections on all floors
9.1 | 50 pair tel. tag block |  | Each | [8 empty] | 0 |  |  |  | 0
9.2 | 100 pair tel. tag block |  | Each | [8 empty] | 0 |  |  |  | 0
9.3 | 200 pair tel. tag block |  | Each | [8 empty] | 0 |  |  |  | 0
| TOTAL CARRIED TO SUMMARY | [12 empty] | 125750 |  | 56400