## All Summary
VYAN VENTURES PVT LTD
| Description of Work | Vyan Venture-R1 | PO Amount
| DEMOLITION WORKS | 0
| CIVIL WORKS | 651199.609
| CIVIL WORK | 1033455.9896
| CEILING WORK | 435360.5908
| PAINTING WORK | 96238.744
| TOTAL DOORS | 55000
| TOTAL CARPENTRY WORK | 3157283.667
| GLASS AND MIRROR WORKS | 120582.6146
| METAL WORKS | 0
| SANITARY FITTING WORKS | 0
| Summary of Civil works aganist PO (A) | 5549121.215 | 5927537
| Summary of Plumbing works against PO (B) | 548294.4024 | 215550
| Discount (C ) | 442888
| Total Amount CIVIL AND PLUMBING (D)= (A+B)-C | 5654527.6175 | 6143087
| Total Amount D+E | 5654527.6175 | 6143087
| Eletrical work aganist PO | 2084647.5 | 2105826
| NET TOTAL | 7739175.1175
| IGST @18% | 1393051.5211 | 1105755.66
| GRAND TOTAL with Taxes | 9132226.6386 | 9354668.66
| GRAND TOTAL with Taxes | 9132226.6386

## C&I BOQ
[7 empty] | Vyan Ventures-R1-ACTUAL QNTY |  |  | TENDER QNTY
Sr no | item | Description | UNIT | NO | MEASUREMENT |  | QUANTITY | Rate | Amount | QUANTITY | Rate | Amount
| GENERAL SITE WORKS |  |  |  | L | B
1 | Pest control at site | Providing Pest Control & Anti-termite treatment by appointing a specialized agency as per the specifications mentioned by the Bureau of Indian Standard & Agencies specification ( Whichever is higher ) for General Civil , Plumbing / Drainage & timber / Carpentry works , Gypsum related work including 5 Years guarantee under suitable undertaking on stamp paper etc complete as directed . ( Mode of Measurement to be on carpet area of floor & not the area of surface treated.) | SQFT | 1 | 92 | 136 | 0 | 6 | 0 | 5000 | 6 | 30000
2 | Site Barricading | Providing and fixing flex board out. Cost to include framework cost, opening for door, flex printing and installation. ( digital file provided by client ) Sizes as mentioned below | [5 empty] | 150 | 0 | 10 | 150 | 1500
DEMOLITION WORKS
1 | Demolition Work | Dismantling / Demolishing the following and carting away the debris from the site and unloading at a approved location as per statutory rules and regulations. | N.A | N.A | SFT
2 | Wall Chasing | Chasing in existing brick/siphorex/concrete wall, up to 200mm wide and 75mm deep, for installation of A.C. copper pipes/drain pipes, electrical conduits as required and making good of chases with cement plaster/POP ready for application of paint. | N.A | N.A | SFT |  |  |  |  | 50 | 100 | 5000
3 | Wall Puncture | Making punctures in existing brick/siphorex/concrete wall block for passing A.C. copper pipes/drain pipes as required and making good the same with cement plaster/POP. | N.A | N.A | NOS |  |  |  |  | 10 | 400 | 4000
4 | Core Cut | Core cuts in mother slab for drain pipes 200mm dia as per required and making good the same with cement plaster and waterproofing before slab waterproofing and kobah. | N.A | N.A | NOS |  |  |  |  | NA
5 | Debris | Removing Debris out of site included loading, unloading & shifting as per statutory rules and regulations. | N.A | N.A | NOS |  |  |  |  | 2 | 4000 | 8000
|  | TOTAL OF DEMOLITION WORKS | [6 empty] | 0 |  |  | 48500
INTERIOR CIVIL WORKS
1 | Waterproofing | P&A Waterproofing on mother slabs & wall till 600mm height, with 4 coats of chemical (Zypex or Equivalent chemical to be used) treatment on the mother slab, before doing the treatment mother slab needs to clean properly up to the mark & dust free surface needs to achieve to apply the chemical (proof bond /BASF, Dr. Fixit / Equivalent make) & chemical needs to dry properly, After all there should be a water pond testing to be done for water tightness & rectifications of defects if any. Complete with 10 years performance guarantee with client's satisfaction. Entire process to be done under guideline & supervision of appointed engineering team.
|  | wall | SQFT | 6 | 1 | 2 | 12 |  |  | 0
|  | wall | SQFT | 6 | 1 | 1 | 6 |  |  | 0
|  | DOMINOSE GT | SQFT | 3 | 1 | 2 | 6 |  |  | 0
|  | GT FLOOR | SQFT | 5 | 1 | 1 | 5 |  |  | 0
|  | DHABA GT | SQFT | 12 | 1 | 1 | 12 |  |  | 0
|  | floor | SQFT | 3 | 1 | 1 | 3 |  |  | 0
|  |  | SQFT | 9 | 1 | 4 | 36 |  |  | 0
|  |  | SQFT | 9 | 1 | 1 | 9 |  |  | 0
|  |  | SQFT | 3 | 1 | 2 | 6 |  |  | 0
|  | NOODLES GT | SQFT | 3 | 1 | 1 | 3 |  |  | 0
|  |  | SQFT | 12 | 1 | 1 | 12 |  |  | 0
|  | GIANIS GT FLOOR | SQFT | 4 | 1 | 1 | 4 |  |  | 0
|  |  | SQFT | 4 | 1 | 1 | 4 |  |  | 0
|  | HANDWASH COMMON AREA | SQFT | 1 | 1 | 1 | 1 |  |  | 0
|  |  | SQFT |  |  |  | 67 | 60 | 4020 | 0 | 60 | 0
2 | Block Work | Providing and constructing Light weight blocks masonry in cement mortar 1:4 of approved make like Aerocon/Siporex etc. Job to include raking out joints, scaffolding, making openings walls, curing etc. in substructure and superstructure to its true line & level in cement mortar proportion as specified in all shapes, size, at all heights, depths, leads & locations etc. complete. The rate shall also include for cleaning of surface, hacking of RCC surface in contact with brickwork, racking of joints, providing, erecting, & dismantling steel scaffolding , curing for 10 days, including 75 mm thk. R.C.C. stiffener at approximately every 1000 mm ht. with required M.S. reinforcement bars and Lintels for Doors and wall openings etc. compete as per the drgs., details & specifications.
a
[10 empty] | 0 | 140 | 0
| Internal Plaster | P&A of single coat backing plaster of 15-18 mm thick in CM 1:4 proportion to the walls & others surface including scaffolding, curing the joints, etc. The rates are inclusive of providing chicken mesh of 18mm gauge & 150mm width at junction of brick & RCC etc. at the walls, columns, beams etc., seven days water treatment as anti crack of plaster. Complete as per site engineer's instruction.
0
0
[10 empty] | 0 | 35
| PCC Work | Providing and laying up to 50-75 mm thick cement concrete flooring with 1:2:4 cement concrete laid to proper level and slope in alternate bays including compactions, filling joints, or as directed, finishing smooth with cement Mortar 1:1 of sufficient minimum thickness to give a smooth & even surface and curing etc. complete as per architects instructions.
|  | BIKANERWALA | SQFT | 1 | 46.416 | 22.75 | 1055.964 |  |  | 0
|  | DOMINOSE | SQFT | 1 | 41 | 21.5 | 881.5 |  |  | 0
|  | DOMINOSE MAMAGER TABLE PLATOFRM | SQFT | 1 | 4 | 2 | 8 |  |  | 0
|  | DISHWASH / GARBAGE ROOM | SQFT | 1 | 13.66 | 11.33 | 154.7678 |  |  | 0
|  | BIKANERWALA RETAIL | SQFT | 1 | 24 | 7.66 | 183.84 |  |  | 0
|  | TEA CONCEPT | SQFT | 1 | 11.75 | 7.66 | 90.005 |  |  | 0
|  | DHABA | SQFT | 1 | 22 | 22.5 | 495 |  |  | 0
|  | NOODLES WOK | SQFT | 1 | 17.75 | 8.833 | 156.7858 |  |  | 0
3 |  | CAFFECCINO | SQFT | 1 | 21 | 7.33 | 153.93 |  |  | 0
|  | GIANIS | SQFT | 1 | 16.166 | 8.833 | 142.7943 |  |  | 0
|  | ROLL KING | SQFT | 1 | 16.166 | 8.5 | 137.411 |  |  | 0
|  |  | SQFT |  |  |  | 3459.9978 | 65 | 224899.8588 | 2000 | 65
| IPS Work | Providing and laying cement concrete flooring 25 - 40 mm thick , C.M. 1:3 laid to proper level and slope cost should including compaction as directed and curing complete in all respect. | [5 empty] | 75 |  |  | 75
| COBA Work | CINDER BLOCK COBA of Avg. thickness mentioned below; After laying of soil pipes, floor traps is completed the floor of the sunken portion shall be covered with cinder coba embedded manually with 15-20 mm wide joints in 20 mm thk. Waterproofing mortar 1:4 ( 1 cement : 4 coarse sand )in layers upto the full ht. of sunken portion, having top layer of 50 mm thk waterproof mortar 1:4 ( 1 cement : 4 coarse sand ) using specialized W.P. chemical, finished smooth / rough with floating coat of neat cement all complete and as per specification.
Kitchen at 250mm
|  | same as pcc | SQFT |  |  |  | 3459.9978
|  | TERRACE | SQFT | 2 | 7 | 7 | 98 |  |  | 0 |  | LL SCOPE
|  | TERRACE | SQFT | 1 | 19 | 6 | 114 |  |  | 0 |  | LL SCOPE
|  |  | SQFT |  |  |  | 3671.9978 | 115 | 422279.7502 | 2000 | 115 | 230000
| Tread and riser | Providing and constructing 18 mm thk Black leather finish Granite steps as per drawings. includes of making all groove/chamfering/rounding/hole where ever required, in proper line and level in all direction, polishing/finishing etc. Complete as per detail drawing, specification and as directed by PMC. | [5 empty] | 415 | 0 |  | 415 | 0
|  | TOTAL OF CIVIL WORKS | [6 empty] | 651199.609 |  |  | 230000
STONE AND TILE WORKS
| KOTA Flooring | Providing and Laying KOTA stone of 19mm thk. on avg 40 mm thk bed of 1:4 cement mortar in proper line and level including neat cement float, filling joints with neat cement slurry of appropriate colour, cleaning, curing, rubbing, complete. Scope includes laying of floor protective cover on the floor and removing of the same when directed along with supply of all necessary materials, labour, tools and tackles complete in line with the Technical Specification, Drawings and as per the direction of the Architect & PMC. Including Polishing.
4 |  | Size : 550x550 mm Basic Rate : 55/SFT
|  | BIKANERWALA | SQFT | 1 | 46.166 | 22.75 | 1050.2765 |  |  | 0
|  | BIKANERWAL RETAIL | SQFT | 1 | 23.66 | 7.916 | 187.2926 |  |  | 0
|  | DISHWASH GARAGE | SQFT | 1 | 13.66 | 11.33 | 154.7678 |  |  | 0
|  | TEA CONCEPT | SQFT | 1 | 11.75 | 7.916 | 93.013 |  |  | 0
|  | DHABA | SQFT | 1 | 22 | 22.5 | 495 |  |  | 0
|  | NOODLES WOK | SQFT | 1 | 17.75 | 8.75 | 155.3125 |  |  | 0
|  | CAFECCINO | SQFT | 1 | 21 | 7.25 | 152.25 |  |  | 0
|  | ROOLS KING | SQFT | 1 | 16.166 | 8.5 | 137.411 |  |  | 0
|  | GIANI | SQFT | 1 | 16.583 | 8.833 | 146.4776 |  |  | 0
|  | DOMNOSE COLD ROOM | SQFT | 1 | 9.583 | 9.583 | 91.8339 |  |  | 0
|  |  | SQFT | 1 | 10.66 | 4 | 42.64 |  |  | 0
|  | BIKANERWALLA DISMANTELLING OF KOTA FLOORING FOR OVEN DRAIN SHIFTING | SQFT | 1 | 10 | 2 | 20 |  |  | 0
|  |  | SQFT |  |  |  | 2726.2749 | 140 | 381678.4843 | 6460 | 140 | 904400
| KOTA Skirting | Fixing & laying of 75mm high tiles for skirting with bedding of appropriate approved make adhesive & colour joint filler inclusive of making all groove/chamfering/rounding/hole where ever required, in proper line and level in all direction, polishing/finishing/cleaning etc. Complete as per detail drawing, specification and as directed by PMC.
7
|  | BIKANERWALA SERVICE COUNTER | RFT | 1 | 46.25 |  | 46.25 |  |  | 0
|  | OVEN WALL | RFT | 2 | 46.25 |  | 92.5 |  |  | 0
|  | LESS DOOR | RFT | -2 | 3 |  | -6 |  |  | 0
|  | COLD ROOM | RFT | 1 | 28.916 |  | 28.916 |  |  | 0
|  | SINK AREA TO STORE ROOM AROUND MEASUREMENT | RFT | 1 | 29 |  | 29 |  |  | 0
1 |  | STORE INSIDE | RFT | 1 | 23.083 |  | 23.083 |  |  | 0
|  | BIKANER& DOMINISE CENTER WALL | RFT | 1 | 15.5 |  | 15.5 |  |  | 0
|  | LT PANEL BIKANERWALA INSIDE | RFT | 1 | 24 |  | 24 |  |  | 0
|  | CASH COUNTE SIDE | RFT | 1 | 7.583 |  | 7.583 |  |  | 0
|  | TILES SKIRTING AROUND MEASURED | RFT | 1 | 28 |  | 28 |  |  | 0
|  | LESS | RFT | -1 | 3.33 |  | -3.33 |  |  | 0
|  | GRANITE DOOR JAMBS | RFT | 1 | 6.33 |  | 6.33 |  |  | 0
|  | DHABA SERVICE COUNTER | RFT | 2 | 22.33 |  | 44.66 |  |  | 0
|  | HOODWALL | RFT | 2 | 16.66 |  | 33.32 |  |  | 0
|  | DB WALL | RFT | 2 | 22.33 |  | 44.66 |  |  | 0
|  | BACK SIDE | RFT | 2 | 11 |  | 22 |  |  | 0
|  | SINK WALL | RFT | 2 | 6.416 |  | 12.832 |  |  | 0
|  | BACK DOOR LESS | RFT | -2 | 4 |  | -8 |  |  | 0
|  | GIANIS | RFT | 2 | 16.583 |  | 33.166 |  |  | 0
|  |  | RFT | 2 | 8.833 |  | 17.666 |  |  | 0
|  | LESS FLUSH DOOR | RFT | -1 | 2.5 |  | -2.5 |  |  | 0
|  | BIKNERWAL RETAIL AREA | RFT | 2 | 23.833 |  | 47.666 |  |  | 0
|  |  | RFT | 2 | 7 |  | 14 |  |  | 0
|  | TEA CONCEPT | RFT | 2 | 11.75 |  | 23.5 |  |  | 0
|  |  | RFT | 1 | 15.5 |  | 15.5 |  |  | 0
|  | door less in retail | RFT | -1 | 2.66 |  | -2.66 |  |  | 0
|  | GIANIS | RFT | 1 | 16.083 |  | 16.083 |  |  | 0
|  |  | RFT | 1 | 16.25 |  | 16.25 |  |  | 0
|  |  | RFT | 1 | 9.66 |  | 9.66 |  |  | 0
|  |  | RFT | 1 | 6.5 |  | 6.5 |  |  | 0
2
|  |  | RFT |  |  |  | 636.135 | 80 | 50890.8 | 565 | 80 | 45200
| Decorative Wall Tiles | Providing and fixing Glazed Decorative wall tiles which includes-approved make of adhesive like bal Endura or equivalent, grey cement paste with backing coat of 1:3 cement mortar not less than 12mm thick as & where ever required, joint filler of approved make and colour, as and where ever required, in proper line and level in all direction, at all height with lead and lift, polishing/finishing/cleaning etc as per design, drawing and directed by PMC etc. all complete. | [5 empty] | 0 | 0 |  | 0 | 0
Size- Subway Tile: 100 X 300 mm Rate : 60/ SFT
|  | GIANIS WALL TILES | SQFT | 2 | 16.583 | 8 | 265.328 |  |  | 0
|  |  | SQFT | 1 | 8.833 | 8 | 70.664 |  | 0 | 0 |  | 0
|  | NOODLE WOK | SQFT | 1 | 20 | 8 | 160 |  | 0 | 0 |  | 0
|  | WALL TILE COLOUMN | SQFT | 1 | 1.66 | 8 | 13.28 |  | 0 | 0 |  | 0
|  | WALL TILES | SQFT | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0
|  | CAFFECCINO | SQFT | 1 | 21 | 1 | 21 |  | 0 | 0 |  | 0
|  | NOODLE WOK WALL TILES SIDE | SQFT | 1 | 7 | 3 | 21 |  | 0 | 0 |  | 0
|  |  | SQFT | 1 | 8.25 | 3 | 24.75 |  | 0 | 0 |  | 0
|  |  | SQFT |  |  |  | 576.022 | 142 | 81795.124 | 5125 | 142 | 727750
| Sada wall tiles | Providing and fixing sada wall tiles white color which includes-approved make of adhesive like bal Endura or equivalent, grey cement paste with backing coat of 1:3 cement mortar not less than 12mm thick as & where ever required, joint filler of approved make and colour, as and where ever required, in proper line and level in all direction, at all height with lead and lift, polishing/finishing/cleaning etc as per design, drawing and directed by PMC etc. all complete.
Size: 300 X 600 mm Rate : 45/ SFT
|  | BIKANERWALL FRONT SERVCIE COUNTER | SQFT | 1 | 46.08 | 3 | 138.24
|  | OVEN WALL | SQFT | 1 | 46.083 | 8 | 368.664
|  | LESS DOOR | SQFT | -1 | 3 | 7 | -21
|  | COLD ROOM WALL | SQFT | 1 | 36.25 | 8 | 290
|  | LESS COLD ROOM DOOR | SQFT | -1 | 4 | 7 | -28
|  | SINK STORAGE OUTER ROUND AREA | SQFT | 1 | 29 | 8 | 232
|  | STORE INSIDE MEASURED | SQFT | 1 | 26 | 8 | 208
|  | BIKANER AND DOMISE CENTER WALL | SQFT | 1 | 7 | 8 | 56
|  | CASH COUNTER SIDE WALL LT OANEL BIKANER INSIDE | SQFT | 1 | 23.5 | 8 | 188
|  | DISHWASH / GARBAGE WALL | SQFT | 0 | 0 | 0 | 0
|  |  | SQFT | -1 | 27.5 | 8 | -220
|  | LESS DOOR | SQFT | -1 | 3.25 | 7 | -22.75
|  | WALL DISHWASH | SQFT | 2 | 0 | 0 | 0
|  | LESS DOOR | SQFT | -1 | 3 | 7 | -21
|  | LESS | SQFT | -1 | 4.583 | 2.25 | -10.3117
|  | ADD | SQFT | 1 | 5.25 | 1 | 5.25
|  |  | SQFT | 1 | 2.33 | 3 | 6.99
|  |  | SQFT | 1 | 4 | 1 | 4
3 |  |  | SQFT | 1 | 3 | 1 | 3
|  | DISHWASH | SQFT | -2 | 11.66 | 8 | -186.56
|  |  | SQFT | -2 | 8 | 8 | -128
|  | LESS DOOR | SQFT | -1 | 4 | 6.75 | -27
|  | PLUS |  |  |  |  | -18
|  | ADHOK QUANTITY | SQFT |  |  |  | 0
|  | DHABA HOOD WALL | SQFT | 1 | 16.5 | 8 | 132
|  | RACK WALL | SQFT | 2 | 11 | 8 | 176
|  | SINK WALL | SQFT | 1 | 6.416 | 7 | 44.912
|  | DB WALL | SQFT | 1 | 13.5 | 8 | 108
|  | EXISTING WALL BACKSIDE | SQFT | 1 | 16 | 8 | 128
|  | SERVCIE COUNTER | SQFT | 1 | 21.166 | 3 | 63.498
4 |  | NODLES WOK SERVICE COUNTER | SQFT | 1 | 14.83 | 3 | 44.49
|  | CAFECCINO | SQFT | 1 | 21 | 3 | 63
|  | GIANISFRONT COUNTER | SQFT | 1 | 6 | 3 | 18
|  | DOMINOSE FRONT COUNTER | SQFT | 1 | 18 | 3 | 54
|  | SPLIT AC | SQFT | 1 | 23.166 | 8 | 185.328
|  | DB WALL | SQFT | 1 | 16.416 | 8 | 131.328
|  | PATITION WALL AOUND MEASURED | SQFT | 1 | 9 | 8 | 72
|  | NEAR PARTITION WALL UPTO SINK | SQFT | 1 | 19.75 | 8 | 158
|  | DOOR WALL TO COLD ROOM | SQFT | 1 | 13.33 | 8 | 106.64
|  | LESS DOOR | SQFT | -2 | 3 | 7 | -42
|  | EXISTING WALL AREA AROOUND MEASURED | SQFT | 1 | 21 | 8 | 168
|  | LEE DOOR | SQFT | 2 | 3 | 7 | 42
|  | OVEN WALL BACK WALL | SQFT | 1 | 4 | 8 | 32
|  | ADHOK QUANTITY MAKING OF FIRST TIME | SQFT |  |  |  | 0
|  | GT | SQFT | 6 | 3 |  | 18
|  |  | SQFT | 1 | 4 | 1 | 4
|  | LESS DOOR | SQFT | -1 | 3.25 | 7 | -22.75
|  |  | SQFT | 1 | 4.166 | 8 | 33.328
|  |  | SQFT | 1 | 4 | 1 | 4
|  |  | SQFT | 1 | 1 | 8 | 8
|  |  | SQFT | 1 | 1 | 3.25 | 3.25
|  | CAFFECCINO | SQFT | 1 | 5 | 3 | 15
|  |  | SQFT | 1 | 5 | 3 | 15
|  |  | SQFT | 1 | 1 | 3 | 3
|  |  | SQFT |  |  |  | 2583.5462 | 125 | 322943.2812 | 8560 | 125 | 1070000
| Pick up / Take away counter | P/F 300mm wide platform to be made of 19mm thk granite finish top. Including fittings such as hinges; handles; ball catch etc. complete in all respect. The rates for the Shutters to be included. as per design and details. | [5 empty] | 450 | 0 | 35 | 450 | 15750
Basic Rate: 275/ SFT
| Window/ door jamb | Providing & Fixing polished Jet black granite stone /Approved stone in "Z" Door Jambs, Window Cills, Architrave, ledge wall top etc. (maximum width upto 300mm) in cement mortar 1:3 & in cement slurry, including necessary filing joints in white cement pigmented to approved shade. Also includes necessary edge polishing, champhering, moulding etc complete as per the direction of INOX. Basic Rate of Black Granite : Rs 150/- per Sft. (Granite shall be Procured by Contractor)
Basic Rate: 275/ SFT
|  | BIKANERWALA COLD ROOM | RFT | 1 | 3.833 |  | 3.833 |  |  | 0
|  | STAFF NESSAGE AREA | RFT | 1 | 3.333 |  | 3.333 |  |  | 0
|  | PICKUP WINDOW | RFT | 1 | 3.333 |  | 3.333 |  |  | 0
|  | HANDWASH AREA | RFT | 1 | 4.25 |  | 4.25 |  |  | 0
[7 empty] | 0 |  |  | 0
|  |  | RFT |  |  |  | 14.749 | 450 | 6637.05 | 0 | 450 | 0
| SS Corner Guard | P&F of 304 grade 3mm thick SS Corner guard (30mm x 30mm, mat finished as per approved sample) fixing with SS full thread screws on each corner of the kitchen's wall before cladding of tiles, so that the corner may be protected from the damages. Complete in proper line & level and site engineer's instruction.
|  | BIKANERWALA | RFT | 16 | 8 |  | 128 |  |  | 0
|  | DOMINOSE | RFT | 22 | 8 |  | 176 |  |  | 0
|  | PICK UP WINDOW | RFT | 0 | 8 |  | 0 |  |  | 0
|  | GARBAGE ROOM | RFT | 1 | 8 |  | 8 |  |  | 0
|  | DISHWASH | RFT | 1 | 8 |  | 8 |  |  | 0
|  | DHABA | RFT | 9 | 8 |  | 72 |  |  | 0
|  | NOODLE WOK | RFT | 2 | 8 |  | 16 |  |  | 0
|  | ALUMNIUM POWDER COATED | RFT | 34 | 8 |  | 272 |  |  | 0
|  |  | RFT |  |  |  | 680 | 250 | 170000 | 400 | 250 | 100000
| T-Section | Providing and fixing of 18mm thk SS T-section on joints between G.I. sheet and brick tile panelling including coating/ finishing/supporting/cutting/required fixture & fasteners etc. as per design, drawing & as directed by Project Manager etc. complete. | [7 empty] | 700 | 300 | 210000
| Tile protection | Providing 6mm thk MDF sheet covering on flooring. | SQFT | 1 | 41.25 | 21.5 | 886.875 | 22 | 19511.25 | 2000 | 22 | 44000
DOMINOSE
|  | TOTAL OF CIVIL WORK | [6 empty] | 1033455.9896 |  |  | 3117100
CEILING WORK
7
| Metal Ceiling | Fitting of false ceiling consisting of 20g non-perforated aluminium planks made of pre-coated ( Top & Bottom ) & Size : 600mmx600mm tiles . False Ceiling with necessary supports , hangers etc. provided to install light fitting , fresh air grill etc. ( from Hunter Douglas /Armstrong or equivalent.)
Size: 600 X 600 mm Rate :150/ SFT
8 |  | BIKANERWALA | SQFT | 1 | 46.083 | 22 | 1013.826 |  |  | 0
|  | LESS COLD ROOM AREA | SQFT | 1 | 17 | 8 | 136 |  |  | 0
|  | GIANIS CEILING | SQFT | 1 | 16.583 | 8.833 | 146.4776 |  |  | 0
|  | BIKANERWAL | SQFT | 1 | 23.66 | 8 | 189.28 |  |  | 0
|  | NOODLES WOK | SQFT | 1 | 17.66 | 8.416 | 148.6266 |  |  | 0
|  | DHABA | SQFT | 1 | 22 | 22.25 | 489.5 |  |  | 0
|  |  | SQFT |  |  |  | 2123.7102 | 205 | 435360.5908 | 4760 | 205 | 975800
| Trap Door | Providing and fixing trap doors for access to the service areas. The trap door shall have an external frame made of 50mm x 50mm in good quality seasoned wood scantling on which the shutter is hinged. Shutter shall be made of 19 mm. Plywood. The exposed side & Internal side shall be laminate finish. Concealed heavy duty hinges shall be used to mount the shutters and locking shall be provided with Allen key and panel locks. Sufficient number of hinges and locks shall be provided to avoid sagging of the shutter. Key also shall be supplied
|  | Size : 3' x 3' | NO |  |  |  |  | 3500 | 0 | 0 | 3500 | 0
9
| Gypsum ceiling | Providing, making and fixing of POP false ceiling as per manufacturer design and drawing including cut-outs for hvac grille, lights etc.at any / all heights. Rate quoted should be including of vertical drop of any heights, mouldings and size mentioned in drawings with necessary required framing in 450x 900 ultra Gyproc sections, fittings, and fixtures, scaffolding, floor covering, masking tape and cleaning the area all complete as per drawing, design & manufactures specification all complete. Rates do not include painting work.
|  |  | SQFT |  |  |  |  | 140 |  | 1250 | 140 | 175000
| Metal Ceiling (Rafter) | Fitting of false ceiling consisting of 20g Aluminium planks made of pre-coated ( Top & Bottom ) & Size : 20mmx40mm rafter . False Ceiling with necessary supports , hangers etc. provided to install light fitting , fresh air grill etc. ( from Hunter Douglas or Armstrong ) | [5 empty] | 160 | 0 |  | 160 | 0
10 |  | Basic cost= 500/SFT
11 |  | TOTAL OF CEILING WORK | [6 empty] | 435360.5908 |  |  | 1150800
POP AND PAINITNG WORK
| POP Punning | Providing and applying Plaster of Paris punning of average thickness 12-18mm to existing wall surfaces in true level and plumb complete as per design and drawing Cleaning the surface properly with sand paper, filling cracks/holes with plaster of Paris. Applying lambi / putty (lambi/putty will be of good quality) sand papering the putty work on chamfers, etc.at any / all heights. Rate include cost for making grooves up to 12mm thick if required in horizontal or vertical direction near doors, windows, skirting, floor covering, masking tape and cleaning the area all complete as per drawing, design & manufactures specification. | [5 empty] | 50 |  |  | 50
1 | Wall Paint | Providing & applying three (03) coats of approved Plastic paint on walls including scraping, primer , filling with putty etc. complete with final coat no brush mark to be visible after painting colour shade as specified.
|  | gianis logo wall paint armeasured | SQFT | 1 | 26.75 | 9.5 | 254.125 |  |  | 0
|  | gianis bulhead in side paint | SQFT | 1 | 16.5 | 1.833 | 30.2445 |  |  | 0
|  | gianis store wall paint | SQFT | 2 | 16.583 | 4 | 132.664 |  |  | 0
|  | geyser wall | SQFT | 1 | 8.25 | 4 | 33 |  |  | 0
|  | main entry façade wall paint | SQFT | 1 | 52.16 | 16.75 | 873.68 |  |  | 0
|  | less main entry door | SQFT | -2 | 10.75 | 16.75 | -360.125 |  |  | 0
|  | main entry door patta | SQFT | 4 | 16.75 | 1 | 67 |  |  | 0
|  | patta above glass door | SQFT | 2 | 1 | 10.75 | 21.5 |  |  | 0
|  | main entry right and left hand wall above brick tile | SQFT | 2 | 8 | 8 | 128 |  |  | 0
2 |  | caffeccino coloumn aint | SQFT | 2 | 7 | 8 | 112 |  |  | 0
|  | ceiling paint as per gyosum ceiling | SQFT |  |  |  | 0 |  |  | 0
|  | MACHINE WALL | SQFT | 1 | 17.5 | 5.166 | 90.405 |  |  | 0
3 |  | OVEN WALL COLD ROOM SIDE | SQFT | 2 | 13 | 5.166 | 134.316 |  |  | 0
|  |  | SQFT |  |  |  | 1516.8095 | 28 | 42470.666 | 0 | 28 | 0
| Ceiling Paint | Providing & applying three (03) coats of approved Plastic paint on exposed surface on ceiling including scraping, primer , filling with putty etc. complete with final coat no brush mark to be visible after painting colour shade as specified.
|  | dominose ceiling paint | SQFT | 1 | 41 | 21 | 861 |  |  | 0
|  | mdf paint above cold room | SQFT | 2 | 10 | 6 | 120 |  |  | 0
wall paint
|  | ac spilt wall | SQFT | 1 | 12.33 | 5 | 61.65 |  |  | 0
4 |  | db wall | SQFT | 1 | 17.083 | 5 | 85.415 |  |  | 0
|  | partition wall | SQFT | 1 | 9 | 5 | 45 |  |  | 0
|  | partition wall to sink wall | SQFT | 1 | 19 | 5 | 95 |  |  | 0
|  | door wall to cold room | SQFT | 1 | 17 | 5 | 85 |  |  | 0
|  | cold room back wall | SQFT | 2 | 10 | 5.33 | 106.6 |  |  | 0
|  | buldhead paint inside | SQFT | 1 | 18.5 | 6.666 | 123.321 |  |  | 0
|  | ice machine wall paint | SQFT | 0 | 0 | 0 | 0 |  |  | 0
1 |  | oven wall paint | SQFT | 1 | 21.25 | 5.33 | 113.2625 |  |  | 0
|  | raceway paint | SQFT | 1 | 88 | 1.25 | 110 |  |  | 0
2 |  | raceway paint | SQFT | 1 | 44 | 0.66 | 29.04 |  |  | 0
|  | beam | SQFT | 4 | 1 | 21.25 | 85 |  |  | 0
|  |  | SQFT |  |  |  | 1920.2885 | 28 | 53768.078 | 1250 | 28 | 35000
| Exposed duct Paint | Providing & applying Three (03) coats of approved paint on exposed ceiling area including HVAC ducts, Sprinkler Pipes etc. as instructed etc. complete with final coat no brush mark to be visible after painting colour shade as specified. | [5 empty] | 28 | 0 |  | 28 | 0
|  | TOTAL OF PAINTING WORK | [6 empty] | 96238.744 |  |  | 35000
CARPENTARY WORKS-DOORS
| Door (Kitchen and common area) | Providing & fixing in position FR Door made up of 38mm thick commercial flush door shutter of approved make & thickness, Inner sidefinished with laminate and outer side with laminate finish including providing & fixing 12 mm thk Wooden lipping all around, including P/F of Door frame made out of CP Teak / Ash wood or equivalent with melamine polish finish. Size of the frame approximate 175mm wide X 50mm thick. Applicable hardware's such as s/s handles, floor spring and any other hardware etc required to complete the related works as per design & detail. door hardware make consider Dorma / Hafele/Ozon /equilient
|  | a. Outlet: 1- Back door Double Leaf | [5 empty] | 30000 | 0 |  | 30000 | 0
|  | Internal doors | [5 empty] | 30000 | 0 |  | 30000 | 0
|  | b. Outlet: 2- Back door Double Leaf | [5 empty] | 30000 | 0 |  | 30000 | 0
|  | Internal doors | [5 empty] | 27500 | 0 |  | 27500 | 0
|  | c. Outlet: 3: BIKANERWALA- Back door Double Leaf | [5 empty] | 30000 | 0 |  | 30000 | 0
|  | Internal doors | [5 empty] | 27500 | 0 |  | 27500 | 0
|  | d. Outlet: 4- Back door Double Leaf | [5 empty] | 30000 | 0 |  | 30000 | 0
|  | Internal doors | [5 empty] | 27500 | 0 |  | 27500 | 0
|  | e. Outlet: 5: Back door Double Leaf | [5 empty] | 25000 | 0 |  | 25000 | 0
|  | Internal doors | [5 empty] | 27500 | 0 |  | 27500 | 0
f. Outlet: 6- Back door
Internal doors
g. Outlet: 7: GIANI'S- Back door Double Leaf
Outlet: 7- pick-up side door
a. Kiosk: 1 : TEA CONCEPT
b. Kiosk: 2 & 3: BIKANERWALA RETAIL
c. Kiosk: 5
d. Kiosk: 6
e. Kiosk: 7
|  | Admin Area | NO |  |  |  | 0 | 27500 | 0 | 0 | 27500 | 0
|  | Admin Area service door Double Leaf | [5 empty] | 30000 | 0 |  | 30000 | 0
|  | Handwash area door | [5 empty] | 30000 | 0 |  | 30000 | 0
4 |  | DOMINOSE DOOR WITH DOOR FRAME AS APPROVED | NO |  |  |  | 2 | 27500 | 55000 | 0 | 27500 | 0
| Entry/ Exit glass door | P/F 12 mm thk. double leaf toughened glass door including all necessary required hardware fitting and handles, floor spring and any other hardware etc required to complete the related works as per design & detail. door hardware make consider Dorma / Hafele/Ozon /equilient | [5 empty] | 58000 | 0 |  | 58000 | 0
Size: 2000 (L) X 2400 (H)
|  | TOTAL DOORS | [6 empty] | 55000 |  |  | 0
CARPENTRY WORK
1
1. COUNTER AND BULKHEAD
Counter top (300mm wide) -300mm wide 19mm thick double plywood top made of approved make, bwr grade backing as directed in detail drawing. -plywood top to be fixed on the existing low height wall's -Counter top to be finished with 12mm thk approved shade of corian
Corian Basic Rate: 500/ SFT
|  | bikanerwala | sqft | 1 | 46.25 | 1 | 46.25 |  |  | 0
|  | DOMINOSE. | sqft | 1 | 18 | 1 | 18 |  |  | 0
|  | SUBWAY | sqft | 1 | 13.166 | 1 | 13.166 |  |  | 0
|  | NOODLE | sqft | 1 | 21.166 | 1 | 21.166 |  |  | 0
|  | BURGER | sqft | 1 | 21 | 1 | 21 |  |  | 0
|  | RETAIL | sqft | 1 | 29 | 1 | 29 |  |  | 0
|  | TEA CONCEPT] | sqft | 1 | 11.166 | 1 | 11.166 |  |  | 0
|  | CAFFECCINO | sqft | 1 | 31.75 | 1 | 31.75 |  |  | 0
|  | ROLL KING | sqft | 1 | 8.583 | 1 | 8.583 |  |  | 0
|  | GIANIS | sqft | 1 | 8.666 | 1 | 8.666 |  |  | 0
|  | DHABA | sqft | 1 | 21.666 | 1 | 21.666 |  |  | 0
|  |  | SQFT |  |  |  | 230.413 | 1500 | 345619.5 | 255.8 | 1500 | 383700
Counter panelling (1050 ht.) Corrogated sheets - Upto 1050mm ht. -Providing and fixing Corrogated sheet of size (1-2mm thk 1st Quality) -Cost includes of making 18mm plywood panel fixed on 20 x 40mm Aluminium box frame at 600mm C/C Horiozontaly and verticaly to maintain gap between wall and panel as directed in detail drawing -Bottom finished with 100mm ht & 19 mm thick leather granite skirting at all exposed sides
G.I. Sheet Basic cost= 60/ SFT
|  | bikanerwala restaurant | sqft | 1 | 44.66 | 3.5 | 156.31 |  | 0 | 0 |  | 0
|  | fdu area | sqft | 1 | 5 | 3.5 | 17.5 |  | 0 | 0 |  | 0
|  | bikanerwala retails | sqft | 1 | 23.66 | 3.5 | 82.81 |  | 0 | 0 |  | 0
|  | less ht | sqft | -1 | 11.833 | 1.5 | -17.7495 |  | 0 | 0 |  | 0
|  | making if first time | sqft | 1 | 11.833 | 1.5 | 17.7495 |  | 0 | 0 |  | 0
2 |  | dhaba | sqft | 1 | 21.166 | 3.5 | 74.081 |  | 0 | 0 |  | 0
|  | hold storage -- 2 times (redo as wall collapsed) | sqft | 2 | 28 | 3.5 | 196 |  | 0 | 0
|  | noodles wok | sqft | 1 | 14.916 | 3.5 | 52.206 |  |  | 0
|  | caffeccino | sqft | 1 | 18.833 | 3.5 | 65.9155 |  | 0 | 0 |  | 0
|  | caffeccino | sqft | 1 | 6 | 3.5 | 21 |  | 0 | 0 |  | 0
|  | caffeccino | sqft | 1 | 4 | 3.5 | 14 |  | 0 | 0 |  | 0
|  | gianis | sqft | 1 | 5.66 | 3.5 | 19.81 |  | 0 | 0 |  | 0
|  | rolls king | sqft | 1 | 5.66 | 3.5 | 19.81 |  | 0 | 0 |  | 0
1.1 |  | subway | sqft | 1 | 10.5 | 3.5 | 36.75 |  |  | 0
|  | dominose | sqft | 1 | 18 | 3.5 | 63 |  |  | 0
|  | TEA CONCEPT | sqft | 1 | 8.166 | 3.416 | 27.8951 |  |  | 0
|  |  | SQFT |  |  |  | 847.0876 | 375 | 317657.8335 | 905 | 375 | 339375
Bulkhead (260mm wide) P & F of 25 x 25 mm MS section framework hang from ceiling having 19mm thk plywood boxing. Rate including all necessary hardware fittings to install the hinges,locks, scaffolding, etc. as required on site. Complete as per architectural detail drawing & site engineer's instruction.
|  | above buld head Panelling | sqft | 2 | 89 | 3 | 534 |  |  | 0
|  |  | sqft | 2 | 56.5 | 4 | 452 |  |  | 0
|  | dominose above cold room panelling | sqft | 2 | 10 | 5.33 | 106.6 |  |  | 0
|  | main entry left hand side | sqft | 1 | 8 | 5 | 40 |  |  | 0
|  | gianis wall panelling texture wall | sqft | 2 | 16.583 | 4.25 | 140.9555 |  |  | 0
|  |  | sqft | 1 | 8.5 | 4.25 | 36.125 |  |  | 0
|  | noodles wok panelling | sqft | 2 | 10.583 | 9 | 190.494 |  |  | 0
|  |  | sqft | 1 | 10.5 | 3.5 | 36.75 |  |  | 0
1.2 |  | gianis front coloumn | sqft | 1 | 1.5 | 9.5 | 14.25 |  |  | 0
|  | gianis front area pipe covered | sqft | 1 | 2 | 10 | 20 |  |  | 0
|  | staff mess rooom | sqft | 1 | 8.5 | 2 | 17 |  |  | 0
|  | canera cable | sqft | 1 | 2.166 | 4.666 | 10.1066 |  |  | 0
|  | garrage room | sqft | 1 | 2 | 9.66 | 19.32 |  |  | 0
|  | dominose | sqft | 2 | 2 | 13.75 | 55 |  |  | 0
|  | bikaner pelmt | sqft | 2 | 3.25 | 2.5 | 16.25 |  |  | 0
|  | dhaba pelmet | sqft | 1 | 3.25 | 2.5 | 8.125 |  |  | 0
|  | dhaba pelmet | sqft | 1 | 4.5 | 2.5 | 11.25 |  |  | 0
|  | noodles wok panelling above hood | sqft | 1 | 16.5 | 0.5 | 8.25 |  |  | 0
|  | gianis window packed | sqft | 2 | 5.833 | 4.833 | 56.3818 |  |  | 0
|  | top left window packed | sqft | 2 | 6 | 3 | 36 |  |  | 0
|  |  | sqft | 2 | 3.333 | 5 | 33.33 |  |  | 0
|  | top | sqft | 2 | 6.66 | 3.5 | 46.62 |  |  | 0
|  |  | sqft | 2 | 5.25 | 5.416 | 56.868 |  |  | 0
|  | top | sqft | 2 | 6.25 | 3 | 37.5 |  |  | 0
|  | subway backside window packed | sqft | 2 | 6.083 | 3.5 | 42.581 |  |  | 0
|  |  | sqft | 0 | 0 | 0 | 0 |  |  | 0
|  | handwash pack | sqft | 1 | 6.5 | 3.5 | 22.75 |  |  | 0
|  | pickup window + side | sqft | 3 | 6.5 | 3.5 | 68.25 |  |  | 0
|  | backside | sqft | 8 | 6.5 | 3.5 | 182 |  |  | 0
|  | bikanerwal back window pack both side | sqft | 2 | 6.5 | 3.5 | 45.5 |  |  | 0
1.3 |  | window packed | sqft | 1 | 5.25 | 4.25 | 22.3125 |  |  | 0
|  | window packed near door | sqft | 1 | 4.33 | 2 | 8.66 |  |  | 0
|  | office back window packed | sqft | 2 | 5.25 | 4.916 | 51.618 |  |  | 0
|  | server back window | sqft | 2 | 5.25 | 4.75 | 49.875 |  |  | 0
|  | top | sqft | 1 | 6 | 3.5 | 21 |  |  | 0
|  | dhaba back entry door window | sqft | 1 | 4.33 | 2 | 8.66 |  |  | 0
|  | add | sqft | 1 | 1.66 | 14 | 23.24 |  |  | 0
|  | bikanerwal logo window | sqft | 1 | 3.333 | 5 | 0 |  |  | 0
|  |  | sqft | 1 | 3.33 | 3.6 | 0 |  |  | 0
|  |  | sqft | 1 | 6.25 | 35 | 0 |  |  | 0
|  |  | sqft | 1 | 5.833 | 5 | 0 |  |  | 0
|  |  | sqft | 4 | 5.33 | 4.916 | 0 |  |  | 0
|  |  | sqft | 1 | 6.25 | 3.416 | 0 |  |  | 0
|  | hodl storage | sqft | 1 | 4.75 | 1.5 | 7.125 |  |  | 0
|  | gianis logo & dhaba logo window s | sqft | 2 | 6.416 | 5.25 | 67.368 |  |  | 0
|  | top | sqft | 2 | 6.5 | 3.5 | 45.5 |  |  | 0
|  |  | sqft | 1 | 3.5 | 5.083 | 17.7905 |  |  | 0
|  | top | sqft | 1 | 3.5 | 3.5 | 12.25 |  |  | 0
window boxing
|  | bikannerwal to dhaba | sqft | 2 | 89 | 8.083 | 1438.774 |  |  | 0
|  | dominose to gianis | sqft | 1 | 65 | 8.083 | 525.395 |  |  | 0
|  | dhaba to noodle wok | sqft | 1 | 56.5 | 8.083 | 456.6895 |  |  | 0
|  | less caffeccino | sqft | -1 | 52 | 8.083 | -420.316 |  |  | 0
|  | extended boxing front of gainis in dominose | sqft | 1 | 18 | 6 | 108 |  |  | 0
|  | extend of boxing front of gianis | sqft | 1 | 17.5 | 6 | 105 |  |  | 0
[7 empty] | 0 |  |  | 0
|  |  | SQFT |  |  |  | 4893.1983 | 250 | 1223299.5835 | 1280 | 250 | 320000
Bulkhead panelling A. Front-side -Providing and fixing Corrogated sheet of size (1-2mm thk 1st Quality) on the above frame work (Refer Pt. 1.3.). Rate including all necessary hardware fittings to install the hinges,locks, scaffolding, etc. as required on site. Complete as per architectural detail drawing & site engineer's instruction.
G.I. Sheet Basic cost= 60/ SFT
|  | ac ducting area | sqft | 1 | 81 | 8.5 | 688.5
|  |  | sqft | 2 | 56 | 8.5 | 952
|  | biaknerside | sqft | 1 | 81 | 4.75 | 384.75
|  |  | SQFT |  |  |  | 2025.25 | 250 | 506312.5 | 515 | 250 | 128750
Bulkhead panelling A. Back-side -Providing and fixing of 1mm thk laminate sheet on exiting plywood farming of make Laminate Make - Euro/Greenlam/Merino/ or equivalent
Laminate Sheet Basic Cost= 40/ SFT
Bulkhead panelling- bottom (260mm wide) -Providing and fixing 12mm thk corian sheet on the above frame work (Refer Pt 1.3.). Rate including all necessary hardware fittings to install the hinges,locks, scaffolding, etc. as required on site. Complete as per architectural detail drawing & site engineer's instruction.
Corian Basic Rate: 500/ SFT
|  | bikanr wala | sqft | 2 | 89 | 1 | 178 |  |  | 0
|  | dominose to gianis | sqft | 1 | 65 | 1 | 65 |  |  | 0
|  | dhaba to noodle | sqft | 1 | 57.33 | 1 | 57.33 |  |  | 0
|  | less caffechino | sqft | -1 | 51.5 | 1 | -51.5 |  |  | 0
|  | pick counter window | sqft | 1 | 4 | 1 | 4 |  |  | 0
|  | f. Outlet: 6 | SQFT |  |  |  | 252.83 | 1100 | 278113 | 249.25 | 1100 | 274175
Above bulkhead panelling -Providing and fixing Corrogated sheet of size (1-2mm thk 1st Quality) -Cost includes of making 18mm plywood panel fixed on 40mm Aluminium box frame at 600mm C/C Horiozontaly and verticaly to maintain gap between wall and panel as directed in detail drawing
|  | bikanerwal to dhaba | sqft | 2 | 89 | 5.25 | 934.5 |  |  | 0
|  | dominose to guanis | sqft | 1 | 65 | 5.25 | 341.25 |  |  | 0
|  | dhaba to noodles | sqft | 1 | 56 | 5.25 | 294 |  |  | 0
|  | less caffeccino area | sqft | -1 | 52 | 5.25 | -273 |  |  | 0
|  |  | SQFT |  |  |  | 1296.75 | 375 | 486281.25 | 0 | 375 | 0
Wicket door (1050 ht.) -Flap door with 50mm x 50mm aluminium framework 400 x 400mm C/C Vertically and horizontally in proper line & Level -12mm thick plywood (selected & approved make, bwr grade) to be fixed on the both sides of the framing -Shutters finished with 1mm thk approved shade of G.I. corrugated sheet from front side and backside to be finished in laminate and exposed edges to be finished with corian -Shutters finished with 1mm thk approved shade laminate on the backside
|  |  | NO |  |  |  | 0 | 15000 | 0 | 0 | 15000 | 0
| Partition-01 | P & F of 50mm thk partition including MS framework of ht. 1200mm, finished in laminate on both sides with 100mm thk skirting black leatherite finish granite -75mm wide app. corian band on top the partition | RFT |  |  |  |  | 2000 | 0 |  | 2000 | 0
Plywood - branded Commercial Ply (MR Calibrated, IS 303) -- Greenply or Equivalent brand
Laminate Make - Euro/Greenlam/Merino/ or equivalent (Basic Rate- 40 Sq. ft.)
| Partition-02 | P & F of 50mm thk partition including MS framework of ht. 900mm, finished in laminate on both sides with 100mm thk skirting black leatherite finish granite -75mm wide app. corian band on top the partition | [5 empty] | 1500 | 0 |  | 1500 | 0
1.5 |  | Plywood - branded Commercial Ply (MR Calibrated, IS 303) -- Greenply or Equivalent brand
Laminate Make - Euro/Greenlam/Merino/ or equivalent (Basic Rate- 40 Sq. ft.)
| Banquet seating-01 | Providing, making and fixing sofa made out of wooden frame work and cladded with 12mm thk approved make branded Commercial Ply (MR Calibrated, IS 303) -- Greenply or Equivalent brand & approved leatheratte with required wooden frame finishing/cleaning/cutting/required fixture & fasteners etc. as per design & drawing & as directed by Project Manager etc. complete. Sofa will have high density rubber foam.(Foam used should be approved and to be certified against poisonous and noxious fumes.) including 100mm granite skirting on bottom. Rate includes upholstery of leatheratte. | [5 empty] | 4000 | 0 |  | 4000 | 0
1.6 |  | leatherette Basic cost @ 450 per MTR
Size: 7270 x 600 x 900 mm
| Banquet seating-02 | Providing, making and fixing sofa made out of wooden frame work and cladded with 12mm thk approved make branded Commercial Ply (MR Calibrated, IS 303) -- Greenply or Equivalent brand & approved leatheratte with required wooden frame finishing/cleaning/cutting/required fixture & fasteners etc. as per design & drawing & as directed by Project Manager etc. complete. Sofa will have high density rubber foam.(Foam used should be approved and to be certified against poisonous and noxious fumes.) including 100mm granite skirting on bottom. Rate includes upholstery of leatheratte. | [5 empty] | 4000 | 0 |  | 4000 | 0
leatherette Basic cost @ 450 per MTR
Size: 12800 x 600 x 900 mm
| Planter box-01 (Triangle) | P & F of planter box made of 18mm thk commercial plywood ht. up to 750mm, finished in laminate on all sides with 100mm thk skirting black leatherite finish granite | [5 empty] | 15000 | 0 |  | 15000 | 0
Size: 650 (a) x 650(b) x930(c), ht. 750mm
1.7 | Planter box-02 (Rectangle) | P & F of planter box made of 18mm thk commercial plywood ht. up to 750mm, finished in laminate on all sides with 100mm thk skirting black leatherite finish granite | [5 empty] | 20000 | 0 |  | 20000 | 0
Size: 1900 (a) x 300(b) , ht. 750mm
| Planter box-03 (Triangle) | P & F of planter box made of 18mm thk commercial plywood ht. up to 750mm, finished in laminate on all sides with 100mm thk skirting black leatherite finish granite | [5 empty] | 35000 | 0 |  | 35000 | 0
Size: 2660 (a) x 1880(b) x 1880(c), ht. 750mm
| Planter box-04 (Triangle) | P & F of planter box made of 18mm thk commercial plywood ht. up to 750mm, finished in laminate on all sides with 100mm thk skirting black leatherite finish granite | [5 empty] | 15000 | 0 |  | 15000 | 0
2 |  | Size: 900 (a) x 650(b) x 650(c), ht. 750mm
| Planter box-05 | P & F of planter box made of 18mm thk commercial plywood ht. up to 750mm, finished in laminate on all sides with 100mm thk skirting black leatherite finish granite | [5 empty] | 15000 | 0 |  | 15000 | 0
Size: 235 (a) x 1300 (b) x 1085 (c) X 755 (d), ht. 750mm
| Planter box-06 (Triangle) | P & F of planter box made of 18mm thk commercial plywood ht. up to 750mm, finished in laminate on all sides with 100mm thk skirting black leatherite finish granite | [5 empty] | 25000 | 0 |  | 25000 | 0
3.1 |  | Size: 1365(a) x 1365 (b) x 1925 , ht. 750mm
| Planter box-07 (Triangle) | P & F of planter box made of 18mm thk commercial plywood ht. up to 750mm, finished in laminate on all sides with 100mm thk skirting black leatherite finish granite | [5 empty] | 20000 | 0 |  | 20000 | 0
Size: 1160(a) x 1160 (b) x 1640 (c), ht. 750mm
3.2
| Planter box-08 (Triangle) | P & F of planter box made of 18mm thk commercial plywood ht. up to 750mm, finished in laminate on all sides with 100mm thk skirting black leatherite finish granite | [5 empty] | 20000 | 0 |  | 20000 | 0
Size: 1500 (a) x 1500 (b) x 2120 (c), ht. 750mm
4.1
| Planter box-09 (Triangle) | P & F of planter box made of 18mm thk commercial plywood ht. up to 750mm, finished in laminate on all sides with 100mm thk skirting black leatherite finish granite | [5 empty] | 17000 | 0 |  | 17000 | 0
Size: 1430(a) x 1430 (b) x 2000 (c), ht. 750mm
4.2 | Planter box-10 (Triangle) | P & F of planter box made of 18mm thk commercial plywood ht. up to 750mm, finished in laminate on all sides with 100mm thk skirting black leatherite finish granite | [5 empty] | 15000 | 0 |  | 15000 | 0
Size: 695 (a) x 695 (b) x 980 (c), ht. 750mm
5.1 | Trash Bin Unit- 01 | P/F counters in laminate finished & 600mm wide top finished in black granite having 2no. plywood drawers . The storage under the Counter should be provided Shutters made out of 19mm thk. plywood finished with 1mm thk. laminate on bith side. The shutters to be provided with fittings such as hinges; handles; ball catch, lock etc. complete in all respect. The rates for the Shutters to be included. as per design and details.. | [5 empty] | 20000 | 0 |  | 20000 | 0
5.2 | Trash Bin Unit- 02 | P/F counters in laminate finished & 600mm wide top finished in black granite having 2no. plywood drawers . The storage under the Counter should be provided Shutters made out of 19mm thk. plywood finished with 1mm thk. laminate on bith side. The shutters to be provided with fittings such as hinges; handles; ball catch, lock etc. complete in all respect. The rates for the Shutters to be included. as per design and details.. | [5 empty] | 20000 | 0 |  | 20000 | 0
5.3 | Trash Bin Unit- 03 | P/F counters in laminate finished & 600mm wide top finished in black granite having 2no. plywood drawers . The storage under the Counter should be provided Shutters made out of 19mm thk. plywood finished with 1mm thk. laminate on bith side. The shutters to be provided with fittings such as hinges; handles; ball catch, lock etc. complete in all respect. The rates for the Shutters to be included. as per design and details.. | [5 empty] | 20000 | 0 |  | 20000 | 0
5.4 |  | TOTAL CARPENTRY WORK | [6 empty] | 3157283.667 |  |  | 1446000
GLASS AND MIRROR WORKS
5.5
| Take away/ Pick up Window | P/F 12 mm thk. toughened glass top sliding openable window with50 x 50mm aluminum framework with anodised finished inculding and all necessary required groove, with approved make adhesive and fasteners, cutting/ chamfering/ groove/rounding wherever required, at all height with lead and lift, finishing, cleaning as per design and drawing etc. all complete. | [5 empty] | 17000 | 0 | 5 | 17000 | 85000
SIZE: 850(W) X 1600 (H)
5.6
| Entry/ Exit Glazing partition | P/F 12 mm thk. toughened glass partitions including hardware fitting and any other hardware etc required to complete the related works as per design & detail. door hardware make consider Dorma / Hafele/Ozon /equilient
|  | bikanerwala | sqft | 1 | 7.833 | 4.5 | 35.2485 |  |  | 0
5.7 |  |  | sqft | 1 | 12.5 | 4.5 | 56.25 |  |  | 0
|  | sneeze guard | sqft | 1 | 5.75 | 1.833 | 10.5397 |  |  | 0
|  |  | sqft | 1 | 12.333 | 1.833 | 22.6064 |  |  | 0
5.8 |  | support | sqft | 4 | 1 | 1 | 4 |  |  | 0
|  | dominose | sqft | 1 | 8.833 | 4.5 | 39.7485 |  |  | 0
|  | gianis s guard | sqft | 1 | 6.5 | 1.833 | 11.9145 |  |  | 0
|  | noodles wok | sqft | 1 | 12 | 1.833 | 21.996 |  |  | 0
5.9 |  | 2nd time | sqft | 1 | 11.5 | 4.5 | 51.75 |  |  | 0
|  | dhaba | sqft | 1 | 15 | 4.5 | 67.5 |  |  | 0
5. 10 |  |  | SQFT |  |  |  | 321.5536 | 375 | 120582.6146 | 0 | 375 | 0
| Toilet Mirror | Providing, making and fixing of wall panelling made of 12mm thk branded Commercial Ply (MR Calibrated, IS 303) -- Greenply or Equivalent brand with 6 mm clear mirror g finish with all necessary required framing, approved make adhesive and fasteners, cutting/ chamfering/ groove/rounding wherever required, at all height with lead and lift, finishing, cleaning as per design and drawing etc. all complete. | [5 empty] | 425 | 0 |  | 425 | 0
6.1 |  | TOTAL OF GLASS AND MIRROR WORKS | [6 empty] | 120582.6146 |  |  | 85000
METAL WORKS
6.2
| Railing | P/F railing framework made out of 40mm x 20mm hollow box sections as per design. Top handle framework finished with black powder coating bottom & vertical member finished with black powder coat. all necessary required groove, framing, approved make adhesive and fasteners, cutting/ chamfering/ groove/rounding wherever required, at all height with lead and lift, finishing, cleaning as per design and drawing etc. all complete. | [5 empty] | 1500 | 0 |  | 1500 | 0
8150 (L) X 1200 (H)
6.3 |  | 3000 (L) X 1200 (H)
3000 (L) X 1200 (H)
4100 (L) X 1200 (H)
5550 (L) X 1200 (H)
8100 (L) X 1200 (H)
|  | TOTAL OF METAL WORKS | [6 empty] | 0 |  |  | 0
1
SANITARY FITTINGS
2 | Wash basin fixture (White color) Duravit- 033856_D-code under counter basin | Fixing under counter Wash Basin of oval shape including pillar cock, waste coupling ,angle cock.bottle trap & connection pipe etc all required to complete the work and make it functional.(Make - Hindware / Parryware or equivalent as approved). All complete as per design and specifications. | [5 empty] | 7500 | 0 | 4 | 7500 | 30000
| Piller cock | Providing and fixing heavy duty pillar cock for manufactured by M/s. Jaguar or equivalent all complete as per standard specifications and as directed by the Architect including heavy duty C.P. Water connectors. | [5 empty] | 2500 | 0 | 4 | 2500 | 10000
| Stop cock | Providing and fixing heavy duty stopcock manufactured by M/s. Jaguar continental series or equivalentin chromium plated with adjustable flange (15 mm dia / 20 mm dia.) all complete as per standard specifications and as directed by the Architect. | [5 empty] | 1250 | 0 | 4 | 1250 | 5000
| Bib cock | Providing and fixing heavy duty 15 mm dia C.P. brass short body bibcock (one in one) of approved manufacturer such as Jaguar in continental series or equivalent with wall flange all complete as per standard specifications and as directed by the in - Charge. | [5 empty] | 1500 | 0 | 4 | 1500 | 6000
|  | TOTAL OF SANITARY FITTING WORKS | [6 empty] | 0 |  |  | 51000
|  | TOTAL OF SUMMARY | [6 empty] | 5549121.215 |  |  | 6163400
3
1
1
a
b
c

## Plumbing
[5 empty] | ACTUAL QUANTITY |  |  | TENDER QUANTITY
Item No. | Description | Unit | NO | L | QNTY | Rate | Amount | QNTY | Rate | Amount
A | WATER SUPPLY PIPING
1 | CPVC Pipes conforming to ASTM D-2846, SDR-11 grade and CPVC solvent weld fittings like elbows, tees, couplars, brass threaded adaptors, insert ring etc. suitable for (domestic and flushing) cold applications rated, concealed piping within wall / floor including jointing with fittings using solvent cement, brass threaded end fittings for making connection to fixtures. The work shall also include chasing the walls with machine wherever required for concealed piping and making good the same after laying of pipes & necessary pressure testing Chasing finishing shall be done with 1:1 cement mixed mortar, restore the same original condition for internal and shaft piping, including necessary hot deep galvanised supports vertical / horizontal, as per direction of Site incharge direction. [The rate shall include supply of S.S.screws and nut bolts etc.chasing in walls done by machine] (For Domestic and flushing water supply) (Pipe shall be tested with 1.5 times working pressure as covered in specifications)
1.1 | 20 mm Dia
GIANIS
| HOT LINE | RFT | 1 | 6 | 6
| RO LINE | RFT | 1 | 8.5 | 8.5
|  | RFT | 1 | 6 | 6
|  | RFT | 1 | 6.16 | 6.16
|  | RFT | 1 | 7 | 7
GIANIS SIDE SHOP
| WATER LINE | RFT | 1 | 17 | 17
| HANDWASH |  |  |  | 0
| RO CHILLED WATER | RFT | 1 | 6.833 | 6.833
|  | RFT | 1 | 9 | 9
|  | RFT | 1 | 14 | 14
|  | RFT | 1 | 7 | 7
| NORMAL LINE | RFT | 1 | 3.25 | 3.25
|  | RFT | 1 | 3.25 | 3.25
|  | RFT | 1 | 9 | 9
|  | RFT | 1 | 14 | 14
|  | RFT | 1 | 7 | 7
| NORMAL LINE | RFT | 1 | 12.5 | 12.5
| DOMINOSE | RFT | 1 |  | 0
| OVEN AREA | RFT | 1 | 10.5 | 10.5
|  | RFT | 1 | 7.5 | 7.5
|  | RFT | 1 | 3.833 | 3.833
|  | RFT | 1 | 7.5 | 7.5
|  | RFT | 1 | 3.916 | 3.916
|  | RFT | 1 | 10 | 10
|  | RFT | 1 | 1.33 | 1.33
|  | RFT | 1 | 5.416 | 5.416
|  | RFT | 1 | 8 | 8
|  | RFT | 1 | 1.25 | 1.25
|  | RFT | 1 | 10 | 10
|  | RFT | 1 | 15 | 15
|  | RFT | 1 | 6.33 | 6.33
|  | RFT | 1 | 6 | 6
|  | RFT | 1 | 4 | 4
|  | RFT | 1 | 9 | 9
MAIN RO WATER
|  | RFT | 1 | 6.33 | 6.33
|  | RFT | 1 | 3.5 | 3.5
|  | RFT | 1 | 4.75 | 4.75
|  | RFT | 1 | 8 | 8
|  | RFT | 1 | 15 | 15
|  | RFT | 1 | 6.33 | 6.33
|  | RFT | 1 | 5 | 5
|  | RFT | 1 | 15 | 15
|  | RFT | 1 | 5 | 5
|  | RFT | 1 | 1 | 1
| HOT LINE | RFT | 1 | 6 | 6
| MAIN LINE | RFT | 1 | 15 | 15
| BIKANERWALA | RFT | 1 | 1 | 1
| CENTRA AREA | RFT | 1 | 8 | 8
|  | RFT | 1 | 6 | 6
|  | RFT | 1 | 44 | 44
|  | RFT | 1 | 7.66 | 7.66
|  | RFT | 1 | 9.5 | 9.5
|  | RFT | 1 | 6.33 | 6.33
|  | RFT | 1 | 5 | 5
|  | RFT | 1 | 6.5 | 6.5
|  | RFT | 1 | 6.5 | 6.5
|  | RFT | 1 | 4 | 4
|  | RFT | 1 | 4 | 4
|  | RFT | 1 | 8 | 8
|  | RFT | 1 | 9 | 9
| RO LINE | RFT | 1 | 8 | 8
|  | RFT | 1 | 4 | 4
|  | RFT | 1 | 11 | 11
|  | RFT | 1 | 24 | 24
|  | RFT | 1 | 7.66 | 7.66
|  | RFT | 1 | 8.5 | 8.5
| RO LINE | RFT | 1 | 6.33 | 6.33
|  | RFT | 1 | 5 | 5
|  | RFT | 1 | 6.5 | 6.5
|  | RFT | 1 | 8 | 8
|  | RFT | 1 | 17 | 17
| DISHWASH WATER LINE | RFT | 1 | 6 | 6
|  | RFT | 1 | 5 | 5
| HOT LINE | RFT | 1 | 3 | 3
|  | RFT | 1 | 11 | 11
|  | RFT | 1 | 5 | 5
| MAL LINE | RFT | 1 | 19 | 19
| TEA CONCEPT | RFT | 1 | 8.583 | 8.583
| HOT LINE | RFT | 1 | 5.416 | 5.416
|  | RFT | 1 | 10 | 10
|  | RFT | 1 | 13.166 | 13.166
|  | RFT | 1 | 8.5 | 8.5
| RO LINE | RFT | 1 | 3.833 | 3.833
|  | RFT | 1 | 10.5 | 10.5
|  | RFT | 1 | 13.16 | 13.16
|  | RFT | 1 | 8.5 | 8.5
|  | RFT | 1 | 8.66 | 8.66
|  | RFT | 1 | 8.25 | 8.25
DHABA
| NORMAL | RFT | 1 | 7.66 | 7.66
|  | RFT | 1 | 4.583 | 4.583
|  | RFT | 1 | 3.66 | 3.66
|  | RFT | 1 | 3 | 3
|  | RFT | 1 | 8 | 8
|  | RFT | 1 | 10.75 | 10.75
|  | RFT | 1 | 17 | 17
|  | RFT | 1 | 1 | 1
| HOT LINE | RFT | 1 | 5.66 | 3
|  | RFT | 1 | 3 | 3
|  | RFT | 1 | 10.75 | 10.75
|  | RFT | 1 | 1.583 | 1.583
|  | RFT | 1 | 1 | 1
| RO LINE | RFT | 1 | 4.416 | 4.416
|  | RFT | 1 | 8 | 8
|  | RFT | 1 | 10.75 | 10.75
|  | RFT | 1 | 5 | 5
|  | RFT | 1 | 10 | 10
| NOODLE WOK | RFT | 1 | 6 | 6
|  | RFT | 1 | 6 | 6
|  | RFT | 1 | 2 | 2
|  | RFT | 1 | 57 | 57
| RO LINE | RFT | 1 | 10 | 10
|  | RFT | 1 | 11 | 11
|  | RFT | 1 | 7.5 | 7.5
|  | RFT | 1 | 14.66 | 14.66
|  | RFT | 1 | 4 | 4
CENTER WALL BETWEEN BOTH GATE
| RO LINE | RFT | 1 | 14.583 | 14.583
| HOT LINE | RFT | 1 | 8.5 | 8.5
|  | RFT | 1 | 20.583 | 20.583
|  | RFT | 1 | 33 | 33
|  | RFT | 1 | 7 | 7
|  | RFT | 1 | 37 | 37
|  | RFT | 1 | 11 | 11
| TERRACE | RFT | 1 | 67 | 67
|  | RFT | 1 | 90 | 90
|  | RFT | 1 | 46 | 46
|  | RFT | 1 | 85 | 85
| EXHAUST MACHINE CONNECTION | RFT | 1 | 61 | 61
|  | RFT | 1 | 2 | 2
| FRESH AIR MACHINE | RFT | 1 | 90 | 90
|  | RFT | 1 | 41 | 36
| GAS BANK | RFT | 1 | 20 | 36
1592.004
OR
|  | RMTR |  |  | 485.3671 | 250 | 121341.7683 | 130 | 250 | 32500
1.2 | 25 mm Dia
| MAIN TAN TO RO | RFT | 1 | 42 | 42
| ROTANK TO ALL SHOP | RFT | 1 | 10 | 10
|  | RFT | 1 | 36 | 36
| MAIN TANK EXHAUST AIR | RFT | 1 | 11.66 | 11.66
|  | RFT | 1 | 20 | 20
|  | RFT |  |  | 119.66
OR
|  | RMTR |  |  | 36.4817 | 300 | 10944.5122 | 12 | 300 | 3600
1.3 | 32mm Dia
| RO TANK TO ALL SHOP | RFT | 1 | 6 | 6
|  | RFT | 1 | 130 | 130
|  | RFT | 1 | 37 | 37
|  | RFT |  |  | 173
OR
|  | RMTR |  |  | 52.7439 | 350 | 18460.3659 | 10 | 350 | 3500
2 | Providing & Fixing of gun metal heavy Ball Valves-PN-16 (approved makes as covered in specification) screwed type for water system of the following diameters. Valve shall have with unions.
2.1 | 20mm Dia
| GIANIS | Nos. |  |  | 1
| GIANIS ADJOINING | Nos. |  |  | 1
| HANDWASH | Nos. |  |  | 2
| DOMINOSE | Nos. |  |  | 4
| BIKANERWALA | Nos. |  |  | 1
| DISHWASH | Nos. |  |  | 1
| TEA CONCEPT | Nos. |  |  | 1
| DHABA | Nos. |  |  | 1
| NOODLE WOK | Nos. |  |  | 2
| CAFFECCINO | Nos. |  |  | 1
| TERRACE RO | Nos. |  |  | 10
| MAIN TANK | Nos. |  |  | 4
| MAIN TANK TERRACE | Nos. |  |  | 6
|  | Nos. |  |  | 35 | 500 | 17500 | 3 | 500 | 1500
2.2 | 25mm Dia
| MAIN TANK | Nos. |  |  | 6 | 600 | 3600 | 1 | 600 | 600
2.3 | 32mm Dia
| BIKANERWALA | Nos. |  |  | 2
| MAIN TANK | Nos. |  |  | 5
|  | Nos. |  |  | 7 | 700 | 4900 | 2 | 700 | 1400
3 | Providing ,fixing, testing and commissioning capstan make Water Meter including providing & fixing matching Isolation valves ,strainer, non-return valve,complete with all necessary fittings etc screwed type(15Kgs/Sq.cm). Valve shall have with union. ( Optional if required at site)
3.1 | 25 mm Dia incoming line | Nos. |  |  |  | 5500 |  |  | 5500
3.2 | 32 mm Dia incoming line | Nos. |  |  |  | 6500 |  |  | 6500
3.3 | 40 mm Dia incoming line | Nos. |  |  |  | 7500 |  |  | 7500
4 | Supply, installation,testing & commissioning of Storage Type Electric Hot Water Generator of mentioned capacity, suitable for 3 KG/cm2 pressure, Wall Mounted / Floor standing type, with Auto Shut-off Thermostat, along with isoltion Valves, Air Release valve, SS flexible connections andall other std accessories
4.1 | 5 L Capacity-
| GIANIS | Nos. |  |  | 1 | 8500 | 8500 | 1 | 8500 | 8500
4.2 | 10 L Capacity | Nos. | [5 empty] | 3 | 1100 | 3300
4.3 | 35 L Capacity- For shower
| GIANIS | Nos. |  |  | 1
| DOMINOSE | Nos. |  |  | 2
| BIKANERWALA | Nos. |  |  | 2
| DHABA | Nos. |  |  | 1
| NOODLE WOK | Nos. |  |  | 1
| GAS BANK | Nos. |  |  | 1
|  | Total |  |  | 8 | 17500 | 140000 |  | 17500 | 0
5 | Supply, installation,testing & commissioning of Stiebel Type Electric Hot Water Generator of mentioned capacity, suitable for 3 KG/cm2 pressure, Wall Mounted / Floor standing type, with Auto Shut-off Thermostat, along with isoltion Valves, Air Release valve, SS flexible connections andall other std accessories (Optional in pantry)
5.1 | 3.5kw in pantry- optional | Nos.
5.2 | 8kw | Nos.
5.3 | 13kw-3ph- Subject to load permits | Nos.
Note- Geyser order shall be placed as per site feasibility/ Possibilitis on load. Other wise 35lit Geyser shall be procured.
6 | SITC of Eco smart RO-100 with all required accessories | Nos
7 | SITCcentralised RO package -500l/hr with all required accessories / interconneting piping /inbuilt pumps etc.( At terrace) | Nos |  |  |  | 350000 |  |  | 350000
8 | RO storage tank - S.S. tank-1000 lit | Nos |  |  |  | 55000 |  |  | 55000
9 | RO storage tank - Tripal layer sintex tank 2000 lit | Nos |  |  |  | 25000 |  |  | 25000
8 | Supply, Installalation , testing commissioning of S.S. Grease trap nurgreen Make -NGT 30 ( 47.5 lit) | Nos |  |  |  | 55000 |  |  | 55000
A | SUB TOTAL OF A
B | DRAINAGE
1 | uPVC-SWR pipes conforming to IS 13592/92 including fittings conforming to IS-14935/99 and agri type pipes above 100 mm dia. conforming to IS: 4985, cutting the pipes to required lengths, laying in the position to required grade and level, jointing, supporting with PVC cleat,hot deep galvanised bracket supports,hot deep galvanised nut-bolts, anchor fastners, PVC coated U-clamp, testing and rectifying leakages for piping within vertical shafts / supported on wall / hung below slab etc. with all material & labor complete and as directed. [The Rate shall include supply and fixing of hotdip galvanised bracket nut bolts/ PVC Coated U-Clamp and screws] Vertical line bracket shall be fixed at every 0.8 mtr to 1.00 mtr.]
1.1 | 40mm Dia
| DRAIN WASTE LINE | RFT | 1 | 19.5 | 19.5
|  | RFT | 1 | 8 | 8
|  | RFT | 1 | 8 | 8
|  | RFT | 1 | 8 | 8
|  | RFT | 1 | 8 | 8
|  | R |  |  | 51.5
OR
|  | R.mt |  |  | 15.7012 | 400 | 6280.4878 | 30 | 400 | 12000
1.2 | 50mm Dia | R.mt |  |  |  |  | 0 | 20 | 425 | 8500
1.3 | 65mm Dia | R.mt |  |  |  |  | 0 | 10 | 450 | 4500
1.4 | 75mm Dia | R.mt |  |  |  |  | 0 | 10 | 500 | 5000
1.5 | 100 mm Dia | R.mt
| GIANIS | RFT | 1 | 4 | 4
|  | RFT | 1 | 5 | 5
|  | RFT | 1 | 7 | 7
| GIANIS SIDE SHOP | RFT | 1 | 8 | 8
| HANDWASH | RFT | 1 | 18 | 18
DOMINOSE
|  | RFT | 1 | 4.166 | 4.166
|  | RFT | 1 | 3 | 3
|  | RFT | 1 | 3 | 3
|  | RFT | 1 | 0.833 | 0.833
|  | RFT | 1 | 14.66 | 14.66
|  | RFT | 1 | 3.916 | 3.916
| OVEN AREA | RFT | 1 | 16 | 16
|  | RFT | 1 | 3 | 3
|  | RFT | 1 | 4.25 | 4.25
|  | RFT | 1 | 6.1266 | 6.1266
BIKANERWALA
R |  | RFT | 1 | 4.5 | 4.5
|  | RFT | 1 | 3.5 | 3.5
|  | RFT | 1 | 5.833 | 5.833
|  | RFT | 1 | 10.25 | 10.25
|  | RFT | 1 | 6.5 | 6.5
|  | RFT | 1 | 6.916 | 6.916
|  | RFT | 1 | 3.583 | 3.583
|  | RFT | 1 | 11.583 | 11.583
|  | RFT | 1 | 7 | 7
|  | RFT | 1 | 7.5 | 7.5
|  | RFT | 1 | 8.583 | 8.583
|  | RFT | 1 | 13 | 13
|  | RFT | 1 | 6.5 | 6.5
|  | RFT | 1 | 10 | 10
|  | RFT | 1 | 4 | 4
| DISHWASH | RFT | 1 | 5.5 | 5.5
| TEA CONCEPT | RFT | 1 | 3 | 3
|  | RFT | 1 | 11 | 11
|  | RFT | 1 | 16.833 | 16.833
|  | RFT | 1 | 13 | 13
| DHABA | RFT | 1 | 2 | 2
|  | RFT | 1 | 3.416 | 3.416
|  | RFT | 1 | 7.583 | 7.583
|  | RFT | 1 | 5.916 | 5.916
|  | RFT | 1 | 3.66 | 3.66
|  | RFT | 1 | 6.833 | 6.833
|  | RFT | 1 | 3.833 | 3.833
| NOODLE WOK | RFT | 1 | 4 | 4
|  | RFT | 1 | 3.75 | 3.75
|  | RFT | 1 | 2.583 | 2.583
|  | RFT | 1 | 6.416 | 6.416
|  | RFT | 1 | 3.833 | 3.833
|  | RFT | 1 | 28 | 28
| CAFFECCINO | RFT | 1 | 3.33 | 3.33
|  | RFT | 1 | 1.66 | 1.66
|  | RFT | 1 | 7 | 7
|  | RFT | 1 | 3 | 3
356.3456
|  | RMTR |  |  | 108.642 | 650 | 70617.2683 | 10 | 650 | 6500
2 | Supply, Install PVC P-Traps including fixing with lead caulked joints and rings, c/w Circular SS 304 Grating, ( Subject to site requirement)
| GIANIS | NOS |  |  | 0
| HANDWASH | NOS |  |  | 0
| DOMINOSE | NOS |  |  | 0
| BIKANERWALA | NOS |  |  | 0
| TEA CONCEPT | NOS |  |  | 0
| DHABA | NOS |  |  | 0
| NOODLE WOK | NOS |  |  | 0
| CAFFECCINO | NOS |  |  | 0
|  | NOS |  |  | 0 | 1500 | 0 |  | 1500 | 0
3 | PVC Multi Floor Trap with Circular SS 304 Grating,including making all approved quality Solvent cement joints with material & labour etc. all complete as per direction of the engineer-in-charge. | Nos. |  |  |  | 3500 | 0 | 8 | 3500 | 28000
5 | PVC Floor Trap with Circular SS 304 Grating, including making all approved quality Solvent cement joints with material & labour etc. all complete as per direction of the engineer-in-charge.
| GIANIS | NOS |  |  | 1
| HANDWASH | NOS |  |  | 4
| DOMINOSE | NOS |  |  | 5
| BIKANERWALA | NOS |  |  | 8
| TEA CONCEPT | NOS |  |  | 2
| DHABA | NOS |  |  | 4
| NOODLE WOK | NOS |  |  | 3
| CAFFECCINO | NOS |  |  | 3
|  | NOS |  |  | 30 | 1500 | 45000 | 2 | 1500 | 3000
SUB TOTAL OF B
C | SANITARY AND C. P. FITTINGS & FIXTURES
Only installation, testing and commissioning of sanitary and C.P. fittings
1.1 | Under Counter Sink including waste Coupling | Nos |  |  |  | 2000 |  | 7 | 2000 | 14000
1.2 | Sink Pillar Cock | Nos |  |  |  | 500 |  | 7 | 500 | 3500
1.3 | Bottle Trap for sink with all connecting pipes | Nos |  |  |  | 400 |  | 7 | 400 | 2800
1.4 | Angle Cock with PVC pipe connection upto sink/Geyser /RO connection
| GIANIS | NOS |  |  | 4
| HANDWASH | NOS |  |  | 3
| DOMINOSE | NOS |  |  | 11
| BIKANERWALA | NOS |  |  | 16
| DISHWASH | NOS |  |  | 3
| DHABA | NOS |  |  | 13
| NOODLE WOK | NOS |  |  | 5
| GAS BANK | NOS |  |  | 4
|  | Total |  |  | 59 | 350 | 20650 | 24 | 350 | 8400
1.5 | WC | Nos |  |  |  | 3500 |  |  | 3500 | 0
1.6 | Jet Spary | Nos |  |  |  | 750 |  |  | 750 | 0
1.7 | Two way tap | Nos |  |  |  | 500 |  |  | 500 | 0
1.8 | paper holder | Nos |  |  |  | 250 |  |  | 250 | 0
1.9 | Wash basin including waste Coupling | Nos |  |  |  | 1500 |  | 4 | 1500 | 6000
1.1 | Wash basin Cock | Nos |  |  |  | 650 |  | 4 | 650 | 2600
1.11 | Bottle Trap for basin with all connecting pipes | Nos |  |  |  | 500 |  | 4 | 500 | 2000
SUB TOTAL -C-SANITARY AND C. P. FITTINGS & FIXTURES ( ONLY INSTALLATIONS)
D | S.S. GRATING
Only testing and commissioning of S.S.Gratings
a | Making chamber in brick work including internal tiling etc for S.S Grating size, 300mm x 300mm, in 16 swg 25mm x25mm Square Pipe around the Frame and 20mmX 20mm Square pipe in center of frame with SS perforated tray (304 SWR). Complete as per architectural detail drawing & Site Engineer's instruction.
| GIANIS | NOS |  |  | 1
| GIANIS SIDE SHOP | NOS |  |  | 1
| HANDWASH | NOS |  |  | 1
| DOMISE | NOS |  |  | 1
| BIKANNER WALA | NOS |  |  | 9
| DISHWASH WATER | NOS |  |  | 2
| TEA CONCEPT | NOS |  |  | 1
| DHABA | NOS |  |  | 3
| NOODLE WOK | NOS |  |  | 3
| CAFFECCINO | NOS |  |  | 1
[5 empty] | 23 | 3500 | 80500 | 13 | 3500 | 45500
b | Making chamber in brick work including internal tiling etc for S.S Grating size, 450mm x 450mm, in 16 swg 25mm x25mm Square Pipe around the Frame and 20mmX 20mm Square pipe in center of frame with SS perforated tray (304 SWR). Complete as per architectural detail drawing & Site Engineer's instruction. | Nos. |  |  |  | 3500 |  |  | 3500
c | Making chamber in brick work including internal tiling etc for S.S Grating size, 200mm x 450mm, in 16 swg 25mm x25mm Square Pipe around the Frame and 20mmX 20mm Square pipe in center of frame with SS perforated tray (304 SWR). Complete as per architectural detail drawing & Site Engineer's instruction. | Nos. |  |  |  | 3500 |  |  | 3500
SUB TOTAL -D-S.S. GRATING INSTALLATION ( ONLY INSTALLATIONS)
| GRAND - TOTAL | [5 empty] | 548294.4024 |  |  | 207200
NOTES :
1. Taxes and duties shall be Extra as actual
2. Supply and installation of Sanitary fixtures and fitting in th kitchen and toilets
3. Supply of S.S. gratings in kitchen

## CALCULATION PAINT (hidden)
| 403 | 443.3 | 444 | 67.66 | 6.1 | 73.76 | 517.76 | 518
| 6.6 | 2.1 | 13.86
| 2.6 | 2.1 | 5.46
19.32
|  |  | 21.252 | 22
2.8 | 19.32 | 2.8 | 24.92
|  |  | 27.412 | 28
[6 empty] | 3.3 | 1.2 | 2.1
12 | 3 |  | 36
2.4 | 2 | 1.8 | 8.64
|  |  | 44.64 | 49.104
49