## Equip. schedule_180424_updated
COLD STORAGE & SERVICE LAYOUT
|  | EQUIPMENT SCHEDULE |  | DATE | 2023-05-05
|  | GUWAHATI |  | Rev Date-R1 | 2023-06-19
|  |  |  | Rev Date-R2 | 2024-04-09
MAIN KITCHEN
SR.No. | Eq.No. | DESCRIPTION | BRAND/MODEL NO | DIMENSIONS(L x W x HT) | QTY | Electric Supply | Per Kw | TOTAL KW | AMPS | TYPE OF SWITCH | COMMENTS | VENDOR NAME | OLD PO REF. | PO DATE | PO RELEASE DATE | LEAD TIME | ADVANCE | EXPECTED DELIVERY | REMARKS | REMARK
MAIN KITCHEN
1 | CK-01 | 4" DEEP DISH LANDING TABLE W/GLASS RACK | FABRICATED | 1400 x 650 x 850 + 500+125 O/S | 1 | [5 empty] | IN NEW LAYOUT | Steel Craft | PO/SKPL/23-24/000773 | 2023-07-05 |  | 7 to 10 days
3 | CK-01b | GREASE TRAP | FABRICATED | 500 x 400 x 375Ht. | 1 | [5 empty] | IN NEW LAYOUT | GROSS KITCHEN EQUIPMENTS | PO/SKPL/23-24/000776 | 2023-07-05
4 | CK-02 | LOADING TABLE WITH SINK ON (RHS)L & STRAINER | FABRICATED | 900 x 675 x 850 + 150SPL | 1 | [5 empty] | IN NEW LAYOUT | Steel Craft | PO/SKPL/23-24/000773 | 2023-07-05 |  | 7 to 10 days
5 | CK-03 | PRE RINSE SPARY UNIT - DECK MOUNTED | BAKERS SHOPPEE / EQUIVALENT | STD | 1 | [5 empty] | IN NEW LAYOUT | [8 empty] | Yet To Order | 18000
6 | CK-04 | HOOD TYPE DISH WASH MACHINE | WINTERHALTER / P50 | 735 x 750 x 1480Ht. | 1 | 3PH | 11.8 | 11.8 | 5 Pole Industrial Type | MCB | IN NEW LAYOUT | [8 empty] | Yet To Order | 300000
7 | CK-05 | UNLOADING TABLE 2 U/S | FABRICATED | 1350 x 675 x850+150SPL | 1 | [5 empty] | IN NEW LAYOUT BUT DIMESION CHANGE | Steel Craft | PO/SKPL/23-24/000773 | 2023-07-05 |  | 7 to 10 days
8 | CK-06 | WALL SHELF | FABRICATED | 1100 x 300 | 1 | [5 empty] | IN NEW LAYOUT BUT DIMESION CHANGE | G M ASSOCIATE | PO/SKPL/23-24/000774 | 2023-07-05
9 | CK-08 | UNDER COUNTER GLASS WASHER | IFB-Protech 411 Plus /ELECTROLUX 402116 (EGWSIG) | 540 x 440x 715Ht. | 1 | 1P | 3.1 | 3.1 | 5 / 15 Amp | Switch Socket | IN NEW LAYOUT | [8 empty] | Yet to Order | 240000
10 | CK-10 | POT WASH SINK PERFORETED STRAINER AND BALL VALVE (BOWLS SIZE600 x 450x300mm) | FABRICATED | 750 x 625 x 850+150Ht. | 1 | [5 empty] | IN NEW LAYOUT | Steel Craft | PO/SKPL/23-24/000773 | 2023-07-05 |  | 7 to 10 days |  |  |  |  | 558000
11 | CK-10a | GREASE TRAP | FABRICATED | 500 x 400 x 375Ht. | 1 | [5 empty] | IN NEW LAYOUT | GROSS KITCHEN EQUIPMENTS | PO/SKPL/23-24/000776 | 2023-07-05
12 | CK-11 | POT RACK 4 Nos SHELF W/CASTOR WHEEL | FABRICATED | 1100 x 550 x 1650Ht. | 1 | [5 empty] | IN NEW LAYOUT BUT DIMESION CHANGE | Steel Craft | PO/SKPL/23-24/000773 | 2023-07-05 |  | 7 to 10 days
13 | CK-12 | CLEAN DISH RACK (4 SHELF) | FABRICATED | 900 x 450 x 1650Ht. | 4 | [5 empty] | IN NEW LAYOUT | G M ASSOCIATE | PO/SKPL/23-24/000774 | 2023-07-05
14 | CK-14 | WORK TABLE W/ 2 U/S & 2 O/S | FABRICATED | 95O x 700 x 850+450+300 | 1 | [5 empty] | IN NEW LAYOUT BUT DIMESION CHANGE | G M ASSOCIATE | PO/SKPL/23-24/000774 | 2023-07-05
15 | CK-15 | WORK TABLE HALFSID 2 U/S & HALFSIDE CRTOSS SUPPORT FOR USED OIL STORAGE | FABRICATED | 1300 x 600 x 850Ht. | 1 | [5 empty] | IN NEW LAYOUT | G M ASSOCIATE | PO/SKPL/23-24/000774 | 2023-07-05
16 | CK-27a | GREASE TRAP | FABRICATED | 400 x 335 x 350Ht. | 1 | [5 empty] | IN NEW LAYOUT | GROSS KITCHEN EQUIPMENTS | PO/SKPL/23-24/000776 | 2023-07-05
17 | CK-32 | FOOD PROCESSOR | ROBOT COUPE-R301 ULTRA Robot Coupe R 301 Ultra | 305 x 365 x 300Ht. | 1 | 1P | 2.2 | 2.2 | 5 / 15 Amp | Switch | IN NEW LAYOUT | [8 empty] | Yet to Order
18 | CK-33 | WALL SHELF | FABRICATED | 750 x 300 W | 2 | [5 empty] | IN NEW LAYOUT | G M ASSOCIATE | PO/SKPL/23-24/000774 | 2023-07-05
19 | CK-37 | FOOT OPERATED HAND WASH SINK WITH HOT & COLD WATER CONNECTION & WITH TISSUE HOLDER & SOAP DISPENSER PROVISION & OPEN FROM BACK SIDE | FABRICATED | 500 x 475 x 850+450SPL | 1 | [5 empty] | IN NEW LAYOUT | Steel Craft | PO/SKPL/23-24/000773 | 2023-07-05 |  | 7 to 10 days
20 | CK-42 | ONION, POTATO & COCONUTSTORAGE TROLLEY | FABRICATED | 900 x 450 x 1350Ht. | 1 | [5 empty] | IN NEW LAYOUT | Steel Craft | PO/SKPL/23-24/000773 | 2023-07-05 |  | 7 to 10 days
21 | CK-43 | 3 TIER DIRTY DISH TROLLEY WITH HANDLE (3 SIDE COVER & 2 FRONT DOORS) | FABRICATED | 925 x 700 x 850Ht. | 2 | [5 empty] | IN NEW LAYOUT | GROSS KITCHEN EQUIPMENTS | PO/SKPL/23-24/000775 | 2023-07-05
22 | CK-46 | SINGLE SINK (RHS) TABLE CROSS SUPPORT WITH OHS | FABRICATED | 1075 x 600 x 850+(150SPL)+ 450+300 | 1 | [5 empty] | IN NEW LAYOUT | Steel Craft | PO/SKPL/23-24/000773 | 2023-07-05 |  | 7 to 10 days
Total Kw-Main Kitchen - A | [7 empty] | 17.1
SOE
4 |  | INSECT KILLERS |  |  | 2 | 1P | 0.3 | 0.6 | 5 / 15 Amp | Switch Socket |  | Technocrats Security Systems Private Limited | PO/SKPL/23-24/000772 | 2023-07-05 |  | 7 to 10 days
5 |  | FIRE EXTINGUISHER ABC-4KG |  |  | 1 | [6 empty] | Fire Zone System Enterprise | PO/SKPL/23-24/000771 | 2023-07-05 |  | 7 to 10 days
6 |  | FIRE EXTINGUISHER CO/2-4.5KG |  |  | 1 | [6 empty] | Fire Zone System Enterprise | PO/SKPL/23-24/000771 | 2023-07-05 |  | 7 to 10 days
7 |  | FIRE EXTINGUISHER KTYPE - 6KG |  |  | 1 | [6 empty] | Fire Zone System Enterprise | PO/SKPL/23-24/000771 | 2023-07-05 |  | 7 to 10 days
8 |  | FIRE BLANKET - 6' X 4' |  |  | 1 | [6 empty] | Fire Zone System Enterprise | PO/SKPL/23-24/000771 | 2023-07-05 |  | 7 to 10 days
TOTAL MISCELLANEOUS LOAD IN Kw. - I | [7 empty] | 0.6
Total Kw- (A+ B+C+D+E+F+G+H) | [7 empty] | 17.7

## Equipment Schedule (hidden)
COLD STORAGE & SERVICE LAYOUT
|  | EQUIPMENT SCHEDULE |  | DATE | 2023-05-05
|  | GUWAHATI |  | Rev Date-R1 | 2023-06-19
|  |  |  | Rev Date-R2 | 2024-04-09
MAIN KITCHEN
SR.No. | Eq.No. | DESCRIPTION | BRAND/MODEL NO | DIMENSIONS(L x W x HT) | QTY | Electric Supply | Per Kw | TOTAL KW | AMPS | TYPE OF SWITCH | COMMENTS | VENDOR NAME | OLD PO NO. | PO DATE | PO RELEASE DATE | LEAD TIME | ADVANCE | EXPECTED DELIVERY | REMARKS | REMARK
MAIN KITCHEN
1 | CK-01 | 4" DEEP DISH LANDING TABLE W/GLASS RACK | FABRICATED | 1400 x 650 x 850 + 500+125 O/S | 1 | [5 empty] | IN NEW LAYOUT | Steel Craft | PO/SKPL/23-24/000773 | 2023-07-05 |  | 7 to 10 days
2 | CK-01a | DUST BIN | SOE | LOCAL | 1 | [5 empty] | IN NEW LAYOUT
3 | CK-01b | GREASE TRAP | FABRICATED | 500 x 400 x 375Ht. | 1 | [5 empty] | IN NEW LAYOUT | GROSS KITCHEN EQUIPMENTS | PO/SKPL/23-24/000776 | 2023-07-05
4 | CK-02 | LOADING TABLE WITH SINK ON (RHS)L & STRAINER | FABRICATED | 900 x 675 x 850 + 150SPL | 1 | [5 empty] | IN NEW LAYOUT | Steel Craft | PO/SKPL/23-24/000773 | 2023-07-05 |  | 7 to 10 days
5 | CK-03 | PRE RINSE SPARY UNIT - DECK MOUNTED | BAKERS SHOPPEE / EQUIVALENT | STD | 1 | [5 empty] | IN NEW LAYOUT | [8 empty] | NOT ORDERED
6 | CK-04 | HOOD TYPE DISH WASH MACHINE | WINTERHALTER / P50 | 735 x 750 x 1480Ht. | 1 | 3PH | 11.8 | 11.8 | 5 Pole Industrial Type | MCB | IN NEW LAYOUT | [8 empty] | NOT ORDERED
7 | CK-05 | UNLOADING TABLE 2 U/S | FABRICATED | 1350 x 675 x850+150SPL | 1 | [5 empty] | IN NEW LAYOUT BUT DIMESION CHANGE | Steel Craft | PO/SKPL/23-24/000773 | 2023-07-05 |  | 7 to 10 days
8 | CK-06 | WALL SHELF | FABRICATED | 1100 x 300 | 1 | [5 empty] | IN NEW LAYOUT BUT DIMESION CHANGE | G M ASSOCIATE | PO/SKPL/23-24/000774 | 2023-07-05
9 | CK-07 | CLEAN WIPE TABLE COSS SUPPORT WITH 2O/S | FABRICATED | 700 x 650 x 850+(150SPL)+450+300 | 1 | [5 empty] | REMOVE | G M ASSOCIATE | PO/SKPL/23-24/000774 | 2023-07-05 | [5 empty] | Equipment not mentioned in the layout
10 | CK-08 | UNDER COUNTER GLASS WASHER | IFB-Protech 411 Plus /ELECTROLUX 402116 (EGWSIG) | 540 x 440x 715Ht. | 1 | 1P | 3.1 | 3.1 | 5 / 15 Amp | Switch Socket | IN NEW LAYOUT | [8 empty] | NOT ORDERED
11 | CK-09 | WALL SHELF | FABRICATED | 750 x 300 W | 1 | [5 empty] | REMOVE | G M ASSOCIATE | PO/SKPL/23-24/000774 | 2023-07-05 | [5 empty] | Equipment not mentioned in the layout
12 | CK-10 | POT WASH SINK PERFORETED STRAINER AND BALL VALVE (BOWLS SIZE600 x 450x300mm) | FABRICATED | 750 x 625 x 850+150Ht. | 1 | [5 empty] | IN NEW LAYOUT | Steel Craft | PO/SKPL/23-24/000773 | 2023-07-05 |  | 7 to 10 days
13 | CK-10a | GREASE TRAP | FABRICATED | 500 x 400 x 375Ht. | 1 | [5 empty] | IN NEW LAYOUT | GROSS KITCHEN EQUIPMENTS | PO/SKPL/23-24/000776 | 2023-07-05
14 | CK-11 | POT RACK 4 Nos SHELF W/CASTOR WHEEL | FABRICATED | 1100 x 550 x 1650Ht. | 1 | [5 empty] | IN NEW LAYOUT BUT DIMESION CHANGE | Steel Craft | PO/SKPL/23-24/000773 | 2023-07-05 |  | 7 to 10 days
15 | CK-12 | CLEAN DISH RACK (4 SHELF) | FABRICATED | 900 x 450 x 1650Ht. | 4 | [5 empty] | IN NEW LAYOUT | G M ASSOCIATE | PO/SKPL/23-24/000774 | 2023-07-05
16 | CK-13 | SPARE NUMER
17 | CK-14 | WORK TABLE W/ 2 U/S & 2 O/S | FABRICATED | 95O x 700 x 850+450+300 | 1 | [5 empty] | IN NEW LAYOUT BUT DIMESION CHANGE | G M ASSOCIATE | PO/SKPL/23-24/000774 | 2023-07-05
18 | CK-15 | WORK TABLE HALFSID 2 U/S & HALFSIDE CRTOSS SUPPORT FOR USED OIL STORAGE | FABRICATED | 1300 x 600 x 850Ht. | 1 | [5 empty] | IN NEW LAYOUT | G M ASSOCIATE | PO/SKPL/23-24/000774 | 2023-07-05
19 | CK-16 | TABLE TOP SINGLE BASKET FRYER | KARMA/GF-6SE | 320 x 410 x 285Ht. | 2 | 1P | 3 | 6 | 32 | Metal Clad | REMOVE
20 | CK-17 | EXHAUST HOOD WITH BAFFLE FILTERS & FIRE SUPPRESSION SYSTEM (BOX TYPE) 2500CFM (IN TWO PIECES) | FABRICATED | 2193 x 900 x 600 | 1 | 1P | 1 | 1 | 5 / 15 Amp | Switch | REMOVE
21 | CK-18 | 1/4 GN PAN CONTAINERS | STD | 162 x 265 x 200 Deep. | 2 | [5 empty] | REMOVE
22 | CK-19 | TABLE TOP ELECTRIC HOT PLATE | KARMA-CE270-115 | 730 x 470 x 240Ht. | 1 | 1P | 4.4 | 4.4 | 32 | Metal Clad | REMOVE
23 | CK-20 | WORK TABLE HALFSID 2 U/S & HALFSIDE CRTOSS SUPPORT FOR USED OIL STORAGE | FABRICATED | 1325 x 600 x 850Ht. | 1 | [5 empty] | REMOVE | G M ASSOCIATE | PO/SKPL/23-24/000774 | 2023-07-05
24 | CK-21 | SPARE NUMBER
25 | CK-22 | STAND FOR COMBI OVEN WITH 1/1 GN PAN ARRANGEMENT BELOW | FABRICATED | 950 x 875 x 800Ht. | 1 | [5 empty] | REMOVE
26 | CK-23 | COMBI OVEN 6 TRAY | RATIONAL/6-1/1 GN PAN | 850 x 805 x 842Ht. | 1 | 3PH | 11.8 | 11.8 | 5 Pole Industrial Type | MCB | REMOVE
27 | CK-24 | WORK TABLE 2 U/S | FABRICATED | 600 x 875 x 850+150SPL | 1 |  |  | 0 |  |  | REMOVE | G M ASSOCIATE | PO/SKPL/23-24/000774 | 2023-07-05
28 | CK-25 | ELECTRIC TILTING BRATT PAN 50 LTRS | PRADEEP/FABRICATED | 1200 x 800 x 850Ht. | 1 | 3PH | 5.5 | 5.5 | 5 Pole Industrial Type | MCB | REMOVE
29 | CK-26 | EXHAUST HOOD WITH BAFFLE FILTERS & FIRE SUPPRESSION SYSTEM (BOX TYPE) 5500CFM (IN THREE PIECES) | FABRICATED | 4460 x 950 x 600 | 1 | 1P | 1 | 1 | 5 / 15 Amp | Switch | REMOVE
30 | CK-27 | SINGLE SINK (RHS) TABLE CROSS SUPPORT | FABRICATED | 600 x 830 x 850+150SPL | 1 | [5 empty] | REMOVE | G M ASSOCIATE | PO/SKPL/23-24/000774 | 2023-07-05
31 | CK-27a | GREASE TRAP | FABRICATED | 400 x 335 x 350Ht. | 1 | [5 empty] | IN NEW LAYOUT | GROSS KITCHEN EQUIPMENTS | PO/SKPL/23-24/000776 | 2023-07-05
32 | CK-28 | SALAMANDER | KARAMA-AT936/SIRMAN | 610 x 340 x 280Ht. | 1 | [5 empty] | REMOVE
33 | CK-29 | WORK TABLE 2 U/S | FABRICATED | 850 x 780 x 528Ht. | 1 | [5 empty] | REMOVE | G M ASSOCIATE | PO/SKPL/23-24/000774 | 2023-07-05
34 | CK-30 | 4 HOT PLATE ELECTRIC INDUCTION COOKING TOP RANGE | ELECTROLUX/700XP | 800 x 730 x 322Ht. | 1 | 3PH | 10.4 | 10.4 | 5 Pole Industrial Type | MCB | REMOVE
35 | CK-31 | SPARE NUMBER
36 | CK-32 | FOOD PROCESSOR | ROBOT COUPE-R301 ULTRA Robot Coupe R 301 Ultra | 305 x 365 x 300Ht. | 1 | 1P | 2.2 | 2.2 | 5 / 15 Amp | Switch | IN NEW LAYOUT | [8 empty] | NOT ORDERED
37 | CK-33 | WALL SHELF | FABRICATED | 750 x 300 W | 2 | [5 empty] | IN NEW LAYOUT | G M ASSOCIATE | PO/SKPL/23-24/000774 | 2023-07-05
38 | CK-34 | 2 DOOR U/C REF. WITH LOCKABLE CASTOR WHEELS (2 Nos.WITH BREAK INFRONT & 2 Nos. WITHOUT BREAK) & HEATING ELEMENT FOR DRAIN | ELANPRO-CGN2100TN | 1360 x 700 x 850Ht | 2 | 1P | 1 | 2 | 5 / 15 Amp | Switch | IN NEW LAYOUT | Blue Star Limited | PO/SKPL/23-24/000784 | 2023-07-06 |  | 7 to 10 days | Done 02-08-2023 |  |  | Advance Payment done
39 | CK-35 | 2 DOOR VERTICAL CHILLER WITH LOCKABLE CASTOR WHEELS (2 Nos.WITH BREAK INFRONT & 2 Nos. WITHOUT BREAK) & HEATING ELEMENT FOR DRAIN | ELANPRO -EGN 650TNM | 740 x 830 x 2010Ht. | 1 | 1P | 1 | 1 | 5 / 15 Amp | Switch | IN NEW LAYOUT | Blue Star Limited |  |  |  | 7 to 10 days
40 | CK-36 | 2 DOOR VERTICAL FREEZER WITH LOCKABLE CASTOR WHEELS (2 Nos.WITH BREAK INFRONT & 2 Nos. WITHOUT BREAK) & HEATING ELEMENT FOR DRAIN | ELANPRO -EGN 650BTM | 740 x 830 x 2010Ht. | 1 | 1P | 1 | 1 | 5 / 15 Amp | Switch | IN NEW LAYOUT | Blue Star Limited |  |  |  | 7 to 10 days
41 | CK-36A | 2 DOOR VERTICAL FREEZER WITH LOCKABLE CASTOR WHEELS (2 Nos.WITH BREAK INFRONT & 2 Nos. WITHOUT BREAK) & HEATING ELEMENT FOR DRAIN | ELANPRO -EGN 650BTM | 740 x 830 x 2010Ht. | 1 | 1P | 1 | 1 | 5 / 15 Amp | Switch | NEW ADDED | Blue Star Limited |  |  |  | 7 to 10 days
42 | CK-37 | FOOT OPERATED HAND WASH SINK WITH HOT & COLD WATER CONNECTION & WITH TISSUE HOLDER & SOAP DISPENSER PROVISION & OPEN FROM BACK SIDE | FABRICATED | 500 x 475 x 850+450SPL | 1 | [5 empty] | IN NEW LAYOUT | Steel Craft | PO/SKPL/23-24/000773 | 2023-07-05 |  | 7 to 10 days
43 | CK-38 | SPARE NUMBER
44 | CK-39 | 2 DOOR CHEST FREEZER-534 LTRS CAP. | ELANPRO-EF 535DD | 1650 x 700 x 850Ht. | 2 | 1P | 1 | 2 | 5 / 15 Amp | Switch |  | CANCELLED BY SAEED SIR
45 | CK-40 | 3 DOOR UNDERCOUNTER WITH RAISED BAIN MARIE | ELANPRO/WESTERN OR EQUIVALENT | 1360 x 700 x 850+BAIN MARIE Ht. | 1 | 1P | 1 | 1 | 5 / 15 Amp | Switch | REMOVE | ELAN PROFESSIONAL APPLIANCES PVT LTD | PO/SKPL/23-24/000769 | 2023-07-05 |  |  | Done 02-08-2023
46 | CK-41 | WORK TABLE W/ 2 U/S & 2 O/S | FABRICATED | 1300 x 700 x 850+450+300 | 1 | [5 empty] | REMOVE | Steel Craft | PO/SKPL/23-24/000773 | 2023-07-05 |  | 7 to 10 days
47 | CK-42 | ONION, POTATO & COCONUTSTORAGE TROLLEY | FABRICATED | 900 x 450 x 1350Ht. | 1 | [5 empty] | IN NEW LAYOUT | Steel Craft | PO/SKPL/23-24/000773 | 2023-07-05 |  | 7 to 10 days
48 | CK-43 | 3 TIER DIRTY DISH TROLLEY WITH HANDLE (3 SIDE COVER & 2 FRONT DOORS) | FABRICATED | 925 x 700 x 850Ht. | 2 | [5 empty] | IN NEW LAYOUT | GROSS KITCHEN EQUIPMENTS | PO/SKPL/23-24/000775 | 2023-07-05
49 | CK-44 | VEG CUTTER | SIRMAN-TM-INOX 6 BLADE |  | 1 | 1P | 1 | 1 | 5 / 15 Amp | Switch | IN NEW LAYOUT | WANG PROFESSIONALS PRIVATE LIMITED | PO/SKPL/23-24/000779 | 2023-07-05 | 2023-07-05 |  | Done 22/09/23 | Received on 11/10/23 | PCS Docket No. 1010998 Dt.04.10.23 | Delivered
50 | CK-45 | MS. SLOTTED ANGLE RACK | FABRICATED | 900 x 450 x 1800Ht. | 2 | [5 empty] | REMOVE | G M ASSOCIATE | PO/SKPL/23-24/000774 | 2023-07-05
51 | CK-46 | SINGLE SINK (RHS) TABLE CROSS SUPPORT WITH OHS | FABRICATED | 1075 x 600 x 850+(150SPL)+ 450+300 | 1 | [5 empty] | IN NEW LAYOUT | Steel Craft | PO/SKPL/23-24/000773 | 2023-07-05 |  | 7 to 10 days
52 | CK-47 | WET GRINDER-20Kg.Cap. | NIRAV/COSMOS-CMG 30 | STD | 1 | 3PH | 3 | 3 | 5 Pole Industrial Type | MCB | REMOVE
53 | CK-48 | PULERISER | NIRAV/COSMOS | STD | 1 | 3PH | 3 | 3 | 5 Pole Industrial Type | MCB | REMOVE | GROSS KITCHEN EQUIPMENTS | PO/SKPL/23-24/000775 | 2023-07-05
54 | CK-49 | POTATO PEELER-20Kg Cap. | NIRAV/COSMOS-CP20 | STD | 1 | 1P | 3 | 3 | 5 Pole Industrial Type | MCB | REMOVE
Total Kw-Main Kitchen - A | [7 empty] | 75.2
SOE
1 |  | GARBAGE BINS 60Ltrs.Cap.-FRONTIER PEDAL OPERATED WHEEL | SOE | 460 x 650 x 750Ht. | 2
2 |  | DUST BIN | SOE | 300DIA x 600Ht. | 1
3 |  | GEYSER (Cap. As Per MEP) | SOE | QTY CAN BE MODIFIE AS PER MEP | 2 | 3PH | 3 | 6 | 32 | Metal Clad
4 |  | INSECT KILLERS | SOE |  | 2 | 1P | 0.3 | 0.6 | 5 / 15 Amp | Switch Socket |  | Technocrats Security Systems Private Limited | PO/SKPL/23-24/000772 | 2023-07-05 |  | 7 to 10 days
5 |  | FIRE EXTINGUISHER ABC-4KG | SOE |  | 1 | [6 empty] | Fire Zone System Enterprise | PO/SKPL/23-24/000771 | 2023-07-05 |  | 7 to 10 days
6 |  | FIRE EXTINGUISHER CO/2-4.5KG | SOE |  | 1 | [6 empty] | Fire Zone System Enterprise | PO/SKPL/23-24/000771 | 2023-07-05 |  | 7 to 10 days
7 |  | FIRE EXTINGUISHER KTYPE - 6KG | SOE |  | 1 | [6 empty] | Fire Zone System Enterprise | PO/SKPL/23-24/000771 | 2023-07-05 |  | 7 to 10 days
8 |  | FIRE BLANKET - 6' X 4' | SOE |  | 1 | [6 empty] | Fire Zone System Enterprise | PO/SKPL/23-24/000771 | 2023-07-05 |  | 7 to 10 days
TOTAL MISCELLANEOUS LOAD IN Kw. - I | [7 empty] | 6.6
Total Kw- (A+ B+C+D+E+F+G+H) | [7 empty] | 81.8

## Sheet1 (hidden)
Entity | Vendor Code | Vendor Name | Invoice No | Document No. | External Doc. No. | Due Date/ Payment Date | Document Date | Original Amount
SKPL | V000556 | GOYAL KITCHEN EQUIPMENTS |  | ADV/23-24/000456 | 50%SEMOLINA/PO/23-24/000030 | 2024-01-11 | 2024-01-11 | 34810
SKPL | V000556 | GOYAL KITCHEN EQUIPMENTS |  | ADV/23-24/000457 | 50%SEMOLINA/PO/23-24/000032 | 2024-01-11 | 2024-01-11 | 270377
SKPL | V000556 | GOYAL KITCHEN EQUIPMENTS |  | ADV/23-24/000458 | 50%SEMOLINA/PO/23-24/000034 | 2024-01-11 | 2024-01-11 | 73750
SKPL | V000556 | GOYAL KITCHEN EQUIPMENTS |  | ADV/23-24/000459 | 50%SEMOLINA/PO/23-24/000031 | 2024-01-11 | 2024-01-11 | 202213
SKPL | V000556 | GOYAL KITCHEN EQUIPMENTS |  | ADV/23-24/000559 | 50%SEMOLINA/PO/23-24/000240 | 2024-02-01 | 2024-02-01 | 41005
SKPL | V000556 | GOYAL KITCHEN EQUIPMENTS |  | ADV/23-24/000560 | 50%SEMOLINA/PO/23-24/000242 | 2024-02-01 | 2024-02-01 | 52038
SKPL | V000556 | GOYAL KITCHEN EQUIPMENTS | GKE/23-24/872 | ADV/23-24/000604 | 40%SEMOLINA/PO/23-24/000034 | 2024-02-02 | 2024-02-02 | 59000
SKPL | V000556 | GOYAL KITCHEN EQUIPMENTS | GKE/23-24/871 | ADV/23-24/000605 | 40%SEMOLINA/PO/23-24/000031 | 2024-02-02 | 2024-02-02 | 161770
SKPL | V000556 | GOYAL KITCHEN EQUIPMENTS | GKE/23-24/873 | ADV/23-24/000606 | 40%SEMOLINA/PO/23-24/000032 | 2024-02-02 | 2024-02-02 | 216302
SKPL | V000556 | GOYAL KITCHEN EQUIPMENTS |  | ADV/23-24/000608 | 40%SEMOLINA/PO/23-24/000030 | 2024-02-02 | 2024-02-02 | 27848
SKPL | V000556 | GOYAL KITCHEN EQUIPMENTS | GKE/23-24/874 | ADV/23-24/000621 | 50%SEMOLINA/PO/23-24/000239 | 2024-02-02 | 2024-02-02 | 127529
SKPL | V000556 | GOYAL KITCHEN EQUIPMENTS |  | ADV/23-24/000690 | 100%SEMOLINA/PO/23-24/000390 | 2024-02-13 | 2024-02-13 | 34220
SKPL | V000556 | GOYAL KITCHEN EQUIPMENTS |  | ADV/23-24/000757 | 50%SEMOLINA/PO/23-24/000240 | 2024-03-08 | 2024-03-08 | 41005
SKPL | V000556 | GOYAL KITCHEN EQUIPMENTS | GKE/23-24/875 | ADV/23-24/000758 | 50%SEMOLINA/PO/23-24/000242 | 2024-03-08 | 2024-03-08 | 52038
SKPL | V000556 | GOYAL KITCHEN EQUIPMENTS |  | ADV/23-24/000837 | 30%SEMOLINA/PO/23-24/000714/1 | 2024-03-21 | 2024-03-21 | 379017

## Equip Schedule_10-04-2024 (hidden)
COLD STORAGE & SERVICE LAYOUT
|  | EQUIPMENT SCHEDULE |  | DATE | 2023-05-05
|  | GUWAHATI |  | Rev Date-R1 | 2023-06-19
|  |  |  | Rev Date-R2 | 2024-04-09
MAIN KITCHEN
SR.No. | Eq.No. | DESCRIPTION | BRAND/MODEL NO | DIMENSIONS(L x W x HT) | QTY | Electric Supply | Per Kw | TOTAL KW | AMPS | TYPE OF SWITCH | COMMENTS | VENDOR NAME | OLD PO NO. | PO DATE | PO RELEASE DATE | LEAD TIME | ADVANCE | EXPECTED DELIVERY | REMARKS | REMARK
MAIN KITCHEN
1 | CK-01 | 4" DEEP DISH LANDING TABLE W/GLASS RACK | FABRICATED | 1400 x 650 x 850 + 500+125 O/S | 1 | [5 empty] | IN NEW LAYOUT | Steel Craft | PO/SKPL/23-24/000773 | 2023-07-05 |  | 7 to 10 days
2 | CK-01a | DUST BIN | SOE | LOCAL | 1 | [5 empty] | IN NEW LAYOUT
3 | CK-01b | GREASE TRAP | FABRICATED | 500 x 400 x 375Ht. | 1 | [5 empty] | IN NEW LAYOUT | GROSS KITCHEN EQUIPMENTS | PO/SKPL/23-24/000776 | 2023-07-05
4 | CK-02 | LOADING TABLE WITH SINK ON (RHS)L & STRAINER | FABRICATED | 900 x 675 x 850 + 150SPL | 1 | [5 empty] | IN NEW LAYOUT | Steel Craft | PO/SKPL/23-24/000773 | 2023-07-05 |  | 7 to 10 days
5 | CK-03 | PRE RINSE SPARY UNIT - DECK MOUNTED | BAKERS SHOPPEE / EQUIVALENT | STD | 1 | [5 empty] | IN NEW LAYOUT | [8 empty] | NOT ORDERED
6 | CK-04 | HOOD TYPE DISH WASH MACHINE | WINTERHALTER / P50 | 735 x 750 x 1480Ht. | 1 | 3PH | 11.8 | 11.8 | 5 Pole Industrial Type | MCB | IN NEW LAYOUT | [8 empty] | NOT ORDERED
7 | CK-05 | UNLOADING TABLE 2 U/S | FABRICATED | 1350 x 675 x850+150SPL | 1 | [5 empty] | IN NEW LAYOUT BUT DIMESION CHANGE | Steel Craft | PO/SKPL/23-24/000773 | 2023-07-05 |  | 7 to 10 days
8 | CK-06 | WALL SHELF | FABRICATED | 1100 x 300 | 1 | [5 empty] | IN NEW LAYOUT BUT DIMESION CHANGE | G M ASSOCIATE | PO/SKPL/23-24/000774 | 2023-07-05
10 | CK-08 | UNDER COUNTER GLASS WASHER | IFB-Protech 411 Plus /ELECTROLUX 402116 (EGWSIG) | 540 x 440x 715Ht. | 1 | 1P | 3.1 | 3.1 | 5 / 15 Amp | Switch Socket | IN NEW LAYOUT | [8 empty] | NOT ORDERED
11 | CK-09 | WALL SHELF | FABRICATED | 750 x 300 W | 1 | [5 empty] | REMOVE | G M ASSOCIATE | PO/SKPL/23-24/000774 | 2023-07-05 | [5 empty] | Equipment not mentioned in the layout
12 | CK-10 | POT WASH SINK PERFORETED STRAINER AND BALL VALVE (BOWLS SIZE600 x 450x300mm) | FABRICATED | 750 x 625 x 850+150Ht. | 1 | [5 empty] | IN NEW LAYOUT | Steel Craft | PO/SKPL/23-24/000773 | 2023-07-05 |  | 7 to 10 days
13 | CK-10a | GREASE TRAP | FABRICATED | 500 x 400 x 375Ht. | 1 | [5 empty] | IN NEW LAYOUT | GROSS KITCHEN EQUIPMENTS | PO/SKPL/23-24/000776 | 2023-07-05
14 | CK-11 | POT RACK 4 Nos SHELF W/CASTOR WHEEL | FABRICATED | 1100 x 550 x 1650Ht. | 1 | [5 empty] | IN NEW LAYOUT BUT DIMESION CHANGE | Steel Craft | PO/SKPL/23-24/000773 | 2023-07-05 |  | 7 to 10 days
15 | CK-12 | CLEAN DISH RACK (4 SHELF) | FABRICATED | 900 x 450 x 1650Ht. | 4 | [5 empty] | IN NEW LAYOUT | G M ASSOCIATE | PO/SKPL/23-24/000774 | 2023-07-05
17 | CK-14 | WORK TABLE W/ 2 U/S & 2 O/S | FABRICATED | 95O x 700 x 850+450+300 | 1 | [5 empty] | IN NEW LAYOUT BUT DIMESION CHANGE | G M ASSOCIATE | PO/SKPL/23-24/000774 | 2023-07-05
18 | CK-15 | WORK TABLE HALFSID 2 U/S & HALFSIDE CRTOSS SUPPORT FOR USED OIL STORAGE | FABRICATED | 1300 x 600 x 850Ht. | 1 | [5 empty] | IN NEW LAYOUT | G M ASSOCIATE | PO/SKPL/23-24/000774 | 2023-07-05
19 | CK-16 | TABLE TOP SINGLE BASKET FRYER | KARMA/GF-6SE | 320 x 410 x 285Ht. | 2 | 1P | 3 | 6 | 32 | Metal Clad | REMOVE
20 | CK-17 | EXHAUST HOOD WITH BAFFLE FILTERS & FIRE SUPPRESSION SYSTEM (BOX TYPE) 2500CFM (IN TWO PIECES) | FABRICATED | 2193 x 900 x 600 | 1 | 1P | 1 | 1 | 5 / 15 Amp | Switch | REMOVE
21 | CK-18 | 1/4 GN PAN CONTAINERS | STD | 162 x 265 x 200 Deep. | 2 | [5 empty] | REMOVE
22 | CK-19 | TABLE TOP ELECTRIC HOT PLATE | KARMA-CE270-115 | 730 x 470 x 240Ht. | 1 | 1P | 4.4 | 4.4 | 32 | Metal Clad | REMOVE
23 | CK-20 | WORK TABLE HALFSID 2 U/S & HALFSIDE CRTOSS SUPPORT FOR USED OIL STORAGE | FABRICATED | 1325 x 600 x 850Ht. | 1 | [5 empty] | REMOVE | G M ASSOCIATE | PO/SKPL/23-24/000774 | 2023-07-05
24 | CK-21 | SPARE NUMBER
25 | CK-22 | STAND FOR COMBI OVEN WITH 1/1 GN PAN ARRANGEMENT BELOW | FABRICATED | 950 x 875 x 800Ht. | 1 | [5 empty] | REMOVE
26 | CK-23 | COMBI OVEN 6 TRAY | RATIONAL/6-1/1 GN PAN | 850 x 805 x 842Ht. | 1 | 3PH | 11.8 | 11.8 | 5 Pole Industrial Type | MCB | REMOVE
27 | CK-24 | WORK TABLE 2 U/S | FABRICATED | 600 x 875 x 850+150SPL | 1 |  |  | 0 |  |  | REMOVE | G M ASSOCIATE | PO/SKPL/23-24/000774 | 2023-07-05
28 | CK-25 | ELECTRIC TILTING BRATT PAN 50 LTRS | PRADEEP/FABRICATED | 1200 x 800 x 850Ht. | 1 | 3PH | 5.5 | 5.5 | 5 Pole Industrial Type | MCB | REMOVE
29 | CK-26 | EXHAUST HOOD WITH BAFFLE FILTERS & FIRE SUPPRESSION SYSTEM (BOX TYPE) 5500CFM (IN THREE PIECES) | FABRICATED | 4460 x 950 x 600 | 1 | 1P | 1 | 1 | 5 / 15 Amp | Switch | REMOVE
30 | CK-27 | SINGLE SINK (RHS) TABLE CROSS SUPPORT | FABRICATED | 600 x 830 x 850+150SPL | 1 | [5 empty] | REMOVE | G M ASSOCIATE | PO/SKPL/23-24/000774 | 2023-07-05
31 | CK-27a | GREASE TRAP | FABRICATED | 400 x 335 x 350Ht. | 1 | [5 empty] | IN NEW LAYOUT | GROSS KITCHEN EQUIPMENTS | PO/SKPL/23-24/000776 | 2023-07-05
32 | CK-28 | SALAMANDER | KARAMA-AT936/SIRMAN | 610 x 340 x 280Ht. | 1 | [5 empty] | REMOVE
33 | CK-29 | WORK TABLE 2 U/S | FABRICATED | 850 x 780 x 528Ht. | 1 | [5 empty] | REMOVE | G M ASSOCIATE | PO/SKPL/23-24/000774 | 2023-07-05
34 | CK-30 | 4 HOT PLATE ELECTRIC INDUCTION COOKING TOP RANGE | ELECTROLUX/700XP | 800 x 730 x 322Ht. | 1 | 3PH | 10.4 | 10.4 | 5 Pole Industrial Type | MCB | REMOVE
35 | CK-31 | SPARE NUMBER
36 | CK-32 | FOOD PROCESSOR | ROBOT COUPE-R301 ULTRA Robot Coupe R 301 Ultra | 305 x 365 x 300Ht. | 1 | 1P | 2.2 | 2.2 | 5 / 15 Amp | Switch | IN NEW LAYOUT | [8 empty] | NOT ORDERED
37 | CK-33 | WALL SHELF | FABRICATED | 750 x 300 W | 2 | [5 empty] | IN NEW LAYOUT | G M ASSOCIATE | PO/SKPL/23-24/000774 | 2023-07-05
38 | CK-34 | 2 DOOR U/C REF. WITH LOCKABLE CASTOR WHEELS (2 Nos.WITH BREAK INFRONT & 2 Nos. WITHOUT BREAK) & HEATING ELEMENT FOR DRAIN | ELANPRO-CGN2100TN | 1360 x 700 x 850Ht | 2 | 1P | 1 | 2 | 5 / 15 Amp | Switch | IN NEW LAYOUT | Blue Star Limited | PO/SKPL/23-24/000784 | 2023-07-06 |  | 7 to 10 days | Done 02-08-2023 |  |  | Advance Payment done
39 | CK-35 | 2 DOOR VERTICAL CHILLER WITH LOCKABLE CASTOR WHEELS (2 Nos.WITH BREAK INFRONT & 2 Nos. WITHOUT BREAK) & HEATING ELEMENT FOR DRAIN | ELANPRO -EGN 650TNM | 740 x 830 x 2010Ht. | 1 | 1P | 1 | 1 | 5 / 15 Amp | Switch | IN NEW LAYOUT | Blue Star Limited |  |  |  | 7 to 10 days
40 | CK-36 | 2 DOOR VERTICAL FREEZER WITH LOCKABLE CASTOR WHEELS (2 Nos.WITH BREAK INFRONT & 2 Nos. WITHOUT BREAK) & HEATING ELEMENT FOR DRAIN | ELANPRO -EGN 650BTM | 740 x 830 x 2010Ht. | 1 | 1P | 1 | 1 | 5 / 15 Amp | Switch | IN NEW LAYOUT | Blue Star Limited |  |  |  | 7 to 10 days
41 | CK-36A | 2 DOOR VERTICAL FREEZER WITH LOCKABLE CASTOR WHEELS (2 Nos.WITH BREAK INFRONT & 2 Nos. WITHOUT BREAK) & HEATING ELEMENT FOR DRAIN | ELANPRO -EGN 650BTM | 740 x 830 x 2010Ht. | 1 | 1P | 1 | 1 | 5 / 15 Amp | Switch | NEW ADDED | Blue Star Limited |  |  |  | 7 to 10 days
42 | CK-37 | FOOT OPERATED HAND WASH SINK WITH HOT & COLD WATER CONNECTION & WITH TISSUE HOLDER & SOAP DISPENSER PROVISION & OPEN FROM BACK SIDE | FABRICATED | 500 x 475 x 850+450SPL | 1 | [5 empty] | IN NEW LAYOUT | Steel Craft | PO/SKPL/23-24/000773 | 2023-07-05 |  | 7 to 10 days
47 | CK-42 | ONION, POTATO & COCONUTSTORAGE TROLLEY | FABRICATED | 900 x 450 x 1350Ht. | 1 | [5 empty] | IN NEW LAYOUT | Steel Craft | PO/SKPL/23-24/000773 | 2023-07-05 |  | 7 to 10 days
48 | CK-43 | 3 TIER DIRTY DISH TROLLEY WITH HANDLE (3 SIDE COVER & 2 FRONT DOORS) | FABRICATED | 925 x 700 x 850Ht. | 2 | [5 empty] | IN NEW LAYOUT | GROSS KITCHEN EQUIPMENTS | PO/SKPL/23-24/000775 | 2023-07-05
49 | CK-44 | VEG CUTTER | SIRMAN-TM-INOX 6 BLADE |  | 1 | 1P | 1 | 1 | 5 / 15 Amp | Switch | IN NEW LAYOUT | WANG PROFESSIONALS PRIVATE LIMITED | PO/SKPL/23-24/000779 | 2023-07-05 | 2023-07-05 |  | Done 22/09/23 | Received on 11/10/23 | PCS Docket No. 1010998 Dt.04.10.23 | Delivered
51 | CK-46 | SINGLE SINK (RHS) TABLE CROSS SUPPORT WITH OHS | FABRICATED | 1075 x 600 x 850+(150SPL)+ 450+300 | 1 | [5 empty] | IN NEW LAYOUT | Steel Craft | PO/SKPL/23-24/000773 | 2023-07-05 |  | 7 to 10 days
Total Kw-Main Kitchen - A | [7 empty] | 63.2
SOE
1 |  | GARBAGE BINS 60Ltrs.Cap.-FRONTIER PEDAL OPERATED WHEEL | SOE | 460 x 650 x 750Ht. | 2
2 |  | DUST BIN | SOE | 300DIA x 600Ht. | 1
3 |  | GEYSER (Cap. As Per MEP) | SOE | QTY CAN BE MODIFIE AS PER MEP | 2 | 3PH | 3 | 6 | 32 | Metal Clad
4 |  | INSECT KILLERS | SOE |  | 2 | 1P | 0.3 | 0.6 | 5 / 15 Amp | Switch Socket |  | Technocrats Security Systems Private Limited | PO/SKPL/23-24/000772 | 2023-07-05 |  | 7 to 10 days
5 |  | FIRE EXTINGUISHER ABC-4KG | SOE |  | 1 | [6 empty] | Fire Zone System Enterprise | PO/SKPL/23-24/000771 | 2023-07-05 |  | 7 to 10 days
6 |  | FIRE EXTINGUISHER CO/2-4.5KG | SOE |  | 1 | [6 empty] | Fire Zone System Enterprise | PO/SKPL/23-24/000771 | 2023-07-05 |  | 7 to 10 days
7 |  | FIRE EXTINGUISHER KTYPE - 6KG | SOE |  | 1 | [6 empty] | Fire Zone System Enterprise | PO/SKPL/23-24/000771 | 2023-07-05 |  | 7 to 10 days
8 |  | FIRE BLANKET - 6' X 4' | SOE |  | 1 | [6 empty] | Fire Zone System Enterprise | PO/SKPL/23-24/000771 | 2023-07-05 |  | 7 to 10 days
TOTAL MISCELLANEOUS LOAD IN Kw. - I | [7 empty] | 6.6
Total Kw- (A+ B+C+D+E+F+G+H) | [7 empty] | 69.8