## EXTRA QUANTITY
EXTRA QUANTITY
SN | LOCATION | ITEM DESCRIPTION | UNIT | QUANTITY | RATE |  |  | AMOUNT
1 | WOODEN PARTITION FOR BACK STORE | Providing and fixing of 75mm partition upto false ceiling height consisting of wooden partition with 12mm commercial ply with 1.5" x 2" Aluminium framing with inside approved laminate. (GreenLam - 5080 PURE ELM) | SQFT | 93.6 | 600
[6 empty] | Total | 111.23
[6 empty] | BOQ Qty | 93.6
[6 empty] | Extra Qty | 17.63 | 10578
2 | WALL TILES FOR BACK AREA | Providing , Fixing Vitrified tile of 18” X 12” in Dado as detailed in drawing. Tile to be fixed with cement paste over surface including , joints to be cleaned and grouted with matching colour approved epoxy based grout, curing, cleaning, including making cut-outs for plumbing and electrical points, any sleeves in tiles, scaffolding,etc. to required line, level, etc. all complete at all heights, lifts and leads to the entire satisfaction of the Project Head.(Make: KAJARIA/SOMANY - WHITE GLOSSY) | SQFT | 323 | 180
[6 empty] | Total | 342.5
[6 empty] | BOQ Qty | 323
[6 empty] | Extra Qty | 19.5 | 3510
3 | Display GLASS | Providing and Fixing Customer interface Counter of L - 6' x W - 2' x H - 20". The counter will finished in 12mm thik extra clear toughened glass, the base will be back painted white glass fixed with UV lighting and 25mm X 25mm hollow box section in matt 305 SS frame work. With profile lights Note : Rate should be inclusive of all hardware, polish,LED lights and paint. | SQFT | 12 | 2500
[6 empty] | TOTAL | 15
[6 empty] | BOQ QTY | 12
[6 empty] | EXTRA QTY | 3 | 7500
4 | BACK PAINTED GLASS | Providing and fixing of TEAL BACK PAINTED 6 mm thick toughened glass on the wall in FOH area as shown in the elevations. ( Teal colour - 9272 Green Wave - Asian Paint) | SQFT | 52 | 500
[6 empty] | TOTAL | 102.342
[6 empty] | BOQ QTY | 52
[6 empty] | EXTRA QTY | 50.342 | 25171
[6 empty] | GRAND TOTAL |  | 46759