## Extra Qauntity
DOMINOS EXTRA QAUNTITY
| RCC and PCC |  | BOQ Qty | Rate |  |  | Amount
PCC | Providing & Laying Plain cement concrete specified grade (M10) including the cost of centering and shuttering & required curing. Approved make cement is PPC (ACC, Ultra tech , Birla) | cuft | 173.376 | 200
[5 empty] | Total | 302.9299
[5 empty] | BOQ Qty | 173
[5 empty] | Extra Qty | 129.9299 | 25985.98
Rolling Shutter , Awning & Mild Steel work
HEAVY M.S Work & Framework | Providing, fabricating & erection of Steel work in built up section/ framed work i/c cutting, welding, hoisting, fixing in position & applying a priming coat of approved steel primer using steel etc, as required. In structure slab (ISMB, ISMC etc.) or stringers, treads, landing of stair case i/c use of chequered plate wherever required, all complete. Including primer and 2 coat paints | KG | 280.8588 | 110
[5 empty] | Total | 1329.52
[5 empty] | BOQ Qty | 280.8588
[5 empty] | Extra Qty | 1048.6612 | 115352.732
Flooring and Cladding
Skirting -(Details- Refer Material Spec. sheet) no.- 2a, FF02 (Kitchen & BOH) | Providing and fixing in position 100 mm ht. Skirting as per detail in drawing. Over 20 mm thk bed of cement mortar 1:4 (cement : fine sand ) with thick grey cement slurry, with hairline joints using cement grout. The job including cutting of tiles & making smooth edges wherever required for drain pipes. The work shall also include cost of materials, wastages, labour, all lead and lift at all levels, loading and unloading, transportation, curing etc. and all other incidental charges etc., complete and as directed by Engineer-in-charge. Finish of skirting to match with individual areas as per flooring plan. | Rft | 115 | 90
[5 empty] | Total | 129.1
[5 empty] | BOQ Qty | 115
[5 empty] | Extra Qty | 14.1 | 1269
Skirting (Booth seating) FF 04 - Kajaria Sheesham Rosewood or Somany Strio Verano wood Teak . (Details- Refer Material Spec. sheet) | Providing and fixing in position 100 mm ht. Skirting as per detail in drawing.Over 20 mm thk bed of cement mortar 1:4 (cement : fine sand ) with thick grey cement slurry, with hairline joints using cement grout. The job including cutting of tiles & making smooth edges wherever required for drain pipes. The work shall also include cost of materials, wastages, labour, all lead and lift at all levels, loading and unloading, transportation, curing etc. and all other incidental charges etc., complete and as directed by Engineer-in-charge. Finish of skirting to match with individual areas as per flooring plan. | Rft | 9.0816 | 90
[5 empty] | Total | 13.8
[5 empty] | BOQ Qty | 9.0816
[5 empty] | Extra Qty | 4.8 | 432
Wall Tile Cladding - 2 (Kitchen & BOH area). (Details- Refer Material Spec. sheet) no.B(3) | Providing and fixing in position dado tile of approved make & shade on any surface as per details in drawing and Over 12 mm thk bed of cement mortar 1:3 (cement : fine sand ) with thick grey cement slurry, with hairline joints using cement grout. The job including cutting of tiles & making smooth edges wherever required . The work shall also include cost of materials, wastages, labour, all lead and lift at all levels, loading and unloading, transportation, curing etc. and all other incidental charges etc. Complete as specified in the drawing & to the satisfaction of the Site Engineer. Ceramic wall tile (Printed) With customize line work | Sq. Ft | 468.4764 | 130
[5 empty] | Total | 669.95
[5 empty] | BOQ Qty | 468.4764
[5 empty] | Extra Qty | 201.4736 | 26191.568
C | P.O.P/Painting
POP Punning | Providing & applying wall punning up to 12mm to 15mm thick layer of super fine Plaster of Paris applied on specified area over existing plastered surface on walls and columns, to be finished smooth. Surface to be prepared by hacking, sand papering and applying coat of cement slurry if required including all incidentals, making grooves, patties, sills etc. complete and as directed by engineer in charge. The finish surface should be smooth, cover up all the patch work done by electrical agencies so as to avoid unevenness and ready to take on paint. Rate including cost of transportation, loading, unloading, scaffolding, wastage, taxes etc. as directed by Engineer-in-charge. | Sq. Ft | 371.6748 | 60
[5 empty] | Total | 530.14
[5 empty] | BOQ Qty | 371.6748
[5 empty] | Extra Qty | 158.14 | 9488.4
Painting - Asain coal mine 8301 (Ceiling) | Providing and applying Plastic Emulsion Paint on Ceiling of approved make & shade filling the dents with approved Acrylic putty gypsum / or approved crack filler, binder, cleaning and making the surface dust free, preparing surfaces, applying a coat of sealer or primer as per the manufacturers specifications, applying two under coats and one finished coat of paint to achieve the required finish including scrapping the existing paint, scaffolding, cleaning etc. complete as per detail drawing, as specified and as directed by Engineer-in-charge. | Sq. Ft | 516 | 70
[5 empty] | Total | 530.14
[5 empty] | BOQ Qty | 516
[5 empty] | Extra Qty | 14.14 | 989.8
Furniture /WOOD Work
Order Counter | Providing and fixing in position Order counter : Counter top finished in 6mm thick Acrylic Solid Surface LG Hausys-HI-MACS G109 Beige Island over 19 mm thick WPC/Marine Ply. 150mm height Drawers (2 nos )to be provided below each POS.Internal area to be finish with 1 mm thick approved laminate with necessary hardwares(Lock ,Telescopic channel etc). MS powder coated framework (40x40x1.5mm) as per detail drawing to be provided with necessay arrangement and Ledge having LED cove strip as per detail drawing Complete in all respect . Cost to include all materials, DMB Framing ,labours and necessary leads & lift etc. -Counter Height-3'6" | RFT | 8.456 | 7500
[5 empty] | Total | 16.7
[5 empty] | BOQ Qty | 8.456
[5 empty] | Extra Qty | 8.7 | 65250
INTERNAL WATER SUPPLY SYSTEM
Providing & fixing on walls / ceiling / floors, medium grade having embossed ISI Mark CPVC pipes of diameter as mentioned below with fittings i.e.connector, clamps, tees, elbows, reducers, male-female etc. necessary fittings. (Supreme / Prince/Astral or as approved. )
| 20mm nominal bore for sink+ gyser+ RO+ Basin+papsi machine | RMT | 22 | 120
[5 empty] | Total | 44
[5 empty] | BOQ Qty | 22
[5 empty] | Extra Qty | 22 | 2640
INTERNAL DRAINAGE SYSTEM
| Providing ,laying, testing & commissioning of approved Multi floor trap / Nahani trap with Chilly trap of required sizes, including jointing etc. complete and as directed. (GMGR/Chilly or equivalent) | Nos. | 2 | 600
[5 empty] | Total | 7
[5 empty] | BOQ Qty | 2
[5 empty] | Extra Qty | 5 | 3000
Sanitarywares & Fittings
Sink Mixer For 3 way Sink | Providing and fixing C.P brass wall mounted sink mixer with swinging spout including cutting and making good the walls where required. (3 way Sink ) | Each | 1 | 2000
[5 empty] | Total | 4
[5 empty] | BOQ Qty | 1
[5 empty] | Extra Qty | 3 | 6000
Waste Coupling | Waste Coupling for 3Way sink and Makeline sink | No. | 1 | 600
[5 empty] | Total | 2
[5 empty] | BOQ Qty | 1
[5 empty] | Extra Qty | 1 | 600
Isolators /ELCB /RCBO & SWITCH SOCKETS
Supplying and fixing of following sizes of MS conduit along with accessories in surface/recess including painting in case of surface conduit, or cutting the wall and making good the same in case of recessed conduit as required.
| 20 mm | Rmtr | 24 | 50
[5 empty] | Total | 36
[5 empty] | BOQ Qty | 24
[5 empty] | Extra Qty | 12 | 600
| 25 mm | Rmtr | 30 | 80
[5 empty] | Total | 50
[5 empty] | BOQ Qty | 30
[5 empty] | Extra Qty | 20 | 1600
| Supplying & erecting M.S flexible Conduit 25 mm dia.conforming to I.S. and approved make with required number of couplings, bushes, check nuts etc. | Rmtr | 7 | 80
[5 empty] | Total | 90
[5 empty] | BOQ Qty | 7
[5 empty] | Extra Qty | 83 | 6640
Cat-6 Cable for Switch to Camera inlcuding conduit. | Cat-6 Cable for Switch to Camera inlcuding conduit. | Rmtr | 120 | 35
[5 empty] | Total | 390
[5 empty] | BOQ Qty | 120
[5 empty] | Extra Qty | 270 | 9450
8.1 | Chilled Water Pipe Insulation | Rmt | 25 | 110
[5 empty] | Total | 39
[5 empty] | BOQ Qty | 25
[5 empty] | Extra Qty | 14 | 1540
Supplying and fixing of following sizes of MS conduit along with accessories in surface/recess including painting in case of surface conduit, or cutting the wall and making good the same in case of recessed conduit as required.
| 20 mm | Rmtr | 24 | 50
|  |  |  | Total |  | 32
|  |  |  | BOQ Qty |  | 24
|  |  |  | Extra Qty |  | 8 | 400
| 25 mm | Rmtr | 30 | 80
|  |  |  | Total |  | 45
|  |  |  | BOQ Qty |  | 30
|  |  |  | Extra Qty |  | 15 | 1200
| Supplying & erecting M.S flexible Conduit 25 mm dia.conforming to I.S. and approved make with required number of couplings, bushes, check nuts etc. | Rmtr | 7 | 80
|  |  |  | Total |  | 90
|  |  |  | BOQ Qty |  | 7
|  |  |  | Extra Qty |  | 83 | 6640
| Cat-6 Cable for Switch to Camera inlcuding conduit. | Rmtr | 120 | 35
|  |  |  | Total |  | 370
|  |  |  | BOQ Qty |  | 120
|  |  |  | Extra Qty |  | 250 | 8750
|  |  |  | Grand Total |  |  | 294019.48