## PI
DAYSPRING ENTERPRISES
B/14, HAPPY HOME APTS, OPP. SWEEKAR HOTEL
SAIBABA NAGAR, BORIVLI (WEST), MUMBAI - 400 092
Contact no: +91 98202 30523 Email : dayspringent@gmail.com
Proforma Invoice for Budweiser Repair and Maintance Work
To, | Simolina Kitchen Pvt. Ltd. |  | Date |  | 2024-09-11
Lucknow Airport terminal -3 , The Irish House
Kindly Attn.:- Mr. Irfaan
Sr. No. | Category | Description | Unit | QTY | Rate | Amount
1 | Repair and maintance | Dismentling work of Budweiser Repair and maintance work. | NOS | 1 | 1207265 | 1207265
[5 empty] | Basic Total | 1207265
[5 empty] | Add GST @ 18% | 217307.7
[5 empty] | Grand Total | 1424572.7
Work Completion Time Period
Material Delivery 1o days from the Date of PO with advance
Payment terms :
50% Advance with Work order
No Retention
For DAYSPRING ENTERPRISES
Authorised Signatory

## Pioneer balance work PR
DAYSPRING ENTERPRISES
SUMMARY FOR Budweiser Repair and maintance LKO LUCKNOW AIRPORT
Sr. no | Discreption | Unit | Total Qty | Rate | Amount | Remarks
1 | Kota Stone Polishing and Repair joints and whichever required change damage kota stone or as per project incharge. | Sqm | 18 | 755 | 13590 | Quality and workmanship issues from Pioneer.
2 | BOH Area tiles Joints to be fill epoxy grouts matching the tile. | Sqm | 98 | 130 | 12740 | Quality and workmanship issues from Pioneer.
3 | BOH area existing tiles dismentel and re- fix new tiles in line and level or as per project incharge | Sqm | 14 | 1455 | 20370 | Quality and workmanship issues from Pioneer.
5 | Supply, Installation, Testing and Commissioning & fixing of powder coated extruded Aluminium Continuous Grille as per specifications
i | 150 MM Aluminium Continuos Grille | RM | 5 | 6500 | 32500 | Pioneer scope of work, delivery not done till date.
ii | 100 MM Aluminium Continuos Grille | RM | 30 | 6000 | 180000 | Pioneer scope of work, delivery not done till date.
iii | Supply, Installation, Testing and Commissioning & fixing of powder coated extruded aluminium Supply / Exhaust Air Grills as per specifications | Sqm | 2 | 6000 | 12000 | Pioneer scope of work, delivery not done till date.
10 | Providing and fixing Electric metre as per approved make and specification or as per project in-charge MAKE- secure | Nos | 1 | 14000 | 14000 | Pioneer scope of work, not done till date.
11 | providing and fixing water metre with all accesseries Make - Kranti or as per approved make | Nos | 1 | 7500 | 7500 | Pioneer scope of work, not done till date.
12 | Supply, installation,testing & commissioning of Storage Type Electric Hot Water Gyeser of mentioned capacity, suitable for 3 KG/cm2 pressure, Wall Mounted / Floor standing type, with Auto Shut-off Thermostat, along with isoltion Valves, Air Release valve, SS flexible connections andall other std accessories Make Recold ,jaquar
i | 6 Ltr | Nos | 1 | 9500 | 9500 | Pioneer scope of work, not done till date. 2 nos given in BOQ.
13 | Providing and fixing water tank capicty 200 ltr. With all accesseries and fittingOr as per design and project incharge | Nos | 1 | 12500 | 12500 | piioneer scope of work, not done tiill date.
14 | MS Deck slab above ceiling level for water tank sixe (1200 x 1500 mm) | Sqm | 1.85 | 3800 | 7030 | piioneer scope of work, not done tiill date.
15 | Chamber S.S Grating size, 300mm x 300mm, in 16 swg 25mm x25mm Square Pipe around the Frame and 20mmX 20mm Square pipe in center of frame with SS perforated tray (304 SWR). Complete as per architectural detail drawing & Site Engineer's instruction. | Nos | 4 | 7500 | 30000 | piioneer scope of work, not done tiill date.
17 | Supply, Laying, Testing & Commissioning of 75x75mm Floor Trap Cockroch trap with Approved Make heavy duty round or Square. | Nos | 10 | 2350 | 23500 | piioneer scope of work, not done tiill date.
18 | water supply connection taken from existing point complete with all necessary fittings. | Nos | 1 | 5000 | 5000 | piioneer scope of work, not done tiill date.
19 | Providing & Fixing Sink Cock . Make-Jaquar or Equivelent | Nos | 2 | 3250 | 6500 | piioneer scope of work, not done tiill date.
20 | Providing & Fixing Sink Table Mixer Make-Jaquar or Equivelent | Nos | 1 | 5500 | 5500 | piioneer scope of work, not done tiill date.
21 | Providing & fixing 32mm CP finished Bottle Trap with wall flanges. (Make – JAQUAR / OZONE) | Nos | 3 | 2450 | 7350 | piioneer scope of work, not done tiill date.
22 | Providing Waste Coupling 32mm size full thread waste coupling to be use for 3-bowl sink. | Nos | 1 | 9500 | 9500 | piioneer scope of work, not done tiill date.
25 | Providing and fixing BTU Metre Make- Belimo | Nos | 3 | 55000 | 165000 | Pioneer scope of work, not done till date.
28 | Providing and Applying 2 coat Putty and oil base Primer for smooth finsh of wallpaper or Texture Bar counter Front wall both side (inside and passage side) | Sqm | 120 | 193 | 23160 | Pioneer scope of work, not done till date.
29 | IPS: Providing and laying Smooth Cement finish on rough concrete surface with Upto 20 mm thick (or desired thickness) paste of 1:1 cement mortar , complete including necessary surface preparation and curing, all complete as per Project Manager's instructions. | Sqm | 260 | 400 | 104000 | Pioneer scope of work, level not done properly. Need to redo. | Remove this scope and top up with self leveling/IPS
31 | PIBCV VALVES
SITC of Pressure Independent Balancing cum Control Valves (PIBCV) including integrated motorised control valve and balancing device for combined flow and water balancing requirement. Valve body to be rated for PN 16. The valve design flow rate should be factory calibrated with +/- 5% flow accuracy. Valve shall have necessary measuring ports, drain port, flanges etc., Valve shall also provide temperature sensor with necessary cabling (min 2mtr length to be considered with each valve). The balancing to be done through microprocessor based hand held terminal / POT and the same results shall be furnished in the water balancing report as part of commissioning report and handing over manual.
Make: Oventrop / Siemens / Danfoss
| Φ 40 mm | NOS | 3 | 7500 | 22500 | Pioneer scope, not done till date.
32 | Auto Air Vent Valves
Make: Anergy / Flamco
Providing and fitting Auto Vent Valves.
| SITC of Auto air vent in each risers & common headers & AHU. 3/4" auto vent valves at each coil / riser/ header. | NOS | 6 | 2550 | 15300 | Pioneer scope, not done till date.
33 | SITC of Pressure gauges & Thermometers
Make: H Guru / Waree
Necessary pressure gauges and thermometers 4" Dial type.
i | Water Pressure gauges 150mm dial complete with gauge valves, mounting, fittings and copper tubing extension wherever required. Pressure gauges Range 0-10 Kg/CM2 | NOS | 6 | 6500 | 39000 | Pioneer scope, not done till date.
III | Thermometers of the mercury in glass stem type and copper separable well complete with guard etc., of industrial grade mounting on water lines. Length 9/12 inches, Thermometer, Range 0-50 deg C | NOS | 6 | 3200 | 19200 | Pioneer scope, not done till date.
iii | Thermowells | NOS | 6 | 2450 | 14700 | Pioneer scope, not done till date.
34 | Fiiting and commissioning AHU 3 nos with all fiiting or as per project incharge | Nos | 3 | 10000 | 30000 | Pioneer scope, not done till date.
36 | Supply, Installation, testing and commissioning of 3.0 KVA UPS System Single Phase I/C & Single Phase O/G complete with 15 Minutes Battery Back-up the required accessories as specified in the drawings & the specifications. | nos | 1 | 110000 | 110000 | Pioneer scope, delivery not done till date.
39 | Supply & Installation of 25mm.dia. GI conduit with pull box/ junction box & all accessories for CCTV wiring as per the requirement. | Rmt | 245 | 185 | 45325 | Pioneer scope, delivery not done till date.
41 | Installation, Testing and Commissioning of Dry Type Scrubber each comprising of extract air intake section, electrostatic precipitation technology, dry type air cleaner to remove oil, smoke and fumes from exhaust air, as per the Specifications. Electrostatic section shall be made of 16 gauge galvanised sheet, high bake epoxy powder coated, washable type aluminium mesh filters, stainless steel spiked ionizers to create high voltage DC field, aluminum collector plates which should be alternatively charged positive and negative with large collecting area with 14" deep cell, to work as magnet for charged smoke and oil particles. Average efficiency of 90-95% in single pass as per ASHRAE test method. Electrostatic Precipitator should be able to charge particles from 0.01 micron to 10 microns through solid state power supply. Collector cell should be of permanent type and incorporate slide out facility for easy removal for cleaning. Power supplies shall be 100% solid state UL Listed, Module of capacity above 3000 CFM shall be equipped with Pulse width modulating (PWM)
The system should be fitted with interlock switch for safety . The system should allow connection to a fan section to achieve 500 FPM velocity across the air
Operating Voltage : 220V, 50 Hz
Ionizing Voltage : 12.5 to 13 KVDC
Collector Cell Voltage : 6 to 6.5 KVDC
Power Consumption : Not more than 50W per cell.
Capacities :4000 CFM
| MAKE- Z air | Nos | 1 | 210000 | 210000 | Pioneer scope, delivery not done till date , and also installation and commisisoning to be done.
| Total Amount |  |  |  | 1207265

## NT items
DAYSPRING ENTERPRISES
SUMMARY FOR Budweiser Repair and maintance LKO LUCKNOW AIRPORT
Sr. no | Discreption | Unit | Total Qty | Rate | Amount | Remarks
8 | Providing and fixing Solid core wooden flush door on site 50mm thick made of FR ply DOOR SIZE 1000X2400 finished in 1.5mm thick laminate as per approved colour and make, complete in all respects including all fittings as required with door frame of hard wood. 75 mm width | nos | 2 | 25500 | 51000 | One door under Pioneer scope, not done till date, second additional work.
12 | Supply, installation,testing & commissioning of Storage Type Electric Hot Water Gyeser of mentioned capacity, suitable for 3 KG/cm2 pressure, Wall Mounted / Floor standing type, with Auto Shut-off Thermostat, along with isoltion Valves, Air Release valve, SS flexible connections andall other std accessories Make Recold ,jaquar
ii | 35 Ltr | Nos | 1 | 28000 | 28000 | Additional requirement
24 | Providing & Fixing PPR Ball Valve ISI mark. (For Inlet) | Nos | 1 | 6000 | 6000 | Additional requirement due to pressure from adani end supply
26 | Providing and applying of POP Punning on plastered walls with plaster of paris of average thickness of 15 to 20 mm thk of approved make to true line, level, plumb including leveling, sanding of surface fit to receive further finish. ( For Wall Only) Bar & Buffet counter wall. | Sqm | 62 | 510 | 31620 | Additional requirement as required by Brand
27 | Providing and Applying 2 coat Putty and oil base Primer for smooth finsh of wallpaper or Texture Bar counter wall | Sqm | 62 | 193 | 11966 | Additional requirement as required by Brand
30 | Installation, testing & commissioning of the following concealed / surface mounted or suspended light fixtures AS PER FINAL APPROVAL FROM ARCHITECT/CLIENT/CONSULTANT with lamps, ballast & all necessary mounting & supporting accessories. No additional cost shall be paid for supporting.
i | Ceiling Conclead light | Nos | 28 | 250 | 7000
ii | decorative light | Nos | 2 | 650 | 1300
III | celing Suspending Leinar light | Nos | 50 | 300 | 15000
31 | PIBCV VALVES
SITC of Pressure Independent Balancing cum Control Valves (PIBCV) including integrated motorised control valve and balancing device for combined flow and water balancing requirement. Valve body to be rated for PN 16. The valve design flow rate should be factory calibrated with +/- 5% flow accuracy. Valve shall have necessary measuring ports, drain port, flanges etc., Valve shall also provide temperature sensor with necessary cabling (min 2mtr length to be considered with each valve). The balancing to be done through microprocessor based hand held terminal / POT and the same results shall be furnished in the water balancing report as part of commissioning report and handing over manual.
Make: Oventrop / Siemens / Danfoss
| Φ 40 mm | NOS | 3 | 7500 | 22500 | Pioneer scope, not done till date.
32 | Auto Air Vent Valves
Make: Anergy / Flamco
Providing and fitting Auto Vent Valves.
| SITC of Auto air vent in each risers & common headers & AHU. 3/4" auto vent valves at each coil / riser/ header. | NOS | 6 | 2550 | 15300 | Pioneer scope, not done till date.
33 | SITC of Pressure gauges & Thermometers
Make: H Guru / Waree
Necessary pressure gauges and thermometers 4" Dial type.
i | Water Pressure gauges 150mm dial complete with gauge valves, mounting, fittings and copper tubing extension wherever required. Pressure gauges Range 0-10 Kg/CM2 | NOS | 6 | 6500 | 39000 | Pioneer scope, not done till date.
III | Thermometers of the mercury in glass stem type and copper separable well complete with guard etc., of industrial grade mounting on water lines. Length 9/12 inches, Thermometer, Range 0-50 deg C | NOS | 6 | 3200 | 19200 | Pioneer scope, not done till date.
iii | Thermowells | NOS | 6 | 2450 | 14700 | Pioneer scope, not done till date.
34 | Fiiting and commissioning AHU 3 nos with all fiiting or as per project incharge | Nos | 3 | 10000 | 30000 | Pioneer scope, not done till date.
35 | Supplying, installation, Testing and commissioning flush mounting floor metallic boxes(POP-UP BOX) IP 66 3 module of 6/16A International switch & socket outlet + 1 set complete with all installation kits, accessories, required to finish the installation Make- Legrand | Nos | 14 | 5450 | 76300 | additional requirement as required by Brand for flooring charging points
36 | Supply, Installation, testing and commissioning of 3.0 KVA UPS System Single Phase I/C & Single Phase O/G complete with 15 Minutes Battery Back-up the required accessories as specified in the drawings & the specifications. | nos | 1 | 110000 | 110000 | Pioneer scope, delivery not done till date.
37 | MAIN LT PANEL Testing and commissioning as per drawing . | nos | 1 | 25000 | 25000 | Pioneer scope, everything done, commissioning pending.
38 | Testing and Commissioning Fire Sprinkler system if already commissioning done not required | nos | 1 | 7500 | 7500 | Work done, final testing pending from Pioneer.
39 | Supply & Installation of 25mm.dia. GI conduit with pull box/ junction box & all accessories for CCTV wiring as per the requirement. | Rmt | 245 | 185 | 45325 | Pioneer scope, delivery not done till date.
40 | Electrical Additional point for Gas detector and Bar Area or as per desire whichever with all include | nos | 5 | 7500 | 37500 | additional requirement
41 | Installation, Testing and Commissioning of Dry Type Scrubber each comprising of extract air intake section, electrostatic precipitation technology, dry type air cleaner to remove oil, smoke and fumes from exhaust air, as per the Specifications. Electrostatic section shall be made of 16 gauge galvanised sheet, high bake epoxy powder coated, washable type aluminium mesh filters, stainless steel spiked ionizers to create high voltage DC field, aluminum collector plates which should be alternatively charged positive and negative with large collecting area with 14" deep cell, to work as magnet for charged smoke and oil particles. Average efficiency of 90-95% in single pass as per ASHRAE test method. Electrostatic Precipitator should be able to charge particles from 0.01 micron to 10 microns through solid state power supply. Collector cell should be of permanent type and incorporate slide out facility for easy removal for cleaning. Power supplies shall be 100% solid state UL Listed, Module of capacity above 3000 CFM shall be equipped with Pulse width modulating (PWM)
The system should be fitted with interlock switch for safety . The system should allow connection to a fan section to achieve 500 FPM velocity across the air
Operating Voltage : 220V, 50 Hz
Ionizing Voltage : 12.5 to 13 KVDC
Collector Cell Voltage : 6 to 6.5 KVDC
Power Consumption : Not more than 50W per cell.
Capacities :4000 CFM
| MAKE- Z air | Nos | 1 | 210000 | 210000 | Pioneer scope, delivery not done till date , and also installation and commisisoning to be done.
| Total Amount |  |  |  | 804211

## Reference details
DAYSPRING ENTERPRISES
SUMMARY FOR Budweiser Repair and maintance LKO LUCKNOW AIRPORT
Sr. no | Discreption | Unit | Total Qty | Rate | Amount | Remarks
1 | Kota Stone Polishing and Repair joints and whichever required change damage kota stone or as per project incharge. | Sqm | 18 | 755 | 13590 | Quality and workmanship issues from Pioneer.
2 | BOH Area tiles Joints to be fill epoxy grouts matching the tile. | Sqm | 98 | 130 | 12740 | Quality and workmanship issues from Pioneer.
3 | BOH area existing tiles dismentel and re- fix new tiles in line and level or as per project incharge | Sqm | 14 | 1455 | 20370 | Quality and workmanship issues from Pioneer.
4 | BOH Area metal ceiling removing and rework to achive 100 mm Level down or Hanging rod with butterfly claim or as per project incharge | Sqm | 30 | 1885 | 56550 | Quality and workmanship issues from Pioneer.
5 | Supply, Installation, Testing and Commissioning & fixing of powder coated extruded Aluminium Continuous Grille as per specifications
i | 150 MM Aluminium Continuos Grille | RM | 5 | 6500 | 32500 | Pioneer scope of work, delivery not done till date.
ii | 100 MM Aluminium Continuos Grille | RM | 30 | 6000 | 180000 | Pioneer scope of work, delivery not done till date.
iii | Supply, Installation, Testing and Commissioning & fixing of powder coated extruded aluminium Supply / Exhaust Air Grills as per specifications | Sqm | 2 | 6000 | 12000 | Pioneer scope of work, delivery not done till date.
6 | Supply, Installation, Testing and Commissioning of multiblade Al volume control Collar / Grille / exhaust Air Opening damper complete with suitable links, lever and quadrants for manual control of airflow and with suitable links , lever and quadrants for manual control of airflow and neoprene rubber gaskets, nuts, bolts, screws, flanges etc., as per specifications. | Sqm | 2 | 8000 | 16000 | Pioneer scope of work, delivered but not fixed.
7 | Supply,Installation, Testing and Commissioning of GI multiblade volume control duct damper complete with neoprene rubber gaskets, nuts, bolts, screws linkages, flanges etc., as per specifications. | Sft | 14 | 10500 | 147000 | Pioneer scope of work, delivered but not fixed.
8 | Providing and fixing Solid core wooden flush door on site 50mm thick made of FR ply DOOR SIZE 1000X2400 finished in 1.5mm thick laminate as per approved colour and make, complete in all respects including all fittings as required with door frame of hard wood. 75 mm width | nos | 2 | 25500 | 51000 | One door under Pioneer scope, not done till date, second additional work.
9 | 36 watt - 600mm x 600mm recessed led panel light makes: i- Syska, ii-Panasonic, iii-Havels, iv- Wipro. | Nos | 8 | 2450 | 19600 | PR already rasied for the same on Safal, Please suggest should we take from them.
10 | Providing and fixing Electric metre as per approved make and specification or as per project in-charge MAKE- secure | Nos | 1 | 14000 | 14000 | Pioneer scope of work, not done till date.
11 | providing and fixing water metre with all accesseries Make - Kranti or as per approved make | Nos | 1 | 7500 | 7500 | Pioneer scope of work, not done till date.
12 | Supply, installation,testing & commissioning of Storage Type Electric Hot Water Gyeser of mentioned capacity, suitable for 3 KG/cm2 pressure, Wall Mounted / Floor standing type, with Auto Shut-off Thermostat, along with isoltion Valves, Air Release valve, SS flexible connections andall other std accessories Make Recold ,jaquar
i | 6 Ltr | Nos | 1 | 9500 | 9500 | Pioneer scope of work, not done till date. 2 nos given in BOQ.
ii | 35 Ltr | Nos | 1 | 28000 | 28000 | Additional requirement
13 | Providing and fixing water tank capicty 200 ltr. With all accesseries and fittingOr as per design and project incharge | Nos | 1 | 12500 | 12500 | piioneer scope of work, not done tiill date.
14 | MS Deck slab above ceiling level for water tank sixe (1200 x 1500 mm) | Sqm | 1.85 | 3800 | 7030 | piioneer scope of work, not done tiill date.
15 | Chamber S.S Grating size, 300mm x 300mm, in 16 swg 25mm x25mm Square Pipe around the Frame and 20mmX 20mm Square pipe in center of frame with SS perforated tray (304 SWR). Complete as per architectural detail drawing & Site Engineer's instruction. | Nos | 4 | 7500 | 30000 | piioneer scope of work, not done tiill date.
16 | Angle valve/ Cock with PVC pipe connection upto WHB/sink/Geyser connection | Nos | 15 | 2350 | 35250 | piioneer scope of work,
17 | Supply, Laying, Testing & Commissioning of 75x75mm Floor Trap Cockroch trap with Approved Make heavy duty round or Square. | Nos | 10 | 2350 | 23500 | piioneer scope of work, not done tiill date.
18 | water supply connection taken from existing point complete with all necessary fittings. | Nos | 1 | 5000 | 5000 | piioneer scope of work, not done tiill date.
19 | Providing & Fixing Sink Cock . Make-Jaquar or Equivelent | Nos | 2 | 3250 | 6500 | piioneer scope of work, not done tiill date.
20 | Providing & Fixing Sink Table Mixer Make-Jaquar or Equivelent | Nos | 1 | 5500 | 5500 | piioneer scope of work, not done tiill date.
21 | Providing & fixing 32mm CP finished Bottle Trap with wall flanges. (Make – JAQUAR / OZONE) | Nos | 3 | 2450 | 7350 | piioneer scope of work, not done tiill date.
22 | Providing Waste Coupling 32mm size full thread waste coupling to be use for 3-bowl sink. | Nos | 1 | 9500 | 9500 | piioneer scope of work, not done tiill date.
23 | Providing and fixing Sink Make Nirali aur equivelent | Nos | 0 | 6500 | 0
24 | Providing & Fixing PPR Ball Valve ISI mark. (For Inlet) | Nos | 1 | 6000 | 6000 | Additional requirement due to pressure from adani end supply
25 | Providing and fixing BTU Metre Make- Belimo | Nos | 3 | 55000 | 165000 | Pioneer scope of work, not done till date.
26 | Providing and applying of POP Punning on plastered walls with plaster of paris of average thickness of 15 to 20 mm thk of approved make to true line, level, plumb including leveling, sanding of surface fit to receive further finish. ( For Wall Only) Bar & Buffet counter wall. | Sqm | 62 | 510 | 31620 | Additional requirement as required by Brand
27 | Providing and Applying 2 coat Putty and oil base Primer for smooth finsh of wallpaper or Texture Bar counter wall | Sqm | 62 | 193 | 11966 | Additional requirement as required by Brand
28 | Providing and Applying 2 coat Putty and oil base Primer for smooth finsh of wallpaper or Texture Bar counter Front wall both side (inside and passage side) | Sqm | 120 | 193 | 23160 | Pioneer scope of work, not done till date.
29 | IPS: Providing and laying Smooth Cement finish on rough concrete surface with Upto 20 mm thick (or desired thickness) paste of 1:1 cement mortar , complete including necessary surface preparation and curing, all complete as per Project Manager's instructions. | Sqm | 260 | 400 | 104000 | Pioneer scope of work, level not done properly. Need to redo. | Remove this scope and top up with self leveling/IPS
30 | Installation, testing & commissioning of the following concealed / surface mounted or suspended light fixtures AS PER FINAL APPROVAL FROM ARCHITECT/CLIENT/CONSULTANT with lamps, ballast & all necessary mounting & supporting accessories. No additional cost shall be paid for supporting.
i | Ceiling Conclead light | Nos | 28 | 250 | 7000
ii | decorative light | Nos | 2 | 650 | 1300
III | celing Suspending Leinar light | Nos | 50 | 300 | 15000
31 | PIBCV VALVES
SITC of Pressure Independent Balancing cum Control Valves (PIBCV) including integrated motorised control valve and balancing device for combined flow and water balancing requirement. Valve body to be rated for PN 16. The valve design flow rate should be factory calibrated with +/- 5% flow accuracy. Valve shall have necessary measuring ports, drain port, flanges etc., Valve shall also provide temperature sensor with necessary cabling (min 2mtr length to be considered with each valve). The balancing to be done through microprocessor based hand held terminal / POT and the same results shall be furnished in the water balancing report as part of commissioning report and handing over manual.
Make: Oventrop / Siemens / Danfoss
| Φ 40 mm | NOS | 3 | 7500 | 22500 | Pioneer scope, not done till date.
32 | Auto Air Vent Valves
Make: Anergy / Flamco
Providing and fitting Auto Vent Valves.
| SITC of Auto air vent in each risers & common headers & AHU. 3/4" auto vent valves at each coil / riser/ header. | NOS | 6 | 2550 | 15300 | Pioneer scope, not done till date.
33 | SITC of Pressure gauges & Thermometers
Make: H Guru / Waree
Necessary pressure gauges and thermometers 4" Dial type.
i | Water Pressure gauges 150mm dial complete with gauge valves, mounting, fittings and copper tubing extension wherever required. Pressure gauges Range 0-10 Kg/CM2 | NOS | 6 | 6500 | 39000 | Pioneer scope, not done till date.
III | Thermometers of the mercury in glass stem type and copper separable well complete with guard etc., of industrial grade mounting on water lines. Length 9/12 inches, Thermometer, Range 0-50 deg C | NOS | 6 | 3200 | 19200 | Pioneer scope, not done till date.
iii | Thermowells | NOS | 6 | 2450 | 14700 | Pioneer scope, not done till date.
34 | Fiiting and commissioning AHU 3 nos with all fiiting or as per project incharge | Nos | 3 | 10000 | 30000 | Pioneer scope, not done till date.
35 | Supplying, installation, Testing and commissioning flush mounting floor metallic boxes(POP-UP BOX) IP 66 3 module of 6/16A International switch & socket outlet + 1 set complete with all installation kits, accessories, required to finish the installation Make- Legrand | Nos | 14 | 5450 | 76300 | additional requirement as required by Brand for flooring charging points
36 | Supply, Installation, testing and commissioning of 3.0 KVA UPS System Single Phase I/C & Single Phase O/G complete with 15 Minutes Battery Back-up the required accessories as specified in the drawings & the specifications. | nos | 1 | 110000 | 110000 | Pioneer scope, delivery not done till date.
37 | MAIN LT PANEL Testing and commissioning as per drawing . | nos | 1 | 25000 | 25000 | Pioneer scope, everything done, commissioning pending.
38 | Testing and Commissioning Fire Sprinkler system if already commissioning done not required | nos | 1 | 7500 | 7500 | Work done, final testing pending from Pioneer.
39 | Supply & Installation of 25mm.dia. GI conduit with pull box/ junction box & all accessories for CCTV wiring as per the requirement. | Rmt | 245 | 185 | 45325 | Pioneer scope, delivery not done till date.
40 | Electrical Additional point for Gas detector and Bar Area or as per desire whichever with all include | nos | 5 | 7500 | 37500 | additional requirement
41 | Installation, Testing and Commissioning of Dry Type Scrubber each comprising of extract air intake section, electrostatic precipitation technology, dry type air cleaner to remove oil, smoke and fumes from exhaust air, as per the Specifications. Electrostatic section shall be made of 16 gauge galvanised sheet, high bake epoxy powder coated, washable type aluminium mesh filters, stainless steel spiked ionizers to create high voltage DC field, aluminum collector plates which should be alternatively charged positive and negative with large collecting area with 14" deep cell, to work as magnet for charged smoke and oil particles. Average efficiency of 90-95% in single pass as per ASHRAE test method. Electrostatic Precipitator should be able to charge particles from 0.01 micron to 10 microns through solid state power supply. Collector cell should be of permanent type and incorporate slide out facility for easy removal for cleaning. Power supplies shall be 100% solid state UL Listed, Module of capacity above 3000 CFM shall be equipped with Pulse width modulating (PWM)
The system should be fitted with interlock switch for safety . The system should allow connection to a fan section to achieve 500 FPM velocity across the air
Operating Voltage : 220V, 50 Hz
Ionizing Voltage : 12.5 to 13 KVDC
Collector Cell Voltage : 6 to 6.5 KVDC
Power Consumption : Not more than 50W per cell.
Capacities :4000 CFM
| MAKE- Z air | Nos | 1 | 210000 | 210000 | Pioneer scope, delivery not done till date , and also installation and commisisoning to be done.
| Total Amount |  |  |  | 1779851

## Masala Kitchen MB (hidden)
MASALA KITCHEN
Masala Kitchen Area | 1 | 55.485 | 10.76 | 597.0186
Antitermite Work | 1 | 55.485 | 10.76 | 597.0186
600
Waterproofing Work
| 1 | 55.485 |  | 597.0186
| 1 | 40.495 | 0.45 | 196.0768
| 2 | 3.315 | 0.45 | 32.1025
| 2 | 5.815 | 0.45 | 56.3125
| 2 | 4.63 | 0.45 | 44.8369
| 2 | 1.875 | 0.45 | 18.1575
944.5047
94.4505
1038.9552
1040
Light Weight Concrete
| 1 | 55.485 |  | 597.0186
Less Not filling area afterUltra bar counter area | -1 | 9.824 |  | -105.7062
491.3124
49.1312
540.4436
540
Screeding
| 1 | 55.485 |  | 55.485
597.0186
600
100mm Block Work | 1 | 2.265 | 4.295 | 9.7282
| 1 | 5.715 | 4.295 | 24.5459
Less Opening | -1 | 0.8 | 2.1 | -1.68
Room near shaft | 1 | 2.43 | 4.295 | 10.4368
Door walls | 1 | 1.805 | 4.295 | 7.7525
Less Opening | -1 | 0.85 | 2.1 | -1.785
| 1 | 3.305 | 4.295 | 14.195
| -1 | 0.95 | 2.1 | -1.995
Ultra Counter Wall | 1 | 1.876 | 1.05 | 1.9698
Ultra Counter Wall | 1 | 4.63 | 1.05 | 4.8615
0
0
68.0297
731.9996
73.2
805.1995
805
Plaster on Block work 100mm thick
| 2 | 2.265 | 4.295 | 19.4564
Masala Kitchen & Ultra bar side wall partition | 2 | 5.715 | 4.295 | 49.0919
Less Opening | -2 | 0.8 | 2.1 | -3.36
Room near shaft | 2 | 2.43 | 4.295 | 20.8737
Door walls | 2 | 1.805 | 4.295 | 15.5049
Less Opening | -2 | 0.85 | 2.1 | -3.57
Ultra Bar Counter side wall | 2 | 3.305 | 4.295 | 28.3899
Less Door | -2 | 0.95 | 2.1 | -3.99
Masala Kitchen side wall | 2 | 6.935 | 4.295 | 59.5716
Ultra Bar Counter wall | 2 | 1.876 | 1.05 | 3.9396
Ultra Bar Counter wall | 2 | 4.63 | 1.05 | 9.723
0
195.631
2104.9901
210.499
2315.4891
2315
RCC Lintel
| 1 | 1.4 |  | 4.592
| 1 | 1.45 |  | 4.756
0
9.348
0.9348
10.2828
10
Flooring
| 1 | 55.485 |  | 597.0186
| -1 | 9.824 |  | -105.7062
491.3124
59.7019
551.0142
550
Skirting | 1 | 51.427 |  | 168.6806
16.8681
185.5486
Bar Area floor tiles | 1 | 9.824 |  | 105.7062
10.5706
116.2769
115
Granite Stone Skirting around Bar counter
Masala Counter Skirting | 1 | 3.315 |  | 10.8732
Around Bar counter wall | 1 | 4.63 |  | 15.1864
Around Bar counter wall | 1 | 1.31 |  | 4.2968
30.3564
3.0356
33.392
35
Granite Door Cill
| 2 | 0.95 |  | 1.9
| 1 | 0.8 |  | 0.8
| 1 | 0.85 |  | 0.85
3.55
11.644
1.1644
12.8084
13
Wall Tiles
BOH AREA WALL Tiles | 1 | 51.427 | 2.455 | 1358.4853
Less Bar Area walls above counter | -1 | 4.63 | 1.5 | -74.7282
Less Bar Area walls above counter | -1 | 1.31 | 1.5 | -21.1434
Bar back wall masala kitchen side | -1 | 1.875 | 1.5 | -30.2625
Masala Kitchen wall Bar Side | -1 | 5.817 | 2.455 | -153.6607
Counter back wall | -1 | 2.278 | 2.455 | -60.1752
Counter side wall | -1 | 2.528 | 2.455 | -66.7791
Counter area no Wall | -1 | 3.23 | 2.455 | -85.323
Above Door | 1 | 0.8 | 0.3 | 2.5824
| 1 | 0.95 | 0.3 | 3.0666
Less Tile fixing with Adhesive | -1 | 3.175 | 2.3 | -78.5749
Commerial Tiles in Masala counter back wall | 1 | 2.265 | 0.9 | 2.0385
795.5258
79.5526
875.0783
875
MS Frame Work with HDHMR BOARD
Back of the house back wall | 1 | 3.175 | 2.4 | 7.62
81.9912
8.1991
90.1903
90
Tile Fixing with Cahemical
Back of the house back wall | 1 | 3.175 | 2.4 | 7.62
81.9912
8.1991
90.1903
90
MOH AREA Wall Tiles
Ultra bar side wall Tiles | 1 | 5.714 | 2.6 | 159.8549
Less Door | -1 | 0.8 | 2.1 | -18.0768
Counter baclk wall | 1 | 2.265 | 2.6 | 63.3656
Less Commercical tile | -1 | 2.265 | 0.9 | -21.9343
KFC Side wall | 1 | 2.535 | 2.6 | 70.9192
Ultra Bar Counter area wall | 1 | 5.715 | 2.6 | 159.8828
Less Door | -1 | 0.8 | 2.1 | -18.0768
Ultra Bar Counter area wall | 1 | 3.195 | 2.6 | 89.3833
Less Door | -1 | 0.95 | 2.1 | -21.4662
Less 300 x 300mm designer tile area |  |  |  | -67.8848
395.9669
39.5967
435.5636
435
WALL Rile 300mm x 300mm
| 1 | 2.265 | 0.6 | 14.6228
| 1 | 2.535 | 0.6 | 16.366
| 1 | 5.715 | 0.6 | 36.896
67.8848
6.7885
74.6733
75
Door Frame | 6 | 2.1 |  | 12.6
| 1 | 0.9 |  | 0.9
| 1 | 0.8 |  | 0.8
| 1 | 0.85 |  | 0.85
15.15
49.692
50
DOOR SHUTTER
800 x 2100 With Vision Panel & SS Kick Plate | 1
850 x 2100 With Vision Panel & SS Kick Plate | 1
950x 2100 With Vision Panel | 1
MASALA KITCHEN COUNTER | 1 | 2.375 | 1.05 | 2.4937
26.8328
2.6833
29.516
30
POS & BAIN MARRY COUNTER
MASALA KITCHEN COUNTER | 1 | 2.375 | 0.9 | 2.1375
22.9995
2.2999
25.2995
25
Ultra Bar Counter
| 1 | 1.875 | 1.05 | 21.1837
| 1 | 4.63 | 1.05 | 52.3097
73.4935
7.3493
80.8428
80
POS COUNTER
| 1 | 1.03 | 0.9 | 9.9745
0.099745
10.0743
10
Granite Stone Cladding
| 2 | 2.765 |  | 18.1384
1.8138
19.9522
20
False Ceiling
| 1 | 55.485 |  | 597.0186
Less Grid False Ceiling BOH AREA | -1 | 16.317 |  | -175.5709
Less Grid False Ceiling STORE AREA | -1 | 2.677 |  | -28.8045
392.6432
39.2643
431.9075
430
GRID FALSE CEILING
BOH AREA | 1 | 16.317 |  | 175.5709
STORE AREA | 1 | 2.677 |  | 28.8045
204.3754
20.4375
224.813
225
Ultra Bar Bulk Head
| 1 | 4.63 |  | 15.1864
| 1 | 1.89 |  | 6.1992
21.3856
2.1386
23.5242

## FOH AREA MB (hidden)
FOH Carpet Area | 1 | 78.806 |  | 10.76 | 847.9526
850
Antitermite Treatment
| 1 | 78.806 |  | 10.76 | 847.9526
847.9526
850
Waterproofing Work
Floor Area | 1 | 78.806 |  | 10.76 | 847.9526
847.9526
84.7953
932.7478
930
PCC Area
| 1 | 78.806 |  | 10.76 | 847.9526
847.9526
850
Flooring Work
Floor Tiles -1 300 x 300 MORACCON MOSAIC
Boh & MOH Area | 1 | 7.515 |  | 3.79 | 306.4647
30.6465
337.1112
340
Tile -2 600 x 1200 FRENCH WENGE ( Sidron ) | 1 | 3.31 |  | 4.975 | 177.1876
17.7188
194.9064
195
Tile -3 AZUL BIANCO 600 x 600 | 1 | 11.76 |  | 5.305 | 671.282
Less Moraccon Mosaic Tiles |  |  |  |  | -306.4647
364.8173
36.4817
401.299
400
Skirting 100mm High | 1 | 0.78 |  | 3.28 | 2.5584
| 1 | 0.175 |  | 3.28 | 0.574
| 2 | 0.25 |  | 3.28 | 1.64
| 1 | 0.95 |  | 3.28 | 3.116
| 1 | 0.9 |  | 3.28 | 2.952
10.8404
1.084
11.9244
12
Granite Stone Cill
| 1 | 2.5 |  | 3.28 | 8.2
| 1 | 2.3 |  | 3.28 | 7.544
| 1 | 1.5 |  | 3.28 | 4.92
| 1 | 1.2 |  | 3.28 | 3.936
24.6
2.46
27.06
27
MS LOW HEIGHT PARTITION
| 1 | 3.76 | 0.8 | 10.76 | 32.3661
| 1 | 0.515 | 0.8 | 10.76 | 4.4331
| 1 | 4.26 | 0.8 | 10.76 | 36.6701
| 1 | 2.3 | 0.8 | 10.76 | 19.7984
| 1 | 2.5 | 0.8 | 10.76 | 21.52
| 1 |  |  | 10.76 | 0
114.7877
11.4788
126.2664
125
Trasition Profile
FOH AREA | 1 | 3.935 |  |  | 12.9068
| 1 | 7.515 |  |  | 24.6492
| 1 | 3.79 |  |  | 12.4312
| 1 | 4.975 |  |  | 16.318
66.3052
6.6305
72.9357
False Ceiling |  |  |  |  | 75
| 1 | 15.125 |  | 5.35 | 870.6857
Less HDHMR Board Ceiling | -1 | 18.618 |  |  | -200.3297
| 1 | 19.775 | 3.28 | 1 | 64.862
735.2181
183.8045
919.0226
920
HDHMR BORAD CEILING
Less HDHMR Board Ceiling | 1 | 18.618 |  |  | 200.3297
20.033
220.3626
220
Door Frame
D-3 Crew Entry Door Frame | 2 | 7 |  |  | 14
| 1 | 2.5 |  |  | 2.5
D-1 ( MOH Aea Entry Door | 2 | 7 |  |  | 14
| 1 | 3.25 |  |  | 3.25
33.75
3.375
37.125
37
Door Shutter with Vision Panel
D-1 MOH Area Entry door
3'-3" x 7'-0" | 1
D3 Crew Entry Door 2'-6" x 7'-0" | 1
Slidding Door D-2 & D-4
2'-6" x 7'-0" | 2
Over Head Storage
Manager | 1 | 1.36 |  | 0.9 | 1.224
0
1.224
13.1702
1.317
14.4873
15
Manager Table
1310 x 475 | 1 | 1.31 |  | 0.75 | 10.5717
10.5717
1.0572
11.6289
12
Soft Board
Manager | 1 | 1.36 |  | 0.35 | 0.476
0.476
5.1218
0.51218
5.6339
6
POS Counter
| 1 | 3.35 |  | 0.825 | 2.7637
0.27637
3.0401
32.7117
33
Crew Eating Table with legs
| 1 | 1.15 |  | 0.75 | 9.2805
0.92805
10.2086
10
Open Over Head Shelves
Crew 300mm Wide | 2 | 1.15 |  |  | 7.544
0.07544
7.6194
[5 empty] | 8 | Rft
Looking Mirror
Crew Area wall | 1 | 1.2 |  | 0.675 | 8.7156
0.87156
9.5872
10
Wall Paneling with MS Frame work with 12mm thick HDHMR Board & 8mm thick HDHMR Board finish with paint
| 1 | 4.92 |  | 9 | 44.28
| 1 | 11.83 |  | 9 | 106.47
Less door | -1 | 3.25 |  | 7 | -22.75
128
12.8
140.8
140
Corian Paneling over HDHMR Board paneling
| 1 | 2.6 |  | 0.95 | 26.5772
2.6577
29.2349
30
Wall Paneling with MS Frame work with 12mm thick HDHMR Board & 8mm thick HDHMR Board finish with paint
| 1 | 18.75 |  |  | 18.75 | Rft
| 1 | 5.58 |  |  | 5.58
24.33
2.433
26.763
27
3D Backlit KFC Sinage 3mm thick Acrylic Sheet Router Cut white Sheet At front & Black at back side | 1 | No
300 x 945
False Ceiling
GYPSUM FALSE CEILING
BOH Area | 1 | 32.208 |  | 10.76 | 346.5581
Vertical side walk in freezer | 1 | 1.92 | 1.85 | 10.76 | 38.2195
Vertical side walk in freezer Shaft side | 1 | 1.525 | 1.85 | 10.76 | 30.3566
Vertical side walk in freezer Shaft side | 1 | 1.385 | 1.85 | 10.76 | 27.5698
Vertical side walk in freezer Cooking area side | 1 | 2.945 | 1.85 | 10.76 | 58.6232
Vertical side walk in freezer Cooking area side | 1 | 1.295 | 1.85 | 10.76 | 25.7783
Chest frezzer side vertical side | 1 | 0.58 | 1.85 | 10.76 | 11.5455
Chest frezzer side vertical side | 2 | 1.295 | 1.85 | 10.76 | 51.5565
BOH & MOH Area vertical side | 1 | 3.175 | 1.85 | 10.76 | 63.2015
BOH & MOH Area vertical side | 1 | 1.005 | 1.85 | 10.76 | 20.0055
Maneger Room | 1 | 1.493 |  | 10.76 | 16.0647
Change room | 1 | 1.117 |  | 10.76 | 12.0189
Crew Area | 1 | 2.8 |  | 10.76 | 30.128
MOH Area Flase Ceiling
| 1 | 7.802 |  | 10.76 | 83.9495
Vertical side above BOH Counter | 1 | 3.4 | 1.8 | 10.76 | 65.8512
| 1 | 3.4 | 1.8 | 10.76 | 65.8512
947.2781
94.7278
1042.0059
1040
HDHMR Board False Ceiling
| 1 | 3.4 | 0.18 | 10.76 | 6.5851
0.65851
7.2436
10
Drain Pipe
100mm Dia | 1 | 3.75 |  |  | 3.75
| 1 | 4.58 |  |  | 4.58
| 1 | 9.83 |  |  | 9.83
| 1 | 12.42 |  |  | 12.42
| 1 | 3.67 |  |  | 3.67
| 1 | 4.42 |  |  | 4.42
| 1 | 1.67 |  |  | 1.67
| 1 | 3.67 |  |  | 3.67
| 1 | 10.5 |  |  | 10.5
| 1 | 6.92 |  |  | 6.92
| 1 | 10.42 |  |  | 10.42
| 1 | 4.75 |  |  | 4.75
| 1 | 2.17 |  |  | 2.17
| 1 | 6.5 |  |  | 6.5
| 1 | 6.92 |  |  | 6.92
1
92.19
9.219
101.409
[5 empty] | 102 | 30.9174
Drain Pipe
50mm Dia PVC Pipe
| 1 | 0.58 |  |  | 0.58
| 1 | 1.25 |  |  | 1.25
| 1 | 0.42 |  |  | 0.42
| 1 | 0.33 |  |  | 0.33
| 1 | 4.58 |  |  | 4.58
| 1 | 2 |  |  | 2
| 1 | 1.17 |  |  | 1.17
| 1 | 0.67 |  |  | 0.67
11
3.3537
0.33537
3.689
5
20mm Watersupply Pipe
Green Line Water supply | 1 | 16.08 |  |  | 16.08
| 1 | 5.5 |  |  | 5.5
| 1 | 3.83 |  |  | 3.83
| 1 | 7.83 |  |  | 7.83
| 1 | 14.08 |  |  | 14.08
Sky blue Wtersupply line 20mm dia | 1 | 14.67 |  |  | 14.67
| 1 | 15.83 |  |  | 15.83
| 1 | 18.75 |  |  | 18.75
| 1 | 5.67 |  |  | 5.67
| 1 | 18.83 |  |  | 18.83
| 1 | 3.58 |  |  | 3.58
0
124.65
12.465
137.115
41.8034
45

## Basement MB (hidden)
BASEMENT STORE AREA | 1 | 24 |  | 25.25 | 606
Antitermite Treatment | 1 | 24 |  | 25.25 | 606
Waterproofing | 1 | 50.32 |  | 10.76 | 541.4432
| 1 | 63.71 | 3.28 | 1.5 | 313.4532
854.8964
855
Floor raised filling
| 1 | 50.32 | 10.76 |  | 541.4432
541.4432
Screeding |  |  |  |  | 545
| 1 | 50.32 | 10.76 |  | 541.4432
541.4432
545
Block Masonary
Front & Back side wxternal wall | 2 | 24 |  | 12 | 576
Less Door | -1 | 4 |  | 7 | -28
Left side up to column | 1 | 10.75 |  | 12 | 129
Left side after column | 1 | 10.92 |  | 12 | 131.04
Right side wall | 1 | 24.42 |  | 12 | 293.04
Internal walls Rack & chiller Partition walls | 1 | 14.33 |  | 12 | 171.96
Rack & KFC Dry Sry Store partition wall | 1 | 21.25 |  | 12 | 255
Less Dry store entry door | -1 | 4 |  | 7 | -28
KFC Dry Store & Seating area partition wall | 1 | 19.25 |  | 12 | 231
KFC Dry store entry wall | 1 | 5.33 |  | 12 | 63.96
Less Door | -1 | 3.42 |  | 7 | -23.94
Cashier & seating entry partition wall | 1 | 5.67 |  | 12 | 68.04
Less Entry door | -1 | 2.92 |  | 7 | -20.44
0
1818.66
181.866
2000.526
Plaster both sides of wall
Front & Back side wxternal wall | 4 | 24 |  | 12 | 1152
Less Door | -2 | 4 |  | 7 | -56
Left side up to column | 2 | 10.75 |  | 12 | 258
Left side after column | 2 | 10.92 |  | 12 | 262.08
Right side wall | 2 | 24.42 |  | 12 | 586.08
Internal walls Rack & chiller Partition walls | 2 | 14.33 |  | 12 | 343.92
Rack & KFC Dry Sry Store partition wall | 2 | 21.25 |  | 12 | 510
Less Dry store entry door | -2 | 4 |  | 7 | -56
KFC Dry Store & Seating area partition wall | 2 | 19.25 |  | 12 | 462
KFC Dry store entry wall | 2 | 5.33 |  | 12 | 127.92
Less Door | -2 | 3.42 |  | 7 | -47.88
Cashier & seating entry partition wall | 2 | 5.67 |  | 12 | 136.08
Less Entry door | -2 | 2.92 |  | 7 | -40.88
0
3637.32
363.732
4001.052
4000
RCC Lintel
Door Lintel | 2 | 6 |  |  | 12
| 1 | 5 |  |  | 5
| 2 | 5.5 |  |  | 11
28
2.8
30.8
30
Floor Tiles
| 1 | 50.32 |  | 10.76 | 541.4432
54.1443
595.5875
595
Floor Tiles
Skirting | 1 | 63.71 | 3.28 |  | 208.9688
20.8969
229.8657
230
DOOR Cill
| 2 | 4.08 |  |  | 8.16
| 1 | 3 |  |  | 3
| 1 | 3.5 |  |  | 3.5
14.66
1.466
16.126
16
Base Ment Wall tiles
| 1 | 63.71 | 3.28 | 8 | 1671.7504
| -1 | 4 |  | 7 | -28
1643.7504
164.375
1808.1254
1800
Door Frame
| 8 | 7 |  |  | 56
| 2 | 4 |  |  | 8
| 1 | 3 |  |  | 3
| 1 | 3.5 |  |  | 3.5
70.5
7.05
77.55
78
Metal grid Ceiling
| 1 | 50.32 |  | 10.76 | 541.4432
541.4432
545
POP Punning on walls
| 1 | 63.71 | 3.28 | 1 | 208.9688
20.8969
229.8657
230
Paint on walls
| 1 | 63.71 | 3.28 | 1 | 208.9688
20.8969
229.8657
230