## CAR FORMAT
MUMBAI INTERNATIONAL AIRPORT LTD.
CHANGE AUTHORISATION REQUEST & APPROVAL
PROJECT |  |  | CAR NO :- | 1
LOCATION |  |  | WORK ORDER NO & WO DATE :- (Latest amended one) | 5700310682 Dt 14/06/2022
WORK DESCRIPTION | Civil Interior Fit-outs and MEP works for Domino’s Outlet at T2 CSMIA Mumbai |  | OMDA Ref.
CONTRACTOR'S NAME | M/S Lok Pratik Constructions |  | CONTRACTUAL DATE OF COMPLETION :-
ORIGINAL CONTRACT VALUE (Rs) | DEVIATION /VARIATION VALUE (Rs) | REVISED CONTRACT VALUE (Rs) | % VARIATION | REMARKS
(A) | (B) | ( C) = (A) + (B) | (D) = {(B) /(A)}% | (E)
2390242.4896 | 1806915.6904 | 4197158.18
755488.4724
Whether Extention of Time Required :- |  | 4952646.6524
IF YES THEN :-
Note : This extention should be recommended only in case of major increase in scope of work.
COMPLETION DATE AS PER CONTRACT | EXTENTION GRANTED UPTO | REMARKS
AUTHORIZATION
Requested By |  | Recommended by | Approved By
Name |  | Sr Manager E & M | AVP E & M | AVP E&M | GM Finance
Sign
Title
Date
CONTRACTOR'S ACCEPTANCE
Name |  | Note :This document shall form a part of contract & shall be treated as an amendment to the existing Work Order.
Sign
Title
Date

## DEVIATED ITEMS (ANNEX 1 -SECA)
ANNEXURE -1
SO No :- | 5700310682 Dt 14/06/2022
CAR No :- | 1
Civil work for provision of Biometric system at Terminal T-2 .
SECTION: A (DEVIATED ITEMS)
VARIATION
SR.NO | DESCRIPTION | UNIT | BOQ QTY | BOQ RATE (Rs) | BOQ AMOUNT (Rs) | REV QTY | REV AMOUNT (Rs) | Qty |  | Amount(Rs) | REMARKS
Civil Head
A.1.0 | Dismantling and Demolitions
a | Dismantling the existing flooring, ceiling, walls, partition, fixed & loose furniture, toilets, pantry, etc.Cost to include carting away all debris from site, lead and lifts, material, labours, transportation and all other incidental charges etc. complete and as directed by Site Engineer
a.1 | Brick Wall ,Wall tiles, Floor tiles, including base,Partitions,Existing Wall Plaster ,Electrical conduits ,wiring,DB,sockets and Punning removing including old plumbing and sanitary lines | Sq.ft | 500 | 30 | 15000 | 573.49 | 17204.7 |  | 73.49 | 2204.7
a.2 | Removal PCC of thickness upto 5 inches | Sq.ft | 350 | 35 | 12250 | 573.49 | 20072.15 |  | 223.49 | 7822.15
b.1 | Making core cutting of 75 dia | Nos. | 1 | 2300 | 2300 | 0 | 0 |  | -1 | -2300
c | Making cutouts and openings in existing walls for ducts etc. The cost to be inclusive of making good all affected areas with smooth plaster and disposal of debris at an indicated location off site. | Nos. | 4 | 3000 | 12000 | 0 | 0 |  | -4 | -12000
A.2.0 | RCC and PCC | [7 empty] | 0 | 0
| Providing & Laying Plain cement concrete specified grade (M10) including the cost of centering and shuttering & required curing. Approved make cement is PPC (ACC, Ultra tech , Birla) | cuft | 500 | 250 | 125000 | 105.23 | 26307.5 |  | -394.77 | -98692.5
A.3.0 | Brick Wall and Plaster
a | Autoclaved Aerated Concrete Block
b | Brick Work
b.1 | Providing & Constructing 115mm thick wall of class1 Brick with conventional IS type bricks in 1:4 cement mortar inclusive of RCC tie member at every one meter height interval in 1:3:6 Cement Concrete with 2no. of 6mm diameter mild steel reinforcement & 2 no. of hoop iron strips 25mm x 1.6mm, painted with anti-corrosive paint, properly bent and bonded at the end ,inclusive of shuttering, scaffolding, Raking of joints and proper curing etc. complete. | Sq.Ft | 232 | 145 | 33640 | 237.73 | 34470.85 |  | 5.73 | 830.85
b.2 | Providing and laying 9" brick masonry work with well burnt 1st class table moulded, good quality approved bricks in 1:6 Cement Mortar (1 Cement : 6 Coarse Sand by volume) in true line, level and plumb for wall foundations, trenches, pedestals, columns, compound walls, steps, pillars etc., complete with necessary scaffolding, raking of joints, curing etc., complete as directed and specified upto plinth level. Rate to include soaking of bricks adequately before construction, complete as directed and specified. | cuft | 150 | 270 | 40500 | 20.48 | 5529.6 |  | -129.52 | -34970.4
c | Plaster
c.1 | Plastering the Siporex / brick masonry walls with 12mm to 15mm thk. Single coat cement plaster in 1: 4 (cement : sand proportion) with chickenmesh jali wherever required, including scaffolding and curing complete as specified and as directed by Site Engineer. | Sq.Ft | 1750 | 62 | 108500 | 1486.17 | 92142.54 |  | -263.83 | -16357.46
A.4.0 | Brickbat Coba and Water proofing
b | Filling motar Light weight cinder with cement salary - Providing and laying Cinder Coba,cm 1:3 base coat, cinder filling as per site requirement & 1:4 top-finish coat. the mortar for the cinder koba filling shall be cm 1:4 and admixed with integral waterproofing compound and mortar plasticizer, properly compacted, curing, complete. The top-finish coat shall be broom-finished suitable for laying tiles. The cost should include sealing the annular space between the pipe and the masonary, making khurras, river sand screened and washed, at all leads, lifts, heights, with proper slope to drain-off water entirely, complete, etc. Curing shall be done for maximum for 7 days by ponding with water or after getting checked & satisfied by Site Engineer . | cuft | 350 | 320 | 112000 | 301.2 | 96384 |  | -48.8 | -15616
d | P/f one layer of 3mm APP membrane waterproofing ( 1 layer of membrane & Two coat adhesive) of approved make in toilet & kitchen area or as directed by the Site Engineer minimum 2 coats with requisite adhesive / compounds as per the manufacturers specifications on floor, sunken slab and up to height of 24” on wall. Waterproofing works to be carried out by company authorised installers and guarantee/warrantee provided for 5 years. Including protection plaster Ponding test to be carried out for minimum 48 hours. Approved makes : Zydex, sika | Sq. Ft | 351 | 180 | 63180 | 709.28 | 127670.4 |  | 358.28 | 64490.4
A.5.0 | Rolling Shutter , Awning & Mild Steel work
c | Providing, fabricating & erection of Steel work in built up section/ framed work i/c cutting, welding, hoisting, fixing in position & applying a priming coat of approved steel primer using steel etc, as required. In structure slab (ISMB, ISMC etc.) or stringers, treads, landing of stair case i/c use of chequered plate wherever required, all complete. Including primer and 2 coat paints | KG | 350 | 140 | 49000 | 743.71 | 104119.4 |  | 393.71 | 55119.4
A.6.0 | Flooring and Cladding
d.1 (opt.) | Providing and fixing in position Glazed Vitrified Tile flooring as per detail in drawing. It shall be fixed with cement mortar of 1 :4, (required mortar bed is 25mm to 50mm thk),with thick grey cement slurry, with hairline joints using cement grout. The job including cutting of tiles & making smooth edges wherever required for drain pipes. The work shall also include cost of materials, wastages, labour, all lead and lift at all levels, loading and unloading, transportation, curing etc. and all other incidental charges etc., complete and as directed by Engineer-in-charge. The cost should include PVC floor covering material. Including Corrugated sheet /Plastic sheet for tile Protection. | Sq. Ft | 700 | 200 | 140000 | 505.72 | 101144 |  | -194.28 | -38856
g | Providing and fixing in position Glazed Vitrified Tile flooring as per detail in drawing. It shall be fixed with cement mortar of 1 :4,(required mortar bed is 25mm thk) with thick grey cement slurry,with hairline joints using cement grout. The job including cutting of tiles & making smooth edges wherever required for drain pipes. The work shall also include cost of materials, wastages, labour, all lead and lift at all levels, loading and unloading, transportation, curing etc. and all other incidental charges etc., complete and as directed by Engineer-in-charge. The cost should include PVC floor covering material. | Sq. Ft | 15 | 300 | 4500 | 0 | 0 |  | -15 | -4500
j.1 op 1 | Providing and fixing in position 100 mm ht. Skirting as per detail in drawing. Over 20 mm thk bed of cement mortar 1:4 (cement : fine sand ) with thick grey cement slurry, with hairline joints using cement grout. The job including cutting of tiles & making smooth edges wherever required for drain pipes. The work shall also include cost of materials, wastages, labour, all lead and lift at all levels, loading and unloading, transportation, curing etc. and all other incidental charges etc., complete and as directed by Engineer-in-charge. Finish of skirting to match with individual areas as per flooring plan. | Rft | 170 | 125 | 21250 | 177.97 | 22246.25 |  | 7.97 | 996.25
l | Providing and fixing in position dado tile of approved make & shade on any surface as per details in drawing and Over 12 mm thk bed of cement mortar 1:3 (cement : fine sand ) with thick grey cement slurry, with hairline joints using cement grout. The job including cutting of tiles & making smooth edges wherever required . The work shall also include cost of materials, wastages, labour, all lead and lift at all levels, loading and unloading, transportation, curing etc. and all other incidental charges etc. Complete as specified in the drawing & to the satisfaction of the Site Engineer. Ceramic wall tile (Printed) With customize line work | Sq. Ft | 600 | 200 | 120000 | 479.12 | 95824 |  | -120.88 | -24176
m | Providing and fixing in position dado tile of approved make & shade on any surface as per details in drawing and Over 12 mm thk bed of cement mortar 1:3 (cement : fine sand ) with thick grey cement slurry, with hairline joints using cement grout.The job including cutting of tiles & making smooth edges wherever required . The work shall also include cost of materials, wastages, labour, all lead and lift at all levels, loading and unloading, transportation, curing etc. and all other incidental charges etc. Complete as specified in the drawing & to the satisfaction of the Site Engineer. | Sq. Ft | 450 | 175 | 78750 | 322.29 | 56400.75 |  | -127.71 | -22349.25
q | Providing and fixing in position dado tile (White Tile ) as per details in drawing and Over 12 mm thk bed of cement mortar 1:3 (cement : fine sand ) with thick grey cement slurry, with hairline joints using cement grout. The job including cutting of tiles & making smooth edges wherever required . The work shall also include cost of materials, wastages, labour, all lead and lift at all levels, loading and unloading, transportation, curing etc. and all other incidental charges etc. Complete as specified in the drawing & to the satisfaction of the Site Engineer. (Size - 200x250mm) | Sq. Ft | 50 | 150 | 7500 | 0 | 0 |  | -50 | -7500
r | Providing and Fixing 19mm thick, upto 6" wide granite door frames with 6mm champhered edges machine polished edges externally and internally. Rate to include cutting/moulding/polishing/Transport etc. Complete as specified in the drawing & to the satisfaction of the Architect & Site-in-charge. (required mortar bed is 25mm to 50mm thk) | RFt | 35 | 450 | 15750 | 78.13 | 35158.5 |  | 43.13 | 19408.5
u | Providing and fixing in position Glazed Vitrified Tile Dado on Makeline & POS counter as per detail in drawing. Over 12 mm thk bed of cement mortar 1:4 (cement : fine sand ) with thick grey cement slurry, with hairline joints. The job including cutting of tiles & making smooth edges wherever required for drain pipes. The work shall also include cost of materials, wastages, labour, all lead and lift at all levels, loading and unloading, transportation, curing etc. and all other incidental charges etc., complete and as directed by Engineer-in-charge. The cost should include PVC floor covering material. | Sq. Ft | 90 | 225 | 20250 | 48.42 | 10894.5 |  | -41.58 | -9355.5
B.3.0 | Wall Claddings / Wall Partitions /Claddings
Framing-Cutting of section & Providing and fixing M.S frame work in built up tubular section (square hollow tubes 40 mm x 40 mm x 1.5 mm ) framework at 600mm c/c both ways in partition included bolted or welded in built up section to recieve bison pallening . The rate should include applying of two or more coats of primer , putty , complete as per standard technical specification, instructions of site engineer and as per decoration plan.
| Providing & Fixing 8 mm thk Bison board with above mentioned framing details - a.(i) (Rate will be include the cost of framing) | Sq. Ft | 200 | 330 | 66000 | 241.37 | 79652.1 |  | 41.37 | 13652.1
Framing-Cutting of section & Providing and fixing M.S frame work in built up tubular section (square hollow tubes 25 mm x 35 mm x 1.5 mm ) framework at 600mm c/c both ways in partition included bolted or welded in built up section to recieve bison pallening . The rate should include applying of two or more coats of primer , putty , complete as per standard technical specification, instructions of site engineer and as per decoration plan.
| Providing & Fixing 12 mm Marine Ply on Existing Provided Surface. Rate will exclude cost of framing | Sqft | 40 | 200 | 8000 | 10.88 | 2176 |  | -29.12 | -5824
| Providing & Fixing 19 mm Marine Ply on Existing Provided Surface. Rate will exclude cost of framing | Sq.ft | 40 | 310 | 12400 | 119.88 | 37162.8 |  | 79.88 | 24762.8
| Providing & fixing 15mmX15mm anodized Aluminium finish corner guard in approved shade powder coat matching to tile color above skirting level upto 2500 mm. | R. Ft | 70 | 100 | 7000 | 59.27 | 5927 |  | -10.73 | -1073
| Providing & fixing MS Tube 25mmX25mm finish in black Powder coat (0.5 micron) for Booth area articlad wall till skirting level as/drawing. | R. Ft | 46 | 200 | 9200 | 0 | 0 |  | -46 | -9200
| Providing & fixing 15mm wide 'T' shape anodized Aluminium Transition strip | R. Ft | 23 | 140 | 3220 | 0 | 0 |  | -23 | -3220
| Providing and applying textured Paint on wall including 10-12 mm groove (as per drawing) of two coats of approved make & shade . Filling the dents with approved Acrylic putty gypsum / or approved crack filler, binder, cleaning and making the surface dust free, preparing surfaces, applying a coat of sealer or primer as per the manufacturers specifications. Applying two under coats and one finished coat of paint to achieve the required finish including scrapping the existing paint, scaffolding, cleaning etc. Complete as per detail drawing and as directed by Engineer-in-charge. | Sq. Ft | 55 | 150 | 8250 | 0 | 0 |  | -55 | -8250
B.4.0 | Doors & Windows
d | Providing and Fixing in position 35 mm Thk. wooden flush door & section on Teak Wood Door Frame of specified size, section well notched & screwed with cutting of grooves, edges, mouldings over rough ground including necessary hardware, fittings, fixtures, conch bolt, 150 mm high s.s kick Plate (1.5 thickness), Door closure ,Handle,Lock as mentioned in drg, bitumen paint to non exposed surface, matt melamine polish matching to Laminate on door frames & Horizontal grain Laminate on the panel from both sides of approved make & shade, etc. complete as per detail drawing, as specified and as directed by engineer-in-charge. (Cost will include all the hardwares mentioned above) | Sq.ft | 29 | 1300 | 37700 | 24.29 | 31577 |  | -4.71 | -6123
h | 19 MM Thk Solid Core Counter Swing Door with double side Piano S.S hinge 2 nos as mention in the detail drawing and as directed by Site Engineer .Door Front finish to be done with as / Approved Tile with 38 mm corian Profile in all the sides of tile and top of Swing Door and Door inside finish with Approved Laminate. 19 MM thick patti on all the edges on all three sides (Cost will include all the hardwares mentioned above) | Sq.ft | 11 | 1200 | 13200 | 0 | 0 |  | -11 | -13200
B.5.0 | P.O.P/Painting | [5 empty] | 0
a | Providing & applying wall punning up to 12mm to 15mm thick layer of super fine Plaster of Paris applied on specified area over existing plastered surface on walls and columns, to be finished smooth. Surface to be prepared by hacking, sand papering and applying coat of cement slurry if required including all incidentals, making grooves, patties, sills etc. complete and as directed by engineer in charge. The finish surface should be smooth, cover up all the patch work done by electrical agencies so as to avoid unevenness and ready to take on paint. Rate including cost of transportation, loading, unloading, scaffolding, wastage, taxes etc. as directed by Engineer-in-charge. | Sq. Ft | 500 | 32 | 16000 | 313.09 |  |  | -186.91 | -5981.12
b | Providing and applying Lustre Paint on wall of approved make & shade filling the dents with approved Acrylic putty gypsum / or approved crack filler, binder, cleaning and making the surface dust free, preparing surfaces, applying a coat of sealer or primer as per the manufacturers specifications, applying two under coats and one finished coat of paint to achieve the required finish including scrapping the existing paint, scaffolding, cleaning etc. complete as per detail drawing, as specified and as directed by Engineer-in-charge. | Sq. Ft | 300 | 32 | 9600 | 287.28 | 9192.96 |  | -12.72 | -407.04
d | Providing and applying Plastic Emulsion Paint on Ceiling of approved make & shade filling the dents with approved Acrylic putty gypsum / or approved crack filler, binder, cleaning and making the surface dust free, preparing surfaces, applying a coat of sealer or primer as per the manufacturers specifications, applying two under coats and one finished coat of paint to achieve the required finish including scrapping the existing paint, scaffolding, cleaning etc. complete as per detail drawing, as specified and as directed by Engineer-in-charge. | Sq. Ft | 600 | 30 | 18000 | 0 | 0 |  | -600 | -18000
e | Providing and Applying synthetic enamel paint (Armada Blue) of approved make & Shade on Metal surfaces.to be prepared by rubbing with coarser sand paper suitable for painting by filling all dents and crack & two coat of primer .The rate includes scrapping ,Filling with Putty etc complete. - Colour and pattern to be specified at site by site supervisor.Approved make - Asain paint | sq.ft | 450 | 35 | 15750 | 191.96 | 6718.6 |  | -258.04 | -9031.4
Exterior Head
Façade Work
| Providing and fixing in position panelling made out of 8x 150 x 3000 mm Shera board Teak planks (with application of 2 coat of primer on all side of shera plank & finished with Duco paint-Armada blue or colour matching to Pantone shade PMS 2965 C on shera Planks) to be fixed on 25x25x1.5 mm Alluminium/MS framework to be painted with anti -corrosion Paint on all sides and Duco Painted M S Border size of 25X25x1.5 to be fixed all around the signage. Complete as per store front Detail and as specified in Drawing.(Cost will include Shera board Teak Planks & ,Frame)Approved make - Asain paint. | Sq. Ft | 80 | 550 | 44000 | 0 | 0 |  | -80 | -44000
D.1.0 | Furniture /WOOD Work
a | Providing and fixing in position Order counter : Counter top finished in 6mm thick Acrylic Solid Surface LG Hausys-HI-MACS G109 Beige Island over 19 mm thick WPC/Marine Ply. 150mm height Drawers (2 nos )to be provided below each POS.Internal area to be finish with 1 mm thick approved laminate with necessary hardwares(Lock ,Telescopic channel etc). MS powder coated framework (40x40x1.5mm) as per detail drawing to be provided with necessay arrangement and Ledge having LED cove strip as per detail drawing Complete in all respect . Cost to include all materials, DMB Framing ,labours and necessary leads & lift etc. -Counter Height-3'6" | RFT | 10 | 10500 | 105000 | 10.5 | 110250 |  | 0.5 | 5250
b | Providing and fixing in position Makeline : Counter top finished in 6mm thick Acrylic Solid Surface LG Hausys-HI-MACS G109 Beige Island over 19 mm thick Marine Ply / WPC and Ledge having LED cove strip as per detail drawing Complete in all respect. Duco Paint M.S framework with 10 mm toughened Glass as per detail drawing above counter Cost to include all materials, labours and necessary leads & lift etc. | RFT | 14 | 9500 | 133000 | 17.06 | 162070 |  | 3.06 | 29070
c | Providing and fixing in position MOP storage made of 18mm thk. Marine ply in appd. Laminate from outside and white laminate inside with necessary support framework. Cost to include shelves in 18 mm thk. marine ply finished in white laminate with all hardware, fasteners, and rubber / PVC leveller etc. complete in all respect as per detailed drawing and size to be considered in Width x Height for Billing Depth 500 mm | Sq.ft | 1 | 1750 | 1750 | 13.64 | 23870 |  | 12.64 | 22120
e | Providing and placing foldable staff table in position 40mm thk table top made out of 2 nos 19mm thk marine ply finished with 1mm thk laminate LAM01 on both side and edges to be finished with PVC edge bending to be sopported on L bracket with Table bracket (HAFFLE ) complete in all respect as per detailed drawing. Size- 4'x1'6", width can be adjusted as per site. Fixing of table to be kept 3' from thr floor. | Sq.ft | 5.8 | 650 | 3770 | 0 | 0 |  | -5.8 | -3770
i | Providing and placing in position 6mm thk extra clear mirror of size 450mm x 1200 mm with 12mm thk marine ply at back to be fixed over ss stud on wall. Cost to include all hardware, fasteners, and rubber / PVC leveller etc. complete in all respect as per detailed drawing. | No. | 1 | 3500 | 3500 | 1 | 3500 |  | 0 | 0
k | Providing and fixing ceiling mounted ,Metal fabricated Computer Holder for Thin clients above Dough Tray & Router. Complete in all respect as per detailed drawing. | Nos. | 1 | 7000 | 7000 | 0 | 0 |  | -1 | -7000
l | Providing and fixing Wall mounted ,Metal fabricated Computer Holder for Thin clients above Dough Tray & Router. Complete in all respect as per detailed drawing. | Nos. | 1 | 7000 | 7000 | 2 | 14000 |  | 1 | 7000
E | Plumbing
E.1.0 | INTERNAL WATER SUPPLY SYSTEM
a | Providing & fixing on walls / ceiling / floors, medium grade having embossed ISI Mark CPVC pipes of diameter as mentioned below with fittings i.e.connector, clamps, tees, elbows, reducers, male-female etc. necessary fittings. (Supreme / Prince/Astral or as approved. )
a.1 | 15mm nominal bore | RMT | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
a.2 | 20mm nominal bore for sink+ gyser+ RO+ Basin+papsi machine | RMT | 39 | 350 | 13650 | 50.41 | 17643.5 |  | 11.41 | 3993.5
a.3 | 25mm nominal bore for main water supply | RMT | 38 | 475 | 18050 | 23.8 | 11305 |  | -14.2 | -6745
a.4 | 32mm nominal bore | RMT | 1 | 600 | 600 | 0 | 0 |  | -1 | -600
a.5 | 40mm nominal bore | RMT | 5 | 700 | 3500 | 18.05 | 12635 |  | 13.05 | 9135
b | Providing & fixing of ISI Mark CPVC ball valves of followig dia pipes as mentioned below (Make - supreme/prince/astral or as approved)
d | Providing, Fixing, testing and commissioning of ISI marked Gun Metal Screwed pattern full way Gate valve with wheel tested to non shock cold working pressure upto 10 kg /sq cm(Stop Valve) conforming to IS 778 class 1 including jointing, supporting etc complete and as directed.(Danfoss/Jayhiwa/Zoloto or equivalent)
d.1 | 20mm class 1.0 | Nos | 3 | 1500 | 4500 | 5 | 7500 |  | 2 | 3000
d.2 | 25mm class 1.0 | Nos | 4 | 2000 | 8000 | 0 | 0 |  | -4 | -8000
c.3 | 32mm class 1.0 | Nos | 2 | 2800 | 5600 | 3 | 8400 |  | 1 | 2800
c.4 | 40mm class 1.0 | Nos | 0 |  | 0 |  |  |  | 0 | 0
INTERNAL DRAINAGE SYSTEM
a | Providing and fixing UPVC SOIL / VENT / WASTE SWR pipe of required diameter conforming to I.S.-13592, and I.S.-4985 to withstand continous internal hydroulic pressure of 4 kg/cm2 including necessary fixtures and fittings, such as bends, tees,Clean out plugs (for the downtakes near bends). single junctions, double junctions and joining with rubber rings and lubricants, on wall by means of clips or in ground including necessary excavation, laying refilling, trench testing etc. complete. (Prior approval of sample and brand by Ex.Engineer is necessary before use.) (Supreme / Prince/Astral or as approved. )
a.1 | 32 mm dia |  |  |  | 0 |  | 0 |  | 0 | 0
a.2 | 40 mm dia | m | 12 | 150 | 1800 | 8.6 | 1290 |  | -3.4 | -510
a.5 | 75 mm dia. | m | 18 | 450 | 8100 | 2.9 | 1305 |  | -15.1 | -6795
a.6 | 110 mm dia. | m | 18 | 550 | 9900 | 14.1 | 7755 |  | -3.9 | -2145
a.7 | 150 mm dia. | m | 0 |  | 0 | 0 | 0 |  | 0 | 0
b | Providing ,laying, testing & commissioning of approved Multi floor trap / Nahani trap with Chilly trap of required sizes, including jointing etc. complete and as directed. (GMGR/Chilly or equivalent) | Nos. | 5 | 1200 | 6000 | 5 | 6000 |  | 0 | 0
E.4.0 | Sanitarywares & Fittings
a | Providing & Fixing following fixtures, the rate for the following shall be inclusive of all necessary fixtures, accessories & attachments to make them operational, etc. complete to the satisfaction of the Architect COST EXCLUDES INTERNAL CONCEALED PLUMBING WITH C.P.V.C. / P.V.C. PIPES ONLY (part of plumbing boq)
a.4 | Hindware table top wash basin Fornte white 91043 or equivalent | No. | 1 | 13500 | 13500 | 0 | 0 |  | -1 | -13500
a.9 | Hindware -Quadra which is actually “Quadra Bib Cock 2 in 1 with wall flange” or equivalent | No. | 1 | 2500 | 2500 | 0 | 0 |  | -1 | -2500
a.12 | Providing and fixing C.P brass wall mounted sink mixer with swinging spout including cutting and making good the walls where required. (3 way Sink ) | Each | 4 | 3200 | 12800 | 4 | 12800 |  | 0 | 0
a.13 | 40 mm CPVC Dia Pipe for 3 way sink for all inclusive fittings | Each | 1 | 7500 | 7500 | 2 | 15000 |  | 1 | 7500
a.14 | SS Kitchen Paper Holder 9" (Make : Hindware chrome F840008CP or equivalent) | Each | 1 | 1800 | 1800 | 0 | 0 |  | -1 | -1800
a.15 | Waste Coupling for 3Way sink and Makeline sink | No. | 1 | 650 | 650 | 4 | 2600 |  | 3 | 1950
a.16 | PVC Waste flexible Pipe of 1.0m length and 25 mm dia (make :SBD/Shineman etc) | No. | 0 |  | 0 | 0 | 0 |  | 0 | 0
a.17 | Conceal coak for makeline sink (Make- Hindware F310003ACP OR equivalent) Regular Body Suitable for 15mm Pipe Line with Spindle Extension & Plastic Protection Cap (without Exposed Parts) OR equivalent | NO. | 2 | 1250 | 2500 | 0 | 0 |  | -2 | -2500
F | Electrical
b.2 | Triple pole and neutral distribution board (TPNDB) with Double door surface/flush mounted of 8 way (4+ 24 Module) 4 Horizontal Rows in 4 Vertical tiers configuration comprising of following:- | Each | 1 | 28000 | 28000 | 1 | 28000 |  | 0 | 0
DB shall have separate neutral links of rating not less than 100A for each phase. The main incoming neutral link shall be in addition to three outgoing neutral links and shall be of 125A.
8 Way TPN Double door type DB for Power comprising of following:-
Incomer :
40A FP MCB,10kA - 01 No
Sub Incomer
3Nos, DP, 40A, RCBO (30mA).
Outgoing :
6/32A SP MCB - 18 Nos
With all necessary connections
F.3.0 | SPN DB
c.3 | 6 Way SPN Double door type DB for Power comprising of following:- | Each | 3 | 10500 | 31500 | 0 | 0 |  | -3 | -31500
Incomer :
16A DP MCB - 01 No
Outgoing :
10A SP MCB - 03 Nos
16A SP MCB - 1 No
With all necessary connections
F.4.0 | Isolators /ELCB /RCBO & SWITCH SOCKETS
a.2 | Supply , installation, testing comissioning of DP isolator of 32 A | Each | 3 | 1100 | 3300 | 0 | 0 |  | -3 | -3300
| Supply , installation, testing comissioning of DP MCB of 32 A | Each | 3 | 1300 | 3900 | 0 | 0 |  | -3 | -3900
| Supply , installation, testing comissioning of DP MCB of 40 A | Each | 1 | 1800 | 1800 | 0 | 0 |  | -1 | -1800
| Supply, Installation, testing comissioning of 32 amp TPN MCB | Each | 2 | 2500 | 5000 | 0 | 0 |  | -2 | -5000
| Providing and fixing TPN/DP enclosure box (Wheather Proof) for outdoor purposes | Each | 2 | 1800 | 3600 | 0 | 0 |  | -2 | -3600
b | ISOLATOR - (BEFORE SERVO STABILIZER) |  |  |  | 0 |  | 0 |  | 0 | 0
b.2 | 100A FP, 25kA Thermal magneticr based MCCB with LSIG Protection with Box(As per the instruction of the Engineer Inchrge) | Each | 1 | 20500 | 20500 | 0 | 0 |  | -1 | -20500
c | 6/16 Amp Electrical Top | Each | 5 | 300 | 1500 | 0 | 0 |  | -5 | -1500
d | Wiring for the following light points with 2X1.5 sq mm PVC insulated copper conductor 650V grade FRLS wires in concealed or surface mounted 20/25mm dia MMS PVC conduit as required including providing 6 amps flush type PVC moulded switches, cover plate,5 sided 1.2mm thick G.I. Box one module for housing switches and earthing of the fixtures and outlet box with 1.5 mm PVC insulated copper conductor 650V grade green earth wire.(switches-as/approved make)- upto 10 Mt. wire length is inclusive.
d.1 | Primary (First) light point controlled by a 6A switch. | Nos | 4.568 | 1500 | 6852 | 13 | 19500 |  | 8.432 | 12648
d.2 | Primary (First) light point controlled by a MCB in the DB. | Nos | 4.568 | 1500 | 6852 | 2 | 3000 |  | -2.568 | -3852
d.3 | Secondary (Loop) light point looped to first point and so on.(upto 6 mtr) wire length | Nos | 9.136 | 800 | 7308.8 | 14 | 11200 |  | 4.864 | 3891.2
d.4 | Supply, Installation, Testing & Commissioning of mains with 2 X 1.5 sq.mm and earth wire 1.5 sqmm FRLS PVC copper wire ,in rigid MMS PVC conduit min.25 mm dia, for light/fan/exhaust point from DB to point including all required accessories,etc as per specification.(If wire length increase above 10 mt mentioned in lighting circuit) | RMT | 9.136 | 130 | 1170 | 0 | 0 |  | 0 | 0
d.6 | Supplying & erecting mains with 2x4 sq.mm and earth wire 2.5 sqmm FRLS PVC copper wire laid with conduit/trunking/inside pole/Bus bars or any other places. | RMT | 50 | 170 | 8500 | 0 | 0 |  | -50 | -8500
e.5 | Supply, Installation, Testing & Commissioning of mains with 2 X 2.5 sq.mm and earth wire 2.5 sqmm FRLS PVC copper wire ,in rigid MS conduit min.20 mm dia,including all required accessories,etc as per specification. | Rmtr | 130 | 150 | 19500 | 194 | 29100 |  | 64 | 9600
f | Power Point
f.1 | First Point wiring with 6A,5pin wall socket outlet and controlled by a 6A switch | Nos | 2.7 | 1900 | 5130 | 7 | 13300 |  | 4.3 | 8170
f.2 | Extra loop point wiring with 6A, 5 pin wall socket outlet and controlled by a 6A switch upto 6 mtr length | Nos | 9 | 1350 | 12150 | 11 | 14850 |  | 2 | 2700
f.3 | First Point wiring with 16A,5pin wall socket outlet and controlled by a 16A switch | Nos | 2 | 2450 | 4900 | 2 | 4900 |  | 0 | 0
f.4 | Extra loop point wiring with 16A, 5 pin wall socket outlet and controlled by a 16A switch upto 6 mtr length | Nos | 5 | 1250 | 6250 | 0 | 0 |  | -5 | -6250
g.1 | First Point wiring with 16A, 3Pin combined shuttered wall socket outlet and controlled by a 16A one way switch with indicator. | Nos | 4.568 | 3000 | 13704 | 18 | 54000 |  | 13.432 | 40296
g.2 | Extra loop point wiring with 16A, 3Pin combined shuttered wall socket outlet and controlled by a 16A one way switch with indicator.upto 6 mtr wiring | Nos | 13.7611 | 1450 | 19953.595 | 16 | 23200 |  | 2.2389 | 3246.405
g.4 | Supply and Laying of Wiring for light/ power plug with 4X4 sq. mm FRLS PVC insulated copper conductor single core wire in surface/recessed medium class MMS PVC conduit alongwith 2 Nos. 4 sq. mm FRLS PVC insulated copper conductor single core cable for loop earthing as required. | Rmtr | 128.1895 | 250 | 32047.375 | 144.5 | 36125 |  | 16.3105 | 4077.625
h | Power Point wiring(MS conduit)
j | Supplying and fixing of following sizes of medium class PVC conduit along with accessories in surface/recess including cutting the wall/floor and making good the same in case of recessed conduit as required.
j.1 | 20 mm | Rmtr | 50.0047 | 75 | 3750.3525 | 250 | 18750 |  | 199.9953 | 14999.6475
m | Supplying & erecting M.S flexible Conduit 25 mm dia.conforming to I.S. and approved make with required number of couplings, bushes, check nuts etc. | Rmtr | 8 | 150 | 1200 | 69 | 10350 |  | 61 | 9150
n | Supplying & erecting PVC flexible Conduit 50 mm dia.conforming to I.S. and approved make with required number of couplings, bushes, check nuts etc. | Rmtr | 7 | 180 | 1260 | 0 | 0 |  | -7 | -1260
F.5.0 | LT CABLES & TERMINATIONS | [7 empty] | 0 | 0
a.7 | 3.5Cx70 Sq.mm AL Arm. XLPE | Rmtr | 5.4816 | 600 | 3000 | 0 | 0 |  | 5 | 3000
a.12 | 4Cx10 Sq.mm Cu. Arm. XLPE | Rmtr | 3.6544 | 650 | 2600 | 0 | 0 |  | 6 | 3900
F.7.0 | Cable Trays | [5 empty] | 0 |  | 0 | 0
a.2 | Providing & erecting Hot deeped Galvanised Non -Perforated type Cable tray manufactured from 18 swg (1.6 mm thick) GI sheet of 300 mm width & 50 mm height complete with necessary coupler plates & hardware in approved manner Including Paint | Rmtr | 15 | 1050 | 15750 | 0 | 0 |  | -15 | -15750
a.6 | Providing & erecting Hot deeped Galvanised Non- Perforated type Cable tray manufactured from 18 swg (1.6 mm thick) GI sheet of 100 mm width & 50 mm height complete with necessary coupler plates & hardware in approved manner.Including Paint | Rmtr | 34 | 600 | 20400 | 0 | 0 |  | -34 | -20400
Electrical Related Civil work
a.1 | Excavation/ Cheselling under floor for laying cables/ conduits in wall or floor as per requirement, complete with finishing etc | Sq.Mtr | 21.0805 | 450 | 9486.204 | 0 | 0 |  | -21.0805 | -9486.204
F.9.0 | Geyser | [5 empty] | 0
a.1 | SITC of Digital instant GEYSER ABOVE SINK 3 ltr (Ao Smith or equivalent)instant with required accessories) | No. | 1 | 7500 | 7500 | 1 | 7500 |  | 0 | 0
a.2 | SITC of Storage Geyser (25 ltr) AO smith or equivalent used above 3 way sink with required accessories | No | 1 | 17500 | 17500 | 1 | 17500 |  | 0 | 0
F.10.0 | Music System/ CONDUITING/WIRING FOR TELEPHONE/DATA/ MUSIC AND COMPUTER SYSTEM
a.2 | Wiring to music speakers with 2 pairs 40/0.076 flexible wire (PVC insulator, annealed or surface mounted 20/25 mm PVC conduit as directed (from speaker outlet to music junction box). | Rmtr | 67.3552 | 99 | 6668.1631 | 0 | 0 |  | -67.3552 | -6668.1631
a.3 | Two nos. telephone jack outlet in 2 module GI outlet -{Refer Details- Electrical (C) below} | Nos | 3 | 400 | 1200 | 0 | 0 |  | -3 | -1200
a.4 | Providing and drawing RG-58 co-axial cable for computer system in existing PVC conduit. | Rmtr | 230 | 125 | 28750 | 0 | 0 |  | -230 | -28750
a.5 | Cat-6 Cable for Switch to Camera inlcuding conduit. | Rmtr | 280 | 55 | 15400 | 555 | 30525 |  | 275 | 15125
a.6 | I O Plate including necessary Jack and connections | Nos | 4 | 400 | 1600 | 0 | 0 |  | -4 | -1600
a.7 | VGA cable Including spliter | Rmtr | 73 | 150 | 10950 | 0 | 0 |  | -73 | -10950
b | [5 empty] | 0 | 0
b.1 | 150mm x 200 x 40mm (W x H) - (18 SWG - 2 mm) with cover with one partition. | Each | 2 | 550 | 1100 | 0 | 0 |  | -2 | -1100
b.2 | 100 x 100 x 40mm deep with cover plate for makeline /Slap Table/Biometric | Each | 20 | 450 | 9000 | 0 | 0 |  | -20 | -9000
b.3 | 300 x 300 x 100 mm deep boxes with cover plate for Electrical Panel | Each | 5 | 850 | 4250 | 0 | 0 |  | -5 | -4250
G | Fire Detection and Alarm System | [5 empty] | 0 |  | 0 | 0
a | Supply, installation, testing & commissioning of Conventional Type optical Smoke Detector with inbuilt scattered light measurement, rate of rise and fixed temperature based technology and LED indication should be on the centre of the detector with mounting base complete as required. | No. | 5 | 3500 | 17500 | 0 | 0 |  | -5 | -17500
c | Supply, installation, testing & commissioning of conventional Manual Call Point (break glass type)complete with push button,enclosed in box with provision of conduit/cable coupling.The unit to be painted fire red outside ,white inside and written "in case of fire break glass" or as required. | No. | 2 | 2500 | 5000 | 0 | 0 |  | -2 | -5000
d | Supply, installation, testing & commissioning of Conventional Hooter cum Strobe complete as required.110 cd light & 85 dB adjustable at different locations complete with all fixing accessories etc under false ceiling ,roof,wall etc complete as required. | No. | 2 | 2500 | 5000 | 0 | 0 |  | -2 | -5000
e | Supply, installation, testing & commissioning of 2 zone based conventional Fire alarm control panel with standard set complete as required. | Set | 1 | 15000 | 15000 | 0 | 0 |  | -1 | -15000
f | Supplying and erecting PVC armoured cable 2 core 1.5 sq. mm FRLS copper conductor complete erected on wall / celling as per specification | Mtr. | 100 | 115 | 11500 | 0 | 0 |  | -100 | -11500
H.1.0 | DUCTING : ( MAKE: ZECO/TATA/JINDAL/SAIL/ROLASTAR/NUTECH)
b | Supply, Installation, Testing and Commissioning of Site Fabricated rectangular GI ducting of approved makes complying with IS: 277 and having 120 GSM coating classification. The price shall include the cost of necessary accessories & supports (like flanges, neoprene gaskets, wire ropes, corner saddles, guide vanes, vibration isolators, fire retardant canvas connection in all fan outlet connections, joints, sealing around the duct at wall crossings, labeling, (M.S supports / M.S Frame For Duct travelling Vertical up to Terrace, necessary flange type opening at specific interval for duct cleaning etc. for kitchen exhaust duct )as per specifications. The price shall include the cost of threaded rod support. The item also include providing & applying two coat of approved make anti corrosive paint over a coat of primer as per manufacturers/architect's recommendations,also with cheisling and scaffolding if required.
b.1 | 22 gauge galvanized sheet - For Exhaust & fresh Air Duct | Sq.mtr | 24 | 1500 | 36000 | 0 | 0 |  | -24 | -36000
b.2 | 24 gauge galvanized sheet - For Exhaust & fresh Air Duct | Sq.mtr | 13 | 1800 | 23400 | 59.98 | 107964 |  | 46.98 | 84564
b.3 | SITC of Canvas cloth at fan mouth for Exhaust & Fresh air unit as per detail specification | Nos | 2 | 5000 | 10000 | 2 | 10000 |  | 0 | 0
H.2.0 | THERMAL INSULATION | [5 empty] | 0
a.2 | 09 mm thick for Internal Insulation of duct | Sq.mtr | 24 | 750 | 18000 | 0 | 0 |  | -24 | -18000
a.3 | 09 mm thick for External Insulation of Exhaust duct | Sq.mtr | 13 | 850 | 11050 | 59.98 | 50983 |  | 46.98 | 39933
H.4.0 | Exhaust Fan for Toilet supply | [5 empty] | 0
a.1 | Supplying and erecting fresh air cum Exhaust fan of light duty 250 V A.C. 50 cycles 300mm/400mm. 1400 RPM rust proof body & blades, wiremesh, duly erected in an approved manner.(Havells/Usha/Crompton or Orient.) | Each | 1 | 3000 | 3000 | 0 | 0 |  | -1 | -3000
a.2 | Heavy Duty 450 mm Dia Exhaust Fan (Make Cromptoon & Equivalent) | Each | 1 | 5000 | 5000 | 0 | 0 |  | -1 | -5000
I | Miscellaneous work
I.1.0 | Extra Frequent Item
a | SS Brush Finish pole 4" x 4" and ht as per site (and as per drawing) with Sheet thickness of 1.6 mm minimum and to be fixed on floor with S.S plate with fastner and above M.S member support to be taken from Slab till 2500 mm ht .It shall be fixed with the top slab where ever possible with minimum 6" SS 2 mm thick plate with 4 Nos 8mm Fastners and Wire should run through conduit inside pole and socket to be placed above 300 mm from finished floor level. All The material must be SS 304 and the vendor shall share the certifcate for the same. the installation shall be as per enginner incharge. | R Ft | 10 | 1150 | 11500 | 5 | 5750 |  | -5 | -5750
b | Providing stand and fixing Micro wave Oven above staff lunch table to be source locally & as approved. | NOS | 1 | 3200 | 3200 | 0 | 0 |  | -1 | -3200
c | 3mm shock proof rubber mat with 11 kVA certification required | sq ft | 32 | 150 | 4800 | 11.19 | 1678.5 |  | -20.81 | -3121.5
f | Supply, installation, testing & commissioning of sensor with 180 deg coverage & 1 mtr range used for air curtain complete with all required accessories. Make: Any make readily available with min warranty of 1 year. | Nos | 4 | 2000 | 8000 | 0 | 0 |  | -4 | -8000
h | Providing and fixing water level sensor fully automatic with high and low indicator with alarm (Make : microtail ,OS or equivalent ) | Nos | 2 | 12000 | 24000 | 0 | 0 |  | -2 | -24000
I.2.0 | Fitting / Fixing of following item with necessary arrangement as directed | [5 empty] | 0
b | Safe/Furniture /Staff locker/IT Rack | Each | 1 | 500 | 500 | 0 | 0 |  | -1 | -500
c | Money box fixing | Each | 1 | 500 | 500 | 0 | 0 |  | -1 | -500
d | Air Curtain with all fixing arrangement | Each | 1 | 1500 | 1500 | 1 | 1500 |  | 0 | 0
e | Suspension & hanging of Exhaust hood from ceiling | Each | 1 | 2500 | 2500 | 1 | 2500 |  | 0 | 0
h | Computer rack | Each | 3 | 500 | 1500 | 0 | 0 |  | -3 | -1500
i | Strip curtain for oven hood | Job | 1 | 2500 | 2500 | 0 | 0 |  | -1 | -2500
j | Strip curtain for cold room | Job | 1 | 2500 | 2500 | 0 | 0 |  | -1 | -2500
k | Makeline SS sink with fastener | Each | 1 | 1250 | 1250 | 1 | 1250 |  | 0 | 0
l | Loading/Unloading of truck (Domino's material/equipment) | Nos | 1 | 5000 | 5000 | 0 | 0 |  | -1 | -5000
m | Loading/Unloading & disposable of debris (per truck) | Nos | 1 | 8500 | 8500 | 6 | 51000 |  | 5 | 42500
n | Loading / Unloading of Servo | Nos | 1 | 5000 | 5000 | 0 | 0 |  | -1 | -5000
o | Water dispenser connection with fittings | Each | 1 | 2500 | 2500 | 0 | 0 |  | -1 | -2500
q | P/F Door Stopper for Makeline /Slap Table | Each | 6 | 350 | 2100 | 0 | 0 |  | -6 | -2100
r | Fixing Wall Shelf above Slap Table /Sink | Each | 2 | 500 | 1000 | 0 | 0 |  | -2 | -1000
s | Fixing of Tissue Paper Holder /Helmet Stand | Each | 4 | 250 | 1000 | 0 | 0 |  | -4 | -1000
t | L.T Panel commisioning as per site requirement | Each | 1 | 4500 | 4500 | 0 | 0 |  | -1 | -4500
u | Servo connections as per site requirement | Each | 1 | 5500 | 5500 | 0 | 0 |  | -1 | -5500
v | Housekeeping | Sqft | RO | 750 |  | RO
w | Installation of Fresh air and Exhaust Unit | Each | RO | 3500 |  | RO
y | Bike Fixing with providing nutbolt and labour charge | Each | RO |  |  | RO
ac | Fixing of Light Fixtures Provided by JFL (Hood lights are in hood vendor scope) | Each | 59 | 200 | 11800 | 0 | 0 |  | -59 | -11800
ae | Supplying and erecting double pole metal clad switch with fuse and neutral link 240V, 25A on iron / GI frame switch socket with ISI mark approved make duly erected with modular box , cover plate & all wiring connections complete. (Single phase) | Each | 4 | 2200 | 8800 | 0 | 0 |  | -4 | -8800
af | Fixing and installation of fresh air fan | Each | 1 | 600 | 600 | 0 | 0 |  | -1 | -600
ag | Fixing and installation of Exhaust air fan | Each | 1 | 600 | 600 | 0 | 0 |  | -1 | -600
ah | OGT Installation with all required plumbing fittings (CPVC) pipe of 32mm dia under three sink unit | Each | 1 | 3000 | 3000 | 1 | 3000 |  | 0 | 0
| Fire Fighting System | [5 empty] | 0
A.2.0 | (PIPING AND ACCESSORIES) | [5 empty] | 0
a.5 | 50mm dia. | Meter | 15 | 1200 | 18000 | 10.3 | 12360 |  | -4.7 | -5640
a.8 | 25mm dia. | Meter | 25 | 800 | 20000 | 14.2 | 11360 |  | -10.8 | -8640
f | Supplying, Installation, Testing and Commissioning of 15mm dia. Quartzoid bulb type sprinkler with temperature rating at 68°/79°C made out of forged brass and in powder coated finish. | [7 empty] | 0 | 0
f.1 | Pendent/Upright 68° C Chrome Plated | Each | 6 | 1200 | 7200 | 11 | 13200 |  | 5 | 6000
i | Providing and fixing flexible connectors consisting of flexible core 1.5 mtr. in lenghth of corrugated stainless steel tubing under the braid, (Braiding to be SS-304, tubing to be SS-304) for minimum working pressure rating of 200 PSI to be installed at connections from branch pipes to pendant sprinklers blow false ceiling as per specification of the manufacturers. | Each | 6 | 4000 | 24000 | 11 | 44000 |  | 5 | 20000
| TOTAL |  |  |  | 2390242.4896 |  | 2074244.6 |  |  | -292309.0096
| CGST @ 9% |  |  |  | 215121.8241 |  | 186682.014 |  |  | -26307.8109
| SGST @ 9% |  |  |  | 215121.8241 |  | 186682.014 |  |  | -26307.8109
| GRAND TOTAL |  |  |  | 2820486.1378 |  | 2447608.628 |  |  | -344924.6314

## Extra Items (Annexure II)
ANNEXURE -II EXTRA ITEMS
SO No :- 5700310682 Dt 14/06/2022
CAR No :- 1
Civil work for modifications of Rooms (CISF Offices ) at T1C Building , CSMIA , Mumbai
SECTION: B (EXTRA ITEMS)
SR.NO. | DESCRIPTION | UNIT | OLD QTY | OLD RATE | OLD AMT (Rs) | Old qty | Old rate | old Amt | NEW QTY | New RATE (Rs.) | AMOUNT (Rs)
1 | Removal of Cold Storage and shifting the same outside airport premise SIZE - 10'-0" L X 8'-0" W X 8'-0" H | Lump | [6 empty] | 1 | 10000 | 10000
2 | Disconnecting all the cables and removal and shifting the existing HT electrical panel outside the store premise SIZE -1.70 L X 1.90 H X 0.45 W | Lump | [6 empty] | 1 | 30000 | 30000
3 | Shifting the HT electrical panel inside the store / Testing / Connecting / Commissioning the same. SIZE -1.70 L X 1.90 H X 0.45 W | Lump | [6 empty] | 1 | 45000 | 45000
4 | Removal of HOOD and shifting the same. SIZE - 1.85 X 2.0 | Lump | [6 empty] | 1 | 4000 | 4000
5 | Existing Cable Trays ,Duct Removing from the site and carting away from the site | sft | [6 empty] | 573.49 | 60 | 34409.4
6 | Removal PCC of thickness between 6 inches to 12 inches | Sq.ft | [6 empty] | 379.9 | 100 | 37990
7 | False Ceiling removing inclusive wire & Light | Sq.ft | [6 empty] | 573.9 | 75 | 43042.5
8 | Removal from Façade - Glass ,Signgage with ACP Boxing ,Frames etc | Sq.ft | [6 empty] | 94.31 | 100 | 9431
9 | Dismantling existing counter along with shifting of debris. SIZE -17'-0" L X 3'-0"H X 2'-6" W | Lump | [6 empty] | 1 | 10000 | 10000
10 | Laying 12mm on mother slab mortar including cement punning for smoothening of surface for Membrane purpose | sft | [6 empty] | 573.9 | 65 | 37303.5
11 | Providing & fixing perforated GI powder coated grid ceiling system of size 600mm x 600mm including framing of Armstrong make etc complete | sft | [6 empty] | 573.9 | 315 | 180778.5
12 | Supply and installation of Fire damper | EA | [6 empty] | 2 | 30000 | 60000
13 | Supply and installation of fresh air unit as per required 3000 CFM | EA | [6 empty] | 1 | 175000 | 175000
14 | Supply and installation of 1.5 tier split air conditioner make - Blue Star (5 star Inverter ) | EA | [6 empty] | 1 | 55000 | 55000
15 | Supply and installation of 2 tier split air conditioner make - Blue Star (5 star Inverter ) | EA | [6 empty] | 1 | 72000 | 72000
16 | Supply and installation of 3 tier cassete air conditioner make - Blue Star | EA | [6 empty] | 1 | 150000 | 150000
17 | Supply and Fixing Copper pipe for AC | M | [6 empty] | 57.34 | 1500 | 86010
18 | Supply and installation of exhaust air unit as per site requirement -2800 CFM | EA | [6 empty] | 1 | 180000 | 180000
19 | Filling 3mm wide x 20mm Deep Grove with Zed Black shade Epoxy Grout matching with Dominos Design Tile. | Sft | [6 empty] | 574.14 | 45 | 25836.3
20 | Providing and Making Wooden table with 19mm Marine ply,1mm laminate on both sides,Drawers ,computer try and all necessary Hardware etc Complete.Size - 4'-0" X 2'-0" | EA | [6 empty] | 1 | 19000 | 19000
21 | Removing & Refixing wooden Barricading.Size- 40'-0" x 12'-0" | LS | [6 empty] | 1 | 15000 | 15000
22 | Providing & Fixing Wooden frame, 6mm ply as per MIAL standards. And install White FLEX as per artworks provided by Client. The cost includes Labour, Transportation, Hardwares, etc Complete including Removing the same after completion of work. | Sft | [6 empty] | 96 | 120 | 11520
23 | Fire Detection and Alarm System | [9 empty] | 0
| SITC of Smoke Detector with Base -EST-3 make. | EA | [6 empty] | 5 | 5000 | 25000
24 | SITC of Heat Detector with Base -EST-3 make. | EA | [6 empty] | 1 | 5100 | 5100
25 | MCP -EST-3 make. | EA | [6 empty] | 1 | 6000 | 6000
26 | Hooter Cum strobe -EST-3 make. | EA | [6 empty] | 1 | 6800 | 6800
27 | Response Indicator | EA | [6 empty] | 2 | 350 | 700
28 | Supplying and erecting PVC armoured cable 2 core 1.5 sq. mm FRLS copper conductor complete erected on wall / celling as per specification | M | [6 empty] | 80 | 160 | 12800
29 | Junction Box ( 400x 400 ) | EA | [6 empty] | 3 | 700 | 2100
30 | Installation & Commissioning. | Lot | [6 empty] | 1 | 14000 | 14000
31 | Providing and fixing/welding in position Signage panelling made out of MS Pipe 50mm x 25mm , 0.6mm GI Corrugated Sheet, 12mm thick Bison board ,hanging with ceiling rafters and finished with 2 coat of primer & finaly finished with Duco paint-Armada blue or colour matching to Pantone shade PMS 2965 C Complete as per store front Detail and as specified in Drawing. Size - 5150 mm Long X 760mm High. | EA | [6 empty] | 1 | 40000 | 40000
32 | SITC of 600mm x 600mm 40W Sleek LED Panel of Wipro make. | EA | [6 empty] | 18 | 2700 | 48600
33 | SITC of 2 Mega Pixel 180 dig HD CCTV IP Dome Camara of Hikvision make. | EA | [6 empty] | 7 | 4500 | 31500
34 | SITC of 8 port DVR- IDS- 7108HQHI-M1/S of Hikvision make. | EA | [6 empty] | 1 | 15000 | 15000
35 | SITC of 2TB HDD Memory Card Seagate SV35 HDD | EA | [6 empty] | 1 | 9000 | 9000
36 | SITC of 24 Port Patch Panel of Dlink. | EA | [6 empty] | 1 | 4900 | 4900
37 | Supply, installation, testing and commissioning of Data outlet RJ 45 jack mounted with plates . Make: D-link. | EA | [6 empty] | 5 | 1500 | 7500
38 | Crimping, ferroling, testing & commisioning, lebling of I/O's both user end & rack side. | EA | [6 empty] | 48 | 500 | 24000
39 | SITC of IT Rack VE Tech make. Size - 600mm L X 600mm W x 2000mm H | EA | [6 empty] | 1 | 40000 | 40000
40 | Providing and Fixing 4 mm thk ACP in cladding in Grey colour of Timex or equivalent make with Aluminium Frame including cutting joint filling with silicone etc complete | Sqmt | [6 empty] | 2.46 | 4900 | 12054
41 | Providing and fixing Mirror polish Kota stone with Cement morter 1:4 ,filling joints etc. | Sft | [6 empty] | 73.96 | 175 | 12943
42 | Supplying & Fixing Angle cock Jaquar Make. | EA | [6 empty] | 4 | 1800 | 7200
43 | Supplying & Fixing Bottel Trap Jaquar Make. | EA | [6 empty] | 1 | 1800 | 1800
44 | Supplying & Fixing SS finish Flxible PVC Connector. | EA | [6 empty] | 7 | 650 | 4550
45 | Making Manhole with AAC Blocks with cement morter 1:6 , Cement plaster all sides with cement morter 1:4 & Finaly finished with Ceramic Tiles etc Complete. SIZE - Internal 350mm X 650mm | EA | [6 empty] | 1 | 7500 | 7500
46 | Making Manhole with AAC Blocks with cement morter 1:6 , Cement plaster all sides with cement morter 1:4 & Finaly finished with Ceramic Tiles etc Complete. SIZE - Internal 350mm X 500mm | EA | [6 empty] | 1 | 7500 | 7500
47 | Supplying & Fixing 4 piece SS 304 GRADE Manhole Cover with Lid using SS Angle frame with Hold fast , SS Hollow pipe grating , SS Mesh and SS sheet Lid with Handle etc Complete. SIZE - Internal 350mm X 650mm | EA | [6 empty] | 1 | 14000 | 14000
48 | Supplying & Fixing 4 piece SS 304 GRADE Manhole Cover with Lid using SS Angle frame with Hold fast , SS Hollow pipe grating , SS Mesh and SS sheet Lid with Handle etc Complete. SIZE - Internal 350mm X 500mm | EA | [6 empty] | 1 | 12500 | 12500
49 | Supplying and erecting PVC Flexible cable 16Sqmm 5 core FRLS copper conductor complete erected on wall / celling as per specification | M | [6 empty] | 32 | 1300 | 41600
50 | Supplying and erecting PVC Flexible cable 10Sqmm 5 core FRLS copper conductor complete erected on wall / celling as per specification | M | [6 empty] | 6 | 950 | 5700
51 | Supply, Installation, Testing & Commissioning of 63A Industrial Point with Powder coated MS Box, 63A 4 Pole MCB ,5 Pin Industrial Socket & Top of Legrand make. | EA | [6 empty] | 2 | 18000 | 36000
52 | Supply, Installation, Testing & Commissioning of 32A Industrial Point with Powder coated MS Box,MCB ,5 Pin Industrial Socket & Top of Legrand make. | EA | [6 empty] | 2 | 9800 | 19600
53 | Supplying & Fixing 50 x 50mm Aluminium pipe Skirting i/c fillig gap with silicon. | M | [6 empty] | 21.82 | 900 | 19638
54 | Providing & Fixing 12mm thk Pinup board with 12mm thk backing ply and alround frame and finished with approved Cloth with all necessary hard ware etc.completed. | sft | [6 empty] | 6.51 | 450 | 2929.5
55 | Providing & Fixing LED Tube Light. | EA | [6 empty] | 5 | 800 | 4000
56 | Supplying & Fixing wall Mounted Broom Stick /Mop Holder with 5 slots of approved make. | EA | [6 empty] | 1 | 2500 | 2500
57 | Fixing Cold storage Out door unit. | EA | [6 empty] | 1 | 5000 | 5000
58 | Supplying & Fixing Self Adhesive Silicon Door Bottom gap Sealing strip for air gap,cockroach insect bug stopper etc . | M | [6 empty] | 1 | 3000 | 3000
59 | Supplying & Fixing PVC Clear Strip curtain with all necessary hardware etc complete. | sft | [6 empty] | 50.13 | 300 | 15039
60 | Unloading Dominos Equipment at Airport entry, Shifting the same inside T1C and site carefully.Placing all the Equipment as per Layout and instruction of Incharge. | LS | [6 empty] | 1 | 90000 | 90000
61 | 12 Way SPN DB for Power comprising of following:- 40A ELCB-1 & 16A MCB -8 nos | EA | [6 empty] | 2 | 22000 | 44000
62 | Supply, Installation, Testing & Commissioning of mains with 2 X 6 sq.mm and earth wire 6 sqmm FRLS PVC copper wire ,in rigid MS conduit min.20 mm dia,including all required accessories,etc as per specification. | RMT | [6 empty] | 109 | 350 | 38150
63 | Supply, Installation, Testing & Commissioning of CCTV 4+1 Cable. | RMT | [6 empty] | 110 | 130 | 14300
64 | Supplying and erecting PVC armoured cable 4sqmm 4 core FRLS copper conductor complete erected on wall / celling as per specification | RMT | [6 empty] | 96 | 400 | 38400
65 | Supplying and erecting PVC armoured cable 6sqmm 4 core FRLS copper conductor complete erected on wall / celling as per specification | RMT | [6 empty] | 58 | 600 | 34800
66 | Termination of cables with Brass Glands ,Lags etc. | [9 empty] | 0
a | 120Sqmm Alu Armoured Cable | EA | [6 empty] | 2 | 3000 | 6000
b | 16sqmm X 5 core Copper Flexible cable | EA | [6 empty] | 2 | 2000 | 4000
c | 10sqmm X 5 core Copper Flexible cable | EA | [6 empty] | 2 | 1500 | 3000
d | 6Sqmm x 4 core Copper Armoured Cable | EA | [6 empty] | 2 | 1200 | 2400
e | 4Sqmm x 4 core Copper Armoured Cable | EA | [6 empty] | 4 | 1200 | 4800
| Total of Section B :- Extra Items |  | Rs | [7 empty] | 2099224.7
| CGST @ 9% |  | Rs
SGST @ 9%
GRAND TOTAL
Total(Section A + Section B) without taxes Rs.

## Sheet1 (hidden)
WO No 7500000002 SWD
S No | DESCRIPTION | NOS | L | B | H | T.QTY
1 | S/L 5 nos of 10 mts RCC Hume pipe
|  | 1 |  |  |  | 1 | LS
2 | Drains 600mm width
| Annawadi road corner to main nallah | 1 | 47.9 |  |  | 47.9
|  | 1 | 3.2 |  |  | 3.2
Annawadi road corner to Plot-2
| office gate | 1 | 52 |  |  | 52
| Plot-2 off gate to Annawadi | 1 | 67.3 |  |  | 67.3
[6 empty] | 170.4 | Rmt
Extra Items
1 | Demolishing cement concrete PQC
Main road drain
| Sides of drain | 2 | 67.3 | 0.5 | 0.85 | 57.205
0
| Bottom | 1 | 67.3 | 2 | 0.3 | 40.38
| Concrete road | 1 | 52 | 3.95 | 0.129 | 26.4966
0
|  | 1 | 55.8 | 3.95 | 0.15625 | 34.4391
0
| 1st Lair | 1 | 24 | 3.95 | 0.175 | 16.59
0
| 2nd Lair | 1 | 24 | 3.95 | 0.1 | 9.48
[6 empty] | 184.5907 | Cumt
2 | Demolishing RCC work 1:2:4
Main road drain
| Slab of drain | 1 | 67.3 | 2 | 0.15 | 20.19 | Cumt
3 | Demolishing Random Rubble Masonry
| Main road to proj Entrance | 1 | 22 | 0.6 | 0.6 | 7.92
|  | 1 | 22 | 0.45 | 2.27 | 22.473
| Proj off Ent to Proj Exit | 1 | 64.8 | 0.6 | 0.6 | 23.328
|  | 1 | 64.8 | 0.45 | 2.27 | 66.1932
| Proj Exit to Yellow Fever gate | 1 | 185.7 | 0.6 | 0.6 | 66.852
|  | 1 | 185.7 | 0.45 | 2.27 | 189.6926
| Plot 2 canteen to Entrance | 1 | 24.1 | 0.6 | 0.6 | 8.676
|  | 1 | 24.1 | 0.45 | 2.47 | 26.7872
| Gate to L&T office | 1 | 36.9 | 0.6 | 0.6 | 13.284
|  | 1 | 36.9 | 0.45 | 2.47 | 41.0144
| L&T to Annawadi | 1 | 37.3 | 0.6 | 0.6 | 13.428
|  | 1 | 37.3 | 0.45 | 2.47 | 41.459
| Yellow fever hos | 1 | 64.7 | 0.6 | 0.6 | 23.292
|  | 1 | 64.7 | 0.45 | 2.27 | 66.091
[6 empty] | 610.4902 | Cumt
4 | Dismentling/Removing chainlink
| Main road Hiranandani plot | 1 | 28.45 |  | 2.4 | 68.28
| Gate | 1 | 4.5 |  | 2.4 | 10.8
|  | 1 | 17.8 |  | 2.4 | 42.72
| Plot 2 canteen to Entrance | 1 | 24.1 |  | 1.25 | 30.125
| Gate to L&T office | 1 | 36.9 |  | 1.25 | 46.125
| Yellow fever hos | 1 | 64.7 |  | 1.3 | 84.11
[6 empty] | 282.16 | Sqmt
5 | Earthwork in excavation
For Drain
| Main rd to Proj off end | 1 | 91.6 | 2.95 | 1.5 | 405.33
| Proj Exit to Yellow Fever gate | 1 | 30 | 2.95 | 1.5 | 132.75
|  | 1 | 157.7 | 2.95 | 1.83 | 851.3434
| Yellow fever hos | 1 | 64.7 | 2.95 | 1.83 | 349.283
| For manhole | 1 | 3.4 | 3.4 | 2.25 | 26.01
| For Hume pipe,Road crossing | 1 | 7.5 | 2.4 | 2.23 | 40.14
|  | 1 | 7.5 | 2.4 | 2.2 | 39.6
| Plot 2 crossing | 1 | 12.5 | 2.4 | 2.05 | 61.5
| Yellow fever hos crossing | 1 | 5 | 2.4 | 1.83 | 21.96
| Road crossings | 3 | 7 | 2 | 1.9 | 79.8
| For Curb stone wide item no 18 | 1 | 120.1 | 0.2 | 0.2 | 4.804
[6 empty] | 2012.5204 | Cumt
6 | Soling with hard stone
| Between Proj Ent to Proj Exit | 1 | 36 | 2.95 | 0.23 | 24.426
| Drain from Proj Exit to Yellow Fever gate | 1 | 157.7 | 2.95 | 0.23 | 106.9994
| Yellow fever hos | 1 | 34.7 | 2.95 | 0.23 | 23.5439
| For manhole | 1 | 2.5 | 2.5 | 0.23 | 1.4375
| For Hume pipe,Road crossing | 2 | 7.5 | 1.8 | 0.23 | 6.21
| Plot 2 crossing | 1 | 12.5 | 1.8 | 0.23 | 5.175
| Yellow fever hos crossing | 1 | 5 | 1.8 | 0.23 | 2.07
| Road crossings | 3 | 7 | 1 | 0.23 | 4.83
For comp wall
| Proj off Ent to Proj Exit | 1 | 64.8 | 0.45 | 0.23 | 6.7068
| Proj Exit to Yellow Fever gate | 1 | 185.7 | 0.45 | 0.23 | 19.22
| Plot 2 canteen to Entrance | 1 | 24.1 | 0.45 | 0.23 | 2.4943
| Gate to L&T office | 1 | 36.9 | 0.45 | 0.23 | 3.8192
| L&T to Annawadi | 1 | 37.3 | 0.45 | 0.23 | 3.8605
| Yellow fever hos | 1 | 64.7 | 0.45 | 0.23 | 6.6964
[6 empty] | 217.4891 | Cumt
7 | Refilling with excavated earth
For Drain
Main rd to Proj off ent
|  | 2 | 21 | 0.15 | 0.5 | 3.15
|  | 2 | 21 | 0.45 | 0.5 | 9.45
|  | 2 | 21 | 0.75 | 0.5 | 15.75
| Proj off ent to Proj exit | 2 | 64.8 | 0.15 | 0.5 | 9.72
|  | 2 | 64.8 | 0.45 | 0.5 | 29.16
|  | 1 | 64.8 | 0.75 | 0.5 | 24.3
|  | 1 | 64.8 | 0.15 | 0.5 | 4.86
| Proj Exit to Yellow Fever gate | 2 | 187.7 | 0.15 | 0.5 | 28.155
|  | 2 | 187.7 | 0.45 | 0.5 | 84.465
|  | 1 | 187.7 | 0.75 | 0.5 | 70.3875
|  | 1 | 187.7 | 0.15 | 0.5 | 14.0775
| Yellow fever hos | 2 | 64.7 | 0.15 | 0.5 | 9.705
|  | 2 | 64.7 | 0.45 | 0.5 | 29.115
|  | 1 | 64.7 | 0.75 | 0.5 | 24.2625
|  | 1 | 64.7 | 0.15 | 0.5 | 4.8525
| For manhole | 2 | 3.4 | 0.6 | 2.25 | 9.18
|  | 2 | 2.2 | 0.6 | 2.25 | 5.94
| For Hume pipe,Road crossing | 2 | 7.5 | 0.4 | 1.6 | 9.6
|  | 1 | 7.5 | 2.4 | 0.32 | 5.76
|  | 2 | 7.5 | 0.4 | 1.6 | 9.6
|  | 1 | 7.5 | 2.4 | 0.3 | 5.4
| Plot 2 crossing | 2 | 12.5 | 0.4 | 1.6 | 16
|  | 1 | 12.5 | 2.4 | 0.12 | 3.6
| Yellow fever hos crossing | 2 | 5 | 0.4 | 1.5 | 6
| Road crossings | 6 | 7 | 0.35 | 1.57 | 23.079
[6 empty] | 455.569 | Cumt
8 | P/L cement concrete 1:2:4
PCC for drain
| Between Proj Ent to Proj Exit | 1 | 36 | 2.95 | 0.1 | 10.62
| Drain from Proj Exit to Yellow Fever gate | 1 | 157.7 | 2.95 | 0.1 | 46.5215
| Yellow fever hos | 1 | 34.7 | 2.95 | 0.1 | 10.2365
| PCC for manhole at main road | 1 | 2.5 | 2.5 | 0.1 | 0.625
PCC for comp wall
| Proj off Ent to Proj Exit | 1 | 64.8 | 0.45 | 0.1 | 2.916
| Proj Exit to Yellow Fever gate | 1 | 185.7 | 0.45 | 0.1 | 8.3565
| Plot 2 canteen to Entrance | 1 | 24.1 | 0.45 | 0.1 | 1.0845
| Gate to L&T office | 1 | 36.9 | 0.45 | 0.1 | 1.6605
| L&T to Annawadi | 1 | 37.3 | 0.45 | 0.1 | 1.6785
| Yellow fever hos | 1 | 64.7 | 0.45 | 0.1 | 2.9115
PCC on top of RR masonery
| Proj Exit to Yellow Fever gate | 1 | 185.7 | 0.45 | 0.1 | 8.3565
| L&T to Annawadi | 1 | 36.9 | 0.45 | 0.1 | 1.6605
| Yellow fever hos | 1 | 34.7 | 0.45 | 0.1 | 1.5615
| Ele Panel box fou | 1 | 1.25 | 0.85 | 0.3 | 0.31875
PCC for Paver Block
| Main road | 1 | 27.8 | 1.22 | 0.1 | 3.3916
|  | 1 | 4.41 | 3.5 | 0.1 | 1.5435
|  | 1 | 17.5 | 1.2 | 0.1 | 2.1
| PCC for Footpath | 1 | 21.3 | 1.9 | 0.15 | 6.0705
|  | 1 | 20.22 | 1.9 | 0.15 | 5.7627
| Less Manhole | 8 | 1.1 | 0.8 | 0.15 | -1.06
| PCC for Curb stone wide item no 18 | 1 | 120.1 | 0.15 | 0.1 | 1.8015
For Pole fixing
| Hiranandani plot | 19 | 0.3 | 0.3 | 0.3 | 0.513
| Proj off | 23 | 0.2 | 0.23 | 0.23 | 0.24334
| Plot-2 | 29 | 0.2 | 0.23 | 0.23 | 0.30682
[6 empty] | 119.1807 | Cumt
9 | P/L Ready mix concrete
a)M10
| For Hume pipe,Road crossing | 2 | 7.5 | 1.8 | 0.1 | 2.7
| Plot 2 crossing | 1 | 12.5 | 1.8 | 0.1 | 2.25
| Yellow fever hos crossing | 1 | 5 | 1.8 | 0.1 | 0.9
| Road crossings | 3 | 7 | 1 | 0.1 | 2.1
[6 empty] | 7.95 | Cumt
b)M15 (Encasing)
a)900mm dia hume pipe
| Main rd crossing | 2 | 7.5 | 1.3 | 1.5 | 29.25
| Plot-2 gate crossing | 1 | 12.5 | 1.3 | 1.5 | 24.375
| Less hume pipe | 1 | 27.5 | 0.635 |  | -17.4625
b)600mm dia
| Opp yellow fever hos crossing | 3 | 7 | 1 | 1.2 | 25.2
| Less hume pipe | 1 | 21 | 0.0706 |  | -1.4826
[6 empty] | 59.8799 | Cumt
c)M25 (Slab)
| Main road drain | 1 | 52.3 | 1.5 | 0.15 | 11.7675
| Less Manhole | 8 | 1.1 | 0.8 | 0.15 | -1.06
| Annawadi road corner to Plot-2 gate | 1 | 51.1 | 1.5 | 0.15 | 11.4975
| Less Manhole | 7 | 1.04 | 0.7 | 0.15 | -0.76
| Plot-2 off gate to Annawadi | 1 | 67.3 | 1.5 | 0.15 | 15.1425
| Less Manhole | 7 | 1.04 | 0.7 | 0.15 | -0.76
| Main road to proj Entrance | 1 | 26.8 | 1.5 | 0.15 | 6.03
| Proj Entrance | 1 | 7.07 | 1.5 | 0.23 | 2.4392
| Proj Ent end to proj exit | 1 | 50.66 | 1.5 | 0.15 | 11.3985
| Proj exit | 1 | 7.07 | 1.5 | 0.23 | 2.4392
| Proj Exit to Yellow Fever gate | 1 | 185.7 | 1.5 | 0.15 | 41.7825
| Less Manhole | 29 | 1.04 | 0.7 | 0.15 | -3.17
| Yellow fever hos | 1 | 64.7 | 1.5 | 0.15 | 14.5575
| Less Manhole | 4 | 1.04 | 0.7 | 0.15 | 0.4368
| Yellow Fever Ent | 1 | 4.9 | 1.5 | 0.23 | 1.6905
[6 empty] | 113.4316 | Cumt
10 | Reinforcement
12mm dia bar 100mm c/c
Short Span
| Main road drain i.e 52.30 rmt | 523 | 1.5 |  |  | 784.5
| Annawadi rd corner to Plot-2 gate i.e 52 | 521 | 1.5 |  |  | 781.5
| Plot-2 off gate to Annawadi i.e 67.30 | 674 | 1.5 |  |  | 1011
| Main road to proj Entrance i.e 26.8 | 269 | 1.5 |  |  | 403.5
| Proj Entrance i.e 2 X 7.07 | 144 | 1.5 |  |  | 216
| Proj Ent end to proj exit i.e 50.66 | 508 | 1.5 |  |  | 762
| Proj exit i.e 2 X 7.07 | 144 | 1.5 |  |  | 216
| Proj Exit to Yellow Fever gate i.e 185.70 | 1858 | 1.5 |  |  | 2787
| Yellow fever hos i.e 34.7 | 348 | 1.5 |  |  | 522
| Yellow Fever Ent i.e 2 X 4.90 | 100 | 1.5 |  |  | 150
| Less Manhole i.e 8 | 88 | 0.8 |  |  | -70.4
| Less Manhole i.e 47 | 517 | 0.8 |  |  | -413.6
[6 empty] | 7149.5 | Rmt
| Wt 0.89 Kg/rmt 7149.50 X 0.89 = |  |  |  | a) | 6363.06 | Kgs
10 mm dia bar 150mm c/c
Long Span
| Main road drain i.e 52.30 rmt | 11 | 52.3 |  |  | 575.3
| Lap | 8 | 0.6 |  |  | 4.8
| Annawadi rd corner to Plot-2 gate i.e 52 | 11 | 52 |  |  | 572
| Lap | 8 | 0.6 |  |  | 4.8
| Plot-2 off gate to Annawadi i.e 67.30 | 11 | 67.3 |  |  | 740.3
| Lap | 11 | 0.6 |  |  | 6.6
| Main road to proj Entrance i.e 26.8 | 11 | 26.8 |  |  | 294.8
| Lap | 5 | 0.6 |  |  | 3
| Proj Entrance i.e 2 X 7.07 | 22 | 7.07 |  |  | 155.54
| Proj Ent end to proj exit i.e 50.66 | 11 | 50.66 |  |  | 557.26
| Lap | 9 | 0.6 |  |  | 5.4
| Proj exit i.e 2 X 7.07 | 22 | 7.07 |  |  | 155.54
| Proj Exit to Yellow Fever gate i.e 185.70 | 11 | 185.7 |  |  | 2042.7
| Lap | 31 | 0.6 |  |  | 18.6
| Yellow fever hos i.e 34.7 | 11 | 34.7 |  |  | 381.7
| Lap | 6 | 0.6 |  |  | 3.6
| Yellow Fever Ent i.e 2 X 4.90 | 22 | 4.9 |  |  | 107.8
| Less Manhole i.e 8 | 40 | 1.1 |  |  | -44
| Less Manhole i.e 47 | 235 | 1.04 |  |  | -244.4
[6 empty] | 5341.34 | Rmt
| Wt 0.62 Kg/rmt 7149.50 X 0.89 = |  |  |  | b) | 3311.63 | Kgs
Coping
10 mm dia bar
| Coping on brick work-Item no 17 | 2 | 123.97
Hooks 230 c/c
Cutting Length0.32
| Proj off Ent to Proj Exit i.e 54.42 | 238 | 0.32 |  |  | 76.16
| Plot 2 canteen to Entrance i.e 24.1 | 106 | 0.32 |  |  | 33.92
| Plot-2 gate to Annawadi i.e 37 | 162 | 0.32 |  |  | 51.84
[6 empty] | 161.92 | Rmt
| Wt 0.62 Kg/rmt |  |  |  | c) | 100.39 | Kgs
[6 empty] | 9775.08 | Kgs
11 | Centring & Shuttring
Drain Slab
| Annawadi road corner to main nallah slab | 1 | 47.9 | 0.6 |  | 28.74
| Sides | 2 | 47.9 | 0.15 |  | 14.37
| Slab | 1 | 3.2 | 0.6 |  | 1.92
| Sides | 2 | 3.2 | 0.15 |  | 0.96
| Annawadi road corner to Plot-2 slab | 1 | 51.1 | 0.6 |  | 30.66
| Side | 1 | 51.1 | 0.15 |  | 7.665
| Side | 1 | 27.9 | 0.15 |  | 4.185
| Plot-2 gate to Annawadi | 1 | 69.8 | 0.6 |  | 41.88
|  | 1 | 69.8 | 0.15 |  | 10.47
| Main rd to Proj off Exit | 1 | 91.6 | 0.6 |  | 54.96
|  | 1 | 91.6 | 0.15 |  | 13.74
|  | 2 | 7.07 | 0.23 |  | 3.2522
|  | 2 | 7.07 | 0.08 |  | 1.1312
|  | 1 | 21 | 0.15 |  | 3.15
| Proj off Exit to Yellow Fever hospital | 1 | 187.7 | 0.6 |  | 112.62
|  | 1 | 187.7 | 0.15 |  | 28.155
| Yellow fever hospital | 1 | 64.7 | 0.6 |  | 38.82
|  | 1 | 64.7 | 0.15 |  | 9.705
Hume pipe Encasing
| Main rd crossing | 4 | 7.5 | 1.6 |  | 48
|  | 2 | 12.5 | 1.6 |  | 40
| Opp yellow fever hos crossing | 6 | 7 | 1 |  | 42
Copping above RR masonery
| Proj off Exit to Yellow fever hospital | 2 | 185.7 | 0.15 |  | 55.71
| Plot 2 gate to Annawadi | 2 | 37.3 | 0.15 |  | 11.19
| Yellow fever hospital | 2 | 64.7 | 0.15 |  | 19.41
| Coping on brick work-Item no 17 | 2 | 123.97 | 0.1 |  | 24.794
[6 empty] | 647.4874 | Sqmt
12 | P/L NP-2 hume pipe
a)900mm dia
| Main rd crossing | 2 | 7.5 |  |  | 15
| Plot-2 gate crossing | 1 | 12.5 |  |  | 12.5
[6 empty] | 27.5 | Rmt
b)600mm dia
| Opp yellow fever hos crossing | 3 | 7 |  |  | 21 | Rmt
13 | RR Masonery wall
| Proj off Ent to Proj Exit foundation | 1 | 64.32 | 0.6 | 0.6 | 23.1552
| Proj off Exit to Yellow fever hospital foun | 1 | 185.7 | 0.6 | 0.6 | 66.852
| Wall | 1 | 185.7 | 0.45 | 2.27 | 189.6926
| Plot 2 canteen to Entrance foun | 1 | 24.1 | 0.6 | 0.6 | 8.676
| Plot-2 gate to Annawadi foun | 1 | 74.8 | 0.6 | 0.6 | 26.928
| Wall | 1 | 37.3 | 0.45 | 2.4 | 40.284
| Yellow fever hospital foun | 1 | 64.7 | 0.6 | 0.6 | 23.292
| wall | 1 | 64.7 | 0.45 | 2.27 | 66.091
Drain
| Main rd to Proj off Exit | 2 | 91.6 | 1 | 0.5 | 91.6
|  | 2 | 91.6 | 0.7 | 0.5 | 64.12
|  | 2 | 91.6 | 0.4 | 0.5 | 36.64
| Proj off Exit to Yellow Fever hospital | 2 | 187.7 | 1 | 0.5 | 187.7
|  | 2 | 187.7 | 0.7 | 0.5 | 131.39
|  | 2 | 187.7 | 0.4 | 0.5 | 75.08
| Yellow fever hospital | 2 | 64.7 | 1 | 0.5 | 64.7
|  | 2 | 64.7 | 0.7 | 0.5 | 45.29
|  | 2 | 64.7 | 0.4 | 0.5 | 25.88
| Main rd Manhole | 2 | 2.2 | 0.6 | 2 | 5.28
|  | 2 | 1 | 0.6 | 2 | 2.4
| End of drain | 4 | 0.6 | 0.6 | 1.5 | 2.16
1177.2108
14 | Pointing work on RR Masonery
| Proj off Exit to Yellow fever hospital | 2 | 187.5 |  | 2.27 | 851.25
| Plot-2 gate to Annawadi | 2 | 37.3 |  | 2.4 | 179.04
| Yellow fever hospital | 2 | 64.7 |  | 2.27 | 293.738
[6 empty] | 1324.028 | Sqmt
15 | Brick work in cement morter
| Proj off Ent to Proj Exit | 1 | 54.42 | 0.23 | 1.12 | 14.0186
| Pillers | 23 | 0.4 | 0.1 | 1.12 | 1.0304
| Plot 2 canteen to Entrance | 1 | 24.1 | 0.23 | 1.12 | 6.2082
| Pillers | 8 | 0.4 | 0.1 | 1.12 | 0.3584
| Plot-2 gate to Annawadi | 1 | 36.9 | 0.23 | 1.12 | 9.5054
| Pillers | 16 | 0.4 | 0.1 | 1.12 | 0.7168
| Car parking wall | 1 | 1.1 | 0.23 | 1.2 | 0.3036
|  | 1 | 0.5 | 0.23 | 0.45 | 0.05175
|  | 1 | 0.43 | 0.23 | 0.37 | 0.036593
| Piller | 2 | 0.37 | 0.16 | 1.22 | 0.14445
| Gate opening | 1 | 7.35 | 0.23 | 1.2 | 2.0286
[6 empty] | 34.4028 | Cumt
16 | 15mm Cement plaster
| Proj off Ent to Proj Exit | 2 | 54.42 |  | 1.22 | 132.7848
| Top | 1 | 54.42 |  | 0.25 | 13.605
| Piller jams | 46 | 0.12 |  | 1.22 | 6.7344
| Piller top | 23 | 0.4 |  | 0.12 | 1.104
| Plot 2 canteen to Entrance | 2 | 24.1 |  | 1.22 | 58.804
| Top | 1 | 24.1 |  | 0.25 | 6.025
| Piller jams | 16 | 0.12 |  | 1.22 | 2.3424
| Piller top | 8 | 0.4 |  | 0.12 | 0.384
| Plot-2 gate to Annawadi | 2 | 36.9 |  | 1.22 | 90.036
| Top | 1 | 36.9 |  | 0.25 | 9.225
| Piller jams | 32 | 0.12 |  | 1.22 | 4.6848
| Piller top | 16 | 0.4 |  | 0.12 | 0.768
| Column sides | 24 | 0.5 |  | 2.65 | 31.8
| Column top | 6 | 0.5 |  | 0.5 | 1.5
| RR Masonery patta |  |  |  |  | 0
| Proj off Exit to Yellow fever hospital | 1 | 187.5 |  | 0.7 | 131.25
| Plot-2 gate to Annawadi | 1 | 37.3 |  | 0.7 | 26.11
| Yellow fever hospital | 1 | 64.7 |  | 0.7 | 45.29
| Car parking wall | 1 | 1.1 |  | 1.2 | 1.32
|  | 1 | 0.5 |  | 0.45 | 0.225
|  | 1 | 0.43 |  | 0.37 | 0.1591
| Piller | 2 | 0.37 |  | 1.22 | 0.9028
| Gate opening | 1 | 7.35 |  | 1.2 | 8.82
| Toilet |  |  |  |  | 573.8743 | Sqmt
17 | 100mm coping
| Proj off Ent to Proj Exit | 1 | 54.42 |  |  | 54.42
| Plot 2 canteen to Entrance | 1 | 24.1 |  |  | 24.1
| Plot-2 gate to Annawadi | 1 | 36.9 |  |  | 36.9
| Car parking wall | 1 | 2.3 |  |  | 2.3
| Gate opening | 1 | 7.35 |  |  | 7.35
[6 empty] | 125.07 | Rmt
18 | P/F cement concrete curb stone
| Car parking area | 1 | 5 |  |  | 5
|  | 1 | 10 |  |  | 10
|  | 1 | 1.03 |  |  | 1.03
|  | 1 | 1.8 |  |  | 1.8
|  | 1 | 2.53 |  |  | 2.53
| Garden | 1 | 54.92 |  |  | 54.92
| Foot path | 1 | 24.6 |  |  | 24.6
|  | 1 | 20.22 |  |  | 20.22
[6 empty] | 120.1 | Rmt
19 | P/F S F R C gratting cover of size 1000 X 700
X 50mm
| Foot path | 8 |  |  |  | 8
| Car parking area (Broken) | 6 |  |  |  | 6
[6 empty] | 14 | Nos
20 | P/F S F R C gratting cover of size 1000 X 1000
| X 100mm | 1 |  |  |  | 1 | No
21 | P/F S F R C gratting cover of size 1200 X 1000
| X 100mm | 1 |  |  |  | 1 | No
22 | P/F S F R C gratting cover of size 1070 X 670
X 100mm
| Main rd to Annawadi | 14 |  |  |  | 14
| Main rd to Yellow fever | 29 |  |  |  | 29
| Yellow Fever hos | 4 |  |  |  | 4
[6 empty] | 47 | Nos
23 | P/F Paver block
a) 60mm thk
| Main rd Footpath | 1 | 21.3 | 1.9 |  | 40.47
|  | 1 | 20.22 | 1.9 |  | 38.418
| Less Manhole | 8 | 1.1 | 0.8 |  | -7.04
[6 empty] | 71.848 | Sqmt
b)100mm thk
| Main road | 1 | 27.8 | 1.5 |  | 41.7
|  | 1 | 4.41 | 3.5 |  | 15.435
|  | 1 | 17.5 | 1.5 |  | 26.25
[6 empty] | 83.385 | Sqmt
24 | Fixing St Steel grill
| Proj off | 1 | 52.4 |  | 1.5 | 78.6
| Plot-2 | 1 | 24.1 |  | 1.5 | 36.15
|  | 1 | 36.9 |  | 1.5 | 55.35
| Yellow fever hos | 1 | 64.7 |  | 1.3 | 84.11
| Garden | 1 | 54.92 |  | 0.6 | 32.952
| Gate of Hiranandani | 1 | 4.5 |  | 2.4 | 10.8
[6 empty] | 297.962 | Sqmt
25 | Fixing chainlink fencing
| Main road Hiranandani plot | 1 | 28.45 |  | 2.4 | 68.28
|  | 1 | 17.8 |  | 2.4 | 42.72
| Car parking area | 1 | 24.1 |  | 1.2 | 28.92
|  | 1 | 30 |  | 1.2 | 36
[6 empty] | 175.92 | Sqmt
26 | P/F Chainlink fencing
| Car parking area | 1 | 80.2 |  | 1.25 | 100.25
| Ele Panel box | 1 | 2.9 |  | 1.25 | 3.625
[6 empty] | 103.875 | Sqmt
27 | Steel work
Angle 50 X 50 X 6mm
| Car parking area fencing Post | 13 | 1.5 |  |  | 19.5 | Rmt
| Wt 4.50 Kg/rmt |  |  |  | a) | 87.75 | Kgs
Angle 40 X 40 X 6mm
| Car parking area fencing Post | 17 | 1.5 |  |  | 25.5
|  | 2 | 80.2 |  |  | 160.4
| Ele Panel box Post | 4 | 1.5 |  |  | 6
| Clits | 34 | 0.15 |  |  | 5.1
| Clits for Pipe poles | 77 | 0.15 |  |  | 11.55
[6 empty] | 208.55 | Rmt
| Wt 3.5 Kg/rmt |  |  |  | b) | 729.93 | Kgs
ISMC 150 X 75
| To support cover | 2 | 1.8 |  |  | 3.6
| Wt 16.80 Kg/rmt |  |  |  | c) | 60.48
| For Yellow fever Gate approx |  |  |  | d) | 1100 | Kgs
[6 empty] | 1978.16 | Kgs
28 | P/F welding C class GI pipe
a)50mm dia pipe
| Proj off | 23 | 1.5 |  |  | 34.5
| Plot-2 | 11 | 1.5 |  |  | 16.5
|  | 18 | 1.5 |  |  | 27
[6 empty] | 78 | Rmt
b)32 mm dia pipe
| Garden area | 25 | 0.9 |  |  | 22.5 | Rmt
29 | Painting two coats of synthetic enamal paint
St Steel grill
| Proj off | 2 | 52.4 |  | 1.5 | 157.2
| Plot-2 | 2 | 24.1 |  | 1.5 | 72.3
|  | 2 | 36.9 |  | 1.5 | 110.7
| Yellow fever hos | 2 | 64.7 |  | 1.3 | 168.22
| Garden | 2 | 54.92 |  | 0.6 | 65.904
Chainlink fencing
| Car parking area | 2 | 80.2 |  | 1.25 | 200.5
| Ele Panel box | 2 | 2.9 |  | 1.25 | 7.25
[6 empty] | 782.074 | Sqmt
30 | Disposal of bldg debris
Total excavation for drain & wall wide item
| No 5 | 1 | 1862.87 |  |  | 1862.9
| Refilling of earth wide item No 7 | 1 | 465.17 |  |  | -465.17
[6 empty] | 1397.73 | Cumt
31 | Credit of stone
| Dismentling of RR wall wide item no 3 | 1 | 567.81 |  |  | 567.81
| 50 % stone obtained from above i.e 567.81 X50% = |  |  |  |  | 283.9 | Cumt