## COLD KITCHEN SUMMARY
COLD KITCHEN-GUWAHATI
SUMMARY FOR ELECTRICAL LOAD
REVISION: R0, DATE: 03.11.2023
Sr.No. | DESCRIPTION | WATTAGE (KW) | No of Units | CONNECTED LOAD | MAX. DMD LOAD | DIVERSITY | UPS LOAD
1 | LIGHTING LOAD
i | 2'x2' CEILING MOUNT LIGHT | 22 | 8 | 0.176 | 0.1584 | 90%
ii | 2'x2' CEILING MOUNT LIGHT EMERGENCY | 22 | 3 | 0.066 | 0.0594 | 90% | 0.0594
3 | KITCHEN & SOE EQUIPMENTS |  |  | 29.7 | 19.305 | 65%
4 | Exhaust System | 5500 | 1 | 5.5 | 4.4 | 80%
5 | Fresh - Air System | 5500 | 1 | 5.5 | 4.4 | 80%
6 | MISCELLANEOUS |  |  | 1 | 0.5 | 50%
| TOTAL LOAD IN KW |  |  | 41.942 | 28.8228 |  | 0.0594
UPS CALCULATIONS
| Total C & S Load | [5 empty] | 0.0594
| TOTAL EMERGENCY LOAD 15% of total lighting load | [5 empty] | 0.00891
| Total Emergency / Critical Load (kW) | [5 empty] | 0.06831
| 20% Spare Load | [5 empty] | 0.013662
| Grand total Load (kW) | [5 empty] | 0.081972
| Total Load (kVA) @ 0.9 PF | [5 empty] | 0.10247
| Recommended UPS rating (KVA) -1PH. I/C & O/G .(with Plus Minus 5%) | [5 empty] | 1
| Nearest size available--(1#1KVA) | [5 empty] | 1

## Equipment Schedule
CENTRAL KITCHEN
|  | EQUIPMENT SCHEDULE |  | DATE | 2023-05-05
|  | GUWAHATI |  | Rev Date-R1 | 2023-06-19
MAIN KITCHEN
SR.No. | Eq.No. | DESCRIPTION | BRAND/MODEL NO | DIMENSIONS(L x W x HT) | QTY | Electric Supply | Per Kw | TOTAL KW | AMPS | TYPE OF SWITCH | COMMENTS | VENDOR NAME | PO NO. | PO DATE | PO RELEASE DATE | LEAD TIME | ADVANCE | EXPECTED DELIVERY | REMARKS
|  | MAIN KITCHEN | [17 empty] | R | Y | B | 3PH
1 | CK-01 | 4" DEEP DISH LANDING TABLE W/GLASS RACK | FABRICATED | 1400 x 650 x 850 + 500+125 O/S | 1 | [5 empty] | IN NEW LAYOUT | Steel Craft | PO/SKPL/23-24/000773 | 2023-07-05 |  | 7 to 10 days
2 | CK-01a | DUST BIN | SOE | LOCAL | 1 | [5 empty] | IN NEW LAYOUT
3 | CK-01b | GREASE TRAP | FABRICATED | 500 x 400 x 375Ht. | 1 | [5 empty] | IN NEW LAYOUT | GROSS KITCHEN EQUIPMENTS | PO/SKPL/23-24/000776 | 2023-07-05
4 | CK-02 | LOADING TABLE WITH SINK ON (RHS)L & STRAINER | FABRICATED | 900 x 675 x 850 + 150SPL | 1 | [5 empty] | IN NEW LAYOUT | Steel Craft | PO/SKPL/23-24/000773 | 2023-07-05 |  | 7 to 10 days
5 | CK-03 | PRE RINSE SPARY UNIT - DECK MOUNTED | BAKERS SHOPPEE / EQUIVALENT | STD | 1 | [5 empty] | IN NEW LAYOUT
6 | CK-04 | HOOD TYPE DISH WASH MACHINE | WINTERHALTER / P50 | 735 x 750 x 1480Ht. | 1 | 3PH | 11.8 | 11.8 | 5 Pole Industrial Type | MCB | IN NEW LAYOUT | [11 empty] | 11.8
7 | CK-05 | UNLOADING TABLE 2 U/S | FABRICATED | 1350 x 675 x850+150SPL | 1 | [5 empty] | IN NEW LAYOUT BUT DIMESION CHANGE | Steel Craft | PO/SKPL/23-24/000773 | 2023-07-05 |  | 7 to 10 days
8 | CK-06 | WALL SHELF | FABRICATED | 1100 x 300 | 1 | [5 empty] | IN NEW LAYOUT BUT DIMESION CHANGE | G M ASSOCIATE | PO/SKPL/23-24/000774 | 2023-07-05
9 | CK-07 | CLEAN WIPE TABLE COSS SUPPORT WITH 2O/S | FABRICATED | 700 x 650 x 850+(150SPL)+450+300 | 1 | [5 empty] | REMOVE | G M ASSOCIATE | PO/SKPL/23-24/000774 | 2023-07-05
10 | CK-08 | UNDER COUNTER GLASS WASHER | IFB-Protech 411 Plus /ELECTROLUX 402116 (EGWSIG) | 540 x 440x 715Ht. | 1 | 1P | 3.1 | 3.1 | 5 / 15 Amp | Switch Socket | IN NEW LAYOUT | [8 empty] | 3.1
11 | CK-09 | WALL SHELF | FABRICATED | 750 x 300 W | 1 | [5 empty] | REMOVE | G M ASSOCIATE | PO/SKPL/23-24/000774 | 2023-07-05
12 | CK-10 | POT WASH SINK PERFORETED STRAINER AND BALL VALVE (BOWLS SIZE600 x 450x300mm) | FABRICATED | 750 x 625 x 850+150Ht. | 1 | [5 empty] | IN NEW LAYOUT | Steel Craft | PO/SKPL/23-24/000773 | 2023-07-05 |  | 7 to 10 days
13 | CK-10a | GREASE TRAP | FABRICATED | 500 x 400 x 375Ht. | 1 | [5 empty] | IN NEW LAYOUT | GROSS KITCHEN EQUIPMENTS | PO/SKPL/23-24/000776 | 2023-07-05
14 | CK-11 | POT RACK 4 Nos SHELF W/CASTOR WHEEL | FABRICATED | 1100 x 550 x 1650Ht. | 1 | [5 empty] | IN NEW LAYOUT BUT DIMESION CHANGE | Steel Craft | PO/SKPL/23-24/000773 | 2023-07-05 |  | 7 to 10 days
15 | CK-12 | CLEAN DISH RACK (4 SHELF) | FABRICATED | 900 x 450 x 1650Ht. | 4 | [5 empty] | IN NEW LAYOUT | G M ASSOCIATE | PO/SKPL/23-24/000774 | 2023-07-05
16 | CK-13 | SPARE NUMER
17 | CK-14 | WORK TABLE W/ 2 U/S & 2 O/S | FABRICATED | 95O x 700 x 850+450+300 | 1 | [5 empty] | IN NEW LAYOUT BUT DIMESION CHANGE | G M ASSOCIATE | PO/SKPL/23-24/000774 | 2023-07-05
18 | CK-15 | WORK TABLE HALFSID 2 U/S & HALFSIDE CRTOSS SUPPORT FOR USED OIL STORAGE | FABRICATED | 1300 x 600 x 850Ht. | 1 | [5 empty] | IN NEW LAYOUT | G M ASSOCIATE | PO/SKPL/23-24/000774 | 2023-07-05
21 | CK-18 | 1/4 GN PAN CONTAINERS | STD | 162 x 265 x 200 Deep. | 2 | [5 empty] | REMOVE
23 | CK-20 | WORK TABLE HALFSID 2 U/S & HALFSIDE CRTOSS SUPPORT FOR USED OIL STORAGE | FABRICATED | 1325 x 600 x 850Ht. | 1 | [5 empty] | REMOVE | G M ASSOCIATE | PO/SKPL/23-24/000774 | 2023-07-05
24 | CK-21 | SPARE NUMBER
25 | CK-22 | STAND FOR COMBI OVEN WITH 1/1 GN PAN ARRANGEMENT BELOW | FABRICATED | 950 x 875 x 800Ht. | 1 | [5 empty] | REMOVE
27 | CK-24 | WORK TABLE 2 U/S | FABRICATED | 600 x 875 x 850+150SPL | 1 |  |  | 0 |  |  | REMOVE | G M ASSOCIATE | PO/SKPL/23-24/000774 | 2023-07-05
30 | CK-27 | SINGLE SINK (RHS) TABLE CROSS SUPPORT | FABRICATED | 600 x 830 x 850+150SPL | 1 | [5 empty] | REMOVE | G M ASSOCIATE | PO/SKPL/23-24/000774 | 2023-07-05
31 | CK-27a | GREASE TRAP | FABRICATED | 400 x 335 x 350Ht. | 1 | [5 empty] | IN NEW LAYOUT | GROSS KITCHEN EQUIPMENTS | PO/SKPL/23-24/000776 | 2023-07-05
32 | CK-28 | SALAMANDER | KARAMA-AT936/SIRMAN | 610 x 340 x 280Ht. | 1 | [5 empty] | REMOVE
33 | CK-29 | WORK TABLE 2 U/S | FABRICATED | 850 x 780 x 528Ht. | 1 | [5 empty] | REMOVE | G M ASSOCIATE | PO/SKPL/23-24/000774 | 2023-07-05
35 | CK-31 | SPARE NUMBER
36 | CK-32 | FOOD PROCESSOR | ROBOT COUPE-R301 ULTRA Robot Coupe R 301 Ultra | 305 x 365 x 300Ht. | 1 | 1P | 2.2 | 2.2 | 5 / 15 Amp | Switch | IN NEW LAYOUT | [9 empty] | 2.2
37 | CK-33 | WALL SHELF | FABRICATED | 750 x 300 W | 2 | [5 empty] | IN NEW LAYOUT | G M ASSOCIATE | PO/SKPL/23-24/000774 | 2023-07-05
38 | CK-34 | 2 DOOR U/C REF. WITH LOCKABLE CASTOR WHEELS (2 Nos.WITH BREAK INFRONT & 2 Nos. WITHOUT BREAK) & HEATING ELEMENT FOR DRAIN | ELANPRO-CGN2100TN | 1360 x 700 x 850Ht | 2 | 1P | 1 | 2 | 5 / 15 Amp | Switch | IN NEW LAYOUT | Blue Star Limited | PO/SKPL/23-24/000784 | 2023-07-06 |  | 7 to 10 days | Done 02-08-2023 |  |  |  | 1 | 1
39 | CK-35 | 2 DOOR VERTICAL CHILLER WITH LOCKABLE CASTOR WHEELS (2 Nos.WITH BREAK INFRONT & 2 Nos. WITHOUT BREAK) & HEATING ELEMENT FOR DRAIN | ELANPRO -EGN 650TNM | 740 x 830 x 2010Ht. | 1 | 1P | 1 | 1 | 5 / 15 Amp | Switch | IN NEW LAYOUT | Blue Star Limited | PO/SKPL/23-24/000784 | 2023-07-06 |  | 7 to 10 days | Done 02-08-2023 |  |  |  |  | 1
40 | CK-36 | 2 DOOR VERTICAL FREEZER WITH LOCKABLE CASTOR WHEELS (2 Nos.WITH BREAK INFRONT & 2 Nos. WITHOUT BREAK) & HEATING ELEMENT FOR DRAIN | ELANPRO -EGN 650BTM | 740 x 830 x 2010Ht. | 1 | 1P | 1 | 1 | 5 / 15 Amp | Switch | IN NEW LAYOUT | Blue Star Limited | PO/SKPL/23-24/000784 | 2023-07-06 |  | 7 to 10 days | Done 02-08-2023 |  |  | 1
41 | CK-36A | 2 DOOR VERTICAL FREEZER WITH LOCKABLE CASTOR WHEELS (2 Nos.WITH BREAK INFRONT & 2 Nos. WITHOUT BREAK) & HEATING ELEMENT FOR DRAIN | ELANPRO -EGN 650BTM | 740 x 830 x 2010Ht. | 1 | 1P | 1 | 1 | 5 / 15 Amp | Switch | NEW ADDED | Blue Star Limited | PO/SKPL/23-24/000784 | 2023-07-06 |  | 7 to 10 days | Done 02-08-2023 |  |  |  | 1
42 | CK-37 | FOOT OPERATED HAND WASH SINK WITH HOT & COLD WATER CONNECTION & WITH TISSUE HOLDER & SOAP DISPENSER PROVISION & OPEN FROM BACK SIDE | FABRICATED | 500 x 475 x 850+450SPL | 1 | [5 empty] | IN NEW LAYOUT | Steel Craft | PO/SKPL/23-24/000773 | 2023-07-05 |  | 7 to 10 days
43 | CK-38 | SPARE NUMBER
44 | CK-39 | 2 DOOR CHEST FREEZER-534 LTRS CAP. | ELANPRO-EF 535DD | 1650 x 700 x 850Ht. | 2 | 1P | 1 | 2 | 5 / 15 Amp | Switch |  | CANCELLED BY SAEED SIR
46 | CK-41 | WORK TABLE W/ 2 U/S & 2 O/S | FABRICATED | 1300 x 700 x 850+450+300 | 1 | [5 empty] | REMOVE | Steel Craft | PO/SKPL/23-24/000773 | 2023-07-05 |  | 7 to 10 days
47 | CK-42 | ONION, POTATO & COCONUTSTORAGE TROLLEY | FABRICATED | 900 x 450 x 1350Ht. | 1 | [5 empty] | IN NEW LAYOUT | Steel Craft | PO/SKPL/23-24/000773 | 2023-07-05 |  | 7 to 10 days
48 | CK-43 | 3 TIER DIRTY DISH TROLLEY WITH HANDLE (3 SIDE COVER & 2 FRONT DOORS) | FABRICATED | 925 x 700 x 850Ht. | 2 | [5 empty] | IN NEW LAYOUT | GROSS KITCHEN EQUIPMENTS | PO/SKPL/23-24/000775 | 2023-07-05
49 | CK-44 | VEG CUTTER | SIRMAN-TM-INOX 6 BLADE |  | 1 | 1P | 1 | 1 | 5 / 15 Amp | Switch | IN NEW LAYOUT | WANG PROFESSIONALS PRIVATE LIMITED | PO/SKPL/23-24/000779 | 2023-07-05 | 2023-07-05 |  | Done 22/09/23 | Received on 11/10/23 | PCS Docket No. 1010998 Dt.04.10.23 |  |  | 1
50 | CK-45 | MS. SLOTTED ANGLE RACK | FABRICATED | 900 x 450 x 1800Ht. | 2 | [5 empty] | REMOVE | G M ASSOCIATE | PO/SKPL/23-24/000774 | 2023-07-05
51 | CK-46 | SINGLE SINK (RHS) TABLE CROSS SUPPORT WITH OHS | FABRICATED | 1075 x 600 x 850+(150SPL)+ 450+300 | 1 | [5 empty] | IN NEW LAYOUT | Steel Craft | PO/SKPL/23-24/000773 | 2023-07-05 |  | 7 to 10 days
Total Kw-Main Kitchen - A | [7 empty] | 25.1
SOE
1 |  | GARBAGE BINS 60Ltrs.Cap.-FRONTIER PEDAL OPERATED WHEEL | SOE | 460 x 650 x 750Ht. | 2
2 |  | DUST BIN | SOE | 300DIA x 600Ht. | 1
3 |  | GEYSER (Cap. As Per MEP) | SOE | QTY CAN BE MODIFIE AS PER MEP | 2 | 3PH | 3 | 6 | 32 | Metal Clad | [12 empty] | 6
4 |  | INSECT KILLERS | SOE |  | 2 | 1P | 0.3 | 0.6 | 5 / 15 Amp | Switch Socket |  | Technocrats Security Systems Private Limited | PO/SKPL/23-24/000772 | 2023-07-05 |  | 7 to 10 days |  |  |  | 0.3 |  | 0.3
5 |  | FIRE EXTINGUISHER ABC-4KG | SOE |  | 1 | [6 empty] | Fire Zone System Enterprise | PO/SKPL/23-24/000771 | 2023-07-05 |  | 7 to 10 days
6 |  | FIRE EXTINGUISHER CO/2-4.5KG | SOE |  | 1 | [6 empty] | Fire Zone System Enterprise | PO/SKPL/23-24/000771 | 2023-07-05 |  | 7 to 10 days
7 |  | FIRE EXTINGUISHER KTYPE - 6KG | SOE |  | 1 | [6 empty] | Fire Zone System Enterprise | PO/SKPL/23-24/000771 | 2023-07-05 |  | 7 to 10 days
8 |  | FIRE BLANKET - 6' X 4' | SOE |  | 1 | [6 empty] | Fire Zone System Enterprise | PO/SKPL/23-24/000771 | 2023-07-05 |  | 7 to 10 days
TOTAL MISCELLANEOUS LOAD IN Kw. - I | [7 empty] | 6.6 | [11 empty] | 4.4 | 4.2 | 3.3 | 17.8
Total Kw- (A+ B+C+D+E+F+G+H) | [7 empty] | 31.7 | [11 empty] | 11.9 |  |  | 17.8
29.7