## SUMMARY
|  |  | 2023-09-20 |  |  | R0
Annexure I
BOQ of Total C&I works for Copper Chimney
Location : | Pune- Wakad
Sr. No. | Item Description | PO Amount in INR. | Revised Amount in INR. | : | DEVIATION | Remarks | : | VIPL
1 | Civil Works. | 3350530 | 3779000 |  | 428470 |  |  | 3506328.3713
4 | Interior Work | 3449150 | 4818150 |  | 1369000 |  |  | 4413950.875
4.a | Additional Interior Work |  | 2302324.7386 |  | 2302324.7386 |  |  | 1689752.8705
5 | bells | 263000 | 0 |  | -263000
9 | Façade Sigange | 237500 | 0 |  | -237500
6 | Miscellaneous | 506000 | 506000 |  | 0
7 | Additional works | [6 empty] | 1888930.6201
| Subtotal amount INR. (without taxes) | 7806180 | 11405474.7386 |  | 3599294.7386 |  |  | 11498962.7369
| GST @ 18% | 1405112.4 | 2052985.453 |  | 647873.053 |  |  | 2069813.2926
| Grand Total | 9211292.4 | 13458460.1916 |  | 4247167.7916 |  |  | 13568776.0295
*
Note: This is tentative BOQ for Civil Interior works, without services coordination. Items will be added / alterted as per coordinated layout and scheme. The structural support grid required for services and ceiling support will be additional as per required.

## CIVIL WORK
BOQ of Civil work for Copper Chimney Project, Pune-Wakad | [6 empty] | 45185 |  |  | 20/9/2023 |  |  | R1 | [5 empty] | 20/9/2023
|  | GROUND FLOOR |  |  |  |  | FT |  | BOQ | [8 empty] | ACTUAL
SR.NO. | ITEM | DESCRIPTION | DRAWING NO | DIMENSION | UNIT | QTY. | RATE | AMOUNT | QTY. | RATE | AMOUNT | DEVIATION | REMARK | Purchase Remark | VIPL Remark 17.10.2023 | ARA Remark | VIPL Remark 13.11.2023 | QTY. | RATE | AMOUNT
GENERAL SITE WORKS
1 | Pest control at site | Providing Pest Control & Anti-termite treatment by appointing a specialized agency as per the specifications mentioned by the Bureau of Indian Standard & Agencies specification ( Whichever is higher ) for General Civil , Plumbing / Drainage & timber / Carpentry works , Gypsum related work including 5 Years guarantee under suitable undertaking on stamp paper etc complete as directed . ( Mode of Measurement to be on carpet area of floor & not the area of surface treated.) | N.A | N.A | SFT | 2600 | 15 | 39000 | 2600 | 15 | 39000 | 0 | [5 empty] | 2455.805 | 15 | 36837.075
DEMOLITION WORKS
1 | Demolition Work | Demolition of existing 100/125 mm thick Brick wall with marble, including cleaning the surface & dump the debris's at ground floor debris point.Demolition of existing Pantry counter & wash basin counter, including cleaning the surface & dump the debris's at ground floor debris point. | N.A | N.A | SFT | 100 | 35 | 3500 | 100 | 35 | 3500 | 0 | Area may increase as per actuals |  |  |  |  | 0 | 35 | 0
2 | Wall Chasing | Removing of existing wall including 200-300mm thick wall/ sand cement layer, including cleaning the surface & dump the debris's at ground floor debris point. |  |  | RFT | 50 | 35 | 1750 | 50 |  | 0 | -1750 | [5 empty] | 0 |  | 0
2 | Wall Puncture | Removing of POP punning and making wall puncture size of 200-600mm wide on existing wall, including cleaning the surface and proper plaster in line and level ready to paint & dump the debris's at ground floor debris point. | N.A | N.A | NO's | 5 | 1000 | 5000 | 5 | 1000 | 5000 | 0 | As actual |  |  |  |  | 0 | 1000 | 0
3 | Debris | Removing Debris out of site included loading, unloading & shifting as per statutory rules and regulations. | N.A | N.A | NO's | 2 | 7000 | 14000 | 2 | 7000 | 14000 | 0 | As actual |  |  |  |  | 63 | 7000 | 441000
INTERIOR CIVIL WORK
1 | Membrane Waterproofing | P&A Waterproofing on mother slabs & wall till 450mm height, with membrane water proofing treatment on the mother slab, before doing the treatment mother slab needs to clean properly up to the mark & dust free surface needs to achieve to apply the chemical (proof bond /BASF, Dr. Fixit / Equivalent make) & chemical needs to dry properly, After all there should be a water pond testing to be done for water tightness & rectifications of defects if any. Complete with 10 years performance guarantee with client's satisfaction. Entire process to be done under guideline & supervision of appointed engineering team. | [18 empty] | Rate to be check
| a | Kitchen -floor up to 1000mm |  | N.A | SFT | 720 | 90 | 64800 | 1000 | 90 | 90000 | 25200 | Upto 1meter Height | Rates are okay |  | Chnages done by mall team. |  | 742.9325 | 90 | 66863.925
| b | Kitchen -wall up to 600mm 1000mm |  | N.A | SFT | 300 | 90 | 27000 | 450 | 90 | 40500 | 13500 | Upto 1meter Height | Rates are okay |  |  |  | 565.5 | 90 | 50895
| c | Live kitchen -floor up to 1000mm |  | N.A | SFT | 120 | 90 | 10800 | 180 | 90 | 16200 | 5400 | Upto 1meter Height | Rates are okay |  |  |  | 103.5 | 90 | 9315
| d | Live kitchen -wall up to 600mm 1000mm |  | N.A | SFT | 80 | 90 | 7200 | 120 | 90 | 10800 | 3600 | Upto 1meter Height | Rates are okay |  |  |  | 117.75 | 90 | 10597.5
| e | Bar -floor up to 1000mm |  | N.A | SFT | 95 | 90 | 8550 | 150 | 90 | 13500 | 4950 | Upto 1meter Height | Rates are okay |  |  |  | 99.9125 | 90 | 8992.125
| f | Bar -wall up to 600mm 1000mm |  | N.A | SFT | 60 | 90 | 5400 | 90 | 90 | 8100 | 2700 | Upto 1meter Height | Rates are okay |  |  |  | 99 | 90 | 8910
2 | Block Work | Providing and constructing Light weight blocks masonry in cement mortar 1:4 of approved make like Aerocon/Siporex etc. Job to include raking out joints, scaffolding, making openings walls, curing etc. in substructure and superstructure to its true line & level in cement mortar proportion as specified in all shapes, size, at all heights, depths, leads & locations etc. complete. The rate shall also include for cleaning of surface, hacking of RCC surface in contact with brickwork, racking of joints, providing, erecting, & dismantling steel scaffolding , curing for 10 days, including 75 mm thk. R.C.C. stiffener at approximately every 1000 mm ht. with required M.S. reinforcement bars and Lintels for Doors and wall openings etc. compete as per the drgs., details & specifications.
| a | Using 150mm thk Walls upto 1200 mm |  | N.A | SFT | 90 | 190 | 17100 | 90 | 190 | 17100 | 0 | [5 empty] | 128 | 190 | 24320
| b | Using 150mm thk Walls upto 5000mm |  | N.A | SFT | 1500 | 190 | 285000 | 1500 | 190 | 285000 | 0 | [5 empty] | 1347.125 | 190 | 255953.75
| c | Using 100mm thk Walls upto 5000mm |  |  | SFT |  |  | 0 | 1700 | 170 | 289000 | 289000 |  | Ravi please re check the qty |  |  |  | 1445.875 | 170 | 245798.75
3 | Internal Plaster | P&A of single coat backing plaster of 15-18 mm thick in CM 1:4 proportion to the walls & others surface including scaffolding, curing the joints, etc. The rates are inclusive of providing chicken mesh of 18mm gauge & 150mm width at junction of brick & RCC etc. at the walls, columns, beams etc., seven days water treatment as anti crack of plaster. Complete as per site engineer's instruction. | N.A | N.A
| a | Bar Area & Live Kitchen (low height wall 1200mm) |  |  | SFT | 178 | 70 | 12460 | 178 | 70 | 12460 | 0 | [5 empty] | 286.64 | 70 | 20064.8
| b | Wall height (3600mm) consider |  |  | SFT | 4459 | 70 | 312130 | 2000 | 70 | 140000 | -172130 | [5 empty] | 4038.6 | 70 | 282702
4 | PCC Work | Providing and laying up to 50-75 mm thick cement concrete flooring with 1:2:4 cement concrete laid to proper level and slope in alternate bays including compactions, filling joints, or as directed, finishing smooth with cement Mortar 1:1 of sufficient minimum thickness to give a smooth & even surface and curing etc. complete as per architects instructions. | N.A | N.A | SFT | 1000 | 120 | 120000 | 1000 | 120 | 120000 | 0 | [5 empty] | 985.5 | 120 | 118260
5 | COBA Work (Modiform) | Modiform of Avg. thickness mentioned below; After laying of soil pipes, floor traps is completed the floor of the sunken portion shall be covered with Modiform manually with 15-20 mm wide joints in 20 mm thk. Waterproofing mortar 1:4 ( 1 cement : 4 coarse sand )in layers upto the full ht. of sunken portion, having top layer of 50 mm thk waterproof mortar 1:4 ( 1 cement : 4 coarse sand ) using specialized W.P. chemical, finished smooth / rough with floating coat of neat cement all complete and as per specification. | [18 empty] | Rate to be check
| a | Kitchen (300mm) appox | N.A | N.A | SFT | 720 | 250 | 180000 | 720 | 250 | 180000 | 0 | [5 empty] | 739.3125 | 250 | 184828.125
| b | Live kitchen (300mm) appox | N.A | N.A | SFT | 105 | 250 | 26250 | 105 | 250 | 26250 | 0 | [5 empty] | 101.25 | 250 | 25312.5
| c | Bar (150mm) appox | N.A | N.A | SFT | 85 | 250 | 21250 | 85 | 250 | 21250 | 0 | [5 empty] | 99.4375 | 250 | 24859.375
STONE & TILE WORKS
1 | KOTA Flooring | Providing and Laying KOTA stone of 19mm thk. on avg 40 mm thk bed of 1:4 cement mortar in proper line and level including neat cement float, filling joints with neat cement slurry of appropriate colour, cleaning, curing, rubbing, complete. Scope includes laying of floor protective cover on the floor and removing of the same when directed along with supply of all necessary materials, labour, tools and tackles complete in line with the Technical Specification, Drawings and as per the direction of the Architect & PMC. Including Polishing.
Size : 550x550 Basic Rate : 55 Per SFT
| a | Kitchen |  | N.A | SFT | 695 | 180 | 125100 | 680 | 180 | 122400 | -2700 | [5 empty] | 740.685 | 180 | 133323.3
| b | Live kitchen |  |  | SFT | 120 | 180 | 21600 | 120 | 180 | 21600 | 0 | [5 empty] | 101.25 | 180 | 18225
| c | Bar |  |  | SFT | 95 | 180 | 17100 | 95 | 180 | 17100 | 0 | [5 empty] | 79.4375 | 180 | 14298.75
| d | Liquor Store Room |  |  | SFT |  |  | 0 | 30 | 180 | 5400 | 5400 |  | Basic rate to reduced to Rs135 | Rate Quoted as per PO approved Rates | ok |  | 20 | 180 | 3600
2 | Wooden finish herringbone pattern Tile Flooring | Fixing & laying of tiles for flooring which includes --bedding of appropriate thickness with mortar of 1:6 ratio (1cement:6sand), spreading of grey cement slurry with minimum of 2kg/ Sq.mt. ratio over bedding mortar, including 3mm spacer with epoxy grout of approved colour, adhesive of bal Endura or approved equivalent, making of hole where ever required, in proper line and level in all direction, at all height with lead and lift, polishing/finishing/cleaning etc. as per design and drawing and directed by PMC etc. complete. | GROUND FLOOR | N.A | SFT | 1200 | 300 | 360000 | 1200 | 300 | 360000 | 0 | [5 empty] | 970.9375 | 300 | 291281.25
size - 200x1200. Basic Rate : 150 Per SFT (make kajaria)
3 | Pattern Tile Flooring | Fixing & laying of tiles for flooring which includes --bedding of appropriate thickness with mortar of 1:6 ratio (1cement:6sand), spreading of grey cement slurry with minimum of 2kg/ Sq.mt. ratio over bedding mortar, including 3mm spacer with epoxy grout of approved colour, adhesive of bal Endura or approved equivalent, making of hole where ever required, in proper line and level in all direction, at all height with lead and lift, polishing/finishing/cleaning etc. as per design and drawing and directed by PMC etc. complete. | GROUND+MEZZANINE FLOOR | N.A | SFT | 500 | 450 | 225000 | 500 | 450 | 225000 | 0 | [5 empty] | 520 | 450 | 234000
size - 300x300. Basic Rate : 220 Per SFT
4 | Wooden finish Tile skirting | Fixing & laying of 100mm high tiles for skirting with bedding of appropriate approved make adhesive & colour joint filler inclusive of making all groove/chamfering/rounding/hole where ever required, in proper line and level in all direction, polishing/finishing/cleaning etc. Complete as per detail drawing, specification and as directed by PMC. | GROUND+MEZZANINE FLOOR | N.A | RFT | 200 | 200 | 40000 | 200 | 200 | 40000 | 0 | [5 empty] | 117.25 | 200 | 23450
size - 100x1200. Basic Rate : 120 Per SFT
5 | Decorative Wall Tiles | Providing and fixing Glazed Decorative wall tiles which includes-approved make of adhesive like bal Endura or equivalent, grey cement paste with backing coat of 1:3 cement mortar not less than 12mm thick as & where ever required, joint filler of approved make and colour, as and where ever required, in proper line and level in all direction, at all height with lead and lift, polishing/finishing/cleaning etc as per design, drawing and directed by PMC etc. all complete.
Size : 75x300 Rate : 275per SFT
| a | Live kitchen Wall tiles upto 2400mm ht |  |  | SFT | 300 | 500 | 150000 | 300 | 500 | 150000 | 0 | [5 empty] | 232.25 | 500 | 116125
| b | Bar Wall tiles upto 2400mm ht |  |  | SFT | 200 | 500 | 100000 | 200 | 500 | 100000 | 0 | [5 empty] | 0 | 500 | 0
6 | Sada Wall Tiles for kitchen | Providing and fixing Ceramic wall tiles which includes-approved make of adhesive like bal Endura or equivalent, dry cladding on bison board panelling, joint filler of approved make and colour, as and where ever required, in proper line and level in all direction, at all height with lead and lift, polishing/finishing/cleaning etc as per design, drawing and directed by PMC etc. all complete. (Color - white/ ivory)
Size : 300x600. Rate : 45per SFT
| a | Main kitchen and under counter wall tiles upto 2400mm ht |  |  | SFT | 1340 | 180 | 241200 | 1340 | 180 | 241200 | 0 | [5 empty] | 1502.425 | 180 | 270436.5
| b | Live Kitchen |  |  | SFT | 85 | 180 | 15300 | 85 | 180 | 15300 | 0 | [5 empty] | 114.9375 | 180 | 20688.75
| c | Bar Area |  |  | SFT | 65 | 180 | 11700 | 65 | 180 | 11700 | 0 | [5 empty] | 113.75 | 180 | 20475
| d | Liquor Store Room |  |  | SFT | 150 | 180 | 0 | 150 | 180 | 27000 | 27000 |  | Basic rate should be 125/- as tile basic rate given Rs 45/- | Rate Quoted as per PO approved Rates | OK |  | 170 | 180 | 30600
7 | SS Corner Guard | P&F of 304 grade 3mm thick SS Corner guard (30mm x 30mm, mat finished as per approved sample) fixing with conceal tile on each corner of the kitchen's wall before cladding of tiles, so that the corner may be protected from the damages. Complete in proper line & level and site engineer's instruction. |  | N.A | RFT | 80 | 300 | 24000 | 80 | 300 | 24000 | 0 | [6 empty] | 300 | 0
8 | Brass Inlay in Flooring | P&F ofe3mm thick antique brass floor inlay fixing with thread screws on each corner of the kitchen's wall before cladding of tiles, so that the corner may be protected from the damages. Complete in proper line & level and site engineer's instruction. |  | N.A | RFT | 100 | 300 | 30000 | 100 | 300 | 30000 | 0 | [5 empty] | 99.25 | 300 | 29775
9 | pass window jamb line | Providing and fixing 300mm wide granite jamb line for pass window in live kitchen area which includes-approved make of adhesive like bal Endura or equivalent, joint filler of approved make and colour, as and where ever required, in proper line and level in all direction, at all height with lead and lift, polishing/finishing/cleaning etc as per design, drawing and directed by PMC etc. all complete. (Color - white/ ivory) |  |  | RFT |  |  | 0 | 6 | 600 | 3600 | 3600 |  | Require granite basic price | Granite Basic price 300/- per sqft |  |  | 25 | 600 | 15000
|  | TOTAL OF CIVIL WORK | [5 empty] | 2522190 |  |  | 2725960 | 203770 | [7 empty] | 3036788.475
POP & PAINTING WORK
1 | POP Punning | Providing and applying Plaster of Paris punning of average thickness 20-25mm to existing wall surfaces/ on existing tiles including chicken mesh in true level and plumb complete as per design and drawing Cleaning the surface properly with sand paper, filling cracks/holes with plaster of Paris. Applying lambi / putty (lambi/putty will be of good quality) sand papering the putty work on chamfers, etc.at any / all heights. Rate include cost for making grooves up to 12mm thick if required in horizontal or vertical direction near doors, windows, skirting, floor covering, masking tape and cleaning the area all complete as per drawing, design & manufactures specification.
| a | block work walls |  | N.A | SFT | 3500 | 50 | 175000 | 3500 | 50 | 175000 | 0 | [5 empty] | 361.5 | 50 | 18075
| b | Exposed ceiling |  | N.A | SFT | 2600 | 50 | 130000 | 2600 | 50 | 130000 | 0 | [5 empty] | 1248.875 | 50 | 62443.75
2 | Gypsum Ceiling | Providing, making and fixing of POP false ceiling as per manufacturer design and drawing including cut-outs for hvac grille, lights etc.at any / all heights. Rate quoted should be including of vertical drop of any heights, mouldings and size mentioned in drawings with necessary required framing in 450x 900 ultra Gyproc sections, fittings, and fixtures, scaffolding, floor covering, masking tape and cleaning the area all complete as per drawing, design & manufactures specification all complete. Rates do not include painting work. |  | N.A | SFT | 750 | 170 | 127500 | 750 | 170 | 127500 | 0 | [5 empty] | 644.25 | 170 | 109522.5
3 | Metal Ceiling | Fitting of false ceiling consisting of 20g Aluminium planks made of pre-coated ( Top & Bottom ) & Size : 600mmx600mm tiles . False Ceiling with necessary supports , hangers etc. provided to install light fitting , fresh air grill etc. ( from Hunter Douglas or Armstrong ) |  | N.A | SFT | 900 | 290 | 261000 | 900 | 290 | 261000 | 0 | [5 empty] | 96 | 290 | 27840
4 | Textured Wall Paint | Providing & applying three (03) coats of approved Plastic paint on walls including scraping, primer , filling with putty etc. complete with final coat no brush mark to be visible after painting colour shade as specified. |  | N.A | SFT | 2000 | 32 | 64000 | 2000 | 132 | 264000 | 200000 |  | why is rates escalated from 32 Psft to 100 Psft | Revised Rates Quoted As per ARA Design approved Stucco Texture Paint - 8473 - Royal Play | The team has seen the KG site before giving the quotation. Thye should have give considered this before. As the paint finish was clear. | It was a type of error from our 32/- per sqft is never for Texture paint | 1023.7975 | 132 | 135141.27
5 | Ceiling Paint ON Gypsum | Providing & applying three (03) coats of approved Plastic paint on exposed surface on ceiling including scraping, primer , filling with putty etc. complete with final coat no brush mark to be visible after painting colour shade as specified. |  | N.A | SFT | 690 | 32 | 22080 | 690 | 32 | 22080 | 0 | [5 empty] | 807.25 | 32 | 25832
6 | Expose Ceiling Paint including all beams | Providing & applying Three (03) coats of approved Plastic paint on exposed surface on ceiling including HVAC ducts, Sprinkler Pipes etc. complete with final coat no brush mark to be visible after painting colour shade as specified. |  | N.A | SFT | 1030 | 32 | 32960 | 1030 | 32 | 32960 | 0 | [5 empty] | 1085.635 | 32 | 34740.32
7 | Duct painting | Providing & applying Three (03) coats of powder coat (as per approved shade) on exposed surface on metal duct including removing of old paint, required zink oxide paint etc. complete with final coat no brush mark to be visible after painting colour shade as specified. |  |  | SFT | 500 | 27 | 13500 | 500 | 70 | 35000 | 21500 |  | Rates are approved | Spray Paint |  |  | 526.75 | 70 | 36872.5
8 | Fire Sprinkler paint | Providing & applying Three (03) coats of fire rated paint as per standard on exposed surface on metal including removing of old paint etc. complete with final coat no brush mark to be visible after painting colour shade as specified. |  |  | SFT | 100 | 23 | 2300 | 100 | 55 | 5500 | 3200 |  | Rates should be 55/-SFt | Rate is revised |  |  | 346.7738 | 55 | 19072.5563
TOTAL of POP & PAINTING WORK | [7 empty] | 828340 |  |  | 1053040 | 224700 | [7 empty] | 469539.8963

## Civil MS
NO | ITEM | DESCRIPTION | UNIT | No | Length | Width | Height | Total Qty
Interior Civil Works
GENERAL SITE WORKS
1 | Pest control at site | Providing Pest Control & Anti-termite treatment by appointing a specialized agency as per the specifications mentioned by the Bureau of Indian Standard & Agencies specification | Sqft
| a | FOH Area floor |  | 1 | 48.5 | 27 | - | 1309.5
|  | Less entrance side column |  | -2 | 4.65 | 1.15 | - | -10.695
|  | Buffet counter area |  | 1 | 13.75 | 12.25 | - | 168.4375
| b | Bar area |  | 1 | 10.25 | 7.75 | - | 79.4375
|  | Bar store |  | 1 | 5 | 4 | - | 20
| c | Live kitchen |  | 1 | 11.25 | 9 | - | 101.25
| d | Dish wash area |  | 1 | 11.25 | 12.25 | - | 137.8125
| e | Kitchen |  | 1 | 40.25 | 14.75 | - | 593.6875
|  | Less column |  | -1 | 5.25 | 3 | - | -15.75
|  | Niche near bar store |  | 1 | 4.75 | 1 | - | 4.75
|  | Kitchen passage |  | 1 | 12.25 | 5.5 | - | 67.375
|  | Total | [5 empty] | 2455.805
DEMOLITION WORKS
1 | Debris | Removing Debris out of site included loading, unloading & shifting as per statutory rules and regulations. | Nos
|  | Debris trip |  | 63 | - | - | - | 63
|  | Total | [5 empty] | 63
INTERIOR CIVIL WORKS
1 | Membrane Waterproofing | P&A Waterproofing on mother slabs & wall till 450mm height, with membrane water proofing treatment on the mother slab, | Sqft
| a | Kitchen floor |  | 1 | 40.25 | 14.75 | - | 593.6875
|  | Less column |  | -1 | 5.25 | 3 | - | -15.75
|  | Less dish wash area |  | -1 | 12.25 | 2.5 | - | -30.625
|  | Less bar store area |  | -1 | 4.15 | 3.45 | - | -14.3175
|  | Niche near bar store |  | 1 | 4.75 | 1 | - | 4.75
|  | Dish wash area |  | 1 | 11.25 | 12.25 | - | 137.8125
|  | Kitchen passage |  | 1 | 12.25 | 5.5 | - | 67.375
|  | Total | [5 empty] | 742.9325
| b | Kitchen wall
|  | Back side wall |  | 1 | 40.25 | - | 3 | 120.75
|  | RHS Wall near gas meter |  | 1 | 9 | - | 3 | 27
|  | Shaft |  | 1 | 7.5 | - | 3 | 22.5
|  | Passage wall shaft side |  | 1 | 8.25 | - | 3 | 24.75
|  | 2nd shaft |  | 1 | 7.5 | - | 3 | 22.5
|  | Passage DB Wall |  | 1 | 12.25 | - | 3 | 36.75
|  | Dish wash area from kitchen side |  | 1 | 9.25 | - | 3 | 27.75
|  | Wall edge |  | 1 | 0.75 | - | 3 | 2.25
|  | Dish wash area sink wall |  | 1 | 8.5 | - | 3 | 25.5
|  | Dish washer side wall |  | 1 | 11 | - | 3 | 33
|  | buffet counter side wall |  | 1 | 7.75 | - | 3 | 23.25
|  | Kitchen entry wall |  | 1 | 2.25 | - | 3 | 6.75
|  | Wall edge |  | 1 | 0.75 | - | 3 | 2.25
|  | Live kitchen entry wall |  | 1 | 4.5 | - | 3 | 13.5
|  | Live kitchen entry wall |  | 1 | 3.5 | - | 3 | 10.5
|  | Live kitchen back wall |  | 1 | 12.5 | - | 3 | 37.5
|  | Niche wall |  | 1 | 1 | - | 3 | 3
|  | Niche wall |  | 1 | 4.75 | - | 3 | 14.25
|  | Bar store wall |  | 1 | 4.5 | - | 3 | 13.5
|  | Bar store wall |  | 1 | 4.25 | - | 3 | 12.75
|  | LHS Wall |  | 1 | 12.25 | - | 3 | 36.75
|  | Column near gas meter |  | 1 | 16.25 | - | 3 | 48.75
|  | Total | [5 empty] | 565.5
| c | Live kitchen floor |  | 1 | 11.25 | 9 | - | 101.25
|  | Below door |  | 1 | 3 | 0.75 | - | 2.25
|  | Total | [5 empty] | 103.5
| d | Live kitchen wall
|  | LHS & RHS Wall |  | 2 | 11.25 | - | 3 | 67.5
|  | Back side wall |  | 1 | 9 | - | 3 | 27
|  | Entrance wall |  | 1 | 4.5 | - | 3 | 13.5
|  | Entrance wall |  | 1 | 3.25 | - | 3 | 9.75
|  | Total | [5 empty] | 117.75
| e | Bar area floor |  | 1 | 10.25 | 7.65 | - | 78.4125
|  | Below door |  | 1 | 2 | 0.75 | - | 1.5
|  | Bar store |  | 1 | 5 | 4 | - | 20
|  | Total | [5 empty] | 99.9125
| f | Bar area wall
|  | LHS & RHS Wall |  | 2 | 7.75 | - | 3 | 46.5
|  | Back side & Entrance wall |  | 2 | 10.25 | - | 3 | 61.5
|  | Less door |  | -2 | 2 | - | 3 | -12
|  | Entrance wall |  | 1 | 1 | - | 3 | 3
|  | Total | [5 empty] | 99
2 | Block works | Providing and constructing Light weight blocks masonry in cement mortar 1:4 of approved make like Aerocon/Siporex etc. Job to include raking out joints, scaffolding, making openings walls, curing etc. | Sqft
| a | Using 150mm thk Walls upto 1200 mm
|  | Bar counter wall |  | 1 | 10.25 | - | 4 | 41
|  | Live kitchen front wall |  | 1 | 12.5 | - | 4 | 50
|  | Dish wash area wall near water cooler |  | 1 | 3.25 | - | 4 | 13
|  | Near pot wash ( Rework ) |  | 2 | 3 | - | 4 | 24
|  | Total | [5 empty] | 128
| b | Using 150mm thk Walls upto 5000 mm
|  | Kitchen & Live kitchen front wall |  | 1 | 28.5 | - | 15.5 | 441.75
|  | Wall near kitchen door |  | 1 | 2.25 | - | 9 | 20.25
|  | Less Kitchen door |  | -1 | 4 | - | 8 | -32
|  | Less passage door |  | -1 | 3 | - | 8 | -24
|  | Less live kitchen glass |  | -1 | 12.75 | - | 7.75 | -98.8125
|  | Dish wash area RHS Wall |  | 1 | 12.5 | - | 15.75 | 196.875
|  | Dish wash area back side wall |  | 1 | 8.5 | - | 15.75 | 133.875
|  | Live kitchen entrance & Back side wall |  | 2 | 10 | - | 15.75 | 315
|  | Less door |  | -1 | 3 | - | 6.5 | -19.5
|  | Live kitchen RHS wall |  | 1 | 11.25 | - | 15.75 | 177.1875
|  | Niche wall |  | 1 | 1 | - | 15.75 | 15.75
|  | Niche wall |  | 1 | 4.75 | - | 15.75 | 74.8125
|  | Bar store entry wall |  | 1 | 10.25 | - | 15.75 | 161.4375
|  | Less door |  | -1 | 2 | - | 7.75 | -15.5
|  | Total | [5 empty] | 1347.125
| c | Using 100mm thk Walls upto 5000 mm
|  | Bar store RHS Wall |  | 1 | 4.5 | - | 15.75 | 70.875
|  | Bar store RHS Wall |  | 1 | 4.25 | - | 15.75 | 66.9375
|  | Kitchen LHS Wall |  | 1 | 12.25 | - | 15.75 | 192.9375
|  | Kitchen back side wall |  | 1 | 40.25 | - | 15.75 | 633.9375
|  | RHS Wall near gas meter |  | 1 | 9 | - | 15.75 | 141.75
|  | Shaft |  | 1 | 7.5 | - | 15.75 | 118.125
|  | Passage wall shaft side |  | 1 | 8.25 | - | 15.75 | 129.9375
|  | 2nd shaft |  | 1 | 2.5 | - | 15.75 | 39.375
|  | 2nd shaft |  | 1 | 5 | - | 1 | 5
|  | Bar area LHS Wall |  | 1 | 11.75 | - | 4 | 47
|  | Total | [5 empty] | 1445.875
3 | Internal plaster | P&A of single coat backing plaster of 15-18 mm thick in CM 1:4 proportion to the walls & others surface including scaffolding, | Sqft
| a | Bar Area & Live Kitchen (low height wall 1200mm)
|  | Bar counter wall |  | 2 | 10.25 | - | 4 | 82
|  | Wall edge |  | 2 | 1 | - | 4 | 8
|  | Live kitchen front wall |  | 2 | 12.5 | - | 4 | 100
|  | Wall edge |  | 2 | 1 | - | 4 | 8
|  | Dish wash area wall near water cooler |  | 2 | 3.25 | - | 4 | 26
|  | Wall edge |  | 2 | 0.83 | - | 4 | 6.64
|  | Near pot wash |  | 4 | 3 | - | 4 | 48
|  | Wall edge |  | 2 | 1 | - | 4 | 8
|  | Total | [5 empty] | 286.64
| b | Wall height (3600mm) consider
|  | Kitchen & Live kitchen front wall |  | 2 | 28.75 | - | 15.75 | 905.625
|  | Wall near kitchen door |  | 2 | 2.25 | - | 15.75 | 70.875
|  | Wall edge |  | 1 | 1 | - | 9 | 9
|  | Less Kitchen door |  | -2 | 4 | - | 7.75 | -62
|  | Less passage door |  | -2 | 3 | - | 7.75 | -46.5
|  | Less live kitchen glass |  | -2 | 12.55 | - | 7.75 | -194.525
|  | Dish wash area RHS Wall |  | 2 | 12.5 | - | 15.75 | 393.75
|  | Dish wash area back side wall |  | 2 | 8.5 | - | 15.75 | 267.75
|  | Live kitchen entrance & Back side wall |  | 2 | 10 | - | 15.75 | 315
|  | Less door |  | -2 | 2.9 | - | 6.5 | -37.7
|  | Live kitchen RHS wall |  | 2 | 11.25 | - | 15.75 | 354.375
|  | Niche wall |  | 2 | 1 | - | 15.75 | 31.5
|  | Niche wall |  | 2 | 4.75 | - | 15.75 | 149.625
|  | Bar store entry wall |  | 2 | 10.25 | - | 15.75 | 322.875
|  | Less door |  | -2 | 1.85 | - | 7.75 | -28.675
Using 100mm thk Walls
|  | Bar store RHS Wall |  | 2 | 4.5 | - | 15.75 | 141.75
|  | Bar store RHS Wall |  | 2 | 4.25 | - | 15.75 | 133.875
|  | Kitchen LHS Wall |  | 1 | 12.25 | - | 15.75 | 192.9375
|  | Kitchen back side wall |  | 1 | 40.5 | - | 15.75 | 637.875
|  | RHS Wall near gas meter |  | 1 | 9 | - | 15.75 | 141.75
|  | Shaft |  | 1 | 7.5 | - | 15.75 | 118.125
|  | Passage wall shaft side |  | 1 | 8.25 | - | 15.75 | 129.9375
|  | 2nd shaft |  | 1 | 2.5 | - | 15.75 | 39.375
|  | 2nd shaft |  | 1 | 5 | - | 1 | 5
|  | Bar area LHS Wall |  | 1 | 11.75 | - | 4 | 47
|  | Total | [5 empty] | 4038.6
4 | PCC Work | Providing and laying up to 50-75 mm thick cement concrete flooring with 1:2:4 cement concrete laid to proper level and slope in alternate bays including compactions, | Sqft | [5 empty] | 25mm thk for protaction
| a | Bar area |  | 1 | 10.25 | 7.75 | - | 79.4375
|  | Bar store |  | 1 | 5 | 4 | - | 20
| b | Live kitchen |  | 1 | 11.25 | 9 | - | 101.25
| c | Dish wash area |  | 1 | 11 | 12.25 | - | 134.75
| d | Kitchen |  | 1 | 40.25 | 14.75 | - | 593.6875
|  | Less column |  | -1 | 5.25 | 3 | - | -15.75
|  | Niche near bar store |  | 1 | 4.75 | 1 | - | 4.75
|  | Kitchen passage |  | 1 | 12.25 | 5.5 | - | 67.375
|  | Total | [5 empty] | 985.5
5 | COBA Work (Modiform) | Modiform of Avg. thickness mentioned below; After laying of soil pipes, floor traps is completed the floor of the sunken portion shall be covered with Modiform manually with 15-20 mm wide joints in 20 mm thk. | Sqft
| a | Kitchen |  | 1 | 40.25 | 14.75 | - | 593.6875
|  | Less column |  | -1 | 5.25 | 3 | - | -15.75
|  | Less dish wash area |  | -1 | 12.25 | 2.5 | - | -30.625
|  | Less bar store area |  | -1 | 4.25 | 3.5 | - | -14.875
|  | Niche near bar store |  | 1 | 4.75 | 1 | - | 4.75
|  | Dish wash area |  | 1 | 11 | 12.25 | - | 134.75
|  | Kitchen passage |  | 1 | 12.25 | 5.5 | - | 67.375
|  | Total | [5 empty] | 739.3125
| b | Live kitchen |  | 1 | 11.25 | 9 | - | 101.25
|  | Total | [5 empty] | 101.25
| c | Bar area |  | 1 | 10.25 | 7.75 | - | 79.4375
|  | Bar store |  | 1 | 5 | 4 | - | 20
|  | Total | [5 empty] | 99.4375
STONE & TILE WORKS
1 | Kota flooring | Providing and Laying KOTA stone of 19mm thk. on avg 40 mm thk bed of 1:4 cement mortar in proper line and level including neat cement float, filling joints with neat cement slurry of appropriate colour, | Sqft
| a | Kitchen |  | 1 | 40.25 | 14.75 | - | 593.6875
|  | Less column |  | -1 | 5.15 | 2.9 | - | -14.935
|  | Less dish wash area |  | -1 | 12.25 | 2.5 | - | -30.625
|  | Less bar store area |  | -1 | 4.15 | 3.45 | - | -14.3175
|  | Niche near bar store |  | 1 | 4.75 | 1 | - | 4.75
|  | Dish wash area |  | 1 | 11 | 12.25 | - | 134.75
|  | Kitchen passage |  | 1 | 12.25 | 5.5 | - | 67.375
|  | Total | [5 empty] | 740.685
| b | Live kitchen |  | 1 | 11.25 | 9 | - | 101.25
|  | Total | [5 empty] | 101.25
| c | Bar area |  | 1 | 10.25 | 7.75 | - | 79.4375
|  | Total | [5 empty] | 79.4375
| d | Bar store |  | 1 | 5 | 4 | - | 20
|  | Total | [5 empty] | 20
2 | Wooden finish herringbone pattern Tile Flooring | Fixing & laying of tiles for flooring which includes --bedding of appropriate thickness with mortar of 1:6 ratio (1cement:6sand), spreading of grey cement slurry with minimum of 2kg/ Sq.mt. ratio over bedding mortar, complete. | Sqft
| a | FOH Area floor |  | 1 | 48.5 | 27.25 | - | 1321.625
|  | Buffet counter area |  | 1 | 13.75 | 12.25 | - | 168.4375
|  | Less shaft area |  | -1 | 5 | 2 | - | -10
|  | Less pattern tile in center area |  | -1 | 27.75 | 10 | - | -277.5
|  | Less pattern tile in entrance area |  | -1 | 8.5 | 27.25 | - | -231.625
|  | Total | [5 empty] | 970.9375
3 | Pattern tile flooring | Fixing & laying of tiles for flooring which includes --bedding of appropriate thickness with mortar of 1:6 ratio (1cement:6sand), spreading of grey cement slurry with minimum of 2kg/ Sq.mt. ratio over bedding mortar, complete. | Sqft
|  | Pattern tile in center area |  | 1 | 27.75 | 10 | - | 277.5
|  | Pattern tile in entrance area |  | 1 | 8.5 | 27 | - | 229.5
|  | DB Area |  | 1 | 4 | 1.25 | - | 5
|  | DB Area |  | 1 | 4 | 2 | - | 8
|  | Total | [5 empty] | 520
4 | Wooden finish Tile skirting | Fixing & laying of 100mm high tiles for skirting with bedding of appropriate approved make adhesive & colour joint filler inclusive of making all groove/chamfering/rounding/hole where ever required, | Rft
| a | From RHS DB To center column |  | 1 | 15 | - | - | 15
|  | Column side |  | 2 | 1.25 | - | - | 2.5
|  | Column |  | 1 | 5.5 | - | - | 5.5
|  | column to buffet counter |  | 1 | 6.75 | - | - | 6.75
|  | Buffet counter |  | 1 | 13.75 | - | - | 13.75
|  | Buffet counter |  | 1 | 5 | - | - | 5
|  | Buffet counter |  | 1 | 9 | - | - | 9
|  | Shaft |  | 1 | 5 | - | - | 5
| b | Entrance side behind Screen |  | 1 | 1.75 | - | - | 1.75
|  | LHS DB Paneling |  | 1 | 9 | - | - | 9
|  | DB Side |  | 1 | 1.5 | - | - | 1.5
|  | From DB To center column |  | 1 | 15 | - | - | 15
|  | Column side |  | 2 | 1.25 | - | - | 2.5
|  | Column |  | 1 | 5.75 | - | - | 5.75
|  | From column to bar counter |  | 1 | 19.25 | - | - | 19.25
|  | Total | [5 empty] | 117.25
5 | Decorative Wall Tiles | Providing and fixing Glazed Decorative wall tiles which includes-approved make of adhesive like bal Endura or equivalent, grey cement paste with backing coat of 1:3 cement mortar not less than 12mm thick as & where ever required, | Sqft
| a | Live kitchen wall
|  | RHS Wall |  | 1 | 11.25 | - | 8 | 90
|  | LHS Wall |  | 2 | 0.75 | - | 5.5 | 8.25
|  | Back side wall |  | 1 | 9 | - | 8 | 72
|  | Entrance wall |  | 1 | 4.5 | - | 8 | 36
|  | Entrance wall |  | 1 | 3.25 | - | 8 | 26
|  | Total | [5 empty] | 232.25
6 | Sada Wall Tiles for kitchen | Providing and fixing Ceramic wall tiles which includes-approved make of adhesive like bal Endura or equivalent, | Sqft
| a | Kitchen wall
|  | Back side wall |  | 1 | 40.5 | - | 8 | 324
|  | RHS Wall near gas meter |  | 1 | 9 | - | 8 | 72
|  | Shaft |  | 1 | 7.5 | - | 8 | 60
|  | Passage wall shaft side |  | 1 | 8.25 | - | 8 | 66
|  | 2nd shaft |  | 1 | 7.5 | - | 8 | 60
|  | Less shaft shutter |  | -1 | 2.5 | - | 5.83 | -14.575
|  | Passage DB Wall |  | 1 | 12.5 | - | 8 | 100
|  | Ramp side |  | 2 | 5 | - | 0.5 | 5
|  | Dish wash area from kitchen side |  | 1 | 9.25 | - | 8 | 74
|  | Wall edge |  | 1 | 0.75 | - | 8 | 6
|  | Dish wash area sink wall |  | 1 | 8.5 | - | 8 | 68
|  | Dish washer side wall |  | 1 | 11 | - | 8 | 88
|  | buffet counter side wall |  | 1 | 7.75 | - | 8 | 62
|  | Kitchen entry wall |  | 1 | 2.25 | - | 8 | 18
|  | Wall edge |  | 1 | 0.75 | - | 8 | 6
|  | Live kitchen entry wall |  | 1 | 4.5 | - | 8 | 36
|  | Live kitchen entry wall |  | 1 | 3.5 | - | 8 | 28
|  | Live kitchen back wall |  | 1 | 12.5 | - | 8 | 100
|  | Niche wall |  | 1 | 1 | - | 8 | 8
|  | Niche wall |  | 1 | 4.75 | - | 8 | 38
|  | Bar store wall |  | 1 | 4.5 | - | 8 | 36
|  | Bar store wall |  | 1 | 4.25 | - | 8 | 34
|  | LHS Wall |  | 1 | 12.25 | - | 8 | 98
|  | Column near gas meter |  | 1 | 16.25 | - | 8 | 130
|  | Total | [5 empty] | 1502.425
| b | Live kitchen wall
|  | RHS Wall |  | 1 | 11.25 | - | 3 | 33.75
|  | LHS Wall |  | 1 | 11.25 | - | 2.75 | 30.9375
|  | Back side wall |  | 1 | 9 | - | 3 | 27
|  | Entrance wall |  | 1 | 4.5 | - | 3 | 13.5
|  | Entrance wall |  | 1 | 3.25 | - | 3 | 9.75
|  | Total | [5 empty] | 114.9375
| c | Bar area
|  | RHS Wall |  | 1 | 6.75 | - | 3.5 | 23.625
|  | LHS Wall |  | 1 | 6.75 | - | 3.5 | 23.625
|  | Counter wall |  | 1 | 8.5 | - | 3.5 | 29.75
|  | Back side wall |  | 1 | 8.5 | - | 3.5 | 29.75
|  | Wall edge |  | 2 | 1 | - | 3.5 | 7
|  | Total | [5 empty] | 113.75
| d | Bar store
|  | RHS Wall |  | 1 | 4 | - | 8 | 32
|  | LHS Wall |  | 1 | 4.75 | - | 8 | 38
|  | Entrance wall |  | 1 | 3.25 | - | 8 | 26
|  | Back side wall |  | 1 | 3.75 | - | 8 | 30
|  | Column |  | 1 | 2 | - | 8 | 16
|  | Wall edge |  | 2 | 1.75 | - | 8 | 28
|  | Total | [5 empty] | 170
8 | Brass Inlay in Flooring | P&F ofe3mm thick antique brass floor inlay fixing with thread screws on each corner of the kitchen's wall before cladding of tiles, | Rft
|  | Near entry |  | 1 | 27.75 | - | - | 27.75
|  | Seating area |  | 2 | 27.75 | - | - | 55.5
|  | Seating area |  | 1 | 10 | - | - | 10
|  | For entrance |  | 1 | 6 | - | - | 6
|  | Total | [5 empty] | 99.25
9 | pass window jamb line | Providing and fixing 300mm wide granite jamb line for pass window in live kitchen area which includes-approved make of adhesive like bal Endura or equivalent, | Rft
|  | Live kitchen window top & Bottom |  | 2 | 2.5 | - | - | 5
|  | Live kitchen window vertical |  | 2 | 1.5 | - | - | 3
|  | Live kitchen door frame vertical |  | 2 | 7 | - | - | 14
|  | Live kitchen door frame top |  | 1 | 3 | - | - | 3
|  | Total | [5 empty] | 25
POP & PAINTING WORKS
1 | POP Punning | Providing and applying Plaster of Paris punning of average thickness 20-25mm to existing wall surfaces | Sqft
| a | Block work walls
|  | Kitchen wall from buffet counter side |  | 1 | 16 | - | 15.5 | 248
|  | Less passage door |  | -1 | 3 | - | 8 | -24
|  | Less kitchen door |  | -1 | 4 | - | 8 | -32
|  | Live kitchen wall edge |  | 2 | 1 | - | 3 | 6
|  | Kitchen door top |  | 1 | 4 | - | 2.25 | 9
|  | Kitchen door wall side |  | 2 | 2.25 | - | 8 | 36
|  | Bar area RHS Wall |  | 1 | 6 | - | 15.75 | 94.5
|  | Bar area LHS Wall |  | 1 | 6 | - | 4 | 24
|  | Total | [5 empty] | 361.5
| b | Exposed ceiling
|  | FOH Area |  | 1 | 36.5 | 27.25 | - | 994.625
|  | Less column entrance side |  | -2 | 4.5 | 1.25 | - | -11.25
|  | Less column center area |  | -2 | 5.5 | 1.25 | - | -13.75
|  | RHS Beam |  | 1 | 36.5 | 1.25 | - | 45.625
|  | LHS Beam |  | 1 | 36.5 | 1.25 | - | 45.625
|  | Entrance side beam |  | 1 | 24 | 1 | - | 24
|  | Rework due to leakage |  | 4 | 8 | 3 | - | 96
|  | Rework due to leakage |  | 4 | 5 | 2 | - | 40
|  | Rework due to leakage |  | 2 | 7 | 2 | - | 28
|  | Total | [5 empty] | 1248.875
2 | Gypsum ceiling | Providing, making and fixing of POP false ceiling as per manufacturer design and drawing including cut-outs for hvac grille, lights etc.at any / all heights.k. | Sqft
|  | FOH Area |  | 1 | 40.75 | 12 | - | 489
|  | Less wooden trap door |  | -1 | 8 | 6.5 | - | -52
|  | Vertical above buffet counter |  | 1 | 12 | - | 1 | 12
|  | Vertical in FOH Area |  | 1 | 27.25 | - | 4.25 | 115.8125
|  | Bar area ceiling |  | 1 | 10.25 | 7.75 | - | 79.4375
|  | Total | [5 empty] | 644.25
3 | Metal Ceiling | Fitting of false ceiling consisting of 20g Aluminium planks made of pre-coated ( Top & Bottom ) & Size : 600mmx600mm tiles. | Sqft
|  | Live kitchen |  | 1 | 12 | 8 | - | 96
|  | Total | [5 empty] | 96
4 | Textured Wall Paint | Providing & applying three (03) coats of approved Plastic paint on walls including scraping, primer , filling with putty etc. complete with final coat no brush mark to be visible after painting colour shade as specified. | Sqft
|  | RHS DB Wall |  | 1 | 9 | - | 11 | 99
|  | DB Side |  | 1 | 1.25 | - | 11 | 13.75
|  | From DB to column |  | 1 | 15 | - | 11 | 165
|  | Column side |  | 2 | 1.25 | - | 11 | 27.5
|  | Column |  | 1 | 5.75 | - | 11 | 63.25
|  | From column to buffet counter corner |  | 1 | 6.5 | - | 11 | 71.5
|  | Wall near kitchen entry |  | 2 | 2.25 | - | 6.5 | 29.25
|  | Above kitchen door |  | 1 | 4 | - | 2.25 | 9
|  | Wall above kitchen door for cane mesh |  | 1 | 16 | - | 2.75 | 44
|  | Wall above kitchen door for cane mesh |  | 1 | 4.25 | - | 1 | 4.25
|  | LHS DB Wall |  | 1 | 9 | - | 10.94 | 98.46
|  | DB Side |  | 1 | 1.5 | - | 11 | 16.5
|  | From DB to column |  | 1 | 15 | - | 11 | 165
|  | Column side |  | 2 | 1.25 | - | 11 | 27.5
|  | From column to bar counter |  | 1 | 19.25 | - | 11 | 211.75
|  | Less wallpaper |  | -2 | 5.25 | - | 7.4 | -77.7
|  | Less wallpaper |  | -1 | 5.5 | - | 7.4 | -40.7
|  | Less wallpaper |  | -1 | 3 | - | 7.4 | -22.2
|  | Less wallpaper |  | -2 | 5 | - | 7.4 | -74
|  | Bar counter front side |  | 1 | 10.25 | - | 1.25 | 12.8125
|  | RHS & LHS wall above bar counter |  | 2 | 1.5 | - | 8 | 24
|  | Vertical near façade |  | 2 | 1 | - | 8.5 | 17
|  | façade top |  | 1 | 22.5 | - | 1 | 22.5
|  | Above façade for cane mesh |  | 1 | 24.5 | - | 4.75 | 116.375
|  | Total | [5 empty] | 1023.7975
5 | Ceiling Paint ON Gypsum | Providing & applying three (03) coats of approved Plastic paint on exposed surface on ceiling including scraping, primer , filling with putty etc. | Sqft
|  | FOH Area |  | 1 | 40.75 | 12 | - | 489
|  | Vertical above buffet counter |  | 1 | 12 | - | 1 | 12
|  | Vertical in FOH Area |  | 1 | 27.25 | - | 4.25 | 115.8125
|  | Bar area ceiling |  | 1 | 10.25 | 7.75 | - | 79.4375
|  | Wooden ceiling |  | 2 | 27.5 | 1.5 | - | 82.5
|  | Wooden ceiling |  | 2 | 9.5 | 1.5 | - | 28.5
|  | Total | [5 empty] | 807.25
6 | Expose Ceiling Paint including all beams | Providing & applying Three (03) coats of approved Plastic paint on exposed surface on ceiling | Sqft
| b | Exposed ceiling
|  | FOH Area |  | 1 | 36.5 | 27.25 | - | 994.625
|  | Less column entrance side |  | -2 | 4.5 | 1.2 | - | -10.8
|  | Less column center area |  | -2 | 5.6 | 1.2 | - | -13.44
|  | RHS Beam |  | 1 | 36.5 | 1.25 | - | 45.625
|  | LHS Beam |  | 1 | 36.5 | 1.25 | - | 45.625
|  | Entrance side beam |  | 1 | 24 | 1 | - | 24
|  | Total | [5 empty] | 1085.635
7 | Duct painting | Providing & applying Three (03) coats of powder coat (as per approved shade) on exposed surface on metal duct including removing of old paint, specified. | Sqft
|  | Duct paint |  | 2 | 33.5 | 7.75 | - | 519.25
|  | End cap |  | 2 | 2.5 | 1.5 | - | 7.5
|  | Total | [5 empty] | 526.75
8 | Fire Sprinkler paint | Providing & applying Three (03) coats of fire rated paint as per standard on exposed surface on metal including removing of old paint etc. | Sqft
|  | G I Pipe 100 mm |  | 1 | 16.5 | 0.5 | 3.14 | 25.905
|  | G I Pipe 80 mm |  | 1 | 50.5 | 0.5 | 3.14 | 79.285
|  | G I Pipe 65 mm |  | 1 | 30 | 0.5 | 3.14 | 47.1
|  | G I Pipe 50 mm |  | 1 | 10 | 0.5 | 3.14 | 15.7
|  | G I Pipe 32 mm |  | 1 | 22 | 0.25 | 3.14 | 17.27
|  | G I Pipe 25 mm |  | 1 | 205.75 | 0.25 | 3.14 | 161.5138
|  | Total | [5 empty] | 346.7738

## INTERIOR WORK
BOQ of Civil work for Copper Chimney Project, Pune-Wakad | [9 empty] | 18/9/2023 |  |  |  | R1
|  | GROUND FLOOR |  |  |  |  | FT |  |  | FT
SR.NO. | ITEM | DESCRIPTION | LOCATION | DIMENSION | UNIT | QTY. | RATE | AMOUNT | QTY. | RATE | AMOUNT | DEVIATION | IMAGE | REMARK | Purchase Remark | VIPL Remark | ARA Remark | VIPL Remark 13.11.2023 | QTY. | RATE | AMOUNT
DOORS |  | CARPENTRY WORK |  |  | BOQ | [13 empty] | ACTUAL
1 | Kitchen Door | Providing & fixing in position of wooden FRD Double Leaf Door made up of 45mm thick firerated flush door shutter of approved make & thickness, Inner side finished with wooden laminate and outer side with veneer finish including providing & fixing 750mm X 200mm fire rated glass Vision panel and 12mm thk Wooden lipping all around, including of 2100mm X 300mm SS push plate and 300mm high SS kick plate, including P/F of Door frame made out of CP Teak / Ash wood or equivalent with melamine polish finish. Size of the frame approximate 175mm wide X 50mm thick. Applicable hardware's such as s/s handles/ ss push plate, floor spring and any other hardware etc required to complete the related works as per design & detail. door hardware make consider Dorma / Hafele/Ozon /equilient Need heavy duty floor spring & both sides openable. | KITCHEN ENTRY | 1200 X 2400 MM | NOS. | 1 | 50000 | 50000 | 1 | 50000 | 50000 | 0 |  | SS PVD Coating to be fixed to all edges of Door shutters. | Proposed rate 49600 | SS PVD 50mm Cosidered | no changes to be accepted. |  | 1 | 50000 | 50000
[20 empty] | 0 | 0
2 | Kitchen Door beside buffet | Providing & fixing in position of wooden FRD single Leaf Door made up of 45mm thick firerated flush door shutter of approved make & thickness, Inner side finished with wooden laminate and outer side with veneer finish including providing & fixing 750mm X 200mm fire rated glass Vision panel and 12mm thk Wooden lipping all around, including of 2100mm X 300mm SS push plate and 300mm high SS kick plate, including P/F of Door frame made out of CP Teak / Ash wood or equivalent with melamine polish finish. Size of the frame approximate 175mm wide X 50mm thick. Applicable hardware's such as s/s handles/ ss push plate, floor spring and any other hardware etc required to complete the related works as per design & detail. door hardware make consider Dorma / Hafele/Ozon /equilient Need heavy duty floor spring & both sides openable. | LIVE KITCHEN ENTRY | 950 X 2400 MM | NOS. | 1 | 35000 | 35000 | 1 | 35000 | 35000 | 0 | [6 empty] | 1 | 35000 | 35000
[20 empty] | 0 | 0
3 | Live Kitchen sliding Door | Providing & fixing in position of wooden FRD sliding door made up of 38mm thick firerated flush door shutter of approved make & thickness, both side to be finished with wooden laminate including providing & fixing 750mm X 200mm fire rated glass Vision panel and 12mm thk Wooden lipping all around, including conceal handle a and 300mm high SS kick plate, including P/F of Door frame made out of CP Teak / Ash wood or equivalent with melamine polish finish. Size of the frame approximate 175mm wide X 50mm thick. Applicable hardware's such as sliding channel, s/s handles/ ss push plate, lock, tower bolt and any other hardware etc required to complete the related works as per design & detail. door hardware make consider Dorma / Hafele/Ozon /equilient Need heavy duty floor spring & both sides openable. | LIVE KITCHEN ENTRY | 900X 2400 MM | NOS. | 1 | 35000 | 35000 | 1 | 35000 | 35000 | 0 | [6 empty] | 1 | 35000 | 35000
4 | Main Door | P/F 10 mm thk. toughened glass double leaf openable door with 20x 40mm MS framework with white/ black powder coating and bottom base wooden partiton height upto 600mm with wooden molding finish with duco paint and all necessary required groove, wooden framing, including glass door with heavy duty floor spring fixing with approved make adhesive and fasteners, cutting/ chamfering/ groove/rounding wherever required, at all height with lead and lift, finishing, cleaning as per design and drawing etc. all complete. including door lock. | MAIN ENTRY | 1800X 2400MM | NOS. | 1 | 74400 | 74400 | 1 | 74400 | 74400 | 0 | [7 empty] | 74400 | 0
5 | Trap Door | Providing and fixing trap doors for access to the service areas. The trap door shall have an external frame made of 50mm x 50mm in good quality seasoned wood scantling on which the shutter is hinged. Shutter shall be made of 19 mm. fire rated Plywood. The exposed side & Internal side shall be laminate finish. Concealed heavy duty hinges shall be used to mount the shutters and locking shall be provided with Allen key and panel locks. Sufficient number of hinges and locks shall be provided to avoid sagging of the shutter. Key also shall be supplied | NEAR LIVE KITCHEN | 1200X 900 MM | NOS. | 3 | 20000 | 60000 | 3 | 20000 | 60000 | 0 | [6 empty] | 1 | 20000 | 20000
TOTAL DOORS | [7 empty] | 254400 |  |  | 254400 | 0 | [8 empty] | 140000
CARPENTRY WORK |  | CARPENTRY WORK | [8 empty] | #REF!
1 | Service Station | P/F service counters in duco finished from outer surface & top finished in veneer. The storage under the Counter should be provided with 6" ht. drawers at top row finished with wooden ribs. top of the shutter having C section brass inlay & below openable shutters finished with duco. the drawer should have internal partiton with fabric finish for cutlary Shutters made out of 19mm thk. firerated plywood finished with 1mm thk. laminate internally. The shutters to be provided with fittings such as hinges; handles; ball catch, locks etc. complete in all respect. The rates for the Shutters to be included. as per design and details. any 1drawer (in each service station) should have 3compartment made in ply finished with fabric for cutlery and bottom storage should have 1shelf for crockery, shelf in ply finished with white laminate | NEAR COLUMN | 1200mm L X 600mmW X 900H | NOS. | 3 | 40000 | 120000 | 3 | 48000 | 144000 | 24000 |  |  | 33%-Cost escalation on acccount of increment of material from commercial ply to fire rated ply |  | give the breakup only for differennce between commercial ply and fire rated plywood. The finishing material is not changing. | 20%-Cost escalation on acccount of increment of material from for Material changed Commercial to Fire Rated Ply | 3 | 48000 | 144000
|  | Plywood - branded firerated -- Greenply or Equivalent brand | [5 empty] | 0 |  |  | 0
|  | Veneer Make - Euro/Greenlam/Merino/ or equivalent (Basic Rate- 140 Sq. ft.) | [5 empty] | 0 |  |  | 0
|  | Laminate Make - Euro/Greenlam/Merino/ or equivalent (Basic Rate- 40 Sq. ft.) | [5 empty] | 0 |  |  | 0
2 | CONSOLE_01 | The base CONSOLE finished in duco from outer surface & top finished in veneer. The storage under the Counter should be provided with 6" ht. drawers at top row finished with wooden ribs. top of the shutter having C section brass inlay & below openable shutters finished with duco. Shutters made out of 19mm thk. plywood finished with 1mm thk. laminate internally. The shutters to be provided with fittings such as hinges; handles; ball catch etc. complete in all respect. Including castor wheels (4nos) equipped wih 100mm wheels for smoothly running. The rates for the Shutters to be included. as per design and details. | NEAR HOSTESS DESK | 1265mm L X 500mmW X 900H | NOS. | 1 | 40000 | 40000 |  |  |  | -40000
Plywood - branded Commercial Ply (MR Calibrated, IS 303) -- Greenply or Equivalent brand
Veneer Make - Euro/Greenlam/Merino/ or equivalent (Basic Rate- 140 Sq. ft.)
Laminate Make - Euro/Greenlam/Merino/ or equivalent (Basic Rate- 40 Sq. ft.)
2a | CONSOLE_02 | The base CONSOLE finished in duco from outer surface & top finished in veneer. The storage under the Counter should be provided with 6" ht. drawers at top row finished with wooden ribs. top of the shutter having C section brass inlay & below openable shutters finished with duco. Shutters made out of 19mm thk. plywood finished with 1mm thk. laminate internally. The shutters to be provided with fittings such as hinges; handles; ball catch etc. complete in all respect. Including castor wheels (4nos) equipped wih 100mm wheels for smoothly running. The rates for the Shutters to be included. as per design and details. | NEAR BANQUETTE | 1540mm L X 500mmW X 900H | NOS. | 2 | 50000 | 100000 |  |  |  | -100000
Plywood - branded Commercial Ply (MR Calibrated, IS 303) -- Greenply or Equivalent brand
Veneer Make - Euro/Greenlam/Merino/ or equivalent (Basic Rate- 140 Sq. ft.)
Laminate Make - Euro/Greenlam/Merino/ or equivalent (Basic Rate- 40 Sq. ft.)
2b | CONSOLE_03 (for salad & dessert) | The base CONSOLE finished in duco from outer surface & top finished in veneer. The storage under the Counter should be provided with 6" ht. drawers at top row finished with wooden ribs. top of the shutter having C section brass inlay & below openable shutters finished with duco. Shutters made out of 19mm thk. plywood finished with 1mm thk. laminate internally. The shutters to be provided with fittings such as hinges; handles; ball catch etc. complete in all respect. Including castor wheels (4nos) equipped wih 100mm wheels for smoothly running. The rates for the Shutters to be included. as per design and details. | NEAR LIVE KITCHEN | 3895mm L X 500mmW X 900H | NOS. | 1 | 135000 | 135000 |  |  |  | -135000
Plywood - branded Commercial Ply (MR Calibrated, IS 303) -- Greenply or Equivalent brand
Veneer Make - Euro/Greenlam/Merino/ or equivalent (Basic Rate- 140 Sq. ft.)
Laminate Make - Euro/Greenlam/Merino/ or equivalent (Basic Rate- 40 Sq. ft.)
3 | MS Display Unit_01 | P/F Display unit having 20 x 20mm MS framework with black powder coat upto ceiling height, having wooden shelf @ every 350mm c/c including all necessary hardware etc. complete. 20mm thk sandwitched glass shelf with cane in center and with wooden frame. Plywood - branded fire rated Ply (MR Calibrated, IS 303) -- Greenply or Equivalent brand Veneer Make - Euro/Greenlam/Merino/ or equivalent (Basic Rate- 140 Sq. ft.) Laminate Make - Euro/Greenlam/Merino/ or equivalent (Basic Rate- 40 Sq. ft.) 20X20mm MS section finish with black powder coat 20mm thk sandwiched glass shelf with cane in center and with veneer finish frame | NEAR ENTRANCE | 1060mm L X 200mm W X 5000H | NOS. | 1 | 50000 | 50000 | 1 | 50000 | 50000 | 0 | [6 empty] | 1 | 50000 | 50000
|  | 20mm thk sandwiched glass shelf with cane in center and with veneer finish frame |  | 500mm x 200mm |  | 6 | 3500 | 21000 | 6 | 4500 | 27000 | 6000 |  |  | Why rate escalation on account of qty increase | Material changed to fire rated Rates Revised | give the breakup only for differennce between commercial ply and fire rated plywood. The finishing material is not changing. | Rates Revised 20%-Cost escalation on acccount of increment of material from for Material changed Commercial to Fire Rated Ply | 6 | 4500 | 27000
4 | MS Display Unit_02 | P/F Display unit having 20 x 20mm MS framework with black powder coat upto ceiling height, having wooden shelf @ every 350mm c/c including all necessary hardware etc. complete. 20mm thk sandwitched glass shelf with cane in center and with veneer finish frame | BEHIND BANQUETE SEATING | 1580mm L X 200mm W X 5000H | NOS. | 2 | 75000 | 150000 | 2 | 75000 | 150000 | 0 | [6 empty] | 2 | 75000 | 150000
|  | Plywood - branded firerated Ply (MR Calibrated, IS 303) -- Greenply or Equivalent brand | [5 empty] | 0 |  |  | 0
|  | Veneer Make - Euro/Greenlam/Merino/ or equivalent (Basic Rate- 140 Sq. ft.) | [5 empty] | 0 |  |  | 0
|  | Laminate Make - Euro/Greenlam/Merino/ or equivalent (Basic Rate- 40 Sq. ft.) | [5 empty] | 0 |  |  | 0
20X20mm MS section finish with black powder coat
|  | 20mm thk sandwiched glass shelf with cane in center and with veneer finish frame |  | 500mm x 200mm |  | 18 | 3500 | 63000 | 18 | 4500 | 81000 | 18000 |  |  | Why rate escalation on account of qty increase | Material changed to fire rated Rates Revised | give the breakup only for differennce between commercial ply and fire rated plywood. The finishing material is not changing. |  | 18 | 4500 | 81000
5 | Hostess Desk | Providing and fixing Hostess desk made out of approved make branded fire rated ply -- Greenply or Equivalent brand and finished with veneer as approved with veneer groves as per design with melamine matt polish 20X20mm MS section finish with black powder coated legs. with ss 3mm thick pvd coated 'CC' Logo |  | 1050mm L X 500mm W X 1050 H | NOS. | 1 | 35000 | 35000 | 1 | 42000 | 42000 | 7000 |  |  | 33% rate escalation on account of material change from commercial to fire rated ply not justified | Rates Revised | give the breakup only for differennce between commercial ply and fire rated plywood. The finishing material is not changing. | Rates Revised 20%-Cost escalation on acccount of increment of material from for Material changed Commercial to Fire Rated Ply | 1 | 42000 | 42000
|  | Desk to have 2 drawers of ht 155mm, finished with duco outside and veneer maching laminate inside with inbuilt recessed handles in wood and polish. | [5 empty] | 0 |  |  | 0
|  | Basic cost of Veneer : 140/- SFT | [5 empty] | 0 |  |  | 0
6 | Banquet back planter Box | Providing and fixing of 19mm thk fire rated Ply-- Greenply or Equivalent brand apron to be cladded with Veneer/Solid Wood all necessary required groove, wooden framing, approved make adhesive and cutting/ chamfering/ groove/rounding wherever required, at all height with lead and lift, finishing, cleaning as per design and drawing etc. all complete. |  | 9145x 300 x 900 HT | NOS. | 1 | 65000 | 65000 | 1 | 78000 | 78000 | 13000 |  |  | 33% rate escalation on account of material change from commercial to fire rated ply not justified | Rates Revised | give the breakup only for differennce between commercial ply and fire rated plywood. The finishing material is not changing. | Rates Revised 20%-Cost escalation on acccount of increment of material from for Material changed Commercial to Fire Rated Ply | 1 | 78000 | 78000
7 | Banquet Seating | Providing, making and fixing sofa made out of wooden frame work and cladded with 12mm thk approved make branded fire rated Ply -- Greenply or Equivalent brand & approved fabric with required wooden frame, top rail having 38mm dia brass metal rail height upto 150mm and side to have a cane paneling with required wooden frame with incline backrest. the bottom to have storage under seat with heavy duty sliding trolly to keep crockey. finishing/cleaning/cutting/required fixture & fasteners etc. as per design & drawing & as directed by Project Manager etc. complete. Sofa will have high density rubber foam in angle.(Foam used should be approved and to be certified against poisonous and noxious fumes.) Rate includes upholstery of fabrics. Under seating Drawers with heavy duty trolley for storage. |  | 9145x 650 x 900 HT | NOS. | 2 | 115000 | 230000 | 2 | 195000 | 390000 | 160000 |  |  | 12,900/Rft for sofa is to high rate suggest the rate to be maintained to 9500/Rft in line with Air side | Rate for Revised Benquet Seating to 9500/- Rft Length 9.145 x 3.28 x 29.99 Rft 30 Rft x 9500/- = 2,85.000/- Per Nos | no change in design why the cost going too high. Only the plywood chnages to fire rated ply. give the breakup only for differennce between commercial ply and fire rated plywood. The finishing material is not changing. | - Rate revised 6500/- Per Rft added for Material changed Commercial to Fire Rated Ply + 38mm Dia brass top Rail add + Heavy duty sliding trolly storge added | 2 | 195000 | 390000
Veneer on exterior finish Basic cost @ 140Rs sft
Fabric Basic cost @ 600 per MTR
Size : W 650 x H 900
38mm dia brass top rail
Heavy duty sliding trolly for storage
8 | Cane Panel Shutter | P/F 75mm thk fire rated plywood partition finished with bamboo Cane from Single side, internal ply finished with laminate. structure to be made out of 40x20mm thk wooden frame with 12mm ply on both side, intermidiate member size of 40 x 20mm wooden frame/ bidding to be finished with melamine polish. to be finished with duco paint finish with necessary fittings as per design and details. | STORY WALL | 1200 x 2000 (H) | SQFT | 45 | 1100 | 49500 | 50 | 1650 | 82500 | 33000 | [6 empty] | 36 | 1650 | 59400
|  | Plywood - branded firerated Ply (MR Calibrated, IS 303) -- Greenply or Equivalent brand |  |  | NOS. | 1 | 8000 | 8000 | 1 | 12000 | 12000 | 4000 | [6 empty] | 1 | 12000 | 12000
9 | Cane Panelling | P/F 75mm thk firerated plywood paneling finished with bamboo Cane from Single side, internal ply finished with laminate. structure to be made out of 40x20mm thk wooden frame with 12mm ply on both side, intermidiate member size of 40 x 20mm wooden frame/ bidding to be finished with melamine polish. to be finished with duco paint finish with necessary fittings as per design and details. | ABOVE BUFFET COUNTER, KITCHEN DOOR, ABOVE SHAFT DOOR, CURTAIN WALL, WALLPAPER WALL |  | SQFT | 190 | 1100 | 209000 | 500 | 1250 | 625000 | 416000 |  |  | Approved as per rate analysis | Rate Analyisis attached in separte sheet | ok |  | 612.6875 | 1250 | 765859.375
Plywood - branded fire rated Ply (MR Calibrated, IS 303) -- Greenply or Equivalent brand
10 | Wall dado - Veneer panelling | Providing, making and fixing of wall panel made of 12mm thk branded fire rated Ply -- Greenply or Equivalent brand with Veneer finish with melamine polish having wooden molding all necessary required wooden framing, approved make adhesive and fasteners, cutting/ chamfering/ groove/rounding wherever required, at all height with lead and lift, finishing, cleaning as per design and drawing etc. all complete. | ALL WALLS | upto 900mm ht | SFT | 370 | 900 | 333000 | 370 | 1000 | 370000 | 37000 |  |  | There is no change in specs for this item so no escalation to be paid | Material changed to fire rated Rates Revised | give the breakup only for differennce between commercial ply and fire rated plywood. The finishing material is not changing. | Rates Revised 20%-Cost escalation on acccount of increment of material from for Material changed Commercial to Fire Rated Ply | 444.5 | 1000 | 444500
|  | Basic Rate of Veneer @ 120 Rs per SFT | [5 empty] | 0 |  |  | 0
11 | Moulding | Providing, making and fixing of \wooden mouldings as per detail drawing with grooves to be added with all necessary required wooden framing, approved make adhesive and fasteners, cutting/ chamfering/ groove/rounding wherever required, at all height with lead and lift, finishing, cleaning as per design and drawing etc. all complete. |  | upto 900mm ht | SFT | 370 | 350 | 129500 | 370 | 350 | 129500 | 0 | [6 empty] | 368.565 | 350 | 128997.75
12 | Ply boxing with Veneer finish on shaft | Providing, making and fixing fire rated ply boxing made out of wooden/ aluminium frame work and cladded with 12mm thk approved make branded fire rated Ply (MR Calibrated, IS 303) -- Greenply or Equivalent brand finished with veneer from all side and top finished with veneer with melamine polish, with one openable shutter on push button. all with required frame finishing/cleaning/cutting/required fixture & fasteners etc. as per design & drawing & as directed by Project Manager etc. complete. |  |  | Sqft | 160 | 650 | 104000 | 180 | 650 | 117000 | 13000 | [6 empty] | 56 | 650 | 36400
Basic Rate of Veneer @ 120 Rs per SFT
13 | Storage Cabinet - with bamboo cane shutter | P/F louver shutter with fire rated plywood framework finished with veneer as per design & detail made in wood with openable shutters with bamboo cane paneling back side of the cane to be finished with laminate. Including all necessary required wooden framing, approved make adhesive and fasteners, Lock, cutting/ chamfering/ groove/rounding wherever required, at all height with lead and lift, finishing, cleaning as per design and drawing etc. all complete. | ELECTRICAL PANEL | 1200 x 2600 (H) | NO. | 1 | 75000 | 75000 | 1 | 115000 | 115000 | 40000 |  |  | Rates approved as material changed to fire rated |  |  |  | 2 | 115000 | 230000
Basic rate of Veneer @ 120 Rs per SFT
Basic rate of laminate @ 50 Rs per SFT
12 | Ply boxing with leather finish granite panelling on façade column | Providing, making and fixing ply boxing made out of wooden/ aluminium frame work and cladded with 12mm thk approved make branded Commercial Ply (MR Calibrated, IS 303) -- Greenply or Equivalent brand finished with 18mm thk leather finish granite. all with required frame finishing/cleaning/cutting/required fixture & fasteners etc. as per design & drawing & as directed by Project Manager etc. complete. |  |  | Sqft | 100 | 1200 | 120000 |  |  |  | -120000
14 | signage bulkhead Ply boxing with leather finish granite panelling on façade | Providing, making and fixing fire rated ply boxing made out of wooden/ aluminium frame work and cladded with 12mm thk approved make branded fire rated Ply (MR Calibrated, IS 303) -- Greenply or Equivalent brand finished with 18mm thk leather finish granite. all with required frame finishing/cleaning/cutting/required fixture & fasteners etc. as per design & drawing & as directed by Project Manager etc. complete. |  |  | Sqft | 100 | 750 | 75000 | 100 | 1450 | 145000 | 70000 |  |  | Ther rate difference between commercial ply & fire rated ply of Rs 50/Sq Ft to be payable whereas actual claim amount is 100% higher | Rate Analysis Attached same as per Items No 29 | give the breakup only for differennce between commercial ply and fire rated plywood. The finishing material is not changing. | Rate Analysis already attached We have not received Sinage Bulkhead drawing at the time of Tender submission | 93.1875 | 1450 | 135121.875
15 | Planter Box above Banquete | Providing and fixing M.S frame stand made out of 20mm x 20mm hollow box sections with 19mm thk approved make branded fire rated Ply-- Greenply or Equivalent brand apron to be cladded with Veneer/Solid Wood all necessary required groove, wooden framing, approved make adhesive and cutting/ chamfering/ groove/rounding wherever required, at all height with lead and lift, finishing, cleaning as per design and drawing etc. all complete. |  | 9145x 3100 x 300 HT | NOS. | 1 | 55000 | 55000 | 1 | 85000 | 85000 | 30000 |  |  | Approved |  |  |  | 1 | 85000 | 85000
16 | Bar Counter | P/F Bar counter to be made out of 19mm thk approved make branded fire rated ply-- Greenply or Equivalent brand apron to be cladded with wood & bamboo cane as per detail and platform in white Marble finished based on ply with necessary ms barcket, Necessary opening should be made for fixing of stainless steel sink. Erecting brick wall for plumbing and Brick platform should be provided on floor below the platform of 100mm high brass skirting from outside. The top platform to have 50mm wide Marble finish fascia horizontally. |  | 2925x 450mm
Plywood - branded fire rated Ply-- Greenply or Equivalent brand
Marble Basic Rate 800/- per SQ.FT.
Veneer Make - Euro/Greenlam/Merino/ or equivalent (Basic Rate- 140 Sq. ft.)
| a | Top service Counter Ply Base with Neccesory Support to receved marble |  | 450mm Width | RFT | 25 | 750 | 18750 | 25 | 1200 | 30000 | 11250 |  |  | Approved |  |  |  | 10.25 | 1200 | 12300
| b | Front Elevation (apron) to be to be made out of 19mm thk approved make branded fire rated Ply) -- Greenply or Equivalent brand with veneer finish frames, ply to be finished with duco and veneer frames to be finished with melamine polish. Top row finished with metal cane and 100mm skirting with veneer as per detailed Drawing & design. Provision for indirect lighting to be made |  |  | SFT | 45 | 1200 | 54000 | 45 | 1800 | 81000 | 27000 |  |  | Approved |  |  |  | 38.4375 | 1800 | 69187.5
| c | 50mm thk Top service platform in Marble |  | 450mm Width | RFT | 25 | 1200 | 30000 | 25 | 1200 | 30000 | 0 | [6 empty] | 10.25 | 1200 | 12300
| d | 38mm Dia Foot rest real brass antique finish at the bottom. |  |  | RFT | 25 | 2000 | 50000 | 25 | 2500 | 62500 | 12500 |  |  | Approved |  |  |  | 0 | 2500 | 0
| e | 750mm Flap door for bar area entry finished same as counter appron |  | 750x 1100mm | Nos | 1 | 5000 | 5000 | 1 | 5000 | 5000 | 0 | [7 empty] | 5000 | 0
| f | 100mm high Wooden Skirting |  |  | RFT | 25 | 450 | 11250 | 25 | 450 | 11250 | 0 | [6 empty] | 0 | 450 | 0
| g | P/F 75mm thk fire rated plywood partition finished with bamboo closed cane matting , internal ply finished with laminate. structure to be made out of 40x20mm thk wooden frame with 12mm ply on both side, intermidiate member size of 40 x 20mm wooden frame/ bidding to be finished with melamine polish. to be finished with duco paint finish with necessary fittings as per design and details. |  |  | SFT | 50 | 950 | 47500 | 50 | 1250 | 62500 | 15000 |  |  | Ther rate difference between commercial ply & fire rated ply of Rs 100/Sq Ft to be payable whereas actual claim amount is 100% higher | Rate revised 1250/- Per sqft same Item No 09 Cane Panlling Rate Considered | give the breakup only for differennce between commercial ply and fire rated plywood. The finishing material is not changing. | Rate Anlysis attached | 0 | 1250 | 0
| f | Plywood - branded fire rated Ply-- Greenply or Equivalent brand | [16 empty] | 0 | 0 | 0
17 | Bar Display unit | P/F 350mm deep Bar display unit to be made out of 19mm thk approved make branded fire rated Ply -- Greenply or Equivalent brand with veneer finish, having brass shelf @ every 400mm c/c. The Backdrop made out of 12mm thk approved make branded fire rated Ply -- Greenply or Equivalent brand with finished with bronze mirror, front panelling to be veneer finsh. The shelves to be provided with necessary fittings etc. complete in all respect. The rates for shelves to be included. as per design and details. |  | 2925x 2000mm | SFT | 11 | 9000 | 99000 | 60 | 2500 | 150000 | 51000 |  |  | Approved | ok |  |  | 53.0625 | 2500 | 132656.25
Plywood - branded fire rated Ply (MR Calibrated, IS 303) -- Greenply or Equivalent brand
Marble Basic Rate 600/- per SQ.FT.
Veneer Make - Euro/Greenlam/Merino/ or equivalent (Basic Rate- 140 Sq. ft.)
Laminate Make - Euro/Greenlam/Merino/ or equivalent (Basic Rate- 40 Sq. ft.)
| a | Mirror Panelling |  |  | SFT | 30 | 850 | 25500 | 30 | 850 | 25500 | 0 | [6 empty] | 22.5 | 850 | 19125
| b | brass shelves |  | 900mm X300mm | no. | 5 | 10000 | 50000 | 5 | 10000 | 50000 | 0 | [6 empty] | 4 | 10000 | 40000
| c | brass patti |  |  | Rft | 50 | 750 | 37500 | 50 | 750 | 37500 | 0 | [6 empty] | 15 | 750 | 11250
| d | Veneer Cladding |  |  | Sqft | 75 | 1300 | 97500 | 75 | 1300 | 97500 | 0 | [6 empty] | 12 | 1300 | 15600
18 | Bar Counter Back | P&F of back counter of 600mm wide granite top working back counter, with 19mm thick fire rated plywood structure & 12mm plywood back, counter having 4 nos. of open able shutters (in 19mm thick plywood) on front side of the unit. Counter top to be finished with 19mm thick black galaxy granite with 38mm dual nose finished, counter front part, & all the visible part to be finished with 1mm thick wooden laminate, counter's internal part to be finished with 1mm thick light walnut laminate (selected make, basic cost INR. 1200.00/ sheet). Rate inclusive of all necessary hardware fittings - like hinges, draw telescopic channels, cup board lock, decorative antique bolt handle, wire managers, etc. (approved & branded make) & necessary cut out for services requirements. Counter having 50mm ht. 18 mm thick flamed granite skirting on front side on existing 150mm ht. kobah. Complete as per architectural detail drawing & site engineer's instruction. |  | 2925x 600mm | Rft | 11 | 5600 | 61600 | 11 | 8500 | 93500 | 31900 |  |  | Approved | ok |  |  | 8.5 | 8500 | 72250
19 | Bar Bulkhead | P&F of 350mm wide Bar Bulkhead/ glass hanger having 25mm X 25MM brass metal/ SS PVD COATING box section in 2 layers having vertical and horizontal member @every 450mm c/c with 10mm thk toughthned glass shelf having provision for led profile light. brass metal to be brushed finish. the base including 8-10mm solid rods band in curve shape to hang the wine glass. the top portion to have 6-8mm thk flutted glass palnelling. Rate including all necessary hardware fittings to install the shelves, anchor fastner, ceiling support, scaffolding, etc. as required on site. Complete as per architectural detail drawing & site engineer's instruction. |  | 2925x 350mm | Rft | 11 | 5600 | 61600 | 11 | 15000 | 165000 | 103400 |  |  | contractore submit rae analysis for this item, contractors justifcation on rate escalation not accepted hence old rates to be maintained | Rate Analysis attached | no changes in design and specification | Rate Analysis attached We have not received Bulkhead drawing at the time of Tender submission | 11 | 15000 | 165000
20 | Buffet Counter_01 | 12mm fire rated ply box structure, wooden 6" high, 2" to 1" dia legs as per drawing finished in approved polish Top made out of fire rated plywood and finished in marble top with mitred Buffet counter to have cutouts on couner top for chaffing dishes as per measurements. Structure to have base boxing to place chaffing dishes which with be finished with veneer as approved ( slot size 300mm x 300mmx 80mm ) Buffet front to have niches in front finished in veneer,polish as approved. Niche to have shelf finished in veneer and polish as per design detail Buffet front to have shutters in fire rated plywood, veneer and rattan mesh screen in beading finished in polish as approved as per design detail Provision of wiremanager slot and trunking as per design |  | 4185 (L) x 600 (D) x 750mm (H) | Rft | 14 | 9900 | 138600 | 14 | 15000 | 210000 | 71400 |  |  | Approved based upon historic rates paid at Airside | ok | ok |  | 14 | 15000 | 210000
Marble Basic Rate 600/- per SQ.FT.
Veneer Make - Euro/Greenlam/Merino/ or equivalent (Basic Rate- 140 Sq. ft.)
Laminate Make - Euro/Greenlam/Merino/ or equivalent (Basic Rate- 40 Sq. ft.)
21 | Buffet Counter_02 | 12mm fire rated ply box structure, wooden 6" high, 2" to 1" dia legs as per drawing finished in approved polish Top made out of fire rated plywood and finished in marble top with mitred Buffet counter to have cutouts on couner top for chaffing dishes as per measurements. Structure to have base boxing to place chaffing dishes which with be finished with veneer as approved ( slot size 300mm x 300mmx 80mm ) Buffet front to have niches in front finished in veneer,polish as approved. Niche to have shelf finished in veneer and polish as per design detail Buffet front to have shutters in fire rated plywood, veneer and rattan mesh screen in beading finished in polish as approved as per design detail Provision of wiremanager slot and trunking as per design |  | 1575 (L) x 600 (D) x 750mm (H) | Rft | 6 | 9900 | 59400 | 6 | 15000 | 90000 | 30600 |  |  | Approved based upon historic rates paid at Airside | ok | ok |  | 5 | 15000 | 75000
Marble Basic Rate 600/- per SQ.FT.
Veneer Make - Euro/Greenlam/Merino/ or equivalent (Basic Rate- 140 Sq. ft.)
Laminate Make - Euro/Greenlam/Merino/ or equivalent (Basic Rate- 40 Sq. ft.)
22 | Buffet Counter_03 | 12mm fire rated ply box structure, wooden 6" high, 2" to 1" dia legs as per drawing finished in approved polish Top made out of fire rated plywood and finished in marble top with mitred Buffet counter to have cutouts on couner top for chaffing dishes as per measurements. Structure to have base boxing to place chaffing dishes which with be finished with veneer as approved ( slot size 300mm x 300mmx 80mm ) Buffet front to have niches in front finished in veneer,polish as approved. Niche to have shelf finished in veneer and polish as per design detail Buffet front to have shutters in fire rated plywood, veneer and rattan mesh screen in beading finished in polish as approved as per design detail Provision of wiremanager slot and trunking as per design |  | 2100 (L) x 600 (D) x 750mm (H) | Rft | 7 | 9900 | 69300 | 7 | 15000 | 105000 | 35700 |  |  | Approved based upon historic rates paid at Airside | ok | ok |  | 7 | 15000 | 105000
Marble Basic Rate 600/- per SQ.FT.
Veneer Make - Euro/Greenlam/Merino/ or equivalent (Basic Rate- 140 Sq. ft.)
Laminate Make - Euro/Greenlam/Merino/ or equivalent (Basic Rate- 40 Sq. ft.)
18 | Bison board/ V board panelling | Providing, making and fixing of wall panelling made of 12mm thk branded bison board/ V board paneling on wall including ALU framework finish with all necessary required framing, approved make adhesive and fasteners, cutting/ chamfering/ groove/rounding wherever required, at all height with lead and lift, finishing, cleaning as per design and drawing etc. all complete. | KITCHEN WINDOW | 3900x 3500mm | SFT | 180 | 550 | 99000 |  |  |  | -99000
23 | Entry Glass Partition | P/F 10 mm thk. toughened glass partitions with 20 x 40mm MS framework with white/ black powder coating and all necessary required groove, wooden framing, with approved make adhesive and fasteners, cutting/ chamfering/ groove/rounding wherever required, at all height with lead and lift, finishing, cleaning as per design and drawing etc. all complete. Providing, making and fixing of wall panel made of 12mm thk fire rated ply -- Greenply or Equivalent brand with MDF finish with Duco paint and wooden molding as per design, all necessary required wooden framing, approved make adhesive and fasteners, cutting/ chamfering/ groove/rounding wherever required, at all height with lead and lift, finishing, cleaning as per design and drawing etc. all complete. skirting in metal, brass finish (same as main door handle) | ENTRANCE | 7700x 3500mm | SFT | 300 | 950 | 285000 | 300 | 950 | 285000 | 0 |  |  | There is no spec change thus rate escalation should not be paid | Material changed to fire rated Rates Revised | give the breakup only for differennce between commercial ply and fire rated plywood. The finishing material is not changing. | Rates Revised 20%-Cost escalation on acccount of increment of material from for Material changed Commercial to Fire Rated Ply | 197.4375 | 950 | 187565.625
24 | Main Door Handle | Providing, Supplying & fixing of double sided 3mm thk Sign handle in brass | ENTRANCE | 450mm x 450mm | NOS | 1 | 7500 | 7500 | 1 | 7500 | 7500 | 0 | [6 empty] | 0 | 7500 | 0
TOTAL CARPENTRY WORK | [7 empty] | 2981000 |  |  | 4241750 | [9 empty] | 3986513.375
ADDITIONAL ITEMS
6 | Liquor Store Room Door | Providing & fixing in position of FRD Glass Single Leaf Door made up of 45mm thick commercial flush door shutter of approved make & thickness, Inner side finished with laminate and outer side with veneer finish including providing & fixing 750mm X 200mm glass Vision panel and 12mm thk Wooden lipping all around, including of 750mm X 200mm SS push plate and 200mm high SS kick plate, including P/F of Door frame made out of CP Teak / Ash wood or equivalent with melamine polish finish. Size of the frame approximate 175mm wide X 50mm thick. Applicable hardware's such as s/s handles, conceal door closer and any other hardware etc required to complete the related works as per design & detail. door hardware make consider Dorma / Hafele/Ozon /equilient | NOS. | [5 empty] | 1 | 30000 | 30000 | 30000 |  |  | Rates are approved | ok |  |  | 1 | 30000 | 30000
2 | CONSOLE | P/F service counters in duco finished from outer surface & top finished in veneer. The storage under the Counter should be provided with 6" ht. drawers at top row finished with wooden ribs. top of the shutter having C section brass inlay & below openable shutters finished with duco. the drawer should have internal partiton with fabric finish for cutlary Shutters made out of 19mm thk. firerated plywood finished with 1mm thk. laminate internally. The shutters to be provided with fittings such as hinges; handles; ball catch, locks etc. complete in all respect. The rates for the Shutters to be included. as per design and details. any 1drawer (in each service station) should have 3compartment made in ply finished with fabric for cutlery and bottom storage should have 1shelf for crockery, shelf in ply finished with white laminate | NEAR BANQUETTE | 1540mm L X 500mmW X 900H | NOS. |  |  |  | 2 | 60000 | 120000 | 120000 |  |  | Addiitional service counter rates approved |  |  |  | 2 | 60000 | 120000
Plywood - branded fire rated Ply (MR Calibrated, IS 303) -- Greenply or Equivalent brand
Veneer Make - Euro/Greenlam/Merino/ or equivalent (Basic Rate- 140 Sq. ft.)
Laminate Make - Euro/Greenlam/Merino/ or equivalent (Basic Rate- 40 Sq. ft.)
25 | Bench Seating | Wooden bench with cane back rest & 25mm wooden framework base with 75mm cousion seat (branded form) approved shade of fabric including 4 number pillow. | WAITING AREA | 2700 x 550mm | NOS |  |  | 0 | 1 | 20000 | 20000 | 20000 | [6 empty] | 0 | 20000 | 0
26 | Bison board/ v- board Paneling | Providing, making and fixing of wall paneling made of 12mm thk branded bison board/ V board paneling on wall including MS framework from slab to slab height of 5000mm. framework to be finished with zink oxide and enamel finish with all necessary required framing, approved make adhesive and fasteners, cutting/ chamfering/ groove/rounding wherever required, at all height with lead and lift, finishing, cleaning as per design and drawing etc. all complete. | All walls | 75mm (thick) 5000mm (height) | SFT |  |  | 0 | 2000 | 479 | 958000 | 958000 |  | MS Pipe 50 x 50 x 02 at 600mm C/c finish with one layer 12mm Fire rated Ply + 12mm Fire rated Gypsum | Approved | ok | ok |  | 1730.5 | 479 | 828909.5
27 | MS framework for curtain wall | P/F of 20 x 20mm MS framework with black powder coat upto ceiling height, having intermediate memebr @ every 900mm c/c including all necessary hardware etc. complete. |  |  | SFT |  |  |  | 1750 | 140.3284 | 245574.7386 | 245574.7386 |  | We have chaged unit from Rft to Sqft | Units should be proposed in Kg | In Kg unit is not workable price | you give the rate analysis for binu to approvae | Rate Anylisis Attached | 1232.775 | 140.3284 | 172993.3705
28 | SS PVD COATING framework for wallpaper | P/F of 20 x 20mm ss brass pvd coating framework upto ceiling height, having intermediate memebr @ every 900mm c/c including all necessary hardware etc. complete. |  |  | SFT |  |  |  | 3300 | 100 | 330000 | 330000 |  |  | Rates approved | ok |  |  |  | 100 | 0
29 | FAÇADE granite bulkhead | Providing, making and fixing of bulkhead 600mm box paneling made of 12mm thk branded bison board/ V board paneling on wall including MS framework from slab. framework to be finished with zink oxide and enamel finish. the boxing to be finisged with black leather finish granite with granite molding in levels as per detail drawing. having required holes to fix the signage letter. cost inlcudes all necessary required framing, approved make adhesive and fasteners, cutting/ chamfering/ groove/rounding wherever required, at all height with lead and lift, finishing, cleaning as per design and drawing etc. all complete. |  |  | SFT |  |  |  | 55 | 1450 | 79750 | 79750 |  |  | Proposed rate 342, attachment missing | Rate Analyisis attached |  |  |  | 1450 | 0
30 | Glass PARTITION on live kitchen | P/F 10 mm thk.fire rated glass partitions with 20 x 40mm MS framework with white/ black powder coating and all necessary required groove, wooden framing, with approved make adhesive and fasteners, cutting/ chamfering/ groove/rounding wherever required, at all height with lead and lift, finishing, cleaning as per design and drawing etc. all complete. | Live kitchen |  | SFT |  |  |  | 60 | 4500 | 270000 | 270000 |  | Saint Goabain FRD Glass with Partion full system price quoted | Check with ARA vishal cinema we had done 560/ Sq ft glass partition why this is required? |  | this is a mall requirement, we have to submit the fire safety certificate to mall team. |  | 108.5 | 4500 | 488250
31 | flutted Glass PARTITION on live kitchen | P/F 8 mm thk. flutted glass partitions with 20 x 40mm MS framework with white/ black powder coating and all necessary required groove, wooden framing, with approved make adhesive and fasteners, cutting/ chamfering/ groove/rounding wherever required, at all height with lead and lift, finishing, cleaning as per design and drawing etc. all complete. | Live kitchen |  | SFT |  |  |  | 45 | 4500 | 202500 | 202500 |  | Spectfication same as per ITEM No 30 | Check with ARA vishal cinema we had done 560/ Sq ft glass partition why this is required? |  | this is a mall requirement, we have to submit the fire safety certificate to mall team. |  | 0 | 4500 | 0
32 | cane screen | P/F of self supported bamboo cane screen having 30mm dia wooden framework with reuqired hinges and wooden frame/ bidding to be finished with melamine polish with necessary fittings as per design and details. | near buffet |  | SFT |  |  |  | 30 | 1550 | 46500 | 46500 |  |  | Proposed rate Rs 1250 | Rates Revised Easty.com site price 36,000/- + 3,900/- Trasportation = Total 39,900 + 7,095/- 20.5% (Shifing Material Ground to 2nd 10% + Overhead 2.5% + Profit 08%) = Grand Total Price = 46,995/- |  |  | 32 | 1550 | 49600
TOTAL CARPENTRY ADDITONAL WORK | [10 empty] | 2302324.7386 | [9 empty] | 1689752.8705
MISCELLANEOUS
1 | Texture wallpaper | P & F of texture wallpaper as per approval |  |  | SFT | 650 | 225 | 146250 | 400 | 200 | 80000 | -66250 | [6 empty] | 219.375 | 200 | 43875
Basic rate- 155/Sq Ft
2 | Ceiling Fans | P & F of ceiling fans paper as per approval |  |  | NOS | 6 | 5000 | 30000 | 6 | 32000 | 192000 | 162000 | [6 empty] | 6 | 32000 | 192000
3 | Bamboo blind curtain on S.S PVD black coating framework / roller blinds | P & F of bamboo blind manual folding curtains as per approval |  |  | SFT | 150 | 250 | 37500 | 200 | 250 | 50000 | 12500 |  |  |  | QTY Variation | lets finalise the mockup first, then close the cost. |  | 206.25 | 250 | 51562.5
TOTAL MISCELLANEOUS | [7 empty] | 213750 |  |  | 322000 | 108250 | [8 empty] | 287437.5

## Interior MS
NO | ITEM | DESCRIPTION | UNIT | No | Length | Width | Height | Total Qty
Interior Civil Works
DOORS
1 | Kitchen door | Providing & fixing in position of wooden FRD Double Leaf Door made up of 45mm thick firerated flush door shutter of approved make & thickness, | Nos
| a | Kitchen door |  | 1 | - | - | - | 1
|  | Total | [5 empty] | 1
2 | Kitchen Door beside buffet | Providing & fixing in position of wooden FRD single Leaf Door made up of 45mm thick firerated flush door shutter of approved make & thickness | Nos
| a | Kitchen door beside buffet |  | 1 | - | - | - | 1
|  | Total | [5 empty] | 1
3 | Live kitchen sliding door | Providing & fixing in position of wooden FRD sliding door made up of 38mm thick firerated flush door shutter of approved make & thickness, both side to be finished with wooden laminate | Nos
| a | Live kitchen sliding door |  | 1 | - | - | - | 1
|  | Total | [5 empty] | 1
5 | Trap door | Providing and fixing trap doors for access to the service areas. The trap door shall have an external frame made of 50mm x 50mm in good quality seasoned wood scantling on which the shutter is hinged. | Nos
| a | Trap door for AHU in Buffet area |  | 1 | - | - | - | 1
|  | Total | [5 empty] | 1
CARPENTRY WORK
1 | Service station | P/F service counters in duco finished from outer surface & top finished in veneer. The storage under the Counter should be provided with 6" ht. drawers at top row finished with wooden ribs. | Nos
| a | Near LHS Column in FOH Area |  | 1 | - | - | - | 1
|  | Near RHS Column in FOH Area |  | 1 | - | - | - | 1
|  | Near kitchen entry |  | 1 | - | - | - | 1
|  | Total | [5 empty] | 3
3 | MS Display Unit_01 | P/F Display unit having 20 x 20mm MS framework with black powder coat upto ceiling height, having wooden shelf @ every 350mm c/c including all necessary hardware etc. complete. | Nos
| a | Near main entry |  | 1 | - | - | - | 1
|  | Total | [5 empty] | 1
|  | 20mm thk sandwiched glass shelf with cane in center and with veneer finish frame |  | 6 | - | - | - | 6
|  | Total | [5 empty] | 6
4 | MS Display Unit_02 | P/F Display unit having 20 x 20mm MS framework with black powder coat upto ceiling height, having wooden shelf @ every 350mm c/c including all necessary hardware etc. complete. | Nos
| a | Above console unit |  | 2 | - | - | - | 2
|  | Total | [5 empty] | 2
|  | 20mm thk sandwiched glass shelf with cane in center and with veneer finish frame |  | 18 | - | - | - | 18
|  | Total | [5 empty] | 18
5 | Hostess Desk | Providing and fixing Hostess desk made out of approved make branded fire rated ply -- Greenply or Equivalent brand and finished with veneer as approved with veneer groves as per design with melamine matt polish | Nos
| a | Near main entry |  | 1 | - | - | - | 1
|  | Total | [5 empty] | 1
6 | Banquet back planter Box | Providing and fixing of 19mm thk fire rated Ply-- Greenply or Equivalent brand apron to be cladded with Veneer | Nos
| a | FOH Area |  | 1 | - | - | - | 1
|  | Total | [5 empty] | 1
7 | Banquet Seating planter Box | Providing, making and fixing sofa made out of wooden frame work and cladded with 12mm thk approved make branded fire rated Ply -- Greenply or Equivalent brand & approved fabric with required wooden frame, top rail having 38mm dia brass metal rail | Nos
| a | FOH Area |  | 2 | - | - | - | 2
|  | Total | [5 empty] | 2
8 | Cane Panel Shutter | P/F 75mm thk fire rated plywood partition finished with bamboo Cane from Single side, internal ply finished with laminate. | Sqft
| a | Electrical & Fire DB |  | 2 | 4 | - | 4.5 | 36
|  | Total | [5 empty] | 36
9 | Cane Panelling | P/F 75mm thk firerated plywood paneling finished with bamboo Cane from Single side, internal ply finished with laminate. | Sqft
| a | Above main entrance |  | 1 | 24.5 | - | 4.75 | 116.375
|  | RHS & LHS DB Boxing |  | 2 | 9.5 | - | 11 | 209
|  | DB Side |  | 1 | 1.25 | - | 11 | 13.75
|  | DB Side |  | 1 | 1.5 | - | 11 | 16.5
|  | Left side vertical panel |  | 7 | 1 | - | 7.5 | 52.5
|  | RHS Wall bottom |  | 4 | 3.75 | - | 1 | 15
|  | RHS Wall top |  | 4 | 3.75 | - | 2.5 | 37.5
|  | RHS Column side top |  | 2 | 1.25 | - | 2.5 | 6.25
|  | RHS Column top |  | 1 | 5.75 | - | 2.5 | 14.375
|  | RHS Column side bottom |  | 2 | 1.25 | - | 1 | 2.5
|  | RHS Column bottom |  | 1 | 5.75 | - | 1 | 5.75
|  | Top paneling next RHS Column |  | 2 | 3.25 | - | 2.5 | 16.25
|  | Bottom paneling next RHS Column |  | 2 | 3.25 | - | 1 | 6.5
|  | Bar counter |  | 1 | 8.25 | - | 1.25 | 10.3125
|  | Bar counter shutter |  | 1 | 2 | - | 1.25 | 2.5
|  | RHS & LHS Paneling above bar counter |  | 2 | 1.5 | - | 8 | 24
|  | Above kitchen door |  | 1 | 4.5 | - | 3.75 | 16.875
|  | Kitchen wall |  | 1 | 12 | - | 2.75 | 33
|  | Shaft paneling |  | 1 | 5 | - | 2.75 | 13.75
|  | Total | [5 empty] | 612.6875
10 | Wall dado - Veneer panelling | Providing, making and fixing of wall panel made of 12mm thk branded fire rated Ply -- Greenply or Equivalent brand with Veneer finish with melamine polish | Sqft
| a | RHS DB paneling |  | 1 | 9 | - | 3 | 27
|  | Above glazing boxing |  | 1 | 0.75 | - | 1.75 | 1.3125
|  | DB Side |  | 1 | 1.25 | - | 3 | 3.75
|  | From DB To center column |  | 1 | 15 | - | 3 | 45
|  | Column side |  | 2 | 1.25 | - | 3 | 7.5
|  | Column |  | 1 | 5.75 | - | 3 | 17.25
|  | column to buffet counter |  | 1 | 6.75 | - | 3 | 20.25
| b | Entrance side behind Screen |  | 1 | 1.75 | - | 9.75 | 17.0625
|  | LHS DB Paneling |  | 1 | 9 | - | 3 | 27
|  | DB Side |  | 1 | 1.5 | - | 3 | 4.5
|  | From DB To center column |  | 1 | 15 | - | 3 | 45
|  | Column side |  | 2 | 1.25 | - | 3 | 7.5
|  | Column |  | 1 | 5.75 | - | 3 | 17.25
|  | From column to bar counter |  | 1 | 19.25 | - | 3 | 57.75
|  | Bar area LHS & Wall |  | 2 | 5.75 | - | 8 | 92
|  | Live kitchen wall |  | 1 | 14.5 | - | 3.75 | 54.375
|  | Total | [5 empty] | 444.5
11 | Moulding | Providing, making and fixing of \wooden mouldings as per detail drawing with grooves to be added with all necessary required wooden framing, | Sqft
| a | RHS DB paneling |  | 1 | 9 | - | 3 | 27
|  | Above glazing boxing |  | 1 | 0.75 | - | 1.67 | 1.2525
|  | DB Side |  | 1 | 1.25 | - | 3 | 3.75
|  | From DB To center column |  | 1 | 15 | - | 3 | 45
|  | Column side |  | 2 | 1.25 | - | 3 | 7.5
|  | Column |  | 1 | 5.75 | - | 3 | 17.25
|  | column to buffet counter |  | 1 | 6.5 | - | 3 | 19.5
| b | Entrance side behind Screen |  | 1 | 1.75 | - | 9.75 | 17.0625
|  | LHS DB Paneling |  | 1 | 9 | - | 3 | 27
|  | DB Side |  | 1 | 1.5 | - | 3 | 4.5
|  | From DB To center column |  | 1 | 15 | - | 3 | 45
|  | Column side |  | 2 | 1.25 | - | 3 | 7.5
|  | Column |  | 1 | 5.75 | - | 3 | 17.25
|  | From column to bar counter |  | 1 | 19.25 | - | 3 | 57.75
|  | Entrance façade LHS boxing |  | 2 | 10.5 | - | 1 | 21
|  | Entrance façade RHS boxing |  | 2 | 9.75 | - | 1 | 19.5
|  | Bar counter wall |  | 1 | 10.25 | - | 3 | 30.75
|  | Total | [5 empty] | 368.565
12 | Ply boxing with Veneer finish on shaft | Providing, making and fixing of wall panel made of 12mm thk branded fire rated Ply -- Greenply or Equivalent brand with Veneer finish with melamine polish | Sqft
|  | Shaft side |  | 1 | 2 | - | 8 | 16
|  | Shaft front side |  | 1 | 5 | - | 8 | 40
|  | Total | [5 empty] | 56
13 | Storage Cabinet - with bamboo cane shutter | P/F louver shutter with fire rated plywood framework finished with veneer as per design & detail made in wood with openable shutters with bamboo cane paneling back side of the cane to be finished with laminate. | Nos
|  | Electrical panel |  | 1 | - | - | - | 1
|  | Electrical DB |  | 1 | - | - | - | 1
|  | Total | [5 empty] | 2
14 | signage bulkhead Ply boxing with leather finish granite panelling on façade | Providing, making and fixing fire rated ply boxing made out of wooden/ aluminium frame work and cladded with 12mm thk approved make branded fire rated Ply | Sqft
|  | Entrance side top |  | 1 | 27 | - | 3 | 81
|  | Entrance side vertical |  | 1 | 1.25 | - | 9.75 | 12.1875
|  | Total | [5 empty] | 93.1875
15 | Planter Box above Banquete | Providing and fixing M.S frame stand made out of 20mm x 20mm hollow box sections with 19mm thk approved make branded fire rated Ply-- Greenply or Equivalent brand apron to be cladded with Veneer | Nos
|  | Planter box in FOH Area |  | 1 | - | - | - | 1
|  | Total | [5 empty] | 1
16 | Bar counter | P/F Bar counter to be made out of 19mm thk approved make branded fire rated ply-- Greenply or Equivalent brand apron to be cladded with wood & bamboo cane as per detail and platform in white Marble finished based on ply with necessary ms barcket
| a | Top service Counter Ply Base with Neccesory Support to receved marble | Sqft | 1 | 10.25 | - | - | 10.25
|  | Total | [5 empty] | 10.25
| b | Front Elevation (apron) to be to be made out of 19mm thk approved make branded fire rated Ply) | Sqft | 1 | 10.25 | - | 3.75 | 38.4375
|  | Total | [5 empty] | 38.4375
17 | Bar Display unit | P/F 350mm deep Bar display unit to be made out of 19mm thk approved make branded fire rated Ply -- Greenply or Equivalent brand with veneer finish, having brass shelf
|  | Back side boxing | Sqft | 1 | 10.25 | - | 8 | 82
|  | Less niche |  | -1 | 4.3 | - | 5 | -21.5
|  | Less door |  | -1 | 1.75 | - | 4.25 | -7.4375
|  | Total | [5 empty] | 53.0625
| a | Mirror paneling | Sqft | 1 | 4.5 | - | 5 | 22.5
|  | Total | [5 empty] | 22.5
| b | Brass shelf | Nos | 4 | - | - | - | 4
|  | Total | [5 empty] | 4
| c | Brass patti | Rft | 2 | 4.5 | - | - | 9
|  |  |  | 1 | 6 | - | - | 6
|  | Total | [5 empty] | 15
| d | Veneer cladding | Sqft | 1 | 12 | 1 | - | 12
|  | Total | [5 empty] | 12
18 | Bar back counter | P&F of back counter of 600mm wide granite top working back counter, with 19mm thick fire rated plywood structure
|  | Counter | Rft | 1 | 8.5 | - | - | 8.5
|  | Total | [5 empty] | 8.5
19 | Bar bulk head | P&F of 350mm wide Bar Bulkhead/ glass hanger having 25mm X 25MM brass metal/ SS PVD COATING box section in 2 layers having vertical and horizontal member @every 450mm c/c with 10mm thk toughthned glass
|  | Bar bulk head | Rft | 1 | 11 | - | - | 11
|  | Total | [5 empty] | 11
20 | Buffet Counter_01 | 12mm fire rated ply box structure, wooden 6" high, 2" to 1" dia legs as per drawing finished in approved polish Top made out of fire rated plywood and finished in marble top
|  | Buffet counter | Rft | 1 | 14 | - | - | 14
|  | Total | [5 empty] | 14
21 | Buffet Counter_02 | 12mm fire rated ply box structure, wooden 6" high, 2" to 1" dia legs as per drawing finished in approved polish Top made out of fire rated plywood and finished in marble top
|  | Buffet counter | Rft | 1 | 5 | - | - | 5
|  | Total | [5 empty] | 5
22 | Buffet Counter_03 | 12mm fire rated ply box structure, wooden 6" high, 2" to 1" dia legs as per drawing finished in approved polish Top made out of fire rated plywood and finished in marble top
|  | Buffet counter | Rft | 1 | 7 | - | - | 7
|  | Total | [5 empty] | 7
23 | Entry Glass Partition | P/F 10 mm thk. toughened glass partitions with 20 x 40mm MS framework with white/ black powder coating and all necessary required groove, wooden framing,
|  | LHS Glass partition | Sqft | 1 | 10.5 | - | 9.75 | 102.375
|  | RHS Glass partition | Sqft | 1 | 9.75 | - | 9.75 | 95.0625
|  | Total | [5 empty] | 197.4375
Additional items
6 | Liquor Store Room Door | Providing & fixing in position of FRD Glass Single Leaf Door made up of 45mm thick commercial flush door shutter of approved make & thickness, Inner side finished with laminate and outer side with veneer finish
|  | Bar store | Nos | 1 | - | - | - | 1
|  | Total | [5 empty] | 1
2 | CONSOLE | P/F service counters in duco finished from outer surface & top finished in veneer. The storage under the Counter should be provided with 6" ht. drawers at top row finished with wooden ribs.
|  | FOH Area | Nos | 2 | - | - | - | 2
|  | Total | [5 empty] | 2
26 | Bison board/ v- board Paneling | Providing, making and fixing of wall paneling made of 12mm thk branded bison board/ V board paneling on wall including MS framework from slab to slab | Sqft
| a | RHS From DB to column |  | 1 | 19 | - | 14 | 266
|  | Column side |  | 1 | 1.25 | - | 14 | 17.5
|  | Column |  | 1 | 5.75 | - | 14 | 80.5
|  | From column to buffet counter corner |  | 1 | 6.75 | - | 14 | 94.5
|  | Buffet counter wall |  | 1 | 13.75 | - | 14 | 192.5
|  | Buffet counter wall |  | 1 | 6.75 | - | 14 | 94.5
|  | Shaft side |  | 1 | 2 | - | 14 | 28
|  | Shaft front side |  | 1 | 10 | - | 14 | 140
|  | Shaft side |  | 1 | 2.5 | - | 14 | 35
|  | Less shaft shutter |  | -2 | 2.5 | - | 6 | -30
| B | LHS From DB to column |  | 1 | 19 | - | 14 | 266
|  | Column side |  | 2 | 1.25 | - | 14 | 35
|  | LHS Column |  | 1 | 5.75 | - | 14 | 80.5
|  | From column to bar store |  | 1 | 30.75 | - | 14 | 430.5
|  | Total | [5 empty] | 1730.5
27 | MS framework for curtain wall | P/F of 20 x 20mm MS framework with black powder coat upto ceiling height, having intermediate memebr @ every 900mm c/c including all necessary hardware etc. complete. | Sqft
| a | RHS From DB to column |  | 1 | 19 | - | 11 | 209
|  | Column side |  | 1 | 1.25 | - | 11 | 13.75
|  | Column |  | 1 | 5.75 | - | 11 | 63.25
|  | From column to buffet counter corner |  | 1 | 6.75 | - | 11 | 74.25
| B | LHS From DB to column |  | 1 | 19 | - | 11 | 209
|  | Column side |  | 2 | 1.25 | - | 11 | 27.5
|  | LHS Column |  | 1 | 5.75 | - | 11 | 63.25
|  | From column to bar counter |  | 1 | 30.75 | - | 11 | 338.25
|  | Ceiling framing above sofa seating |  | 1 | 26.5 | - | 8.85 | 234.525
|  | Total | [5 empty] | 1232.775
30 | Glass PARTITION on live kitchen | P/F 10 mm thk.fire rated glass partitions with 20 x 40mm MS framework with white/ black powder coating and all necessary required groove, | Sqft
| a | Live kitchen partition |  | 1 | 14 | - | 7.75 | 108.5
|  | Total | [5 empty] | 108.5
32 | cane screen | P/F of self supported bamboo cane screen having 30mm dia wooden framework with reuqired hinges and wooden frame/ bidding to be finished with melamine polish with necessary fittings as per design and details. | Sqft
| a | Screen near kitchen entry |  | 1 | 4 | - | 8 | 32
|  | Total | [5 empty] | 32
MISCELLANEOUS
1 | Texture wallpaper | P & F of texture wallpaper as per approval | Sqft
| a | LHS Wall |  | 2 | 5.25 | - | 7.5 | 78.75
|  | LHS Column |  | 1 | 5.75 | - | 7.5 | 43.125
|  | Next to column |  | 1 | 3 | - | 7.5 | 22.5
|  | Near bar counter |  | 2 | 5 | - | 7.5 | 75
|  | Total | [5 empty] | 219.375
2 | Ceiling Fans | P & F of ceiling fans paper as per approval | Sqft
| a | LHS in FOH Area |  | 3 | - | - | - | 3
|  | RHS in FOH Area |  | 3 | - | - | - | 3
|  | Total | [5 empty] | 6
3 | Bamboo blind curtain on S.S PVD black coating framework / roller blinds | P & F of bamboo blind manual folding curtains as per approval | Sqft
| a | From RHS DB to column |  | 1 | 15 | - | 7.5 | 112.5
|  | Column |  | 1 | 5.75 | - | 7.5 | 43.125
|  | From column to buffet counter corner |  | 1 | 6.75 | - | 7.5 | 50.625
|  | Total | [5 empty] | 206.25

## Additional works
Copper Chimney l Wakad Pune l Additional Works
Sr no | Description | Unit | Quantity | Rate | Amount | Remarks
1 | 12mm Additional ply for veneer paneling | Sqft | 311.75 | 217 | 67649.75
2 | Ceiling ply for light & MS Support | Sqft | 50.875 | 217 | 11039.875
3 | Installation of slotted angle rack with MS case & shutter | Nos | 5 | 7500 | 37500
4 | Wooden trap door for signage 1'x1' | Nos | 3 | 1500 | 4500
5 | Replacement of flex with MS Works | Nos | 1 | 27500 | 27500
7 | Hood installation with required hardware | Nos | 5 | 7500 | 37500
8 | MS Case for gas meter with shutter | Sqft | 30 | 450 | 13500
9 | MS Frame for kitchen ceiling light | Nos | 9 | 4500 | 40500
10 | MS Base for cold room machine | Nos | 1 | 9500 | 9500
11 | Supply of PVC Pallate | Nos | 1 | 5500 | 5500
12 | Supply of Safe | Nos | 1 | 20000 | 20000
13 | MS Stand for UPS in kitchen passage | Nos | 1 | 7500 | 7500
14 | Loading, Unloading & shifting all equipment and materials | Job | 1 | 65000 | 65000
15 | Rework for bar counter wall ( door location ) with changing in plumbing & Electrical line | Job | 1 | 15000 | 15000
16 | Wooden box for FOH Ceiling light | Nos | 16 | 2000 | 32000
17 | Fixing of SS Shelf in kitchen | Nos | 15 | 500 | 7500
18 | Supply & Installation of TV with additional breaket | Nos | 1 | 50750 | 50750
19 | Installation of plants in FOH area | Job | 1 | 12500 | 12500
20 | Gas burner works | Job | 1 | 6000 | 6000
21 | Installation of CCTV Screen with breaket | Nos | 1 | 2500 | 2500
22 | Wooden shelf for amplifier with veneer finish | Nos | 2 | 7500 | 15000
23 | Fixing of bells with required fittings | Nos | 230 | 175 | 40250
24 | MS Stand for glass washer & Ice cube machine | Nos | 2 | 7500 | 15000
26 | Supply of staff locker | Nos | 1 | 30000 | 30000
27 | Supply of Aluminium ladder | Nos | 1 | 6500 | 6500
28 | Supply of chair | Nos | 1 | 5500 | 5500
29 | Wooden display box with veneer finish for buffet | Nos | 4 | 6000 | 24000
30 | Laying of fabric in console & Service station | Nos | 13 | 2500 | 32500
31 | Installtion of soap dispensor in kitchen | Nos | 10 | 250 | 2500
32 | Supply of portable LED in DB Area | Nos | 1 | 2000 | 2000
33 | Additional marble on front wall in live kitchen ( 300mm wide ) | Rft | 12.5 | 900 | 11250
34 | Modification of existing SS Table | Nos | 2 | 8500 | 17000
35 | Fixing of double marble patti in pot wash area | Job | 1 | 5000 | 5000
36 | Supply of wooden table for store keeper | Nos | 1 | 8500 | 8500
37 | Wooden shelf for printer in kitchen area | Nos | 1 | 7500 | 7500
38 | Supply & Installation of gypsum trap door ( one is 400mm & one is 600mm ) | Nos | 2 | 3000 | 6000
40 | Supply & fixing of main door handle | Nos | 4 | 6647.1717 | 26588.6868
41 | Supply & Installation of brass skirting | Rft | 24.75 | 1464.9316 | 36257.0583
42 | Grenite step for kitchen entry | Job | 1 |  | 0
43 | Ramp in kitchen passage ( 5'x3' ) | Job | 1 | 15000 | 15000
44 | Supply & fixing of fire rated gypsum on wall paneling | Sqft | 1261 | 136 | 171496
46 | Supply and laying of wallpaper in buffet counter ( Basic rate of wallpaper @ 250 rs per sqft ) | Sqft | 200.625 | 350 | 70218.75
47 | Oil base preparation for wallpaper | Sqft | 421.25 | 35 | 14743.75
48 | Oil base paint on kitchen walls & Ceiling | Sqft | 1800.625 | 40 | 72025
50 | MS Plateform above door level for UPS (5'x3') | Job | 1 | 5000 | 5000
51 | Glass film on live kitchen partition | Sqft | 54.375 | 150 | 8156.25
52 | Bison board for DB & Water tank | Sqft | 63 | 160 | 10080
53 | Red paint on PT Slab | Job | 1 | 10000 | 10000
54 | Sliding channel & Fire rated hinges for door with consultant charges ( Form A ) | Job | 1 | 73868 | 73868
55 | Transportation for equipment from wakad to BKC & Wakad to viman nagar | Job | 1 | 35000 | 35000 | 3 trip
56 | Transportation for Aqua guard (From Mall to Godown & Godown to mall with loading unloading) | Job | 1 | 10000 | 10000
57 | SS Corner guard in kitchen area as per architect approval | Rft | 134 | 550 | 73700
58 | Bond it chemical for expose ceiling | Sqft | 1166.875 | 20 | 23337.5
59 | Main door | Nos | 1 | 88350 | 88350
60 | Rework in live kitchen partition | Job | 1 | 10000 | 10000
61 | Compressure repair | Job | 1 | 22000 | 22000
62 | SS Equipments
a | SS Table in bar area | Nos | 1 | 30000 | 30000
b | Live kitchen overhead shelf | Nos | 1 | 38500 | 38500
c | GN Pan rack wall mounted | Nos | 1 | 22000 | 22000
d | Wall mounted rack for oven | Nos | 1 | 6000 | 6000
e | Oil trey 4"x4" | Nos | 5 | 1500 | 7500
f | Louver for hood | Nos | 1 | 5000 | 5000
g | Heater | Nos | 1 | 12500 | 12500
63 | Attic stock
a | Flooring tile ( wooden ) | Box | 11 | 2010 | 22110
b | Flooring tile ( pattern ) | Box | 2 | 2640 | 5280
c | Metal ceiling tile | Nos | 8 | 800 | 6400
d | Nahani trap jali | Nos | 2 | 750 | 1500
e | Cane mesh jali | Roll | 4 | 3200 | 12800
f | White tile for kitchen | Box | 2 | 540 | 1080
64 | Electronic weighing scale | Nos | 1 | 17500 | 17500
65 | Blue star cold room | Nos | 1 | 66000 | 66000
66 | Rework on bar store door ( Additional veneer ) | Job | 1 | 8500 | 8500
67 | Flap & Wicket door in bar area | Job | 1 | 22500 | 22500
68 | Additional boxing of automation panel | Job | 1 | 5000 | 5000
69 | Temporary vinyl in bar area niche ( work hold ) | Roll | 3 | 1000 | 3000
70 | Scotch guard work on sofa seating ( as per instruction ) | Job | 1 | 40000 | 40000 | Décor
71 | Additional fabric behind sofa seating ( as per RM instruction ) | Job | 1 | 15000 | 15000
72 | Supply of PU foam bottle as per requirement | Nos | 2 | 1500 | 3000
73 | Deep cleaning | Job | 1 | 60000 | 60000
| Total |  |  |  | 1888930.6201

## Additional MS
NO | ITEM | DESCRIPTION | UNIT | No | Length | Width | Height | Total Qty
Interior Civil Works
ADDITIONAL WORKS
1 |  | 12mm Additional ply for veneer paneling | Sqft
|  | From RHS DB To center column |  | 1 | 15 | - | 3 | 45
|  | Column side |  | 2 | 1.25 | - | 3 | 7.5
|  | Column |  | 1 | 5.75 | - | 3 | 17.25
|  | column to buffet counter |  | 1 | 6.75 | - | 3 | 20.25
|  | From LHS DB To center column |  | 1 | 15 | - | 3 | 45
|  | Column side |  | 2 | 1.25 | - | 3 | 7.5
|  | Column |  | 1 | 5.75 | - | 3 | 17.25
|  | From column to bar counter |  | 1 | 19.25 | - | 3 | 57.75
|  | Buffet counter |  | 1 | 13.75 | - | 3 | 41.25
|  | Buffet counter |  | 1 | 5 | - | 3 | 15
|  | Bar store LHS Wall |  | 1 | 4.75 | - | 8 | 38
|  | Total | [5 empty] | 311.75
2 |  | Ceiling ply for light & MS Support | Sqft
|  | Above bar counter |  | 1 | 10.25 | 1.5 | - | 15.375
|  | For hanging light near bar counter |  | 1 | 3 | 1.5 | - | 4.5
|  | For fixing of MS Screen above console |  | 1 | 4 | 1.5 | - | 6
|  | For UPS Plateform in kitchen passage |  | 1 | 5 | - | 3 | 15
|  | Ply Packing above DB as per mall required |  | 2 | 4 | 1.25 | - | 10
|  | Total | [5 empty] | 50.875
3 |  | Installation of slotted angle rack with MS case & shutter | Nos
|  | Kitchen area |  | 5 | - | - | - | 5
|  | Total | [5 empty] | 5
4 |  | Wooden trap door for signage 1'x1' | Nos
|  | Above façade |  | 3 | - | - | - | 3
|  | Total | [5 empty] | 3
5 |  | Replacement of flex with MS Works | Nos
|  | Existing flex in entrance area |  | 1 | - | - | - | 1
|  | Total | [5 empty] | 1
6 |  | MS Plateform for fresh air Machine & Water tank | Nos
|  | Kitchen area above pot wash |  | 1 | - | - | - | 1
|  | Total | [5 empty] | 1
7 |  | Hood installation | Nos
|  | Live kitchen |  | 2 | - | - | - | 2
|  | Kitchen |  | 3 | - | - | - | 3
|  | Total | [5 empty] | 5
8 |  | MS Case for gas meter with shutter | Sqft
|  | Kitchen |  | 1 | 5 | - | 6 | 30
|  | Total | [5 empty] | 30
9 |  | MS Frame kitchen ceiling light | Nos
|  | Kitchen & Dish wash area |  | 1 | - | - | - | 1
|  | Total | [5 empty] | 1
17 |  | Fixing of SS Shelf in kitchen area | Nos
|  | Live kitchen |  | 1 | - | - | - | 1
|  | Dish wash area |  | 2 | - | - | - | 2
|  | Kitchen area |  | 12 | - | - | - | 12
|  | Total | [5 empty] | 15
41 |  | Supply & Installation of brass skirting | Rft
|  | Live kitchen Paneling |  | 1 | 14.5 | - | - | 14.5
|  | Bar area wall |  | 1 | 10.25 | - | - | 10.25
|  | Total | [5 empty] | 24.75
44 |  | Supply & fixing of fire rated gypsum on wall paneling | Sqft
|  | RHS DB Wall |  | 1 | 9 | - | 11 | 99
|  | DB Side |  | 1 | 1.25 | - | 11 | 13.75
|  | From DB to column |  | 1 | 15 | - | 11 | 165
|  | Column side |  | 2 | 1.25 | - | 11 | 27.5
|  | Column |  | 1 | 5.75 | - | 11 | 63.25
|  | From column to buffet counter corner |  | 1 | 6.75 | - | 11 | 74.25
|  | LHS DB Wall |  | 1 | 9 | - | 11 | 99
|  | DB Side |  | 1 | 1.5 | - | 11 | 16.5
|  | From DB to column |  | 1 | 15 | - | 11 | 165
|  | Column side |  | 2 | 1.25 | - | 11 | 27.5
|  | From column to bar counter |  | 1 | 19.25 | - | 11 | 211.75
|  | LHS Wall in bar store |  | 1 | 4.75 | - | 8 | 38
|  | Buffet counter |  | 1 | 13.75 | - | 11 | 151.25
|  | Buffet counter |  | 1 | 5 | - | 11 | 55
|  | Shaft in buffet area |  | 1 | 7 | - | 7.75 | 54.25
|  | Total | [5 empty] | 1261
46 |  | Supply and laying of wallpaper in buffet counter | Sqft
|  | Buffet counter |  | 1 | 13.75 | - | 7.75 | 106.5625
|  | Buffet counter |  | 1 | 6.75 | - | 7.75 | 52.3125
|  | Kitchen wall |  | 1 | 6.75 | - | 5 | 33.75
|  | Kitchen wall |  | 1 | 2 | - | 4 | 8
|  | Total | [5 empty] | 200.625
47 |  | Oil base preparation for wallpaper | Sqft
|  | Buffet counter |  | 1 | 13.75 | - | 7.75 | 106.5625
|  | Buffet counter |  | 1 | 6.75 | - | 7.75 | 52.3125
|  | Kitchen wall |  | 1 | 7 | - | 5 | 35
|  | Kitchen wall |  | 1 | 2 | - | 4 | 8
|  | LHS Wall |  | 2 | 5.25 | - | 7.5 | 78.75
|  | LHS Column |  | 1 | 5.75 | - | 7.5 | 43.125
|  | Next to column |  | 1 | 3 | - | 7.5 | 22.5
|  | Near bar counter |  | 2 | 5 | - | 7.5 | 75
|  | Total | [5 empty] | 421.25
48 |  | Oil base paint on kitchen walls & Ceiling | Sqft
| a | Kitchen wall
|  | Back side wall |  | 1 | 40.25 | - | 5.25 | 211.3125
|  | RHS Wall near gas meter |  | 1 | 9 | - | 5.25 | 47.25
|  | Shaft |  | 1 | 7.5 | - | 5.25 | 39.375
|  | Passage wall shaft side |  | 1 | 8.25 | - | 5.25 | 43.3125
|  | 2nd shaft |  | 1 | 7.5 | - | 5.25 | 39.375
|  | Passage DB Wall |  | 1 | 12.5 | - | 5.25 | 65.625
|  | Dish wash area from kitchen side |  | 1 | 9.25 | - | 5.25 | 48.5625
|  | Wall edge |  | 1 | 0.75 | - | 5.25 | 3.9375
|  | Dish wash area sink wall |  | 1 | 8.5 | - | 5.25 | 44.625
|  | Dish washer side wall |  | 1 | 11 | - | 5.25 | 57.75
|  | buffet counter side wall |  | 1 | 7.75 | - | 5.25 | 40.6875
|  | Kitchen entry wall |  | 1 | 2 | - | 5.25 | 10.5
|  | Wall edge |  | 1 | 0.75 | - | 5.25 | 3.9375
|  | Live kitchen entry wall |  | 1 | 4.5 | - | 5.25 | 23.625
|  | Live kitchen entry wall |  | 1 | 3.5 | - | 5.25 | 18.375
|  | Live kitchen back wall |  | 1 | 12.5 | - | 5.25 | 65.625
|  | Niche wall |  | 1 | 1 | - | 5.25 | 5.25
|  | Niche wall |  | 1 | 4.75 | - | 5.25 | 24.9375
|  | Bar store wall |  | 1 | 4.5 | - | 5.25 | 23.625
|  | Bar store wall |  | 1 | 4.25 | - | 5.25 | 22.3125
|  | LHS Wall |  | 1 | 12.25 | - | 5.25 | 64.3125
|  | Column near gas meter |  | 1 | 16.25 | - | 5.25 | 85.3125
|  | Kitchen ceiling |  | 1 | 40.5 | 14.75 | - | 597.375
|  | Less column |  | -1 | 5.25 | 3 | - | -15.75
|  | Less dish wash area |  | -1 | 12.25 | 2.5 | - | -30.625
|  | Less bar store area |  | -1 | 4.25 | 3.5 | - | -14.875
|  | Niche near bar store |  | 1 | 4.75 | 1 | - | 4.75
|  | Dish wash area ceiling |  | 1 | 11 | 12.25 | - | 134.75
|  | Kitchen passage ceiling |  | 1 | 12.25 | 5.5 | - | 67.375
|  | Capital side |  | 1 | 11 | - | 1 | 11
|  | Capital side |  | 1 | 9.75 | - | 1 | 9.75
|  | Capital side |  | 1 | 12.25 | - | 1 | 12.25
|  | Bar store ceiling |  | 1 | 5 | 4 | - | 20
|  | Paint on ply for UPS Plateform |  | 1 | 5 | 3 | - | 15
|  | Total | [5 empty] | 1800.625
51 |  | Glass film on live kitchen partition | Sqft
|  | Live kitchen partition top side |  | 1 | 14.5 | - | 3 | 43.5
|  | Live kitchen partition bottom |  | 1 | 14.5 | - | 0.75 | 10.875
|  | Total | [5 empty] | 54.375
52 |  | Bison board for DB & Water tank | Sqft
|  | For water tank |  | 1 | 6 | 4 | - | 24
|  | For UPS platform in kitchen passage |  | 1 | 5 | 3 | - | 15
|  | For DB in kitchen passage |  | 1 | 8 | - | 3 | 24
|  | Total | [5 empty] | 63
57 |  | P&F of 304 grade 3mm thick SS Corner guard (30mm x 30mm, mat finished as per approved sample) | Rft
|  | Live kitchen door frame |  | 2 | 7 | - | - | 14
|  | Live kitchen back wall |  | 1 | 8 | - | - | 8
|  | Dish wash area wall edge |  | 2 | 8 | - | - | 16
|  | Dish wash area wall corner near passage |  | 1 | 8 | - | - | 8
|  | Column |  | 4 | 8 | - | - | 32
|  | Shaft near passage |  | 2 | 8 | - | - | 16
|  | Niche near bar store |  | 2 | 8 | - | - | 16
|  | Bar store wall |  | 1 | 8 | - | - | 8
|  | Dish wash low ht wall |  | 4 | 4 | - | - | 16
|  | Total | [5 empty] | 134
58 |  | Bond it chemical for expose ceiling
Exposed ceiling
|  | FOH Area |  | 1 | 36.5 | 27.25 | - | 994.625
|  | Less column entrance side |  | -2 | 4.5 | 1.25 | - | -11.25
|  | Less column center area |  | -2 | 5.5 | 1.25 | - | -13.75
|  | RHS Beam |  | 1 | 36.5 | 1.25 | - | 45.625
|  | LHS Beam |  | 1 | 36.5 | 1.25 | - | 45.625
|  | Entrance side beam |  | 1 | 24 | 1 | - | 24
|  | Rework due to leakage |  | 2 | 8 | 3 | - | 48
|  | Rework due to leakage |  | 2 | 5 | 2 | - | 20
|  | Rework due to leakage |  | 1 | 7 | 2 | - | 14
|  | Total | [5 empty] | 1166.875

## BELLS
[7 empty] | 2023-08-08 |  | R0
BOQ of Civil work for Copper Chimney Project, Pune-Wakad
BELLS
S. N. | DESCRIPTION |  |  |  | UNIT | QTY | RATE | AMOUNT | REMARKS | Purchase remark | VIPL Remark
| Bells | Height | Diameter | Design no.
A |  | (160mm+30mm) | (120mm) | 12 | nos | 30 | 1450 | 43500 |  | Suggest this item be removed from vendor scope , TFS purchase | ok
B |  | 7" (135mm+30mm) | 4" (100mm) | 11 | nos | 50 | 1300 | 65000 |  | Suggest this item be removed from vendor scope , TFS purchase | ok
C |  | 6 ¾" (115mm+30mm) | 3.5" (90mm) | 10 | nos | 60 | 1175 | 70500 |  | Suggest this item be removed from vendor scope , TFS purchase | ok
D |  | 5" (100mm+20mm) | 3" (80mm) | 9 | nos | 80 | 1050 | 84000 |  | Suggest this item be removed from vendor scope , TFS purchase | ok
TOTAL OF BELLS | [5 empty] | 220
263000

## FACADE SIGNAGE
BOQ of Civil work for Copper Chimney Project, Pune-Wakad | [9 empty] | 2023-08-08 |  | R1
|  | GROUND FLOOR |  |  |  |  | FT |  |  | FT
SR.NO. | ITEM | DESCRIPTION | REFERENCE IMAGE | DIMENSION | UNIT | QTY. | RATE | AMOUNT | QTY. | RATE | AMOUNT | REMARK | Remark
FAÇADE SIGNAGE | [13 empty] | VIPL Remark
1 | COPPER CHIMNEY | FRONT LIT SIGNAGE - Providing, Supplying & fixing Single sided Sign Board of size with suitable inner frame and proper support, with sign substrate of suitable size of 4mm front glow acrylic sheet with side facia of SS PVD coated in approved color and symbols accordingly, fixed to inner frame with the help of Very High Bond tape of 24mm wide and 2.3mm thick. The board is to be fixed on RCC wall/pillar/ ACP sheet with dash fasteners of SS pipe of S-304 grade. All stainless steel items shall be of S-304 Grade (EXTERNAL SIGNAGES) (Material should be in compliance with Code of practise for Road signs, Indian Road Congress 2010)
A | Copper Chimney logo - Main signage | SAME AS ABOVE |  | 340mm X 500mm | NO | 1 | 17500 | 17500 | 1 | 17500 | 17500 |  | Suggest this item be removed from vendor scope , TFS purchase | ok
B | Copper Chimney Logo - hostess desk | SAME AS ABOVE |  | 520mm X 350mm | NO | 1 | 12000 | 12000 | 1 | 12000 | 12000 |  | Suggest this item be removed from vendor scope , TFS purchase | ok
C | Copper Chimney Lettering - English | SAME AS ABOVE |  | 4200mm X 340mm | NO | 1 | 75000 | 75000 | 1 | 75000 | 75000 |  | Suggest this item be removed from vendor scope , TFS purchase | ok
D | Copper Chimney Lettering - Regional language (marathi) | NON-LIT SIGNAGE - Providing, Supplying & fixing Single sided Sign Board of size with suitable inner frame and proper support, with of side facia of SS PVD coated letter in approved color and symbols accordingly, fixed to inner frame with the help of Very High Bond tape of 24mm wide and 2.3mm thick. The board is to be fixed on RCC wall/pillar/ ACP sheet with dash fasteners of SS pipe of S-304 grade. All stainless steel items shall be of S-304 Grade (EXTERNAL SIGNAGES) (Material should be in compliance with Code of practise for Road signs, Indian Road Congress 2010) |  | 1400mm X 200mm | NO | 1 | 75000 | 75000 | 1 | 75000 | 75000 |  | Suggest this item be removed from vendor scope , TFS purchase | ok
E | Copper Chimney Slogan | FRONT LIT SIGNAGE - Providing, Supplying & fixing Single sided Sign Board of size with suitable inner frame and proper support, with sign substrate of suitable size of 4mm front glow acrylic sheet with side facia of SS PVD coated in approved color and symbols accordingly, fixed to inner frame with the help of Very High Bond tape of 24mm wide and 2.3mm thick. The board is to be fixed on RCC wall/pillar/ ACP sheet with dash fasteners of SS pipe of S-304 grade. All stainless steel items shall be of S-304 Grade (EXTERNAL SIGNAGES) (Material should be in compliance with Code of practise for Road signs, Indian Road Congress 2010) |  | 500mm x 150mm | NO | 1 | 8000 | 8000 | 1 | 8000 | 8000 |  | Suggest this item be removed from vendor scope , TFS purchase | ok
F | Story wall sigange (Our legacy since 1972) | NON-LIT SIGNAGE - Providing, Supplying & fixing Single sided Sign Board of size with suitable inner frame and proper support, with of side facia of SS PVD coated letter in approved color and symbols accordingly, fixed to inner frame with the help of Very High Bond tape of 24mm wide and 2.3mm thick. The board is to be fixed on RCC wall/pillar/ ACP sheet with dash fasteners of SS pipe of S-304 grade. All stainless steel items shall be of S-304 Grade (EXTERNAL SIGNAGES) (Material should be in compliance with Code of practise for Road signs, Indian Road Congress 2010) |  | 2075MM X 150MM | NO | 1 | 50000 | 50000 | 1 | 50000 | 50000 |  | Suggest this item be removed from vendor scope , TFS purchase | ok
G | Veg & Non-Veg SIGNAGE, | NON-LIT SIGNAGE - Providing, Supplying & fixing Single sided Sign Board of size with suitable inner frame and proper support, with of side facia of SS PVD coated letter in approved color and symbols accordingly, fixed to inner frame with the help of Very High Bond tape of 24mm wide and 2.3mm thick. The board is to be fixed on RCC wall/pillar/ ACP sheet with dash fasteners of SS pipe of S-304 grade. All stainless steel items shall be of S-304 Grade (EXTERNAL SIGNAGES) (Material should be in compliance with Code of practise for Road signs, Indian Road Congress 2010) |  | 200 x 200mm | NO |  |  |  | 2 | 15000 | 30000 |  | Suggest this item be removed from vendor scope , TFS purchase | ok
H | No entry | NON-LIT SIGNAGE - Providing, Supplying & fixing Single sided Sign Board of size with suitable inner frame and proper support, with of side facia of SS PVD coated letter in approved color and symbols accordingly, fixed to inner frame with the help of Very High Bond tape of 24mm wide and 2.3mm thick. The board is to be fixed on RCC wall/pillar/ ACP sheet with dash fasteners of SS pipe of S-304 grade. All stainless steel items shall be of S-304 Grade (EXTERNAL SIGNAGES) (Material should be in compliance with Code of practise for Road signs, Indian Road Congress 2010) |  | 200 x 400mm | NO |  |  |  | 1 | 20000 | 20000 |  | Suggest this item be removed from vendor scope , TFS purchase | ok
TOTAL FAÇADE SIGNAGE
[8 empty] | 237500 |  |  | 287500

## MISCELLANEOUS
BOQ of Civil work for Copper Chimney Project, Pune-Wakad | [6 empty] | 2023-08-08 |  | R0
|  | GROUND FLOOR |  |  |  |  | FT
SR.NO. | ITEM | DESCRIPTION | DRAWING NO | DIMENSION | UNIT | QTY. | RATE | AMOUNT | REMARK
MISCELLANEOUS -2
1 | Story Wall Images | High Resolution Digital printing on HP Canvas STRETCHED on 1 inch wooden frame (stapling on sides)
Back: 3 mm sun board with leather finish vinyl pasted on it.
Size :
|  | Size : 440 x 600mm |  | 440 x 600mm | NOS | 3 | 3000 | 9000
|  | Size : 440 x 340mm |  | 440 x 340mm | NOS | 3 | 3000 | 9000
2 | Chef Photos | Size : 775 x 1050mm |  |  | NOS | 4 | 4500 | 18000
3 | Artifact | P & F of decorative artifact (approx cost - 250000) |  |  | LS | 1 | 260000 | 260000
4 | Natural & Artificial | P & F of planters (approx cost - 200000) |  |  | LS | 1 | 210000 | 210000
TOTAL MISCELLANEOUS - 2 | [7 empty] | 506000

## 26 Rate Analysis
Rate Analysis of Bison board/ v- board Paneling Item No 26
Costing for (4.0m x 5.0m = 20 Sqm)
NO | Item | Percentage | Rate | Per | QTY | Amount
Material
1 | 50 x 50 x 02 MS Pipe
05m x 8 Nos = 40m Vertical Support @ 600mm C/c
04m x 04 Nos = 16m Horizontal support @ 1200mm C/c
| Total = 56m x 3.05 Kg/M = 170.8Kg |  | 70 | Kg | 170.8 | 11956
2 | 12mm Fire Rated Ply |  | 110 | Sft | 215.28 | 23680.8
3 | Fire Rated Gypsum Baord |  | 70 | Sft | 215.28 | 15069.6
| Total |  |  |  |  | 50706.4
| Hardwear & Redoxide Paint | 5% |  |  |  | 2535.32
| Transportation | 5% |  |  |  | 2535.32
| Total |  |  |  |  | 55777.04
| Mathadi / Local Charges, Lead & Lift (Gr Floor to 2nd floor) | 10% |  |  |  | 5577.704
| Total Material |  |  |  |  | 61354.744
Labour
| MS Labour |  | 50 | Kg | 170.8 | 8540
| 12mm Fire Rated Ply |  | 50 | Sqft | 215.28 | 10764
| Fire Rated Gypsum Baord |  | 30 | Sqft | 215.28 | 6458.4 | 40
| Total Labour |  |  |  |  | 25762.4 | 3600 | 1000 | 3600000
| Total Material + Labour |  |  |  |  | 87117.144 |  |  | 432000
| Safety | 4% |  |  |  | 3484.6858 |  |  | 8.3317
| Scaffolding |  |  |  |  | 0
| Mathadi / Local Charges |  |  |  |  | 0
| Insurance | 3% |  |  |  | 2613.5143
| Total |  |  |  |  | 93215.3441
| Overheads | 2.5% |  |  |  | 2330.3836
| Profit | 8% |  |  |  | 7457.2275
| Grand Total for 20 Sqm |  |  | Sqm |  | 103002.9552
| Rate per Sqm |  |  | Sqm |  | 5150.1478
| Rate per Sqft |  |  | Sqft |  | 479

## 29 Rate Analysis
Rate Analysis of Bison board/ v- board Paneling Item No 29
Cost for 55 Sqft
NO | Item | Percentage | Rate | Per | QTY | Amount
Material
1 | 50 x 50 x 02 MS Pipe
0.60m x 15 Nos = 09m Vertical Support @ 600mm C/c
08m x 4 Nos = 20m Horizontal support
| Total = 29m x 3.05 Kg/M = 88.45Kg |  | 70 | Kg | 88.45 | 6191.5
2 | 12mm Bison Board |  | 50 | Sft | 105 | 5250
3 | Lather finish Granite |  | 200 | Sft | 105 | 21000
| Total |  |  |  |  | 32441.5
| Hardwear & Redoxide Paint | 5% |  |  |  | 1622.075
| Transportation | 5% |  |  |  | 1622.075
| Total |  |  |  |  | 35685.65
| Mathadi / Local Charges, Lead & Lift (Gr Floor to 2nd floor) | 10% |  |  |  | 3568.565
| Total Material |  |  |  |  | 39254.215
Labour
| MS Labour |  | 50 | Kg | 88.45 | 4422.5
| 12mm Bison Board |  | 50 | Sqft | 105 | 5250
| Lather finish Granite |  | 100 | Sqft | 105 | 10500
| Grnaite Moulding |  | 80 | Rft | 100 | 8000
| Total Labour |  |  |  |  | 28172.5
| Total Material + Labour |  |  |  |  | 67426.715
| Safety | 4% |  |  |  | 2697.0686
| Scaffolding |  |  |  |  | 0
| Mathadi / Local Charges |  |  |  |  | 0
| Insurance | 3% |  |  |  | 2022.8014
| Total |  |  |  |  | 72146.585
| Overheads | 2.5% |  |  |  | 1803.6646
| Profit | 8% |  |  |  | 5771.7268
| Grand Total for 55 Sqft |  |  | Sqft |  | 79721.9765
| Rate per Sqft |  |  | Sqft |  | 1450

## 27 Rate Analysis
P/F of 20 x 20mm MS framework with black powder coat upto ceiling height, having intermediate memebr @ every 900mm c/c including all necessary hardware etc. complete.
Cost for 87 Sqft (Elevation A-A')
NO | Item | Percentage | Rate | Per | QTY | Amount
Material
1 | 20 x 20 x 02 MS Pipe
4.10m x 16 Nos = 65.60 Rmt Vertical Support
12.00m x 2 Nos = 24.00 Rmt Horizontal support
| Total = 89.60m x 1.04 Kg/M = 93.184 Kg |  | 70 | Kg | 93.184 | 6522.88
2 | Black Powder Coating & Primer Cost |  | 5 | Kg | 93.184 | 465.92
| Total |  |  |  |  | 6988.8
| Hardwear | 2% |  |  |  | 139.776
| Transportation | 5% |  |  |  | 349.44
| Total |  |  |  |  | 7478.016
| Mathadi / Local Charges, Lead & Lift (Gr Floor to 2nd floor) | 2% |  |  |  | 149.5603
| Total Material |  |  |  |  | 7627.5763
Labour
| MS Labour |  | 30 | Kg | 93.184 | 2795.52
| Total Labour |  |  |  |  | 2795.52
| Total Material + Labour |  |  |  |  | 10423.0963
| Safety | 1% |  |  |  | 416.9239
| Scaffolding | 1% |  |  |  | 104.231
| Mathadi / Local Charges |  |  |  |  | 0
| Insurance | 1% |  |  |  | 104.231
| Total |  |  |  |  | 11048.4821
| Overheads | 2.5% |  |  |  | 276.2121
| Profit | 8% |  |  |  | 883.8786
| Grand Total for 87 Sqft |  |  | Sqft |  | 12208.5727 | 136.2564
| Rate per Sqft |  |  | Sqft |  | 140.3284 | 41.5416

## 09 Rate Analysis
Rate Analysis of Cane Panelling Item No 09
Basic Rate Of Materials at Site (Including transport, loading, unloading & all taxes)
NO | Item | Percentage | Rate | Per | QTY | Amount
Material
1 | Bamboo cane |  | 375 | Sqft | 1 | 375
2 | 40x20 Wood frame (CP first wood) |  | 2500 | Cft | 0.02 | 50
3 | 12mm Fire Rated Ply |  | 110 | Sft | 2 | 220
4 | Laminate |  | 40 | Sft | 1 | 40
| Total |  |  |  |  | 685
| Hardwear | 5% |  |  |  | 34.25
| Transportation | 5% |  |  |  | 34.25
| Total |  |  |  |  | 753.5
| Lead & Lift (Gr Floor to 2nd floor) | 10% |  |  |  | 75.35
| Total Material |  |  |  |  | 828.85
Labour
| Bamboo cane |  | 70 | Sqft | 1 | 70
| 40x20 Wood frame (Teak wood) |  | 1500 | Cft | 0.02 | 30
| 12mm Fire Rated Ply (2 Nos) |  | 75 | Sqft | 2 | 150
| Laminate |  | 50 | Sqft | 1 | 50
| Total Labour |  |  |  |  | 300
| Total Material + Labour |  |  |  |  | 1128.85
| Safety | 4% |  |  |  | 45.154
| Scaffolding | 2.5% |  |  |  | 28.2212
| Mathadi / Local Charges | 10% |  |  |  | 112.885
| Insurance | 1% |  |  |  | 11.2885
| Total |  |  |  |  | 1326.3987
| Overheads | 10% |  |  |  | 132.6399
| Profit | 15% |  |  |  | 198.9598
| Grand Total |  |  | Sqft |  | 1657.9984

## 10 Rate Analysis
Rate Analysis of Bison board/ v- board Paneling Item No 29
19 | P&F of 350mm wide Bar Bulkhead/ glass hanger having 25mm X 25MM brass metal/ SS PVD COATING box section in 2 layers having vertical and horizontal member @every 450mm c/c with 10mm thk toughthned glass shelf having provision for led profile light. brass metal to be brushed finish. the base including 8-10mm solid rods band in curve shape to hang the wine glass. the top portion to have 6-8mm thk flutted glass palnelling. Rate including all necessary hardware fittings to install the shelves, anchor fastner, ceiling support, scaffolding, etc. as required on site. Complete as per architectural detail drawing & site engineer's instruction.
2925x 350mm (Running Feet - 9.5 Rft)
NO | Item | Percentage | Rate | Per | QTY | Amount
Cane Panelling
Materials - Woodworks
| 12mm Fluted Glass Shelves |  | 450 | Sqft | 20 | 9000
| Brass Metal Strips (25x25mm) - Solid Rods for Self Brackets |  | 850 | Kg | 50 | 42500
| Solid Rod Bands including Light Provisions |  | 850 | Kg | 30 | 25500
| Clits / brackets Screw & Fastners |  | 150 | Nos | 48 | 7200
| Total |  |  |  |  | 84200
| Lead & Lift (Gr Floor to 2nd floor) | 10% |  |  |  | 8420
| Total Material |  |  |  |  | 92620
Labour
| Fitters for Bending & Fixing |  | 1 | Nos | 25000 | 25000
| Total Labour |  |  |  |  | 25000
| Total Material + Labour |  |  |  |  | 117620
| Safety | 4% |  |  |  | 4704.8
| Scaffolding | 2.5% |  |  |  | 2940.5
| Mathadi / Local Charges |  |  |  |  | 0
| Insurance | 1% |  |  |  | 1176.2
| Total |  |  |  |  | 126441.5
| Overheads | 2.5% |  |  |  | 3161.0375
| Profit | 8% |  |  |  | 10115.32
| Grand Total for 9.5 Rft |  |  | Rft |  | 139717.8575
| Rate per Rft |  |  | Rft |  | 14707.1429

## CALCULATION PAINT (hidden)
| 403 | 443.3 | 444 | 67.66 | 6.1 | 73.76 | 517.76 | 518
| 6.6 | 2.1 | 13.86
| 2.6 | 2.1 | 5.46
19.32
|  |  | 21.252 | 22
2.8 | 19.32 | 2.8 | 24.92
|  |  | 27.412 | 28
[6 empty] | 3.3 | 1.2 | 2.1
12 | 3 |  | 36
2.4 | 2 | 1.8 | 8.64
|  |  | 44.64 | 49.104
49