## Summary
SUMMARY OF COST OF INTERIOR & EXTERNAL-ELECTRICAL & ELV WORK - CC - PUNE WAKAD
SR NO. | DESCRIPTION | Vart Infra | Target Amount | Vart Infra Final Offer | As Per Measurment RA1 | As Per Measurment RA2
1 | PANELS / DBs | 495000 | 321150 | 361800 | 344600 | 6750
2 | CABLES : | 192578 | 138004 | 143134 | 86965 | 107315
3 | POINT WIRING : | 721750 | 362065 | 456720 | 229660 | 255566
4 | RACEWAYS, CABLE TRAYS & JUNCTION BOX | 155750 | 130830 | 135030 | 114500 | 35940
5 | LIGHT FIXTURES INSTALLATION | 0 | 0 | 0 | 5250 | 50450
6 | EARTHING : | 162500 | 55120 | 55120 | 10500 | 0
7 | Miscellaneous Item | 27000 | 6325 | 10365 | 0 | 0
8 | DATA DISTRIBUTION | 81400 | 28032 | 34840 | 10080 | 75240
9 | SUPPLY & INSTALLATION OF SAFETY ITEMS | 10500 | 8350 | 9500 | 0 | 4400
10 | UPS/ INVERTER System: | 95000 | 78600 | 85000 | 0 | 85000
11 | CCTV | 32400 | 15660 | 16200 | 15240 | 0
12 | PA SYSTEM | 83390 | 105370 | 100120 | 23450 | 0
13 | FIRE ALARM SYSTEM (MAKE: HONEYWELL/EST) | 175790 | 126335 | 142935 | 168505 | 12980
| TOTAL | 2233058 | 1375841 | 1550764 | 1008750 | 633641
NOTE:- | GST Extra
Exclusions:
1. Passive data network devices and active networking components are excluded.
2. Epabx & Telephone instruments are excluded.
3. SERVER is excluded.
4. Light Fixture- Supply Excluded.

## TENDER BOQ
BILL OF QUANTITY FOR ELECTRICAL WORK FOR CC - PUNE WAKAD
|  | TENDER BOQ. R0 |  | Vart Infra |  |  | Target Amount |  |  | Final offer |  |  | RA1 BILL |  |  | RA2 BILL
SR. | DESCRIPTION OF ITEM | UNIT | QTY | Supply Rate | Installtion Rate | Amount | Supply Rate | Installtion Rate | Amount | Supply Rate | Installtion Rate | Amount | RA1 QTY | UNIT | RA1 AMOUNT | RA2 QTY | UNIT | RA2 AMOUNT
1 | PANELS / DBs
Supply and Installation of main LT panel,genarally conforming to IS 8623/IS-13947/IEC-439 front operated, dead back floor mounted , totally enclosed, compartmentalised, vermin proof,indoor, non-drawout type,power panel, fabricated out of 2mm thick CRCA sheets, fully powder coated after seven tank treatment, having gasketed & hinged cover on each cubicle with insulated door knob, incorporating horizontal and vertical copper busbars complete with all internal wiring, danger sign board, earth-bus and lugs, cable chamber, busbar chamber,aluminium anodized name plates etc.as required, including 2 nos. of 6" dia instrument cooling fan with switch and ventilation louvres with wire mesh,housing below mentioned switchgears / meters. 9W fitting with CFL lamp, switch shall be provided in each vertical section,:(Panel should conform to Form- 3b of IEC- 439) (GA drawing of the panel to be got approved from the Consultant before taking up fabrication and all panels to be factory inspected before despatch)
Notes: 1. All MCCBs shall have rotary handle
2. All MCCBs shall have phase spreader assembly on
both Line & Load ends.
3. All MCCB shall have Minimum Ics=16KA)
4. Incomer shall have auxilliary ON/OFF & TRIP status contacts and the same shall be wired up
electronic trip setting to Metering Compartment)
5. The panel shall conform to Form-3b as per IEC-439
6. All MCCB to be of Schneider/ABB make
7. All MCCB to be current limiting type, LSIG
8. Incomer MCCB to be shunt trip facility
Refer: SLD
1.1.1 | MAIN PANEL | Set | 1 | 175000 | 18000 | 193000 | 175000 | 18000 | 193000 | 175000 | 15000 | 190000 | 1 |  | 190000 |  |  | 0
1.1.2 | KITCHEN DB | Set | 1 | 85000 | 7500 | 92500 | 18500 | 3000 | 21500 | 22500 | 4000 | 26500 | 1 |  | 26500 | 0 |  | 0
1.1.3 | BAR DB (4WAY TPN - 7 SEGMENT) | Set | 1 | 27500 | 6500 | 34000 | 14500 | 2000 | 16500 | 22000 | 3000 | 25000 | 1 |  | 25000 | 0 |  | 0
1.1.4 | KPDB (8WAY TPN - 7 SEGMENT) | Set | 1 | 30000 | 6500 | 36500 | 16500 | 2500 | 19000 | 24500 | 3000 | 27500 | 1 |  | 27500 | 0 |  | 0
1.1.5 | LDB (8WAY TPN - 7 SEGMENT) | Set | 1 | 30000 | 6500 | 36500 | 16500 | 2500 | 19000 | 24500 | 3000 | 27500 | 1 |  | 27500 | 0 |  | 0
1.1.6 | PDB (8WAY TPN - 7 SEGMENT) | Set | 1 | 30000 | 8500 | 38500 | 16500 | 2500 | 19000 | 24500 | 3000 | 27500 | 1 |  | 27500 | 0 |  | 0
1.2 | Suply and installation of Four -Tier, Multi-Way, TPN,
Distribution Board for Lighting & Power distribution, surface
mounted on wall, sheet metal fabricated,powder coated,
having dust-proof and vermin 'proof, gasketed and hinged
acrylic door with all internals such as DIN rails, neutral-link,
interconnected wiring complete with earthing lugs housing
switchgears: (IP-43 with Metal Door) Refer: SLD & DB Schedule
(Make: Legrand-Ekinoxe /Schneider)
1.2.1 | UPS SPN DB (16WAY SPN) | Set | 1 | 11000 | 3000 | 14000 | 5250 | 1200 | 6450 | 8500 | 1500 | 10000 | 1 |  | 10000 | 0 |  | 0
1.3 | S & I of 32A,DP,MCB +20A NO/NC CONTACTOR, in powder coated sheet metal box for terminating UPS TO UPSDB etc. | Nos | 1 | 11000 | 3000 | 14000 | 1150 | 200 | 1350 | 1350 | 250 | 1600 |  |  | 0 | 1 |  | 1600
1.4 | S & I of 32A, TP, MCB + 32A,415 V, Metal clad,Power socket in powder coated metal box for supplying power to Kitchen equipment etc. | Nos | 3 | 6000 | 2000 | 24000 | 4550 | 500 | 15150 | 4550 | 750 | 15900 | 2 |  | 10600 | 0 |  | 0
1.5 | S & I of 32A,FP,MCB type Isolator, in powder coated sheet metal box for terminating power to equipment etc. | Nos | RO | 3000 | 750 | [9 empty] | 0 |  |  | 0
1.6 | S & I of 63A,,FP,MCB type Isolator, in powder coated sheet metal box for terminating power to equipment etc. | Nos | RO | 3500 | 1000 | [9 empty] | 0 |  |  | 0
1.7 | S & I of 32A 3Pin Socket & 32A DP MCB with MS enclosure IP44 | Set | RO | 3000 | 750 | [9 empty] | 0 |  |  | 0
1.8 | S & I of 32A 4P ELMCB 300mA, Metal clad,Power socket in powder coated metal box for supplying power to AC & Kitchen equipment etc. | Nos | 2 | 4800 | 1200 | 12000 | 4800 | 300 | 10200 | 4800 | 350 | 10300 |  |  | 0 | 1 |  | 5150
1.9 | S & I of 32/63A ELMCB 100mA, Metal clad,Power socket in powder coated metal box for supplying power to equipment etc. | Nos | RO | 7800 | 1200 | [9 empty] | 0 |  |  | 0
| Sub Total of 1.0 |  |  |  |  | 495000 |  |  | 321150 |  |  | 361800 |  |  | 344600 |  |  | 6750
2 | CABLES :
Supply and laying, effecting proper connections, testing & commissioning of the following sizes of 1.1 KV XLPE armoured/ unarmoured PVC insulated PVC sheathed aluminium /copper conductor cables conforming to IS : 1554 and IS 694 for Flexible copper cable Part I - 1976 with latest amendments laid over MS supports in existing RCC ducts/ laid in ground /laid on Cable Trays including clamping the cables to supports in an approved manner as required complete with all accessories.All cables shall have thermo setting insulation XLPE and low emission of smoke and corrosive gas when affected by fire. Necessary Markers shall be provided at the intervals as per the specifications.
2.1.1 | 3.5C x 400 Sq.mm. AL XLPE Cable | R.M | RO | 1890 | 360 | [9 empty] | 0 |  |  | 0
2.1.2 | 3.5C x 300 Sq.mm. AL XLPE Cable | R.M | RO | 1410 | 300 | [9 empty] | 0 |  |  | 0
2.1.3 | 3.5C x 240 Sq.mm. AL XLPE Cable | R.M | RO | 1050 | 300 | [9 empty] | 0 |  |  | 0
2.1.4 | 3.5C x 185 Sq.mm. AL XLPE Cable | R.M | RO | 840 | 300 | [9 empty] | 0 |  |  | 0
2.1.5 | 3.5C x 150 Sq.mm. AL XLPE Cable | R.M | RO | 540 | 240 | [9 empty] | 0 |  |  | 0
2.1.6 | 3.5C x 120 Sq.mm. AL XLPE Cable | R.M | RO | 432 | 240 | [9 empty] | 0 |  |  | 0
2.1.7 | 3.5C x 95 Sq.mm. AL XLPE Cable | R.M | RO | 580 | 240 | [9 empty] | 0 |  |  | 0
2.1.8 | 3.5C x 70 Sq.mm. AL XLPE Cable- MAIN PANEL | R.M | 80 | 480 | 270 | 60000 | 450 | 100 | 44000 | 450 | 100 | 44000 |  |  | 0 |  |  | 0
2.1.9 | 3.5C x 50 Sq.mm. AL XLPE Cable | R.M | RO | 432 | 220 | [9 empty] | 0 |  |  | 0
2.1.10 | 3.5C x 35 Sq.mm. AL XLPE Cable | R.M | RO | 290 | 150 | [9 empty] | 0 |  |  | 0
2.1.11 | 3.5C x 25 Sq.mm. AL XLPE Cable | R.M | RO | 270 | 120 | [9 empty] | 0 |  |  | 0
2.1.12 | 4C x 16 Sq.mm. AL XLPE Cable - PDB, KPDB, KDB, BAR DB & DISHWASHER | R.M | 130 | 180 | 80 | 33800 | 180 | 60 | 31200 | 180 | 60 | 31200 | 172 |  | 41280 | 0 |  | 0
2.1.13 | 4C x 10 Sq.mm. CU XLPE Cable | R.M | RO | 505 | 180 | [9 empty] | 0 |  |  | 0
2.1.14 | 4C x 6 Sq.mm. CU XLPE Cable | R.M | RO | 335 | 145 | [9 empty] | 0 |  |  | 0
2.1.15 | 4C x 4 Sq.mm. CU XLPE Cable - AHU, LDB & PULVERISER | R.M | 57 | 300 | 90 | 22230 | 190 | 70 | 14820 | 200 | 70 | 15390 | 123 |  | 33210 | 78 |  | 21060
2.1.16 | 4C x 2.5 Sq.mm. CU XLPE Cable | R.M | RO | 335 | 120 | [9 empty] | 0 |  |  | 0
2.1.17 | 3C x 16 Sq.mm. CU XLPE Cable | R.M | RO | 390 | 96 | [9 empty] | 0 |  |  | 0
2.1.18 | 3C X 6sq.mm CU XLPE Cable | R.M | RO | 340 | 110 | [9 empty] | 0 |  |  | 0
2.1.19 | 3C X 4sq.mm CU XLPE Cable - UPS & UPS DB, REFRIG., FRESH AIR & EXHAUST | R.M | 84 | 220 | 90 | 26040 | 160 | 65 | 18900 | 160 | 65 | 18900 | 19 |  | 4275 | 87 |  | 19575
2.1.20 | 3C x 2.5 Sq.mm. CU PVC Cable - UPS O/G | R.M | 70 | 110 | 72 | 12740 | 110 | 50 | 11200 | 110 | 50 | 11200 |  |  | 0 | 95 |  | 15200
2.1.21 | 3C X 4sq.mm CU PVC Cable | R.M | RO | 220 | 90 | [9 empty] | 0 |  |  | 0
2.1.22 | 3C X 1.5sq.mm CU PVC Cable-SIGNAGE | R.M | 20 | 105 | 72 | 3540 | 75 | 60 | 2700 | 75 | 60 | 2700 |  |  | 0 |  |  | 0
2.1.23 | 1C x 70 Sq.mm, Copper, Flexible, Bunched together | Mtr. | RO | 480 | 102 |  |  |  |  | 480 | 102 |  |  |  | 0 | 70 |  | 40740
2.1.24 | 1C x 4 Sq.mm, Copper, Flexible, Bunched together -UPS | Mtr. | 25 | 72 | 48 | 3000 | 40 | 10 | 1250 | 50 | 10 | 1500 |  |  | 0 |  |  | 0
2.1.25 | 2C X 2.5sq.mm CU Cable - Kill switch UPS | R.M | 10 | 84 | 48 | 1320 | 80 | 20 | 1000 | 80 | 20 | 1000 |  |  | 0 |  |  | 0
2.2 | CABLE TERMINATION
Making cable and terminations including brass single compression glands and crimping type copper lugs for cable sizes mentioned below for aluminium or copper.
2.2.1 | 3.5C x 400 Sq.mm. AL XLPE Cable | Nos. | RO | 1450 | 960 | [9 empty] | 0 |  |  | 0
2.2.2 | 3.5C x 300 Sq.mm. AL XLPE Cable | Nos. | RO | 1320 | 960 | [9 empty] | 0 |  |  | 0
2.2.3 | 3.5C x 240 Sq.mm. AL XLPE Cable | Nos. | RO | 1200 | 720 | [9 empty] | 0 |  |  | 0
2.2.4 | 3.5C x 185 Sq.mm. AL XLPE Cable | Nos. | RO | 960 | 660 | [9 empty] | 0 |  |  | 0
2.2.5 | 3.5C x 150 Sq.mm. AL XLPE Cable | Nos. | RO | 900 | 540 | [9 empty] | 0 |  |  | 0
2.2.6 | 3.5C x 120 Sq.mm. AL XLPE Cable | Nos. | RO | 1080 | 900 | [9 empty] | 0 |  |  | 0
2.2.7 | 3.5C x 95 Sq.mm. AL XLPE Cable | Nos. | RO | 840 | 600 | [9 empty] | 0 |  |  | 0
2.2.8 | 3.5C x 70 Sq.mm. AL XLPE Cable- MAIN PANEL | Nos. | 2 | 600 | 480 | 2160 | 450 | 80 | 1060 | 550 | 100 | 1300 |  |  | 0 |  |  | 0
2.2.9 | 3.5C x 50 Sq.mm. AL XLPE Cable | Nos. | RO | 480 | 360 | [9 empty] | 0 |  |  | 0
2.2.10 | 3.5C x 35 Sq.mm. AL XLPE Cable | Nos. | RO | 480 | 360 | [9 empty] | 0 |  |  | 0
2.2.11 | 3.5C x 25 Sq.mm. AL XLPE Cable | Nos. | RO | 480 | 360 | [9 empty] | 0 |  |  | 0
2.2.12 | 4C x 16 Sq.mm. AL XLPE Cable - PDB, KPDB, KDB, BAR DB & DISHWASHER | Nos. | 10 | 540 | 480 | 10200 | 225 | 50 | 2750 | 450 | 100 | 5500 | 8 |  | 4400 | 0 |  | 0
2.2.13 | 4C x 10 Sq.mm. CU XLPE Cable | Nos. | RO | 540 | 360 | [9 empty] | 0 |  |  | 0
2.2.14 | 4C x 6 Sq.mm. CU XLPE Cable | Nos. | RO | 480 | 300 | [9 empty] | 0 |  |  | 0
2.2.15 | 4C x 4 Sq.mm. CU XLPE Cable - AHU, LDB & PULVERISER | Nos. | 6 | 300 | 240 | 3240 | 210 | 50 | 1560 | 250 | 70 | 1920 | 10 |  | 3200 | 8 |  | 2560
2.2.16 | 4C x 2.5 Sq.mm. CU XLPE Cable | Nos. | RO | 300 | 240 | [9 empty] | 0 |  |  | 0
2.2.17 | 3C x 16 Sq.mm. CU XLPE Cable | Nos. | RO | 300 | 240 | [9 empty] | 0 |  |  | 0
2.2.18 | 3C X 6sq.mm CU XLPE Cable | Nos. | RO | 320 | 220 | [9 empty] | 0 |  |  | 0
2.2.19 | 3C X 4sq.mm CU XLPE Cable - UPS & UPS DB, REFRIG., FRESH AIR & EXHAUST | Nos. | 14 | 400 | 200 | 8400 | 210 | 50 | 3640 | 250 | 50 | 4200 | 2 |  | 600 | 4 |  | 1200
2.2.20 | 3C x 2.5 Sq.mm. CU PVC Cable - UPS O/G | Nos. | 4 | 200 | 150 | 1400 | 200 | 50 | 1000 | 200 | 50 | 1000 |  |  | 0 | 22 |  | 5500
2.2.21 | 3C X 4sq.mm CU PVC Cable | Nos. | RO | 200 | 150 | [9 empty] | 0 |  |  | 0
2.2.22 | 3C X 1.5sq.mm CU PVC Cable-SIGNAGE | Nos. | 8 | 200 | 150 | 2800 | 175 | 50 | 1800 | 225 | 50 | 2200 |  |  | 0 |  |  | 0
2.2.23 | 1C x 70 Sq.mm, Copper, Flexible, Bunched together | Nos. | RO | 220 | 150 |  |  |  |  | 220 | 150 |  |  |  | 0 | 4 |  | 1480
2.2.24 | 1C x 4 Sq.mm, Copper, Flexible, Bunched together -UPS | Nos. | 12 | 72 | 50 | 1464 | 55 | 20 | 900 | 55 | 20 | 900 |  |  | 0 |  |  | 0
2.2.24 | 2C X 2.5sq.mm CU Cable - Kill switch UPS | Nos. | 2 | 72 | 50 | 244 | 72 | 40 | 224 | 72 | 40 | 224 |  |  | 0 |  |  | 0
| Sub Total of 2 |  |  |  |  | 192578 |  |  | 138004 |  |  | 143134 |  |  | 86965 |  |  | 107315
3 | POINT WIRING :
3.1 | LIGHT POINT
Sub mains / Pre-Primary wiring i.e. from DB to room switch board shall be carried out for Pre-primary point using 1.5 sqmm copper stranded. All lighting fixture, wiring shall be carried out for primary point using 1.5 sqmm copper stranded & for secondary wiring 1.5sqmm copper stranded conductor 660/1100V grade PVC FRLS insulated wire in "MS Conduits" (including flexible conduits for drops to light fittings)". Individual junction / inspection boxes shall be provided for each lighting fitting for the purpose of looping from fitting to fitting.
also including insulated green color copper earth wire for each circuit and providing modular grid plate type switches,sockets etc. as required. Each light point to be terminated using 5A connector or 5A two pin female socket (for cove lighting) as directed at site. Each circuit feeding not more than 12-8 points/800 watts as per following configuration:(LDBs located at two locations as shown) (The Switch Socket cost shall be paid separately.)
From distribution board to switch board will be termed as Pre-primary point, average wiring length for Pre-primary point to be considered as 15 metres. From switch board to first light fitting and switch board to switch board will be termed as primary point, average wiring length for primary point to be considered as 3 metres and First fitting to subsequent fitting on the same circuit shall be termed as secondary point, average wiring length for secondary point to be considered as 5 metres. Light point wiring shall be included submains wiring from D.B. to room switch board.
Note: Length may vary as per actual site condition. Vendor shall be crossverify before bidding.
3.1.1 | Pre-Primary point (sub mains point) | Nos | 20 | 1500 | 750 | 45000 | 1050 | 350 | 28000 | 1400 | 350 | 35000 | 18 |  | 31500 | 0 |  | 0
3.1.2 | Primary point | Nos | 15 | 1800 | 480 | 34200 | 950 | 275 | 18375 | 1300 | 300 | 24000 | 25 |  | 40000 | 7 |  | 11200
3.1.3 | Secondary Point | Nos | 145 | 950 | 480 | 207350 | 735 | 150 | 128325 | 850 | 150 | 145000 | 119 |  | 119000 | 16 |  | 16000
3.2 | LIGHT POINT For Automation
All lighting fixture, wiring shall be carried out for primary point using 1.5 sqmm copper stranded & for secondary wiring 1.5sqmm copper stranded conductor 660/1100V grade PVC FRLS insulated wire in "MS Conduits" & 1 pair 1.5sqmm jacketed cable in Separate Conduit (including flexible conduits for drops to light fittings)". Individual junction / inspection boxes shall be provided for each lighting fitting for the purpose of looping from fitting to fitting.
From DB to first light fitting/driver will be termed as primary point, average wiring length for primary point to be considered as 25 metres and First fitting to subsequent fitting on the same circuit shall be termed as secondary point, average wiring length for secondary point to be considered as 5 metres. Light point wiring shall be included submains wiring from D.B. to room lights/Driver.
Note: Length may vary as per actual site condition. Vendor shall be crossverify before bidding.
3.2.1 | Primary point | Nos | RO | 3000 | 1200 | [9 empty] | 0 |  |  | 0
3.2.2 | Secondary Point | Nos | RO | 1450 | 1680 | [9 empty] | 0 |  |  | 0
3.3 | Power Point (Utility)
Primary wiring i.e. from DB to first power point shall be carried out for primary point using 3R x 2.5 sqmm copper stranded. Secondary wiring 2.5sqmm copper stranded conductor 660/1100V grade PVC FRLS insulated wire in "MS Conduit". Individual junction/inspection boxes shall be provided for each power point to loop from power point to a power point. Only 4 points looped in one circuit) From DB to First Socket.
From distribution board to first power point will be termed as primary point, average wiring length for primary point to be considered as 18 metres. First power point to subsequent power point on the same circuit shall be termed as secondary point, average wiring length for secondary point to be considered as 8 metres. Power point wiring shall be included wiring from D.B. to room indivisual power point.
Note: Length may vary as per actual site condition. Vendor shall be crossverify before bidding.
3.3.1 | Primary point | Nos | 22 | 3500 | 1050 | 100100 | 1450 | 300 | 38500 | 2200 | 800 | 66000 |  |  | 0 | 19 |  | 57000
3.3.1 | Primary point ( Distance between Switch & socket Will be Average Length 2.5 Mtr. ) | Nos | RO | 2150 | 850 | [9 empty] | 0 |  |  | 0
3.3.2 | Secondary Point | Nos | 16 | 2000 | 600 | 41600 | 945 | 150 | 17520 | 1200 | 300 | 24000 |  |  | 0 | 22 |  | 33000
3.4 | Power Point (Kitchen & BAR)
Primary wiring i.e. from DB to first power point shall be carried out for primary point using 3R x 4 sqmm copper stranded. Secondary wiring 4sqmm copper stranded conductor 660/1100V grade PVC FRLS insulated wire in "MS Conduit". Individual junction/inspection boxes shall be provided for each power point to loop from power point to a power point. Only 4 points looped in one circuit) From DB to First Socket.
From distribution board to first power point will be termed as primary point, average wiring length for primary point to be considered as 12 metres. First power point to subsequent power point on the same circuit shall be termed as secondary point, average wiring length for secondary point to be considered as 2 metres. Power point wiring shall be included wiring from D.B. to room indivisual power point.
Note: Length may vary as per actual site condition. Vendor shall be crossverify before bidding.
3.4.1 | Primary point | Nos | 30 | 3500 | 1450 | 148500 | 1750 | 400 | 64500 | 2000 | 600 | 78000 |  |  | 0 | 23 |  | 59800
3.4.2 | Primary point ( Distance between Switch & socket Will be Average Length 2.5 Mtr. ) | Nos | RO | 1550 | 950 | [9 empty] | 0 |  |  | 0
3.4.3 | Secondary Point | Nos | RO | 850 | 550 |  |  |  |  | 850 | 550 |  |  |  | 0 | 20 |  | 28000
3.5 | S & I of MS conduits including all accessories, clamps, spacers, bends, tee, cross etc. as required at site for miscellaneous use in following sizes:
3.5.1 | 20mm dia | Mtr | RO | 145 | 96 | [9 empty] | 0 |  |  | 0
3.5.2 | 25mm dia | Mtr | 100 | 180 | 50 | 23000 | 75 | 40 | 11500 | 140 | 50 | 19000 |  |  | 0 |  |  | 0
3.6 | S & I of flexible GI conduits including all accessories, clamps, spacers, end adopters (Glands) etc. as required at site in following sizes:
3.6.1 | 20mm dia | Mtr | RO | 96 | 48 |  |  |  |  | 96 | 48 |  |  |  | 0 | 24 |  | 3456
3.6.2 | 25mm dia (COMMON) | Mtr | 75 | 150 | 50 | 15000 | 35 | 12 | 3525 | 140 | 40 | 13500 |  |  | 0 |  |  | 0
3.7 | Supply, Installation testing and commission of 240V-AC, wiring devices and its accessories such as modular type switch socket outlets with modular front plate, modular box, G.I. back box and all required accessories etc. Supply & Installation scope includes all civil works related to this job such as chiselling , making good with concrete and plaster, supply of fixing screw / wall plugs and other necessary hardware, marking identification numbers of circuits & interconnections of the switch /sockets as per standard drawing, complete as per site requirement. Switches and sockets may be individual or combined with bigger lighting switchboards, contractor to refer drawings to understand exact scope of work. LEGRAND
3.7.1 | 6A One way plate type switch | Nos. | 14 | 300 | 50 | 4900 | 75 | 15 | 1260 | 75 | 15 | 1260 |  |  | 0 | 19 |  | 1710
3.7.2 | 6A Two way plate type switch | Nos. | RO | 300 | 50 | [9 empty] | 0 |  |  | 0
3.7.3 | 6/16A SOCKET & SWITCH | Nos. | 28 | 450 | 100 | 15400 | 450 | 100 | 15400 | 450 | 100 | 15400 |  |  | 0 | 43 |  | 23650
3.7.4 | 2Nos. 6/16A SOCKET & SWITCH | Sets | 6 | 650 | 100 | 4500 | 650 | 100 | 4500 | 650 | 100 | 4500 |  |  | 0 | 22 |  | 16500
3.7.5 | 6/16A SOCKET & SWITCH - Kitchen | Sets | 42 | 1250 | 250 | 63000 | 450 | 100 | 23100 | 450 | 100 | 23100 | 60 |  | 33000 | 0 |  | 0
3.7.6 | 20A switch & socket outlet - Kitchen | Sets | 8 | 1650 | 350 | 16000 | 650 | 120 | 6160 | 650 | 120 | 6160 | 8 |  | 6160 | 0 |  | 0
3.7.7 | 20A Socket -AC | Nos. | RO | 1250 | 250 | [9 empty] | 0 |  |  | 0
3.7.8 | 20A Industrial Socket (Outdoor IP65)-AC | Nos. | RO | 2250 | 750 | [9 empty] | 0 |  |  | 0
3.7.9 | data cum telephone back GI BACK box 2”x2” suitable for data socket | Nos. | 4 | 500 | 300 | 3200 | 250 | 100 | 1400 | 350 | 100 | 1800 |  |  | 0 | 5 |  | 2250
3.7.10 | Bell Push Switch | Nos. | RO | 350 | 150 |  |  |  |  | 350 | 150 |  |  |  | 0 | 1 |  | 500
3.7.11 | Buzzer Indication Set for 5/6 Bell Push | Nos. | RO | 1750 | 750 |  |  |  |  | 1750 | 750 |  |  |  | 0 | 1 |  | 2500
| Sub Total of 3.0 |  |  |  |  | 721750 |  |  | 362065 |  |  | 456720 |  |  | 229660 |  |  | 255566
4 | RACEWAYS, CABLE TRAYS & JUNCTION BOX
4.1 | S & I of PVC trunking same as above but of size 100mm x 40mm x1.6 mm for power cables.(Electrical Room) | Mtr | RO | 420 | 180 | [9 empty] | 0 |  |  | 0
(PROFAB/ASIAN/Approved equivalent)
4.2 | S & I of trunking same as above but of size 85mm x 38mm x1.6 mm thick for power/data cables. | Mtr | RO | 380 | 120 | [9 empty] | 0 |  |  | 0
4.2 | S & I of trunking same as above but of size 65mm x 38mm x1.6 mm thick for power/data cables. | Mtr | RO | 360 | [10 empty] | 0 |  |  | 0
(PROFAB/ASIAN/Approved equivalent)
4.3 | S & I of 1 Run x 25mm dia, MS Conduit in Floor. | Mtr | 100 | 150 | 50 | 20000 | 75 | 40 | 11500 | 140 | 40 | 18000 |  |  | 0 | 99 |  | 17820
4.4 | S & I of floor junction boxes similar to above but size 350mm x 350mm x 60 mm | Nos | RO | 800 | 400 |  |  |  |  | 800 | 400 |  | 1 |  | 1200 | 0 |  | 0
4.5 | S & I of floor junction boxes similar to above but size 250mm x 250mm x 60 mm | Nos | RO | 650 | 250 | [9 empty] | 0 |  |  | 0
4.6 | S & I of floor junction boxes similar to above but size 150mm x 150mm x 60 mm | Nos | 12 | 550 | 250 | 9600 | 420 | 120 | 6480 | 420 | 120 | 6480 | 12 |  | 6480 | 0 |  | 0
4.7 | S & I of GI Pregalvanizd Perforated type Cable Tay
of following sizes suspended from ceiling or fixed
vertically on wall/column as per route directed at site
including all necessary bends, tees, crosses and also
including all necessary supporting arrangement.
All supporting hardware including nuts, bolts etc.
shall be also of galvanised M.S. as approved
(PROFAB/INDIANA/ASIAN/approved equivalent)
4.7.1 | 100mm x 50mm x 1.6mm | Mtr | 50 | 550 | 130 | 34000 | 360 | 100 | 23000 | 300 | 120 | 21000 |  |  | 0 | 38 |  | 15960
4.7.2 | 150mm x 50mm x 1.6mm | Mtr | 10 | 650 | 150 | 8000 | 450 | 120 | 5700 | 400 | 140 | 5400 |  |  | 0 | 4 |  | 2160
4.7.3 | 300mm x 50mm x 1.6mm | Mtr | 30 | 750 | 180 | 27900 | 750 | 180 | 27900 | 750 | 180 | 27900 | 49 |  | 45570 | 0 |  | 0
4.7.4 | 450mm x 50mm x 2.0mm | Mtr | 45 | 1050 | 200 | 56250 | 1050 | 200 | 56250 | 1050 | 200 | 56250 | 49 |  | 61250 | 0 |  | 0
| Sub Total of 4.0 |  |  |  |  | 155750 |  |  | 130830 |  |  | 135030 |  |  | 114500 |  |  | 35940
5 | LIGHT FIXTURES INSTALLATION
5.1 | Installation of lighting fixtures with lamps as per the details below including necessary hardware such as clamps, nuts, bolts, nails screws and suspension rods as required for fixing the fixtures in position as directed by architect / consultant at site.
5.1.1 | SPOT LIGHT (LT1a) | Nos | 12 |  | 350 |  | 0 | 100 |  | 0 | 300 |  |  |  | 0 | 10 |  | 3000
5.1.2 | SPOT LIGHT (LT1b) | Nos | 10 |  | 350 |  | 0 | 100 |  | 0 | 300 |  |  |  | 0 | 9 |  | 2700
5.1.3 | SPOT LIGHT (LT2) | Nos | 17 |  | 350 |  | 0 | 105 |  | 0 | 300 |  |  |  | 0 | 16 |  | 4800
5.1.4 | SUSPENDED LIGHT (LT3) | Nos | 17 |  | 350 |  | 0 | 110 |  | 0 | 200 |  |  |  | 0 | 16 |  | 3200
5.1.5 | HANGING LIGHT (LT4) | Nos | 6 |  | 450 |  | 0 | 150 |  | 0 | 200 |  |  |  | 0 | 5 |  | 1000
5.1.6 | HANGING LIGHT (LT5) | Nos | 4 |  | 450 |  | 0 | 150 |  | 0 | 200 |  |  |  | 0 | 3 |  | 600
5.1.7 | WALL MOUNTED (LT6) | Nos | 8 |  | 350 |  | 0 | 150 |  | 0 | 200 |  |  |  | 0 | 7 |  | 1400
5.1.8 | 2 X 2 CEILING MOUNT LIGHT (LT7a) | Nos | 3 |  | 350 |  | 0 | 175 |  | 0 | 350 |  | 2 |  | 700 | 2 |  | 700
5.1.9 | 2 X 2 CEILING MOUNT LIGHT (LT7b) | Nos | 14 |  | 350 |  | 0 | 175 |  | 0 | 350 |  |  |  | 0 | 13 |  | 4550
5.1.10 | BULB LIGHT (LT8) | Nos | 70 |  | 350 |  | 0 | 100 |  | 0 | 350 |  | 13 |  | 4550 | 68 |  | 23800
5.1.11 | LED COVE LIGHT (LT9) | MTR | 10 |  | 200 |  | 0 | 60 |  | 0 | 100 |  |  |  | 0 | 15 |  | 1500
5.1.12 | TRACK LIGHT-900MM (TL1) | MTR | 6 |  | 350 |  | 0 | 150 |  | 0 | 200 |  |  |  | 0 | 4 |  | 800
5.1.13 | PALM LEAF CEILING FAN (CF1) | Nos | 7 |  | 500 |  | 0 | 225 |  | 0 | 400 |  |  |  | 0 | 6 |  | 2400
| Sub Total of 5.0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 5250 |  |  | 50450
6 | EARTHING :
6.1 | S & I of earth pit comprising of specially designed SEE/Ashlok brand Earth Electrode system 3.00 meter long including necessary materials like side fill compound etc. as required with standard brick masonary chamber with hinged cover and watering arrangement model SEE-60/C with SFC-20/Equivalent ASHLOK MODEL T39 HD (50MM DIA. 3 MTR) | Nos | 2 | 19500 | 5500 | 50000 | 5500 | 2000 | 15000 | 5500 | 2000 | 15000 |  |  | 0 |  |  | 0
6.2 | S & I of copper /GI earthing wires/strips in following sizes
6.3 | 8 SWG GI bare wire | Mtr | 100 | 100 | 50 | 15000 | 40 | 10 | 5000 | 40 | 10 | 5000 | 210 |  | 10500 | 0 |  | 0
6.4 | 25mm x 3mm thick GI strip welded & painted green | Mtr | 150 | 300 | 150 | 67500 | 110 | 20 | 19500 | 110 | 20 | 19500 |  |  | 0 |  |  | 0
6.5 | 25mm x 3mm thick CU strip welded & painted green | Mtr | 10 | 1200 | 250 | 14500 | 950 | 200 | 11500 | 950 | 200 | 11500 |  |  | 0 |  |  | 0
6.6 | S & I of isolated/dedicated earthing / grounding system for computers etc.using insulated green-yellow copper earthing wire laid/fixed bare on wall/ceiling from separately made earth pit to the equipment in following sizes The rate shall include termination also.
6.6.1 | 6 Sqmm copper, yellow-green/green insulation | Mtr | 20 | 200 | 100 | 6000 | 55 | 15 | 1400 | 55 | 15 | 1400 |  |  | 0 |  |  | 0
6.7 | S & I of Main bus for isolated earth comprising of 300mm x 25 mm x 3mm thick Tinned copper bar fixed on insulated support and having 10 nos of holes and nut bolts studs for clamping the earth leads,all contained in MS/PVC box and having transparent acrylic cover as approved by the consultant | Nos | 1 | 8300 | 1200 | 9500 | 2420 | 300 | 2720 | 2420 | 300 | 2720 |  |  | 0 |  |  | 0
| Sub Total of 6.0 |  |  |  |  | 162500 |  |  | 55120 |  |  | 55120 |  |  | 10500 |  |  | 0
7 | Miscellaneous Item
7.1 | Supply & Install. Of RG 6 TV Cable in 25mm MS Conduit | Mtr. | 30 | 250 | 50 | 9000 | 92 | 40 | 3960 | 150 | 50 | 6000 |  |  | 0 |  |  | 0
7.2 | Supply & Laying of RG11 use for Main Cable TV | Mtr. | 50 | 300 | 50 | 17500 | 25 | 15 | 2000 | 50 | 30 | 4000 |  |  | 0 |  |  | 0
7.3 | Install. Of TV Stand - Only Installation | Nos. | 1 |  | 750 |  | 0 | 200 |  | 0 | 200 |  |  |  | 0 |  |  | 0
7.4 | 4 WAY SPLITTER | Nos. | 1 |  | 500 | 500 | 315 | 50 | 365 | 315 | 50 | 365 |  |  | 0 |  |  | 0
| Sub Total of 7.0 |  |  |  |  | 27000 |  |  | 6325 |  |  | 10365 |  |  | 0 |  |  | 0
8 | DATA DISTRIBUTION
Supply, Installation, termination & testing of data system:
8.1 | Main SERVER / ROUTER | Nos. | 1 |  |  |  | 17500 | 1150 |  | 22500 | 1500 |  |  |  | 0 |  |  | 0
8.2 | ROUTER | Nos. | 1 |  |  |  | 12500 | 750 |  | 15000 | 1200 |  |  |  | 0 |  |  | 0
8.3 | SMART GIGABIT SWITCH 24 PORTS | Nos. | 1 | 45000 | 6000 |  | 9500 | 750 |  | 12500 | 1200 |  |  |  | 0 |  |  | 0
8.4 | Loaded PATCH PANEL for 24 Port | Nos. | 1 | 6000 | 2500 |  | 4450 | 1250 |  | 5500 | 1500 |  |  |  | 0 |  |  | 0
8.5 | LIU switch with Accessories. (Optional : if Fibre Optic Cable terminated) | Job | 1 | 9600 | 1900 |  | 9600 | 1550 |  | 9600 | 1550 |  |  |  | 0 |  |  | 0
8.6 | Supply & Installation of I/O DATA Outlet (RJ-45) | Nos. | 19 | 600 | 200 | 15200 | 300 | 100 | 7600 | 300 | 100 | 7600 |  |  | 0 |  |  | 0
8.7 | S & I of Installation of Wi-Fi ceiling mounted Access Point, managed by controller software | Nos. | 3 | 6000 | 1500 |  | 300 | 120 |  | 300 | 120 |  |  |  | 0 |  |  | 0
8.8 | Supply, installation, termination & testing of all Terminations using Fluke Cable Analyser DTX 1800 for all CAT 6 Information Outlet including Information outlet | Lot | 1 | 30000 | 5000 |  | 30000 | 5000 |  | 30000 | 5000 |  |  |  | 0 |  |  | 0
8.9 | CABLES:
8.9.1 | S&I Optical Fiber Cable with 12 fibers, with core dia. 50/125 µm (OM3), suitable for 1GBps Ethernet distance at 850 nm of wavelength, | Mtr. | RO | [11 empty] | 0 |  |  | 0
8.9.2 | S&I Optical Fiber Cable with 6 fibers, with core dia. 50/125 µm (OM3), suitable for 1GBps Ethernet distance at 850 nm of wavelength, | Mtr. | RO | [11 empty] | 0 |  |  | 0
8.9.3 | Supply & providing of CAT 6 UTP cables in the laid raceways / Conduits including terminations | Mtr. | 154 | 220 | 80 | 46200 | 48 | 10 | 8932 | 50 | 10 | 9240 | 69 |  | 4140 | 546 |  | 32760
8.9.4 | Patch cord (2 mtr-user end) | Each | 19 | 120 | 20 |  | 120 | 15 |  | 120 | 20 |  |  |  | 0 |  |  | 0
0
8.1 | Supply, Installation, Testing & Commissioning of Hardware Packets (20 Nos =1 Pkts) | Pkts | 1 | 500 | 100 |  | 500 | 100 |  | 500 | 100 |  |  |  | 0 |  |  | 0
8.11 | Supply, Installation, Testing & Commissioning of Velcro Ties ( 22 Mtrs = 1 Roll) | Roll | 1 | 150 | 100 |  | 150 | 50 |  | 150 | 50 |  |  |  | 0 |  |  | 0
8.12 | Supply, Installation, Testing & Commissioning of Cable Ties 200mm ( 100 Nos. Pkt) | Pkt. | 1 | 150 | 100 |  | 75 | 10 |  | 75 | 20 |  |  |  | 0 |  |  | 0
8.13 | Project Management including Freight & Forwarding, Cable Bunching, Printed Numbering, tube type Ferruling both sides, Face plate, Patch panel & patch cords both sides, Documentation etc.. | Job | 1 | 35000 | 5000 |  | 35000 | 5000 |  | 35000 | 5000 |  |  |  | 0 |  |  | 0
8.14 | Supplying and fixing 15U Rack Aluminium Frame - 600x600mm with 4 x FAN, Dual Split perforated Door at Front and Back Side, 2 x Vertical Cable Basket, 2 x 12 socket 5/15A PDU with MCB, side Panels of 2 nos and Heavy Duty Castors with break, 19" Reduced Channel - Loop Type (DATA+CCTV+PA) | Nos. | 1 | 35000 | 3000 |  | 12500 | 1750 |  | 15000 | 3000 |  |  |  | 0 |  |  | 0
8.15 | Supply & installation of MS conduits with junction boxes, reducer etc. complete concealed/surface mounting as required.
8.15.1 | 25 dia conduit | Mtr. | 100 | 150 | 50 | 20000 | 75 | 40 | 11500 | 140 | 40 | 18000 | 33 |  | 5940 | 236 |  | 42480
| Sub Total of 8.0 |  |  |  |  | 81400 |  |  | 28032 |  |  | 34840 |  |  | 10080 |  |  | 75240
9 | SUPPLY & INSTALLATION OF SAFETY ITEMS
9.1 | Sand buckets with stand (set of 3 buckets) | Sets | RO | 1950 | 350 | [9 empty] | 0 |  |  | 0
9.2 | Caution boards (11kV) of standard Size | Nos | RO | 1500 | [10 empty] | 0 |  |  | 0
9.3 | Caution boards (415V) of std. Size | Nos | 1 | 1500 |  | 1500 | 1500 | 200 | 1700 | 1500 | 400 | 1900 |  |  | 0 |  |  | 0
9.4 | Rubber mat at panel room 12mm thk. 1mtr. Wide | Mtrs | 2 | 2000 |  | 4000 | 2000 | 200 | 4400 | 2000 | 200 | 4400 |  |  | 0 | 2 |  | 4400
9.5 | Shock treatment chart as per electricity board | Nos | 1 | 1000 |  | 1000 | 1000 | 100 | 1100 | 1500 | 100 | 1600 |  |  | 0 |  |  | 0
9.6 | First aid box with standard items | Nos | RO | 5500 | [10 empty] | 0 |  |  | 0
9.7 | 11 KV rating rubber hand gloves | Sets | 2 | 2000 |  | 4000 | 525 | 50 | 1150 | 750 | 50 | 1600 |  |  | 0 |  |  | 0
9.8 | The contractor to submit all the AS BUILT DRAWINGS after the completion of the project for Electrical & ELV Services executed at site. | Part of Tender
| Sub Total of 9.0 |  |  |  |  | 10500 |  |  | 8350 |  |  | 9500 |  |  | 0 |  |  | 4400
10 | UPS/ INVERTER System:
10.1 | Supply /Install of 3 KVA on line Model UPS with inbuilt battery system (1 Phase In & 1 Phase out) Make: Emerson/APC/Consul Neowatt/Vivtar Electronics | set | 1 | 85000 | 10000 | 95000 | 75600 | 3000 | 78600 | 80000 | 5000 | 85000 |  |  | 0 | 1 |  | 85000
| Sub Total of 10 |  |  |  |  | 95000 |  |  | 78600 |  |  | 85000 |  |  | 0 |  |  | 85000
11 | CCTV
11.1 | Supply & Installation of 2 Megapixel IR-20Mtr. IP Indoor Dome + Night vision. Camera Make: CP-PLUS | Nos. | 12 | 3500 | 1500 |  | 3350 | 450 |  | 3350 | 450 |  |  |  | 0 |  |  | 0
11.2 | Supply & Installation of 2 Megapixel IR-20Mtr. IP Indoor Bullet Camera+ Night vision. Camera Make: CP-PLUS | Nos. | RO | 4000 | 1500 | [9 empty] | 0 |  |  | 0
11.3 | Supply & Installation of 2 Megapixel IR-30Mtr. IP Outdoor Bullet Camera + Night vision. Camera Make: CP-PLUS | Nos. | RO | 4000 | 1500 | [9 empty] | 0 |  |  | 0
11.4 | Supply & Installation of 16 Channel NVR with 4 Sata Hard Disk Slot (Make: Honeywell/CP PLUS) | Nos. | 1 | 15000 | 2000 |  | 7550 | 650 |  | 13000 | 1500 |  |  |  | 0 |  |  | 0
11.5 | Supply & Installation of 24 Channel NVR with 4 Sata Hard Disk Slot (Make: Honeywell/CP PLUS) | Nos. | RO | 35000 | 4000 | [9 empty] | 0 |  |  | 0
11.6 | Supply & Installation of 8 Channel NVR with 2 Sata Hard Disk Slot (Make: Honeywell/CP PLUS) | Nos. | RO | 10500 | 2500 | [9 empty] | 0 |  |  | 0
11.7 | Supply & Installation of 16Port PoE(NVR) Switch (Make: Systimax) | Nos. | 1 | 25000 | 2000 |  | 22500 | 2000 |  | 22500 | 2000 |  |  |  | 0 |  |  | 0
11.8 | 4 TB HDD Hard Disk | Nos. | 4 | 10000 | 1500 |  | 6250 | 650 |  | 6250 | 650 |  |  |  | 0 |  |  | 0
11.9 | Monitor/PC system | Nos. | 2 | 30000 | 1500 |  | 30000 | 1500 |  | 30000 | 1500 |  |  |  | 0 |  |  | 0
11.1 | Supply & Installation of CAT-6 Cable for Camera Signal | Mtr. | 270 | 90 | 30 | 32400 | 48 | 10 | 15660 | 50 | 10 | 16200 | 254 |  | 15240 | 0 |  | 0
| Sub Total of 11 |  |  |  |  | 32400 |  |  | 15660 |  |  | 16200 |  |  | 15240 |  |  | 0
12 | PA SYSTEM
12.1 | Supply & Laying of 2 core 2.5 Sq.mm PVC insulated twisted copper conductor Speaker wires in trunking as required. | RM | 42 | 110 | 60 | 7140 | 125 | 60 | 7770 | 125 | 60 | 7770 | 82 |  | 15170 | 0 |  | 0
12.2 | Control Unit (with volume and on/off switch) ( Smooth stepless control, but the control shall be through dimmer switch, the make of which will be same as the make of light control switches ) | Nos. | 1 | 29000 | 5000 | 34000 | 29000 | 5000 | 34000 | 29000 | 5000 | 34000 |  |  | 0 |  |  | 0
12.3 | Supply & Installation of 6W Ceiling Speaker with box- Bosch | Nos. | 6 | 3500 | 500 | 24000 | 3500 | 500 | 24000 | 3500 | 500 | 24000 |  |  | 0 |  |  | 0
12.4 | Voice Alarm Controller with in built 120W Amplifier & Emergency Messaage Manager |  | 1 | 3500 | 1000 | 4500 | 24150 | 1200 | 25350 | 24150 | 1200 | 25350 |  |  | 0 |  |  | 0
12.5 | Supply of Voice Command Centre consisting of Electronics for Audio Control and shall include Amplifiers, Audio Message Generator, Microphone, table top mic etc. | Set. | RO | 49000 | 7000 | [9 empty] | 0 |  |  | 0
12.6 | Supply & Installation of MS Conduit. | RM | 50 | 240 | 35 | 13750 | 240 | 45 | 14250 | 140 | 40 | 9000 | 46 |  | 8280 | 0 |  | 0
| Sub Total of 12 |  |  |  |  | 83390 |  |  | 105370 |  |  | 100120 |  |  | 23450 |  |  | 0
13 | FIRE ALARM SYSTEM (MAKE: HONEYWELL/EST)
13.1 | Single Loop Analog Addressable Fire Alarm Control panel (Expandable upto 1 Loop) with battery back up for 4 hours normal operation and 15 minutes alarm operation. The control panel per Loop Capacity 250 Detectrs and Devices, battery charger etc., 8.5" Touch Screen LCD Display, TCP/IP Connectivity, 10000 Event Log, Keyless Log on Using RFID Cards. The panel shall be UL listed and preferably FM approved with response time less than 10sec. Installation of fire alarm system shall be done as per IS 2189 or relevant NFPA standard.The panel shall have the web enabled facility which can able to send or receive e-mails with memory of 1000 events recording.Note:The vendor shall provide panel UL 9th edition listing certificate. (Make: Edwards / Honeywell) | Nos | 1 | 48000 | 12000 | 60000 | 48000 | 10000 | 58000 | 48000 | 10000 | 58000 | 1 |  | 58000 | 0 |  | 0 | PARESH
i) Each loop with Min. 99 Devices + 99 Detectors modules connection capability of Addressable FACP) 1 Loop Pannel.
ii) FACP with all in-built modules & displays.
iii) 240 volts AC power supply, automatic battery charger, 24 volts sealed lead acid batteries sufficient for 4 hours normal working.
iv) Programming & setting up
v) system to be capable of operating the system for 2 hours during an emergency condition including all necessary software for remote programming of fire alarm system through central control station.
vi) As the number of hooters are 43, additional power supplies to be provided as required.
Necessary Integration Facility with BMS for following functions:-
Alarm, Trouble condition,Supervisory alerts to BMS
Share Graphics of Security, Fire and HVAC
13.1.1 | Fire alarm Addressable control panel (1 Loop)
13.2 | Active Repeater Panel with 8.5" Touch Screen TFT display with TCP/IP Eable Repeater Panel shall monitor and control (Scroll, Acknowledge, Reset & Mute) all the events of the FACP to which it is connected and it shall have Port Vectoring / Event Filtering capability of showing only ALARMS, TROUBLES or SUPERVISORY or customized combinations of user selected events. | Nos | RO | 48000 | 12000 | [9 empty] | 0 |  |  | 0
13.2.1 | Supply installation and testing of signal loop components in a suitable galvanised steel junction box.
13.3 | Detectors and Devices
13.3.1 | Supply,Installation,Testing & Commissioning of Analogue Addressable Monitor module having Rotary, decimal addressing system for monitoring the field devices & shall be capable of providing DPDTcontact rated at 24V DC, 2A. | Nos | RO | 7800 | 700 | [9 empty] | 0 |  |  | 0
13.3.2 | Supply,Installation,Testing & Commissioning of Analogue Addressable Relay module having Rotary, decimal addressing system for AHU tripping and shall be capable of providing DPDTcontact rated at 24v DC, 2A. | Nos | 1 | 7800 | 700 | 8500 | 3550 | 550 | 4100 | 4000 | 550 | 4550 | 1 |  | 4550 | 0 |  | 0
(For all AHU's, Fans & Acess Control)
13.3.3 | Supply,Installation,Testing & Commissioning of Horn / Strobe rated at 82 dBA @ 3m for Audible annunciation and 75cd flashing at 1 Hz for visual indication with Control modules and necessary accessories including back box. | Nos | 3 | 2500 | 500 | 9000 | 2500 | 400 | 8700 | 4200 | 400 | 13800 | 3 |  | 13800 | 0 |  | 0
13.3.4 | Supply,Installation,Testing & Commissioning of Analogue Addressable Flash scan Type Photoelectric smoke detectors( Below False Ceiling) having Rotary, decimal addressing system with standard base, built in isolation function and junction box. The detector shall be capable to address in the range of 1-159. The detector shall be with Visible bi-color LEDs for 360 deg viewing and shall blink green every time the detector is addressed, and illuminate steady red on alarm. | Nos | 4 | 4200 | 700 | 19600 | 2250 | 250 | 10000 | 3400 | 350 | 15000 | 8 |  | 30000 | 0 |  | 0
13.3.5 | Supply,Installation,Testing & Commissioning of Analogue Addressable Flash scan Type Photoelectric smoke detectors (Above False Ceiling) having Rotary, decimal addressing system with standard base, built in isolation function and junction box. The detector shall be capable to address in the range of 1-159. The detector shall be with Visible bi-color LEDs for 360 deg viewing and shall blink green every time the detector is addressed, and illuminate steady red on alarm. | Nos | 4 | 4200 | 700 | 19600 | 2250 | 250 | 10000 | 3400 | 350 | 15000 |  |  | 0 |  |  | 0
13.3.6 | Supply,Installation,Testing & Commissioning of Analogue Addressable Flash scan Type Heat Detector having Rotary, decimal addressing system with standard base, built in isolation function and junction box. The detector shall be capable to address in the range of 1-159. The detector shall be with Visible bi-color LEDs for 360 deg viewing and shall blink green every time the detector is addressed, and illuminate steady red on alarm. | Nos | 3 | 4200 | 700 | 14700 | 2350 | 265 | 7845 | 2700 | 265 | 8895 | 3 |  | 8895 | 0 |  | 0
13.3.7 | Supply,Installation,Testing & Commissioning of Addressable Break Glass Manual Call Point having Rotary, decimal addressing system and having an integrally mounted addressable module that monitors and reports contact status. | Nos | 3 | 3900 | 600 | 13500 | 3250 | 350 | 10800 | 3250 | 350 | 10800 | 3 |  | 10800 | 0 |  | 0
13.4 | SITC of Fault Isolator. | Nos | 2 | 7500 | 500 | 16000 | 3750 | 320 | 8140 | 3750 | 320 | 8140 | 2 |  | 8140 | 0 |  | 0
13.5 | SITC of 2Cx1.5sq.mm multistranded Armoured FRLS RED Colour,Mylan Shielded Screened cable | Mtrs | 75 | 140 | 42 | 13650 | 90 | 20 | 8250 | 90 | 20 | 8250 | 312 |  | 34320 | 118 |  | 12980
13.6 | Response indicator. | Nos | 4 | 250 | 60 | 1240 | 105 | 20 | 500 | 105 | 20 | 500 |  |  | 0 |  |  | 0
| Sub Total of 13 |  |  |  |  | 175790 |  |  | 126335 |  |  | 142935 |  |  | 168505 |  |  | 12980

## M Sheet
BILL OF QUANTITY FOR ELECTRICAL WORK FOR CC - PUNE WAKAD
|  | TENDER BOQ. R0 |  |  |  |  | RA 1 BILL QTY |  |  |  |  | RA 2 BILL QTY
SR. | DESCRIPTION OF ITEM | UNIT | QTY | LOCATION | FROM | TO | QTY | RUN | TOTAL QTY | UNIT | REMARK | QTY | RUN | TOTAL QTY | UNIT | REMARK
1 | PANELS / DBs
Supply and Installation of main LT panel,genarally conforming to IS 8623/IS-13947/IEC-439 front operated, dead back floor mounted , totally enclosed, compartmentalised, vermin proof,indoor, non-drawout type,power panel, fabricated out of 2mm thick CRCA sheets, fully powder coated after seven tank treatment, having gasketed & hinged cover on each cubicle with insulated door knob, incorporating horizontal and vertical copper busbars complete with all internal wiring, danger sign board, earth-bus and lugs, cable chamber, busbar chamber,aluminium anodized name plates etc.as required, including 2 nos. of 6" dia instrument cooling fan with switch and ventilation louvres with wire mesh,housing below mentioned switchgears / meters. 9W fitting with CFL lamp, switch shall be provided in each vertical section,:(Panel should conform to Form- 3b of IEC- 439) (GA drawing of the panel to be got approved from the Consultant before taking up fabrication and all panels to be factory inspected before despatch)
Notes: 1. All MCCBs shall have rotary handle
2. All MCCBs shall have phase spreader assembly on
both Line & Load ends.
3. All MCCB shall have Minimum Ics=16KA)
4. Incomer shall have auxilliary ON/OFF & TRIP status contacts and the same shall be wired up
electronic trip setting to Metering Compartment)
5. The panel shall conform to Form-3b as per IEC-439
6. All MCCB to be of Schneider/ABB make
7. All MCCB to be current limiting type, LSIG
8. Incomer MCCB to be shunt trip facility
Refer: SLD
1.1.1 | MAIN PANEL | Set | 1 | NEAR MAIN ENTRANCE |  |  | 1 |  | 1
[7 empty] | TOTAL QTY |  | 1
1.1.2 | KITCHEN DB | Set | 1 | NEAR STAFF LOCKER |  |  | 1 |  | 1
[7 empty] | TOTAL QTY |  | 1
1.1.3 | BAR DB (4WAY TPN - 7 SEGMENT) | Set | 1 | NEAR STAFF LOCKER |  |  | 1 |  | 1
[7 empty] | TOTAL QTY |  | 1
1.1.4 | KPDB (8WAY TPN - 7 SEGMENT) | Set | 1 | NEAR STAFF LOCKER |  |  | 1 |  | 1
[7 empty] | TOTAL QTY |  | 1
1.1.5 | LDB (8WAY TPN - 7 SEGMENT) | Set | 1 | NEAR MAIN ENTRANCE |  |  | 1 |  | 1
[7 empty] | TOTAL QTY |  | 1
1.1.6 | PDB (8WAY TPN - 7 SEGMENT) | Set | 1 | NEAR MAIN ENTRANCE |  |  | 1 |  | 1
[7 empty] | TOTAL QTY |  | 1
1.2 | Suply and installation of Four -Tier, Multi-Way, TPN,
Distribution Board for Lighting & Power distribution, surface
mounted on wall, sheet metal fabricated,powder coated,
having dust-proof and vermin 'proof, gasketed and hinged
acrylic door with all internals such as DIN rails, neutral-link,
interconnected wiring complete with earthing lugs housing
switchgears: (IP-43 with Metal Door) Refer: SLD & DB Schedule
(Make: Legrand-Ekinoxe /Schneider)
1.2.1 | UPS SPN DB (16WAY SPN) | Set | 1 | NEAR MAIN ENTRANCE |  |  | 1 |  | 1
[7 empty] | TOTAL QTY |  | 1
1.3 | S & I of 32A,DP,MCB +20A NO/NC CONTACTOR, in powder coated sheet metal box for terminating UPS TO UPSDB etc. | Nos | 1 | BELOW KITCHEN PANEL (FOR UPS) | [7 empty] | 1 |  | 1
[12 empty] | TOTAL QTY |  | 1
1.4 | S & I of 32A, TP, MCB + 32A,415 V, Metal clad,Power socket in powder coated metal box for supplying power to Kitchen equipment etc. | Nos | 3 | FOR DISHWASHER IN DISH WASH AREA |  |  | 1 |  | 1
|  |  |  | FOR PULVERISER IN KITCHEN AREA |  |  | 1 |  | 1
[7 empty] | TOTAL QTY |  | 2
1.5 | S & I of 32A,FP,MCB type Isolator, in powder coated sheet metal box for terminating power to equipment etc. | Nos | RO
1.6 | S & I of 63A,,FP,MCB type Isolator, in powder coated sheet metal box for terminating power to equipment etc. | Nos | RO
1.7 | S & I of 32A 3Pin Socket & 32A DP MCB with MS enclosure IP44 | Set | RO
1.8 | S & I of 32A 4P ELMCB 300mA, Metal clad,Power socket in powder coated metal box for supplying power to AC & Kitchen equipment etc. | Nos | 2
1.9 | S & I of 32/63A ELMCB 100mA, Metal clad,Power socket in powder coated metal box for supplying power to equipment etc. | Nos | RO
Sub Total of 1.0
2 | CABLES :
Supply and laying, effecting proper connections, testing & commissioning of the following sizes of 1.1 KV XLPE armoured/ unarmoured PVC insulated PVC sheathed aluminium /copper conductor cables conforming to IS : 1554 and IS 694 for Flexible copper cable Part I - 1976 with latest amendments laid over MS supports in existing RCC ducts/ laid in ground /laid on Cable Trays including clamping the cables to supports in an approved manner as required complete with all accessories.All cables shall have thermo setting insulation XLPE and low emission of smoke and corrosive gas when affected by fire. Necessary Markers shall be provided at the intervals as per the specifications.
2.1.1 | 3.5C x 400 Sq.mm. AL XLPE Cable | R.M | RO
2.1.2 | 3.5C x 300 Sq.mm. AL XLPE Cable | R.M | RO
2.1.3 | 3.5C x 240 Sq.mm. AL XLPE Cable | R.M | RO
2.1.4 | 3.5C x 185 Sq.mm. AL XLPE Cable | R.M | RO
2.1.5 | 3.5C x 150 Sq.mm. AL XLPE Cable | R.M | RO
2.1.6 | 3.5C x 120 Sq.mm. AL XLPE Cable | R.M | RO
2.1.7 | 3.5C x 95 Sq.mm. AL XLPE Cable | R.M | RO
2.1.8 | 3.5C x 70 Sq.mm. AL XLPE Cable- MAIN PANEL | R.M | 80
2.1.9 | 3.5C x 50 Sq.mm. AL XLPE Cable | R.M | RO
2.1.10 | 3.5C x 35 Sq.mm. AL XLPE Cable | R.M | RO
2.1.11 | 3.5C x 25 Sq.mm. AL XLPE Cable | R.M | RO
2.1.12 | 4C x 16 Sq.mm. AL XLPE Cable - PDB, KPDB, KDB, BAR DB & DISHWASHER | R.M | 130 |  | MAIN PANEL | KITCHEN PANEL | 53 | 1 | 53
[5 empty] | MAIN PANEL | KITCHEN POWER PANEL | 51 | 1 | 51
[5 empty] | MAIN PANEL | BAR DB | 49 | 1 | 49
[5 empty] | MAIN PANEL | PDB | 19 | 1 | 19
[7 empty] | TOTAL QTY |  | 172
2.1.13 | 4C x 10 Sq.mm. CU XLPE Cable | R.M | RO
2.1.14 | 4C x 6 Sq.mm. CU XLPE Cable | R.M | RO
2.1.15 | 4C x 4 Sq.mm. CU XLPE Cable - AHU, LDB & PULVERISER | R.M | 57 |  | MAIN PANEL | LDB | 19 | 1 | 19
[5 empty] | MAIN PANEL | AHU (FOH) | 38 | 1 | 38
[5 empty] | MAIN KITCHEN PANEL | AHU (BOH) | 18 | 1 | 18
[5 empty] | MAIN KITCHEN PANEL | CHILLER | 32 | 1 | 32
[5 empty] | MAIN KITCHEN PANEL | SCRUBBER | 16 | 1 | 16
[7 empty] | TOTAL QTY |  | 123
[5 empty] | AHU (FOH) | STARTER PANEL 1 | [5 empty] | 15 | 1 | 15
[5 empty] | STARTER PANEL 1 | AHU (FOH) | [5 empty] | 13 | 1 | 13
[5 empty] | STARTER PANEL 2 | AHU (BOH) | [5 empty] | 18 | 1 | 18
[5 empty] | STARTER PANEL 2 | CHILLER | [5 empty] | 32 | 1 | 32
[12 empty] | TOTAL QTY |  | 78
2.1.16 | 4C x 2.5 Sq.mm. CU XLPE Cable | R.M | RO
2.1.17 | 3C x 16 Sq.mm. CU XLPE Cable | R.M | RO
2.1.18 | 3C X 6sq.mm CU XLPE Cable | R.M | RO
2.1.19 | 3C X 4sq.mm CU XLPE Cable - UPS & UPS DB, REFRIG., FRESH AIR & EXHAUST | R.M | 84 |  | MAIN PANEL | UDB | 19 | 1 | 19
[7 empty] | TOTAL QTY |  | 19
[5 empty] | MAIN PANEL | UPS | [5 empty] | 53 | 1 | 53
[5 empty] | UPS | UDB | [5 empty] | 34 | 1 | 34
[12 empty] | TOTAL QTY |  | 87
2.1.20 | 3C x 2.5 Sq.mm. CU PVC Cable - UPS O/G | R.M | 70 |  | STARTER PANEL 1 | AHU (FOH) | [5 empty] | 12 | 4 | 48
[5 empty] | MAIN KITCHEN PANEL | MOTOR | [5 empty] | 26 | 1 | 26
[5 empty] | UPS DB | FIRE PANEL | [5 empty] | 6 | 1 | 6
[5 empty] | KITCHEN EQUIPMENT | KITCHEN SOCKET | [5 empty] | 3 | 5 | 15
[12 empty] | TOTAL QTY |  | 95
2.1.21 | 3C X 4sq.mm CU PVC Cable | R.M | RO
2.1.22 | 3C X 1.5sq.mm CU PVC Cable-SIGNAGE | R.M | 20
2.1.23 | 1C x 70 Sq.mm, Copper, Flexible, Bunched together | Mtr. | RO |  | BUILDER TAP OFF | MAIN PANEL | [5 empty] | 35 | 2 | 70
[12 empty] | TOTAL QTY |  | 70
2.1.24 | 1C x 4 Sq.mm, Copper, Flexible, Bunched together -UPS | Mtr. | 25
2.1.25 | 2C X 2.5sq.mm CU Cable - Kill switch UPS | R.M | 10
2.2 | CABLE TERMINATION
Making cable and terminations including brass single compression glands and crimping type copper lugs for cable sizes mentioned below for aluminium or copper.
2.2.1 | 3.5C x 400 Sq.mm. AL XLPE Cable | Nos. | RO
2.2.2 | 3.5C x 300 Sq.mm. AL XLPE Cable | Nos. | RO
2.2.3 | 3.5C x 240 Sq.mm. AL XLPE Cable | Nos. | RO
2.2.4 | 3.5C x 185 Sq.mm. AL XLPE Cable | Nos. | RO
2.2.5 | 3.5C x 150 Sq.mm. AL XLPE Cable | Nos. | RO
2.2.6 | 3.5C x 120 Sq.mm. AL XLPE Cable | Nos. | RO
2.2.7 | 3.5C x 95 Sq.mm. AL XLPE Cable | Nos. | RO
2.2.8 | 3.5C x 70 Sq.mm. AL XLPE Cable- MAIN PANEL | Nos. | 2
2.2.9 | 3.5C x 50 Sq.mm. AL XLPE Cable | Nos. | RO
2.2.10 | 3.5C x 35 Sq.mm. AL XLPE Cable | Nos. | RO
2.2.11 | 3.5C x 25 Sq.mm. AL XLPE Cable | Nos. | RO
2.2.12 | 4C x 16 Sq.mm. AL XLPE Cable - PDB, KPDB, KDB, BAR DB & DISHWASHER | Nos. | 10 |  | MAIN PANEL | KITCHEN PANEL | 2 |  | 2
[5 empty] | MAIN PANEL | KITCHEN POWER PANEL | 2 |  | 2
[5 empty] | MAIN PANEL | BAR DB | 2 |  | 2
[5 empty] | MAIN PANEL | PDB | 2 |  | 2
[7 empty] | TOTAL QTY |  | 8
2.2.13 | 4C x 10 Sq.mm. CU XLPE Cable | Nos. | RO
2.2.14 | 4C x 6 Sq.mm. CU XLPE Cable | Nos. | RO
2.2.15 | 4C x 4 Sq.mm. CU XLPE Cable - AHU, LDB & PULVERISER | Nos. | 6 |  | MAIN PANEL | LDB | 2 |  | 2
[5 empty] | MAIN PANEL | AHU (FOH) | 2 |  | 2
[5 empty] | MAIN KITCHEN PANEL | AHU (BOH) | 2 |  | 2
[5 empty] | MAIN KITCHEN PANEL | CHILLER | 2 |  | 2
[5 empty] | MAIN KITCHEN PANEL | SCRUBBER | 2 |  | 2
[7 empty] | TOTAL QTY |  | 10
[5 empty] | AHU (FOH) | STARTER PANEL 1 | [5 empty] | 2 |  | 2
[5 empty] | STARTER PANEL 1 | AHU (FOH) | [5 empty] | 2 |  | 2
[5 empty] | STARTER PANEL 2 | AHU (BOH) | [5 empty] | 2 |  | 2
[5 empty] | STARTER PANEL 2 | CHILLER | [5 empty] | 2 |  | 2
[12 empty] | TOTAL QTY |  | 8
2.2.16 | 4C x 2.5 Sq.mm. CU XLPE Cable | Nos. | RO
2.2.17 | 3C x 16 Sq.mm. CU XLPE Cable | Nos. | RO
2.2.18 | 3C X 6sq.mm CU XLPE Cable | Nos. | RO
2.2.19 | 3C X 4sq.mm CU XLPE Cable - UPS & UPS DB, REFRIG., FRESH AIR & EXHAUST | Nos. | 14 |  | MAIN PANEL | UDB | 2 |  | 2
[7 empty] | TOTAL QTY |  | 2
[5 empty] | MAIN PANEL | UPS | [5 empty] | 2 |  | 2
[5 empty] | UPS | UDB | [5 empty] | 2 |  | 2
[12 empty] | TOTAL QTY |  | 4
2.2.20 | 3C x 2.5 Sq.mm. CU PVC Cable - UPS O/G | Nos. | 4 |  | STARTER PANEL 1 | AHU (FOH) | [5 empty] | 8 |  | 8
[5 empty] | MAIN KITCHEN PANEL | MOTOR | [5 empty] | 2 |  | 2
[5 empty] | UPS DB | FIRE PANEL | [5 empty] | 2 |  | 2
[5 empty] | KITCHEN EQUIPMENT | KITCHEN SOCKET | [5 empty] | 10 |  | 10
[12 empty] | TOTAL QTY |  | 22
2.2.21 | 3C X 4sq.mm CU PVC Cable | Nos. | RO
2.2.22 | 3C X 1.5sq.mm CU PVC Cable-SIGNAGE | Nos. | 8
2.2.23 | 1C x 70 Sq.mm, Copper, Flexible, Bunched together | Nos. | RO |  | BUOLDER TAP OFF | MAIN PANEL | [5 empty] | 4 |  | 4
[12 empty] | TOTAL QTY |  | 4
2.2.24 | 1C x 4 Sq.mm, Copper, Flexible, Bunched together -UPS | Nos. | 12
2.2.24 | 2C X 2.5sq.mm CU Cable - Kill switch UPS | Nos. | 2
Sub Total of 2
3 | POINT WIRING :
3.1 | LIGHT POINT
Sub mains / Pre-Primary wiring i.e. from DB to room switch board shall be carried out for Pre-primary point using 1.5 sqmm copper stranded. All lighting fixture, wiring shall be carried out for primary point using 1.5 sqmm copper stranded & for secondary wiring 1.5sqmm copper stranded conductor 660/1100V grade PVC FRLS insulated wire in "MS Conduits" (including flexible conduits for drops to light fittings)". Individual junction / inspection boxes shall be provided for each lighting fitting for the purpose of looping from fitting to fitting.
also including insulated green color copper earth wire for each circuit and providing modular grid plate type switches,sockets etc. as required. Each light point to be terminated using 5A connector or 5A two pin female socket (for cove lighting) as directed at site. Each circuit feeding not more than 12-8 points/800 watts as per following configuration:(LDBs located at two locations as shown) (The Switch Socket cost shall be paid separately.)
From distribution board to switch board will be termed as Pre-primary point, average wiring length for Pre-primary point to be considered as 15 metres. From switch board to first light fitting and switch board to switch board will be termed as primary point, average wiring length for primary point to be considered as 3 metres and First fitting to subsequent fitting on the same circuit shall be termed as secondary point, average wiring length for secondary point to be considered as 5 metres. Light point wiring shall be included submains wiring from D.B. to room switch board.
Note: Length may vary as per actual site condition. Vendor shall be crossverify before bidding.
3.1.1 | Pre-Primary point (sub mains point) | Nos | 20 | LDB - R1 | LDB | KITCHEN & TANDOOR SWITCH BOARD | 1 |  | 1
|  |  |  | LDB - R2 | LDB | FOH AREA | 1 |  | 1
|  |  |  | LDB - R3 | LDB | FOH AREA | 1 |  | 1
|  |  |  | LDB - R4 | LDB | FOH AREA | 1 |  | 1
|  |  |  | LDB - R5 | LDB | FOH AREA | 1 |  | 1
|  |  |  | LDB - R6 | LDB | FOH AREA | 1 |  | 1
|  |  |  | LDB - Y1 | LDB | FOH AREA | 1 |  | 1
|  |  |  | LDB - Y2 | LDB | FOH AREA | 1 |  | 1
|  |  |  | LDB - Y3 | LDB | FOH AREA | 1 |  | 1
|  |  |  | LDB - Y4 | LDB | FOH AREA | 1 |  | 1
|  |  |  | LDB - Y5 | LDB | FOH AREA | 1 |  | 1
|  |  |  | LDB - Y6 | LDB | FOH AREA | 1 |  | 1
|  |  |  | LDB - B1 | LDB | LIQUOR STORE | 1 |  | 1
|  |  |  | LDB - B2 | LDB | FOH AREA | 1 |  | 1
|  |  |  | LDB - B3 | LDB | FOH AREA | 1 |  | 1
|  |  |  | LDB - B4 | LDB | FOH AREA | 1 |  | 1
|  |  |  | LDB - B5 | LDB | FOH AREA | 1 |  | 1
|  |  |  | LDB - B6 | LDB | FOH AREA | 1 |  | 1
[7 empty] | TOTAL QTY |  | 18
3.1.2 | Primary point | Nos | 15 | LDB - R1 | KITCHEN SB | TANDOOR SB | 1 |  | 1
|  |  |  | LDB - R1 | KITCHEN SB | LIGHT POINT | 2 |  | 2
|  |  |  | LDB - R1 | TANDOOR SB | LIGHT POINT | 1 |  | 1
|  |  |  | LDB - R2 | LDB | LIGHT POINT | 1 |  | 1
|  |  |  | LDB - R3 | LDB | FAN POINT | 1 |  | 1
|  |  |  | LDB - R4 | LDB | LIGHT POINT | 1 |  | 1
|  |  |  | LDB - R5 | LDB | LIGHT POINT | 1 |  | 1
|  |  |  | LDB - R6 | LDB | LIGHT POINT | 1 |  | 1
|  |  |  | LDB - Y1 | LDB | LIGHT POINT | 1 |  | 1
|  |  |  | LDB - Y2 | LDB | LIGHT POINT | 1 |  | 1
|  |  |  | LDB - Y3 | LDB | FAN POINT | 1 |  | 1
|  |  |  | LDB - Y4 | LDB | LIGHT POINT | 1 |  | 1
|  |  |  | LDB - Y5 | LDB | LIGHT POINT | 1 |  | 1
|  |  |  | LDB - Y6 | LDB | LIGHT POINT | 1 |  | 1
|  |  |  | LDB - B1 | LIQUOR STORE SB | LIGHT POINT | 5 |  | 5
|  |  |  | LDB - B2 | LDB | LIGHT POINT | 1 |  | 1
|  |  |  | LDB - B3 | LDB | LIGHT POINT | 1 |  | 1
|  |  |  | LDB - B4 | LDB | LIGHT POINT | 1 |  | 1
|  |  |  | LDB - B5 | LDB | LIGHT POINT | 1 |  | 1
|  |  |  | LDB - B6 | LDB | LIGHT POINT | 1 |  | 1
[7 empty] | TOTAL QTY |  | 25
|  |  |  | UDB | BAR SB | LIGHT POINT | [5 empty] | 1 |  | 1
[5 empty] | TANDOOR SB | LIGHT POINT | [5 empty] | 1 |  | 1
[5 empty] | KITCHEN SB | LIGHT POINT | [5 empty] | 1 |  | 1
[5 empty] | FOH AREA UDB | LIGHT POINT | [5 empty] | 2 |  | 2
|  |  |  | LDB | TANDOOR AREA | CHIMNEY LIGHT | [5 empty] | 1 |  | 1
|  |  |  | LDB | KITCHEN AREA | CHIMNEY LIGHT | [5 empty] | 1 |  | 1
[12 empty] | TOTAL QTY |  | 7
3.1.3 | Secondary Point | Nos | 145 | LDB - R1 | LIGHT POINT | LIGHT POINT | 9 |  | 9
|  |  |  | LDB - R2 | LIGHT POINT | LIGHT POINT | 4 |  | 4
|  |  |  | LDB - R3 | FAN POINT | FAN POINT | 2 |  | 2
|  |  |  | LDB - R4 | LIGHT POINT | LIGHT POINT | 3 |  | 3
|  |  |  | LDB - R5 | LIGHT POINT | LIGHT POINT | 9 |  | 9
|  |  |  | LDB - R6 | LIGHT POINT | LIGHT POINT | 10 |  | 10
|  |  |  | LDB - Y1 | LIGHT POINT | LIGHT POINT | 8 |  | 8
|  |  |  | LDB - Y2 | LIGHT POINT | LIGHT POINT | 2 |  | 2
|  |  |  | LDB - Y3 | FAN POINT | FAN POINT | 2 |  | 2
|  |  |  | LDB - Y4 | LIGHT POINT | LIGHT POINT | 6 |  | 6
|  |  |  | LDB - Y5 | LIGHT POINT | LIGHT POINT | 10 |  | 10
|  |  |  | LDB - Y6 | LIGHT POINT | LIGHT POINT | 10 |  | 10
|  |  |  | LDB - B1 | LIGHT POINT | LIGHT POINT | 5 |  | 5
|  |  |  | LDB - B2 | LIGHT POINT | LIGHT POINT | 9 |  | 9
|  |  |  | LDB - B3 | LIGHT POINT | LIGHT POINT | 4 |  | 4
|  |  |  | LDB - B4 | LIGHT POINT | LIGHT POINT | 4 |  | 4
|  |  |  | LDB - B5 | LIGHT POINT | LIGHT POINT | 11 |  | 11
|  |  |  | LDB - B6 | LIGHT POINT | LIGHT POINT | 11 |  | 11
[7 empty] | TOTAL QTY |  | 119
|  |  |  | BAR AREA | LIGHT POINT | LIGHT POINT | [5 empty] | 1 |  | 1
|  |  |  | TANDOOR SECTION | LIGHT POINT | LIGHT POINT | [5 empty] | 0 |  | 0
|  |  |  | KITCHEN AREA | LIGHT POINT | LIGHT POINT | [5 empty] | 2 |  | 2
|  |  |  | FOH AREA UDB | LIGHT POINT | LIGHT POINT | [5 empty] | 7 |  | 7
|  |  |  | TANDOOR AREA | CHIMNEY LIGHT | CHIMNEY LIGHT | [5 empty] | 3 |  | 3
|  |  |  | KITCHEN AREA | CHIMNEY LIGHT | CHIMNEY LIGHT | [5 empty] | 3 |  | 3
[12 empty] | TOTAL QTY |  | 16
3.2 | LIGHT POINT For Automation
All lighting fixture, wiring shall be carried out for primary point using 1.5 sqmm copper stranded & for secondary wiring 1.5sqmm copper stranded conductor 660/1100V grade PVC FRLS insulated wire in "MS Conduits" & 1 pair 1.5sqmm jacketed cable in Separate Conduit (including flexible conduits for drops to light fittings)". Individual junction / inspection boxes shall be provided for each lighting fitting for the purpose of looping from fitting to fitting.
From DB to first light fitting/driver will be termed as primary point, average wiring length for primary point to be considered as 25 metres and First fitting to subsequent fitting on the same circuit shall be termed as secondary point, average wiring length for secondary point to be considered as 5 metres. Light point wiring shall be included submains wiring from D.B. to room lights/Driver.
Note: Length may vary as per actual site condition. Vendor shall be crossverify before bidding.
3.2.1 | Primary point | Nos | RO
3.2.2 | Secondary Point | Nos | RO
3.3 | Power Point (Utility)
Primary wiring i.e. from DB to first power point shall be carried out for primary point using 3R x 2.5 sqmm copper stranded. Secondary wiring 2.5sqmm copper stranded conductor 660/1100V grade PVC FRLS insulated wire in "MS Conduit". Individual junction/inspection boxes shall be provided for each power point to loop from power point to a power point. Only 4 points looped in one circuit) From DB to First Socket.
From distribution board to first power point will be termed as primary point, average wiring length for primary point to be considered as 18 metres. First power point to subsequent power point on the same circuit shall be termed as secondary point, average wiring length for secondary point to be considered as 8 metres. Power point wiring shall be included wiring from D.B. to room indivisual power point.
Note: Length may vary as per actual site condition. Vendor shall be crossverify before bidding.
3.3.1 | Primary point | Nos | 22 | PDB R1 | PDB R1 | POWER POINT | [5 empty] | 1 |  | 1
|  |  |  | PDB R2 | PDB R2 | POWER POINT | [5 empty] | 1 |  | 1
|  |  |  | PDB R3 | PDB R3 | POWER POINT | [5 empty] | 1 |  | 1
|  |  |  | PDB R4 | PDB R4 | POWER POINT | [5 empty] | 1 |  | 1
|  |  |  | PDB R5 | PDB R5 | POWER POINT | [5 empty] | 1 |  | 1
|  |  |  | PDB R6 | PDB R6 | POWER POINT | [5 empty] | 1 |  | 1
|  |  |  | PDB Y1 | PDB Y1 | POWER POINT | [5 empty] | 1 |  | 1
|  |  |  | PDB Y2 | PDB Y2 | POWER POINT | [5 empty] | 1 |  | 1
|  |  |  | PDB Y3 | PDB Y3 | POWER POINT | [5 empty] | 1 |  | 1
|  |  |  | PDB Y4 | PDB Y4 | POWER POINT | [5 empty] | 1 |  | 1
|  |  |  | PDB Y5 | PDB Y5 | POWER POINT | [5 empty] | 1 |  | 1
|  |  |  | PDB Y6 | PDB Y6 | POWER POINT | [5 empty] | 1 |  | 1
|  |  |  | PDB B1 | PDB B1 | POWER POINT | [5 empty] | 1 |  | 1
|  |  |  | PDB B2 | PDB B2 | POWER POINT | [5 empty] | 1 |  | 1
|  |  |  | PDB B3 | PDB B3 | POWER POINT | [5 empty] | 1 |  | 1
|  |  |  | PDB B4 | PDB B4 | POWER POINT | [5 empty] | 1 |  | 1
|  |  |  | PDB B5 | PDB B5 | POWER POINT | [5 empty] | 1 |  | 1
|  |  |  | UDB C1 | UDB C1 | POWER POINT | [5 empty] | 1 |  | 1
|  |  |  | UDB C2 | UDB C2 | POWER POINT | [5 empty] | 1 |  | 1
[12 empty] | TOTAL QTY |  | 19
3.3.1 | Primary point ( Distance between Switch & socket Will be Average Length 2.5 Mtr. ) | Nos | RO
3.3.2 | Secondary Point | Nos | 16 | PDB R1 | POWER POINT | POWER POINT | [5 empty] | 0 |  | 0
|  |  |  | PDB R2 | POWER POINT | POWER POINT | [5 empty] | 3 |  | 3
|  |  |  | PDB R3 | POWER POINT | POWER POINT | [5 empty] | 2 |  | 2
|  |  |  | PDB R4 | POWER POINT | POWER POINT | [5 empty] | 0 |  | 0
|  |  |  | PDB R5 | POWER POINT | POWER POINT | [5 empty] | 0 |  | 0
|  |  |  | PDB R6 | POWER POINT | POWER POINT | [5 empty] | 0 |  | 0
|  |  |  | PDB Y1 | POWER POINT | POWER POINT | [5 empty] | 0 |  | 0
|  |  |  | PDB Y2 | POWER POINT | POWER POINT | [5 empty] | 2 |  | 2
|  |  |  | PDB Y3 | POWER POINT | POWER POINT | [5 empty] | 1 |  | 1
|  |  |  | PDB Y4 | POWER POINT | POWER POINT | [5 empty] | 0 |  | 0
|  |  |  | PDB Y5 | POWER POINT | POWER POINT | [5 empty] | 0 |  | 0
|  |  |  | PDB Y6 | POWER POINT | POWER POINT | [5 empty] | 0 |  | 0
|  |  |  | PDB B1 | POWER POINT | POWER POINT | [5 empty] | 0 |  | 0
|  |  |  | PDB B2 | POWER POINT | POWER POINT | [5 empty] | 3 |  | 3
|  |  |  | PDB B3 | POWER POINT | POWER POINT | [5 empty] | 1 |  | 1
|  |  |  | PDB B4 | POWER POINT | POWER POINT | [5 empty] | 0 |  | 0
|  |  |  | PDB B5 | POWER POINT | POWER POINT | [5 empty] | 0 |  | 0
|  |  |  | UDB C1 | POWER POINT | POWER POINT | [5 empty] | 3 |  | 3
|  |  |  | UDB C2 | POWER POINT | POWER POINT | [5 empty] | 7 |  | 7
[12 empty] | TOTAL QTY |  | 22
3.4 | Power Point (Kitchen & BAR)
Primary wiring i.e. from DB to first power point shall be carried out for primary point using 3R x 4 sqmm copper stranded. Secondary wiring 4sqmm copper stranded conductor 660/1100V grade PVC FRLS insulated wire in "MS Conduit". Individual junction/inspection boxes shall be provided for each power point to loop from power point to a power point. Only 4 points looped in one circuit) From DB to First Socket.
From distribution board to first power point will be termed as primary point, average wiring length for primary point to be considered as 12 metres. First power point to subsequent power point on the same circuit shall be termed as secondary point, average wiring length for secondary point to be considered as 2 metres. Power point wiring shall be included wiring from D.B. to room indivisual power point.
Note: Length may vary as per actual site condition. Vendor shall be crossverify before bidding.
3.4.1 | Primary point | Nos | 30 | BAR DB R1 | BAR DB R1 | POWER POINT | [5 empty] | 1 |  | 1
|  |  |  | BAR DB R2 | BAR DB R2 | POWER POINT | [5 empty] | 1 |  | 1
|  |  |  | BAR DB Y1 | BAR DB Y1 | POWER POINT | [5 empty] | 1 |  | 1
|  |  |  | BAR DB Y2 | BAR DB Y2 | POWER POINT | [5 empty] | 1 |  | 1
|  |  |  | BAR DB Y3 | BAR DB Y3 | POWER POINT | [5 empty] | 1 |  | 1
|  |  |  | BAR DB B1 | BAR DB B1 | POWER POINT | [5 empty] | 1 |  | 1
|  |  |  | KPDB R1 | KPDB R1 | POWER POINT | [5 empty] | 2 |  | 2
|  |  |  | KPDB R2 | KPDB R2 | POWER POINT | [5 empty] | 1 |  | 1
|  |  |  | KPDB R3 | KPDB R3 | POWER POINT | [5 empty] | 1 |  | 1
|  |  |  | KPDB R4 | KPDB R4 | POWER POINT | [5 empty] | 1 |  | 1
|  |  |  | KPDB R5 | KPDB R5 | POWER POINT | [5 empty] | 1 |  | 1
|  |  |  | KPDB Y1 | KPDB Y1 | POWER POINT | [5 empty] | 1 |  | 1
|  |  |  | KPDB Y2 | KPDB Y2 | POWER POINT | [5 empty] | 1 |  | 1
|  |  |  | KPDB Y3 | KPDB Y3 | POWER POINT | [5 empty] | 1 |  | 1
|  |  |  | KPDB Y4 | KPDB Y4 | POWER POINT | [5 empty] | 1 |  | 1
|  |  |  | KPDB Y5 | KPDB Y5 | POWER POINT | [5 empty] | 1 |  | 1
|  |  |  | KPDB B1 | KPDB B1 | POWER POINT | [5 empty] | 1 |  | 1
|  |  |  | KPDB B2 | KPDB B2 | POWER POINT | [5 empty] | 1 |  | 1
|  |  |  | KPDB B3 | KPDB B3 | POWER POINT | [5 empty] | 1 |  | 1
|  |  |  | KPDB B4 | KPDB B4 | POWER POINT | [5 empty] | 1 |  | 1
|  |  |  | KPDB B5 | KPDB B5 | POWER POINT | [5 empty] | 1 |  | 1
|  |  |  | KPDB B7 | KPDB B7 | POWER POINT | [5 empty] | 1 |  | 1
[12 empty] | TOTAL QTY |  | 23
3.4.2 | Primary point ( Distance between Switch & socket Will be Average Length 2.5 Mtr. ) | Nos | RO
3.4.3 | Secondary Point | Nos | RO | BAR DB R1 | POWER POINT | POWER POINT | [5 empty] | 1 |  | 1
|  |  |  | BAR DB R2 | POWER POINT | POWER POINT | [5 empty] | 1 |  | 1
|  |  |  | BAR DB Y1 | POWER POINT | POWER POINT | [5 empty] | 1 |  | 1
|  |  |  | BAR DB Y2 | POWER POINT | POWER POINT | [5 empty] | 2 |  | 2
|  |  |  | BAR DB Y3 | POWER POINT | POWER POINT | [5 empty] | 0 |  | 0
|  |  |  | BAR DB B1 | POWER POINT | POWER POINT | [5 empty] | 0 |  | 0
|  |  |  | KPDB R1 | POWER POINT | POWER POINT | [5 empty] | 3 |  | 3
|  |  |  | KPDB R2 | POWER POINT | POWER POINT | [5 empty] | 1 |  | 1
|  |  |  | KPDB R3 | POWER POINT | POWER POINT | [5 empty] | 1 |  | 1
|  |  |  | KPDB R4 | POWER POINT | POWER POINT | [5 empty] | 1 |  | 1
|  |  |  | KPDB R5 | POWER POINT | POWER POINT | [5 empty] | 0 |  | 0
|  |  |  | KPDB Y1 | POWER POINT | POWER POINT | [5 empty] | 1 |  | 1
|  |  |  | KPDB Y2 | POWER POINT | POWER POINT | [5 empty] | 0 |  | 0
|  |  |  | KPDB Y3 | POWER POINT | POWER POINT | [5 empty] | 1 |  | 1
|  |  |  | KPDB Y4 | POWER POINT | POWER POINT | [5 empty] | 2 |  | 2
|  |  |  | KPDB Y5 | POWER POINT | POWER POINT | [5 empty] | 0 |  | 0
|  |  |  | KPDB B1 | POWER POINT | POWER POINT | [5 empty] | 0 |  | 0
|  |  |  | KPDB B2 | POWER POINT | POWER POINT | [5 empty] | 1 |  | 1
|  |  |  | KPDB B3 | POWER POINT | POWER POINT | [5 empty] | 0 |  | 0
|  |  |  | KPDB B4 | POWER POINT | POWER POINT | [5 empty] | 1 |  | 1
|  |  |  | KPDB B5 | POWER POINT | POWER POINT | [5 empty] | 3 |  | 3
|  |  |  | KPDB B7 | POWER POINT | POWER POINT | [5 empty] | 0 |  | 0
[12 empty] | TOTAL QTY |  | 20
3.5 | S & I of MS conduits including all accessories, clamps, spacers, bends, tee, cross etc. as required at site for miscellaneous use in following sizes:
3.5.1 | 20mm dia | Mtr | RO
3.5.2 | 25mm dia | Mtr | 100
3.6 | S & I of flexible GI conduits including all accessories, clamps, spacers, end adopters (Glands) etc. as required at site in following sizes:
3.6.1 | 20mm dia | Mtr | RO | HANGING LIGHT ROPE | [7 empty] | 3 | 8 | 24
[12 empty] | TOTAL QTY |  | 24
3.6.2 | 25mm dia (COMMON) | Mtr | 75
3.7 | Supply, Installation testing and commission of 240V-AC, wiring devices and its accessories such as modular type switch socket outlets with modular front plate, modular box, G.I. back box and all required accessories etc. Supply & Installation scope includes all civil works related to this job such as chiselling , making good with concrete and plaster, supply of fixing screw / wall plugs and other necessary hardware, marking identification numbers of circuits & interconnections of the switch /sockets as per standard drawing, complete as per site requirement. Switches and sockets may be individual or combined with bigger lighting switchboards, contractor to refer drawings to understand exact scope of work. LEGRAND
3.7.1 | 6A One way plate type switch | Nos. | 14 | BAR AREA | [7 empty] | 7 |  | 7
|  |  |  | TANDOOR SECTION | [7 empty] | 3 |  | 3
|  |  |  | KITCHEN AREA | [7 empty] | 7 |  | 7
|  |  |  | FOH AREA BELOW COUNTER (FOR LED STRIP) | [7 empty] | 2 |  | 2
[12 empty] | TOTAL QTY |  | 19
3.7.2 | 6A Two way plate type switch | Nos. | RO
3.7.3 | 6/16A SOCKET & SWITCH | Nos. | 28 | FOH AREA | [7 empty] | 43 |  | 43
[12 empty] | TOTAL QTY |  | 43
3.7.4 | 2Nos. 6/16A SOCKET & SWITCH | Sets | 6
|  |  |  | NEAR LDB \ PDB | [7 empty] | 3 |  | 3
|  |  |  | BILLING COUNTER | [7 empty] | 3 |  | 3
|  |  |  | SERVICE TABLE | [7 empty] | 2 |  | 2
|  |  |  | NEAR KITCHEN PANEL | [7 empty] | 1 |  | 1
|  |  |  | NEAR SERVER RACK | [7 empty] | 2 |  | 2
|  |  |  | KITCHEN AREA DISPLAY | [7 empty] | 1 |  | 1
|  |  |  | KITCHEN AREA FRIDGE | [7 empty] | 1 |  | 1
|  |  |  | DISH WASH AREA | [7 empty] | 1 |  | 1
|  |  |  | ABOVE TANDDOR DOOR | [7 empty] | 1 |  | 1
|  |  |  | BAR AREA | [7 empty] | 1 |  | 1
|  |  |  | KITCHEN AREA BELOW TRAY | [7 empty] | 6 |  | 6
[12 empty] | TOTAL QTY |  | 22
3.7.5 | 6/16A SOCKET & SWITCH - Kitchen | Sets | 42 | ICE CUBE MACHINE (BAR AREA) |  |  | 1 |  | 1
|  |  |  | BACK BAR COOLE (BAR AREA) |  |  | 2 |  | 2
|  |  |  | COFFE MACHINE & GRINDER (BAR AREA) |  |  | 3 |  | 3
|  |  |  | CHILLING MACHINE (BAR AREA) |  |  | 2 |  | 2
|  |  |  | BLENDER (BAR AREA) |  |  | 2 |  | 2
|  |  |  | BAR COOLER (BAR AREA) |  |  | 2 |  | 2
|  |  |  | REFRIGERATOR (TANDOOR SECTION) |  |  | 3 |  | 3
|  |  |  | EXHAUST LIGHT (TANDOOR SECTION) |  |  | 1 |  | 1
|  |  |  | WATER COOLER (KITCHEN AREA) |  |  | 2 |  | 2
|  |  |  | VEER REFER & FREEZER (KITCHEN AREA) |  |  | 1 |  | 1
|  |  |  | COMPUTER (KITCHEN AREA) |  |  | 3 |  | 3
|  |  |  | REFRIGERATOR & POS (KITCHEN AREA) |  |  | 4 |  | 4
|  |  |  | BAIN MARIE (KITCHEN AREA) |  |  | 3 |  | 3
|  |  |  | EXHAUST LIGHT (KITCHEN AREA) |  |  | 2 |  | 2
|  |  |  | REFRIGERATOR (KITCHEN AREA) |  |  | 2 |  | 2
|  |  |  | MEAT MINCER (KITCHEN AREA) |  |  | 2 |  | 2
|  |  |  | REFRIGERATOR (KITCHEN AREA) |  |  | 2 |  | 2
|  |  |  | VEER REFER & FREEZER (KITCHEN AREA) |  |  | 1 |  | 1
|  |  |  | VEER REFER & FREEZER (KITCHEN AREA) |  |  | 1 |  | 1
|  |  |  | VEER REFER & FREEZER (KITCHEN AREA) |  |  | 1 |  | 1
|  |  |  | VISICOOLER (KITCHEN AREA) |  |  | 2 |  | 2
|  |  |  | DEEP FREEZER (KITCHEN AREA) |  |  | 2 |  | 2
|  |  |  | REFRIGERATOR (KITCHEN AREA) |  |  | 3 |  | 3
|  |  |  | AIR CURTAIN (KITCHEN ENTRY DOOR |  |  | 2 |  | 2
|  |  |  | INDUCTION (FOH AREA) |  |  | 11 |  | 11
[7 empty] | TOTAL QTY |  | 60
3.7.6 | 20A switch & socket outlet - Kitchen | Sets | 8 | FOR DEEP FAT FRYER IN KITCHEN AREA |  |  | 2 |  | 2
|  |  |  | FOR STEP IN (KITCHEN AREA) |  |  | 1 |  | 1
|  |  |  | FOR GEYSER IN KITCHEN AREA |  |  | 2 |  | 2
|  |  |  | FOR GEYSER IN DISH WASH AREA |  |  | 2 |  | 2
|  |  |  | FOR GLASS WASHER IN BAR AREA |  |  | 1 |  | 1
[7 empty] | TOTAL QTY |  | 8
3.7.7 | 20A Socket -AC | Nos. | RO
3.7.8 | 20A Industrial Socket (Outdoor IP65)-AC | Nos. | RO
3.7.9 | data cum telephone back GI BACK box 2”x2” suitable for data socket | Nos. | 4 | FOH AREA | [7 empty] | 3 |  | 3
|  |  |  | KITCHEN AREA | [7 empty] | 2 |  | 2
[12 empty] | TOTAL QTY |  | 5
3.7.10 | Bell Push Switch | Nos. | RO | KITCHEN AREA FRIDGE | [7 empty] | 1 |  | 1
[12 empty] | TOTAL QTY |  | 1
3.7.11 | Buzzer Indication Set for 5/6 Bell Push | Nos. | RO | KITCHEN AREA FRIDGE | [7 empty] | 1 |  | 1
[12 empty] | TOTAL QTY |  | 1
Sub Total of 3.0
4 | RACEWAYS, CABLE TRAYS & JUNCTION BOX
4.1 | S & I of PVC trunking same as above but of size 100mm x 40mm x1.6 mm for power cables.(Electrical Room) | Mtr | RO
(PROFAB/ASIAN/Approved equivalent)
4.2 | S & I of trunking same as above but of size 85mm x 38mm x1.6 mm thick for power/data cables. | Mtr | RO
4.2 | S & I of trunking same as above but of size 65mm x 38mm x1.6 mm thick for power/data cables. | Mtr | RO
(PROFAB/ASIAN/Approved equivalent)
4.3 | S & I of 1 Run x 25mm dia, MS Conduit in Floor. | Mtr | 100 |  | JB 1 | PDB | [5 empty] | 9 | 1 | 9
[5 empty] | JB 2 | PDB | [5 empty] | 11 | 1 | 11
[5 empty] | JB 3 | PDB | [5 empty] | 13 | 1 | 13
[5 empty] | JB 4 | PDB | [5 empty] | 15 | 1 | 15
[5 empty] | JB 5 | PDB | [5 empty] | 14 | 1 | 14
[5 empty] | JB 6 | PDB | [5 empty] | 14 | 1 | 14
[5 empty] | JB 7 | PDB | [5 empty] | 8 | 1 | 8
[5 empty] | JB 8 | PDB | [5 empty] | 6 | 1 | 6
[5 empty] | JB 9 | PDB | [5 empty] | 5 | 1 | 5
[5 empty] | JB 10 | PDB | [5 empty] | 4 | 1 | 4
[12 empty] | TOTAL QTY |  | 99
4.4 | S & I of floor junction boxes similar to above but size 350mm x 350mm x 60 mm | Nos | RO | FOH AREA (BELOW PDB) |  |  | 1 |  | 1
[7 empty] | TOTAL QTY |  | 1
4.5 | S & I of floor junction boxes similar to above but size 250mm x 250mm x 60 mm | Nos | RO
4.6 | S & I of floor junction boxes similar to above but size 150mm x 150mm x 60 mm | Nos | 12 | FOH AREA |  |  | 12 |  | 12
[7 empty] | TOTAL QTY |  | 12
4.7 | S & I of GI Pregalvanizd Perforated type Cable Tay
of following sizes suspended from ceiling or fixed
vertically on wall/column as per route directed at site
including all necessary bends, tees, crosses and also
including all necessary supporting arrangement.
All supporting hardware including nuts, bolts etc.
shall be also of galvanised M.S. as approved
(PROFAB/INDIANA/ASIAN/approved equivalent)
4.7.1 | 100mm x 50mm x 1.6mm | Mtr | 50 | KITCHEN AREA | [7 empty] | 19 | 1 | 19
|  |  |  | FOH AREA | [7 empty] | 15 | 1 | 15
|  |  |  | ABOVE LDB \ PDB | [7 empty] | 4 | 1 | 4
[12 empty] | TOTAL QTY |  | 38
4.7.2 | 150mm x 50mm x 1.6mm | Mtr | 10 | VERTICAL DROP BAR DB | [7 empty] | 4 | 1 | 4
[12 empty] | TOTAL QTY |  | 4
4.7.3 | 300mm x 50mm x 1.6mm | Mtr | 30 |  | MAIN ENTRANCE | KITCHEN | 24 | 1 | 24
[5 empty] | MAIN PANEL | LDB/PDB | 10 | 1 | 10
[5 empty] | VERTICAL DROP | KITCHEN PANEL | 5 | 1 | 5
[5 empty] | VERTICAL DROP | KITCHEN POWER PANEL | 5 | 1 | 5
[5 empty] | VERTICAL DROP | BAR DB | 5 | 1 | 5
[7 empty] | TOTAL QTY |  | 49
4.7.4 | 450mm x 50mm x 2.0mm | Mtr | 45 |  | MAN PANEL | KITCHEN | 26 | 1 | 26
[5 empty] | ABOVE PULVERISER | DATA RACK | 14 | 1 | 14
[5 empty] | DATA RACK | BAR COUNTER | 9 | 1 | 9
[7 empty] | TOTAL QTY |  | 49
Sub Total of 4.0
5 | LIGHT FIXTURES INSTALLATION
5.1 | Installation of lighting fixtures with lamps as per the details below including necessary hardware such as clamps, nuts, bolts, nails screws and suspension rods as required for fixing the fixtures in position as directed by architect / consultant at site.
5.1.1 | SPOT LIGHT (LT1a) | Nos | 12 | FOH AREA |  |  | 10 |  | 10
[7 empty] | TOTAL QTY |  | 10
5.1.2 | SPOT LIGHT (LT1b) | Nos | 10 | BAR AREA |  |  | 5 |  | 5
|  |  |  | FOH AREA |  |  | 4 |  | 4
[7 empty] | TOTAL QTY |  | 9
5.1.3 | SPOT LIGHT (LT2) | Nos | 17 | BAR AREA |  |  | 12 |  | 12
|  |  |  | FOH AREA |  |  | 4 |  | 4
[7 empty] | TOTAL QTY |  | 16
5.1.4 | SUSPENDED LIGHT (LT3) | Nos | 17 | FOH AREA |  |  | 16 |  | 16
[7 empty] | TOTAL QTY |  | 16
5.1.5 | HANGING LIGHT (LT4) | Nos | 6 | FOH AREA |  |  | 5 |  | 5
[7 empty] | TOTAL QTY |  | 5
5.1.6 | HANGING LIGHT (LT5) | Nos | 4 | FOH AREA |  |  | 3 |  | 3
[7 empty] | TOTAL QTY |  | 3
5.1.7 | WALL MOUNTED (LT6) | Nos | 8 | FOH AREA |  |  | 7 |  | 7
[7 empty] | TOTAL QTY |  | 7
5.1.8 | 2 X 2 CEILING MOUNT LIGHT (LT7a) | Nos | 3 | TANDOOR SECTION |  |  | 2 |  | 2
[7 empty] | TOTAL QTY |  | 2
5.1.9 | 2 X 2 CEILING MOUNT LIGHT (LT7b) | Nos | 14 | KITCHEN AREA |  |  | 13 |  | 13
[7 empty] | TOTAL QTY |  | 13
5.1.10 | BULB LIGHT (LT8) | Nos | 70 | FOH AREA |  |  | 68 |  | 68
[7 empty] | TOTAL QTY |  | 68
5.1.11 | LED COVE LIGHT (LT9) | MTR | 10 | FOH AREA |  |  | 15 |  | 15
[7 empty] | TOTAL QTY |  | 15
5.1.12 | TRACK LIGHT-900MM (TL1) | MTR | 6 | FOH AREA |  |  | 4 |  | 4
[7 empty] | TOTAL QTY |  | 4
5.1.13 | PALM LEAF CEILING FAN (CF1) | Nos | 7 | FOH AREA |  |  | 6 |  | 6
[7 empty] | TOTAL QTY |  | 6
Sub Total of 5.0
6 | EARTHING :
6.1 | S & I of earth pit comprising of specially designed SEE/Ashlok brand Earth Electrode system 3.00 meter long including necessary materials like side fill compound etc. as required with standard brick masonary chamber with hinged cover and watering arrangement model SEE-60/C with SFC-20/Equivalent ASHLOK MODEL T39 HD (50MM DIA. 3 MTR) | Nos | 2
6.2 | S & I of copper /GI earthing wires/strips in following sizes
6.3 | 8 SWG GI bare wire | Mtr | 100 |  | MAIN PANEL | KITCHEN PANEL | 53 | 1 | 53
[5 empty] | MAIN PANEL | KITCHEN POWER PANEL | 51 | 1 | 51
[5 empty] | MAIN PANEL | BAR DB | 49 | 1 | 49
[5 empty] | MAIN PANEL | PDB | 19 | 1 | 19
[5 empty] | MAIN PANEL | LDB | 19 | 1 | 19
[5 empty] | MAIN PANEL | UDB | 19 | 1 | 19
[7 empty] | TOTAL QTY |  | 210
6.4 | 25mm x 3mm thick GI strip welded & painted green | Mtr | 150
6.5 | 25mm x 3mm thick CU strip welded & painted green | Mtr | 10
6.6 | S & I of isolated/dedicated earthing / grounding system for computers etc.using insulated green-yellow copper earthing wire laid/fixed bare on wall/ceiling from separately made earth pit to the equipment in following sizes The rate shall include termination also.
6.6.1 | 6 Sqmm copper, yellow-green/green insulation | Mtr | 20
6.7 | S & I of Main bus for isolated earth comprising of 300mm x 25 mm x 3mm thick Tinned copper bar fixed on insulated support and having 10 nos of holes and nut bolts studs for clamping the earth leads,all contained in MS/PVC box and having transparent acrylic cover as approved by the consultant | Nos | 1
Sub Total of 6.0
7 | Miscellaneous Item
7.1 | Supply & Install. Of RG 6 TV Cable in 25mm MS Conduit | Mtr. | 30
7.2 | Supply & Laying of RG11 use for Main Cable TV | Mtr. | 50
7.3 | Install. Of TV Stand - Only Installation | Nos. | 1
7.4 | 4 WAY SPLITTER | Nos. | 1
Sub Total of 7.0
8 | DATA DISTRIBUTION
Supply, Installation, termination & testing of data system:
8.1 | Main SERVER / ROUTER | Nos. | 1
8.2 | ROUTER | Nos. | 1
8.3 | SMART GIGABIT SWITCH 24 PORTS | Nos. | 1
8.4 | Loaded PATCH PANEL for 24 Port | Nos. | 1
8.5 | LIU switch with Accessories. (Optional : if Fibre Optic Cable terminated) | Job | 1
8.6 | Supply & Installation of I/O DATA Outlet (RJ-45) | Nos. | 19
8.7 | S & I of Installation of Wi-Fi ceiling mounted Access Point, managed by controller software | Nos. | 3
8.8 | Supply, installation, termination & testing of all Terminations using Fluke Cable Analyser DTX 1800 for all CAT 6 Information Outlet including Information outlet | Lot | 1
8.9 | CABLES:
8.9.1 | S&I Optical Fiber Cable with 12 fibers, with core dia. 50/125 µm (OM3), suitable for 1GBps Ethernet distance at 850 nm of wavelength, | Mtr. | RO
8.9.2 | S&I Optical Fiber Cable with 6 fibers, with core dia. 50/125 µm (OM3), suitable for 1GBps Ethernet distance at 850 nm of wavelength, | Mtr. | RO
8.9.3 | Supply & providing of CAT 6 UTP cables in the laid raceways / Conduits including terminations | Mtr. | 154 | BOH AREA | LV RACK | WIFI 1 (NEAR MAIN ENTRY) | 31 | 1 | 31
|  |  |  | BOH AREA | LV RACK | WIFI 2 (FOH AREA) | 23 | 1 | 23
|  |  |  | BOH AREA | LV RACK | WIFI 3 (NEAR KITCHEN ENTRY) | 15 | 1 | 15
[7 empty] | TOTAL QTY |  | 69
[5 empty] | LV RACK | KITCHEN DESKTOP | [5 empty] | 15 | 2 | 30
[5 empty] | LV RACK | DISHWASHER | [5 empty] | 20 | 2 | 40
[5 empty] | LV RACK | ATTENDANCE MACHINE | [5 empty] | 10 | 1 | 10
[5 empty] | LV RACK | FOH AREA DISPLAY | [5 empty] | 35 | 2 | 70
[5 empty] | LV RACK | FOH AREA DISPLAY | [5 empty] | 40 | 3 | 120
[5 empty] | LV RACK | FOH AREA DISPLAY | [5 empty] | 44 | 3 | 132
[5 empty] | LV RACK | FOH AREA DISPLAY | [5 empty] | 47 | 2 | 94
[5 empty] | LV RACK | BAR AREA | [5 empty] | 25 | 2 | 50
[5 empty] | LV RACK | TANDOOR AREA | [5 empty] | 22 | 2 | 44
[12 empty] | TOTAL QTY |  | 546
8.9.4 | Patch cord (2 mtr-user end) | Each | 19
8.1 | Supply, Installation, Testing & Commissioning of Hardware Packets (20 Nos =1 Pkts) | Pkts | 1
8.11 | Supply, Installation, Testing & Commissioning of Velcro Ties ( 22 Mtrs = 1 Roll) | Roll | 1
8.12 | Supply, Installation, Testing & Commissioning of Cable Ties 200mm ( 100 Nos. Pkt) | Pkt. | 1
8.13 | Project Management including Freight & Forwarding, Cable Bunching, Printed Numbering, tube type Ferruling both sides, Face plate, Patch panel & patch cords both sides, Documentation etc.. | Job | 1
8.14 | Supplying and fixing 15U Rack Aluminium Frame - 600x600mm with 4 x FAN, Dual Split perforated Door at Front and Back Side, 2 x Vertical Cable Basket, 2 x 12 socket 5/15A PDU with MCB, side Panels of 2 nos and Heavy Duty Castors with break, 19" Reduced Channel - Loop Type (DATA+CCTV+PA) | Nos. | 1
8.15 | Supply & installation of MS conduits with junction boxes, reducer etc. complete concealed/surface mounting as required.
8.15.1 | 25 dia conduit | Mtr. | 100 |  | LV RACK | WIFI | 33 | 1 | 33
[7 empty] | TOTAL QTY |  | 33
[5 empty] | LV RACK | KITCHEN DESKTOP | [5 empty] | 15 | 1 | 15
[5 empty] | LV RACK | DISHWASHER | [5 empty] | 20 | 1 | 20
[5 empty] | LV RACK | ATTENDANCE MACHINE | [5 empty] | 10 | 1 | 10
[5 empty] | LV RACK | FOH AREA DISPLAY | [5 empty] | 35 | 1 | 35
[5 empty] | LV RACK | FOH AREA DISPLAY | [5 empty] | 40 | 1 | 40
[5 empty] | LV RACK | FOH AREA DISPLAY | [5 empty] | 44 | 1 | 44
[5 empty] | LV RACK | FOH AREA DISPLAY | [5 empty] | 47 | 1 | 47
[5 empty] | LV RACK | BAR AREA | [5 empty] | 25 | 1 | 25
[5 empty] | LV RACK | TANDOOR AREA | [5 empty] | 22 | 1 | 22
[12 empty] | TOTAL QTY |  | 236
Sub Total of 8.0
9 | SUPPLY & INSTALLATION OF SAFETY ITEMS
9.1 | Sand buckets with stand (set of 3 buckets) | Sets | RO
9.2 | Caution boards (11kV) of standard Size | Nos | RO
9.3 | Caution boards (415V) of std. Size | Nos | 1
9.4 | Rubber mat at panel room 12mm thk. 1mtr. Wide | Mtrs | 2 | MAIN LT PANEL | [7 empty] | 1 |  | 1
|  |  |  | KITCHEN PANEL | [7 empty] | 1 |  | 1
[12 empty] | TOTAL QTY |  | 2
9.5 | Shock treatment chart as per electricity board | Nos | 1
9.6 | First aid box with standard items | Nos | RO
9.7 | 11 KV rating rubber hand gloves | Sets | 2
9.8 | The contractor to submit all the AS BUILT DRAWINGS after the completion of the project for Electrical & ELV Services executed at site. | Part of Tender
Sub Total of 9.0
10 | UPS/ INVERTER System:
10.1 | Supply /Install of 3 KVA on line Model UPS with inbuilt battery system (1 Phase In & 1 Phase out) Make: Emerson/APC/Consul Neowatt/Vivtar Electronics | set | 1 | BELOW KITCHEN PANEL | [7 empty] | 1 |  | 1
[12 empty] | TOTAL QTY |  | 1
Sub Total of 10
11 | CCTV
11.1 | Supply & Installation of 2 Megapixel IR-20Mtr. IP Indoor Dome + Night vision. Camera Make: CP-PLUS | Nos. | 12
11.2 | Supply & Installation of 2 Megapixel IR-20Mtr. IP Indoor Bullet Camera+ Night vision. Camera Make: CP-PLUS | Nos. | RO
11.3 | Supply & Installation of 2 Megapixel IR-30Mtr. IP Outdoor Bullet Camera + Night vision. Camera Make: CP-PLUS | Nos. | RO
11.4 | Supply & Installation of 16 Channel NVR with 4 Sata Hard Disk Slot (Make: Honeywell/CP PLUS) | Nos. | 1
11.5 | Supply & Installation of 24 Channel NVR with 4 Sata Hard Disk Slot (Make: Honeywell/CP PLUS) | Nos. | RO
11.6 | Supply & Installation of 8 Channel NVR with 2 Sata Hard Disk Slot (Make: Honeywell/CP PLUS) | Nos. | RO
11.7 | Supply & Installation of 16Port PoE(NVR) Switch (Make: Systimax) | Nos. | 1
11.8 | 4 TB HDD Hard Disk | Nos. | 4
11.9 | Monitor/PC system | Nos. | 2
11.1 | Supply & Installation of CAT-6 Cable for Camera Signal | Mtr. | 270 |  | NVR | CAMERA 1 (NEAR NVR RACK) | 8 | 1 | 8
[5 empty] | NVR | CAMERA 2 (NEAR PULVERISER) | 20 | 1 | 20
[5 empty] | NVR | CAMERA 3 (NEAR STEP IN) | 10 | 1 | 10
[5 empty] | NVR | CAMERA 4 (BAR COUNTER) | 18 | 1 | 18
[5 empty] | NVR | CAMERA 5 (LIQUOR STORE) | 15 | 1 | 15
[5 empty] | NVR | CAMERA 6 (STAFF LOCKER) | 11 | 1 | 11
[5 empty] | NVR | CAMERA 7 (TANDOOR SECTION) | 15 | 1 | 15
[5 empty] | NVR | CAMERA 8 (KITCHEN AREA) | 10 | 1 | 10
[5 empty] | NVR | CAMERA 9 (DISH WASH) | 12 | 1 | 12
[5 empty] | NVR | CAMERA 10 (FOH AREA KITCHEN ENTRY) | 13 | 1 | 13
[5 empty] | NVR | CAMERA 11 (FOH NEAR SHAFT) | 19 | 1 | 19
[5 empty] | NVR | CAMERA 12 (FOH MIDDLE COLUMN) | 19 | 1 | 19
[5 empty] | NVR | CAMERA 13 (FOH MIDDLE COLUMN) | 26 | 1 | 26
[5 empty] | NVR | CAMERA 14 (NEAR MAIN PANEL) | 34 | 1 | 34
[5 empty] | NVR | CAMERA 15 (NEAR PDB) | 24 | 1 | 24
[7 empty] | TOTAL QTY |  | 254
Sub Total of 11
12 | PA SYSTEM
12.1 | Supply & Laying of 2 core 2.5 Sq.mm PVC insulated twisted copper conductor Speaker wires in trunking as required. | RM | 42 | FOH AREA | RECEPTION | SPEAKER 1 | 12 | 1 | 12
|  |  |  | FOH AREA | SPEAKER 1 | SPEAKER 2 | 11 | 1 | 11
|  |  |  | FOH AREA | SPEAKER 2 | SPEAKER 3 | 9 | 1 | 9
|  |  |  | BOH AREA | RECEPTION | SPEAKER 4 | 34 | 1 | 34
|  |  |  | BOH AREA | SPEAKER 4 | SPEAKER 5 | 9 | 1 | 9
|  |  |  | BOH AREA | SPEAKER 5 | SPEAKER 6 | 7 | 1 | 7
[7 empty] | TOTAL QTY |  | 82
12.2 | Control Unit (with volume and on/off switch) ( Smooth stepless control, but the control shall be through dimmer switch, the make of which will be same as the make of light control switches ) | Nos. | 1
12.3 | Supply & Installation of 6W Ceiling Speaker with box- Bosch | Nos. | 6
12.4 | Voice Alarm Controller with in built 120W Amplifier & Emergency Messaage Manager |  | 1
12.5 | Supply of Voice Command Centre consisting of Electronics for Audio Control and shall include Amplifiers, Audio Message Generator, Microphone, table top mic etc. | Set. | RO
12.6 | Supply & Installation of MS Conduit. | RM | 50 |  | RECEPTION | SPEAKER 6 | 46 | 1 | 46
[7 empty] | TOTAL QTY |  | 46
Sub Total of 12
13 | FIRE ALARM SYSTEM (MAKE: HONEYWELL/EST)
13.1 | Single Loop Analog Addressable Fire Alarm Control panel (Expandable upto 1 Loop) with battery back up for 4 hours normal operation and 15 minutes alarm operation. The control panel per Loop Capacity 250 Detectrs and Devices, battery charger etc., 8.5" Touch Screen LCD Display, TCP/IP Connectivity, 10000 Event Log, Keyless Log on Using RFID Cards. The panel shall be UL listed and preferably FM approved with response time less than 10sec. Installation of fire alarm system shall be done as per IS 2189 or relevant NFPA standard.The panel shall have the web enabled facility which can able to send or receive e-mails with memory of 1000 events recording.Note:The vendor shall provide panel UL 9th edition listing certificate. (Make: Edwards / Honeywell) | Nos | 1
|  |  |  | NEAR RECEPTION |  |  | 1 |  | 1
[7 empty] | TOTAL QTY |  | 1
i) Each loop with Min. 99 Devices + 99 Detectors modules connection capability of Addressable FACP) 1 Loop Pannel.
ii) FACP with all in-built modules & displays.
iii) 240 volts AC power supply, automatic battery charger, 24 volts sealed lead acid batteries sufficient for 4 hours normal working.
iv) Programming & setting up
v) system to be capable of operating the system for 2 hours during an emergency condition including all necessary software for remote programming of fire alarm system through central control station.
vi) As the number of hooters are 43, additional power supplies to be provided as required.
Necessary Integration Facility with BMS for following functions:-
Alarm, Trouble condition,Supervisory alerts to BMS
Share Graphics of Security, Fire and HVAC
13.1.1 | Fire alarm Addressable control panel (1 Loop)
13.2 | Active Repeater Panel with 8.5" Touch Screen TFT display with TCP/IP Eable Repeater Panel shall monitor and control (Scroll, Acknowledge, Reset & Mute) all the events of the FACP to which it is connected and it shall have Port Vectoring / Event Filtering capability of showing only ALARMS, TROUBLES or SUPERVISORY or customized combinations of user selected events. | Nos | RO
13.2.1 | Supply installation and testing of signal loop components in a suitable galvanised steel junction box.
13.3 | Detectors and Devices
13.3.1 | Supply,Installation,Testing & Commissioning of Analogue Addressable Monitor module having Rotary, decimal addressing system for monitoring the field devices & shall be capable of providing DPDTcontact rated at 24V DC, 2A. | Nos | RO
13.3.2 | Supply,Installation,Testing & Commissioning of Analogue Addressable Relay module having Rotary, decimal addressing system for AHU tripping and shall be capable of providing DPDTcontact rated at 24v DC, 2A. | Nos | 1 | NEAR RECEPTION |  |  | 1 |  | 1
| (For all AHU's, Fans & Acess Control) | [5 empty] | TOTAL QTY |  | 1
13.3.3 | Supply,Installation,Testing & Commissioning of Horn / Strobe rated at 82 dBA @ 3m for Audible annunciation and 75cd flashing at 1 Hz for visual indication with Control modules and necessary accessories including back box. | Nos | 3 | NEAR RECEPTION |  |  | 1 |  | 1
|  |  |  | TANDOOR SECTION |  |  | 1 |  | 1
|  |  |  | KITCHEN ENTRY |  |  | 1 |  | 1
[7 empty] | TOTAL QTY |  | 3
13.3.4 | Supply,Installation,Testing & Commissioning of Analogue Addressable Flash scan Type Photoelectric smoke detectors( Below False Ceiling) having Rotary, decimal addressing system with standard base, built in isolation function and junction box. The detector shall be capable to address in the range of 1-159. The detector shall be with Visible bi-color LEDs for 360 deg viewing and shall blink green every time the detector is addressed, and illuminate steady red on alarm. | Nos | 4 | FOH AREA |  |  | 6 |  | 6
|  |  |  | BAR AREA |  |  | 1 |  | 1
|  |  |  | DISH WASH AREA |  |  | 1 |  | 1
[7 empty] | TOTAL QTY |  | 8
13.3.5 | Supply,Installation,Testing & Commissioning of Analogue Addressable Flash scan Type Photoelectric smoke detectors (Above False Ceiling) having Rotary, decimal addressing system with standard base, built in isolation function and junction box. The detector shall be capable to address in the range of 1-159. The detector shall be with Visible bi-color LEDs for 360 deg viewing and shall blink green every time the detector is addressed, and illuminate steady red on alarm. | Nos | 4
13.3.6 | Supply,Installation,Testing & Commissioning of Analogue Addressable Flash scan Type Heat Detector having Rotary, decimal addressing system with standard base, built in isolation function and junction box. The detector shall be capable to address in the range of 1-159. The detector shall be with Visible bi-color LEDs for 360 deg viewing and shall blink green every time the detector is addressed, and illuminate steady red on alarm. | Nos | 3 | BOH AREA (KITCHEN) |  |  | 3 |  | 3
[7 empty] | TOTAL QTY |  | 3
13.3.7 | Supply,Installation,Testing & Commissioning of Addressable Break Glass Manual Call Point having Rotary, decimal addressing system and having an integrally mounted addressable module that monitors and reports contact status. | Nos | 3 | NEAR RECEPTION |  |  | 1 |  | 1
|  |  |  | TANDOOR SECTION |  |  | 1 |  | 1
|  |  |  | KITCHEN ENTRY |  |  | 1 |  | 1
[7 empty] | TOTAL QTY |  | 3
13.4 | SITC of Fault Isolator. | Nos | 2 | BOH AREA |  |  | 1 |  | 1
|  |  |  | FOH AREA |  |  | 1 |  | 1
[7 empty] | TOTAL QTY |  | 2
13.5 | SITC of 2Cx1.5sq.mm multistranded Armoured FRLS RED Colour,Mylan Shielded Screened cable | Mtrs | 75 |  | FAP | HOOTER LOOPING CABLE | 46 | 1 | 46
[5 empty] | FAP | SMOKE DECTOR LOOPING CABLE | 92 | 1 | 92
[5 empty] | FAP | GAS DECTOR LOOPING CABLE | 122 | 1 | 122
[5 empty] | SMOKE DECTOR | MCP LOOPING CABLE | 18 | 1 | 18
[5 empty] | FAP | MALL FAP | 34 | 1 | 34
[7 empty] | TOTAL QTY |  | 312
[5 empty] | FAP | FIRE SUPPRESSION SYSTEM | [5 empty] | 8 | 1 | 8
[5 empty] | FAP | MAIN LT PANEL | [5 empty] | 18 | 1 | 18
[5 empty] | FAP | AC PANEL | [5 empty] | 45 | 1 | 45
[5 empty] | AC PANEL | CHILLER | [5 empty] | 40 | 1 | 40
[5 empty] | FAP | INDICATOR | [5 empty] | 4 | 1 | 4
[5 empty] | MAIN LT PANEL | ABOVE CEILING | [5 empty] | 3 | 1 | 3
[12 empty] | TOTAL QTY |  | 118
13.6 | Response indicator. | Nos | 4
Sub Total of 13

## EXTRA ITEM BOQ
SR. NO. | DESCRIPTION OF ITEM | UNIT | QTY | Supply Rate | Installtion Rate | Amount
1 | Laying, testing & commissioning of 3.5C x 300 Sq.mm. AL XLPE Cable. | MTR. | 45 |  | 300 | 13500
2 | Supply Laying, testing & commissioning of 4C x 16 Sq.mm. CU XLPE Cable. | MTR. | 45 | 950 | 100 | 47250
3 | Supply, Installation testing and commission of 4C x 16 Sq.mm. CU XLPE Cable termination | NOS | 2 | 550 | 150 | 1400
4 | Supply Laying, testing & commissioning of 1C x 1.5 Sq.mm. CU wire. | MTR. | 12 | 16 | 8 | 288
5 | Supply, Installation testing and commission of USB SOCKET | NOS | 18 | 800 | 100 | 16200
6 | Supply, Installation testing and commission of 3 PIN TOP | NOS | 12 |  |  | 0
7 | Supply, Installation testing and commission of 16A 1SWITCH & 1 SOCKET 3M PVC BACK BOX WITH PLATE. | NOS | 6 | 600 | 100 | 4200
8 | Supply, Installation testing and commission of 16A 4SWITCH & 4 SOCKET 12M PVC BACK BOX WITH PLATE. | NOS | 1 | 1300 | 150 | 1450
9 | Supply & Installation of 40A,FP,MCB, in powder coated sheet metal box for terminating power to equipment etc. | NOS | 1 | 4550 | 750 | 5300
10 | Supply & Installation of 40A,FP,ELCB, in powder coated sheet metal box for terminating power to equipment etc. | NOS | 1 | 4900 | 750 | 5650
11 | Removing & refixing of HANGING LIGHT. with flexible | JOB | 1 |  | 8000 | 8000
12 | Removing & refixing of 4C x 16 Sq.mm. AL XLPE Cable. | JOB | 1 |  | 1200 | 1200
13 | Supply & Installation of AUTOMATION SYSTEM FOR FOH AREA | JOB | 1 |  | 5500 | 5500
14 | Supply & Installation of 4FIT 40W LED TUBE LIGHT FIXTURE. | NOS | 6 | 650 | 100 | 4500
15 | Supply & Installation of 5W/MTR LED STRIP. | MTR. | 25 | 550 | 100 | 16250
16 | Removing of Relay Module | NOS | 1 |  | 500 | 500
17 | Removing of Hooter | NOS | 3 |  | 500 | 1500
18 | Removing of Smoke Detector | NOS | 8 |  | 500 | 4000
19 | Removing of Heat Detector | NOS | 3 |  | 500 | 1500
20 | Removing of Manual Call Point | NOS | 3 |  | 500 | 1500
21 | Removing of Fault Isolator | NOS | 2 |  | 500 | 1000
22 | Supply of Addressable single loop Fire Alaram system panel. (Make - Honeybell) Model NFS 320 | NOS | 1 | 268500 |  | 268500
23 | Installation, Programming, Testing & Commisioning of Addressable single loop Fire Alaram system panel. (Make - Honeybell) Model NFS 320 | NOS | 1 |  | 75000 | 75000
24 | Supply, Installation testing and commission of Relay Module UL & FM Approved. (Make - Notifier) | NOS | 11 | 6400 | 550 | 76450
25 | Supply, Installation testing and commission of Horn Cum Strober UL & FM Approved. (Make - Notifier) | NOS | 3 | 10960 | 400 | 34080
26 | Supply, Installation testing and commission of Smoke Detector UL & FM Approved. (Make - Notifier) | NOS | 8 | 5170 | 350 | 44160
27 | Supply, Installation testing and commission of Heat Detector UL & FM Approved. (Make - Notifier) | NOS | 3 | 4870 | 265 | 15405
28 | Supply, Installation testing and commission of Manual call point UL & FM Approved. (Make - Notifier) | NOS | 3 | 5270 | 350 | 16860
29 | Supply, Installation testing and commission of Fault Isolator UL & FM Approved. (Make - Notifier) | NOS | 2 | 5590 | 320 | 11820
30 | Supply, Installation testing and commission of Monitor Module UL & FM Approved. (Make - Notifier) | NOS | 1 | 5530 | 700 | 6230
31 | Installation, Integration & commissioning of fire alarm system with all required modules, relays, SMPS with modular Extinguishers. | NOS | 1 |  | 207500 | 207500
32 | Supply, Installation testing and commission of Fire Exit Signages | NOS | 3 | 6300 | 300 | 19800
33 | Supply, Installation testing and commission of Fire Extinguisher Signages | NOS | 8 | 250 | 50 | 2400
34 | Supply, Installation testing and commission of Fire Extinguisher Stand | NOS | 4 | 700 | 150 | 3400
35 | Supply, Installation testing and commission of Danger Signages | NOS | 4 | 550 | 100 | 2600
36 | Addition & Modification Fire Sprinkler Drain Valve, Pressure Guage, Flow Switch etc. | JOB | 1 |  | 48000 | 48000
37 | Supply, Installation testing and commission of Addressable Smoke Detectors (Make - Notifier) | NOS | 4 | 5100 | 300 | 21600
38 | Replacement of hood lights | Nos | 4 | 2250 | 450 | 10800
39 | Supply & Installation of wall mount fan in dish wash area | JOB | 1 |  | 3800 | 3800
40 | Load balancing certificate | JOB | 1 |  | 30000 | 30000
41 | Replacement of hanging light cable | Nos | 8 | 1200 | 200 | 11200
42 | Supply & Installation 30mA RCCB at main DB in kitchen passage | Nos | 1 | 3000 | 500 | 3500
43 | Installation & Commission of UPS & stebilizer for battery | Job | 1 |  | 10000 | 10000
GRAND TOTAL AMOUNT | [5 empty] | 1063793

## EXTRA ITEM M. SHEET
|  | TENDER BOQ. R0 |  |  |  |  | EXTRA ITEM
SR. NO. | DESCRIPTION OF ITEM | UNIT | QTY | LOCATION | FROM | TO | QTY | RUN | TOTAL QTY | UNIT | REMARK
1 | Laying, testing & commissioning of 3.5C x 300 Sq.mm. AL XLPE Cable. |  |  |  | FLOOR TAP OFF | MAIN LT PANEL | 45 | 1 | 45 | MTR
[7 empty] | TOTAL QTY |  | 45
2 | Supply Laying, testing & commissioning of 4C x 16 Sq.mm. CU XLPE Cable. |  |  |  | MAIN PANEL | KITCHEN PANEL | 45 | 1 | 45 | MTR
[7 empty] | TOTAL QTY |  | 45
3 | Supply, Installation testing and commission of 4C x 16 Sq.mm. CU XLPE Cable termination |  |  |  | MAIN PANEL | KITCHEN PANEL | 2 |  | 2 | NOS
[7 empty] | TOTAL QTY |  | 2
4 | Supply Laying, testing & commissioning of 1C x 1.5 Sq.mm. CU wire. |  |  |  | MAIN PANEL | EM. PUSH BUTTON | 6 | 2 | 12 | MTR
[7 empty] | TOTAL QTY |  | 12
5 | Supply, Installation testing and commission of USB SOCKET |  |  | FOH AREA |  |  | 18 |  | 18 | NOS
[7 empty] | TOTAL QTY |  | 18
6 | Supply, Installation testing and commission of 3 PIN TOP |  |  | FOR KITCHEN EQUIPMENT |  |  | 12 |  | 12
[7 empty] | TOTAL QTY |  | 12
7 | Supply, Installation testing and commission of 16A 1SWITCH & 1 SOCKET 3M PVC BACK BOX WITH PLATE. |  |  | MAIN ENTRANCE |  |  | 1 |  | 1
|  |  |  | TANDOOR AREA |  |  | 1 |  | 1
|  |  |  | DISHWASHER |  |  | 1 |  | 1
|  |  |  | KITCHEN AREA |  |  | 1 |  | 1
|  |  |  | BELOW KITCHEN PANEL |  |  | 1 |  | 1
|  |  |  | EM. EXIT DOOR |  |  | 1 |  | 1
[7 empty] | TOTAL QTY |  | 6
8 | Supply, Installation testing and commission of 16A 4SWITCH & 4 SOCKET 12M PVC BACK BOX WITH PLATE. |  |  | KITCHEN AREA |  |  | 1 |  | 1
[7 empty] | TOTAL QTY |  | 1
9 | Supply & Installation of 40A,FP,MCB, in powder coated sheet metal box for terminating power to equipment etc. |  |  | NEAR KITCHEN PANEL |  |  | 1 |  | 1
[7 empty] | TOTAL QTY |  | 1
10 | Supply & Installation of 40A,FP,ELCB, in powder coated sheet metal box for terminating power to equipment etc. |  |  | NEAR KITCHEN PANEL |  |  | 1 |  | 1
[7 empty] | TOTAL QTY |  | 1
14 | Supply & Installation of 4FIT 40W LED TUBE LIGHT FIXTURE. |  |  | KITCHEN AREA |  |  | 6 |  | 6
[7 empty] | TOTAL QTY |  | 6
15 | Supply & Installation of 5W/MTR LED STRIP. |  |  | BAR AREA |  |  | 12 |  | 12
|  |  |  | FOH AREA TABLE |  |  | 13 |  | 13
[7 empty] | TOTAL QTY |  | 25
16 | Removing of Relay Module |  |  | NEAR RECEPTION |  |  | 1 |  | 1
[7 empty] | TOTAL QTY |  | 1
17 | Removing of Hooter |  |  | NEAR RECEPTION |  |  | 1 |  | 1
|  |  |  | TANDOOR SECTION |  |  | 1 |  | 1
|  |  |  | KITCHEN ENTRY |  |  | 1 |  | 1
[7 empty] | TOTAL QTY |  | 3
18 | Removing of Smoke Detector |  |  | FOH AREA |  |  | 6 |  | 6
|  |  |  | BAR AREA |  |  | 1 |  | 1
|  |  |  | DISH WASH AREA |  |  | 1 |  | 1
[7 empty] | TOTAL QTY |  | 8
19 | Removing of Heat Detector |  |  | BOH AREA (KITCHEN) |  |  | 3 |  | 3
[7 empty] | TOTAL QTY |  | 3
20 | Removing of Manual Call Point |  |  | NEAR RECEPTION |  |  | 1 |  | 1
|  |  |  | TANDOOR SECTION |  |  | 1 |  | 1
|  |  |  | KITCHEN ENTRY |  |  | 1 |  | 1
[7 empty] | TOTAL QTY |  | 3
21 | Removing of Fault Isolator |  |  | BOH AREA |  |  | 1 |  | 1
|  |  |  | FOH AREA |  |  | 1 |  | 1
[7 empty] | TOTAL QTY |  | 2
22 | Supply of Addressable single loop Fire Alaram system panel. (Make - Honeybell) Model NFS 320 |  |  | NEAR RECEPTION |  |  | 1 |  | 1
[7 empty] | TOTAL QTY |  | 1
23 | Installation, Programming, Testing & Commisioning of Addressable single loop Fire Alaram system panel. (Make - Honeybell) Model NFS 320 |  |  | NEAR RECEPTION |  |  | 1 |  | 1
[7 empty] | TOTAL QTY |  | 1
24 | Supply, Installation testing and commission of Relay Module UL & FM Approved. (Make - Notifier) |  |  | FOH & BOH AREA |  |  | 11 |  | 11
[7 empty] | TOTAL QTY |  | 11
25 | Supply, Installation testing and commission of Horn Cum Strober UL & FM Approved. (Make - Notifier) |  |  | NEAR RECEPTION |  |  | 1 |  | 1
|  |  |  | TANDOOR SECTION |  |  | 1 |  | 1
|  |  |  | KITCHEN ENTRY |  |  | 1 |  | 1
[7 empty] | TOTAL QTY |  | 3
26 | Supply, Installation testing and commission of Smoke Detector UL & FM Approved. (Make - Notifier) |  |  | FOH AREA |  |  | 6 |  | 6
|  |  |  | BAR AREA |  |  | 1 |  | 1
|  |  |  | DISH WASH AREA |  |  | 1 |  | 1
[7 empty] | TOTAL QTY |  | 8
27 | Supply, Installation testing and commission of Heat Detector UL & FM Approved. (Make - Notifier) |  |  | BOH AREA (KITCHEN) |  |  | 3 |  | 3
[7 empty] | TOTAL QTY |  | 3
28 | Supply, Installation testing and commission of Manual call point UL & FM Approved. (Make - Notifier) |  |  | NEAR RECEPTION |  |  | 1 |  | 1
|  |  |  | TANDOOR SECTION |  |  | 1 |  | 1
|  |  |  | KITCHEN ENTRY |  |  | 1 |  | 1
[7 empty] | TOTAL QTY |  | 3
29 | Supply, Installation testing and commission of Fault Isolator UL & FM Approved. (Make - Notifier) |  |  | BOH AREA |  |  | 1 |  | 1
|  |  |  | FOH AREA |  |  | 1 |  | 1
[7 empty] | TOTAL QTY |  | 2
30 | Supply, Installation testing and commission of Monitor Module UL & FM Approved. (Make - Notifier) |  |  | NEAR RECEPTION |  |  | 1 |  | 1
[7 empty] | TOTAL QTY |  | 1
32 | Supply, Installation testing and commission of Fire Exit Signages |  |  | FOH & BOH AREA |  |  | 3 |  | 3
[7 empty] | TOTAL QTY |  | 3
33 | Supply, Installation testing and commission of Fire Extinguisher Signages |  |  | FOH & BOH AREA |  |  | 8 |  | 8
[7 empty] | TOTAL QTY |  | 8
34 | Supply, Installation testing and commission of Fire Extinguisher Stand |  |  | FOH & BOH AREA |  |  | 4 |  | 4
[7 empty] | TOTAL QTY |  | 4
35 | Supply, Installation testing and commission of Danger Signages |  |  | FOH & BOH AREA |  |  | 4 |  | 4
[7 empty] | TOTAL QTY |  | 4
37 | Supply, Installation testing and commission of Addressable Smoke Detectors (Make - Notifier) |  |  | FOH & BOH AREA |  |  | 4 |  | 4
[7 empty] | TOTAL QTY |  | 4