## PHE BOQ
COPPER CHIMNEY WAKAD-PHE BOQ
|  |  |  | BOQ |  |  | ACTUAL
Item No. | Description | Unit | Qty | Rate | Amount | : | Qty | Rate | Amount
A | WATER SUPPLY PIPING
1 | CPVC Pipes conforming to ASTM D-2846, SDR-11 grade and CPVC solvent weld fittings like elbows, tees, couplars, brass threaded adaptors, insert ring etc. suitable for (domestic and flushing) cold applications rated, concealed piping within wall / floor including jointing with fittings using solvent cement, brass threaded end fittings for making connection to fixtures. The work shall also include chasing the walls with machine wherever required for concealed piping and making good the same after laying of pipes & necessary pressure testing Chasing finishing shall be done with 1:1 cement mixed mortar, restore the same original condition for internal and shaft piping, including necessary hot deep galvanised supports vertical / horizontal, as per direction of Site incharge direction. [The rate shall include supply of S.S.screws and nut bolts etc.chasing in walls done by machine] (For Domestic and Flushing water-Toilet internal) (Pipe shall be tested with 1.5 times working pressure as covered in specifications)
1.1 | 20 mm Dia | R.mt | 90 | 250 | 22500 |  | 79.27 | 250 | 19817.5
1.2 | 25 mm Dia | R.mt | 40 | 300 | 12000 |  | 37.04 | 300 | 11112
1.3 | 32mm Dia | R.mt | 45 | 350 | 15750 |  | 23.17 | 350 | 8109.5
1.4 | 40mm Dia | R.mt | 0
2 | Providing & Fixing of gun metal heavy Ball Valves-PN-16 (approved makes as covered in specification) screwed type for water system of the following diameters. Valve shall have with unions.
2.1 | 20mm Dia | Nos. | 4 | 930 | 3720 |  | 1 | 930 | 930
2.2 | 25mm Dia | Nos. | 2 | 1080 | 2160 |  | 4 | 1080 | 4320
2.3 | 32mm Dia | Nos. | 1 | 1300 | 1300 |  | 2 | 1300 | 2600
2.4 | 40mm Dia | Nos. | 0
3 | Providing ,fixing, testing and commissioning capstan make Water Meter including providing & fixing matching Isolation valves ,strainer, non-return valve,complete with all necessary fittings etc screwed type(15Kgs/Sq.cm). Valve shall have with union.
3.1 | 25 mm Dia incoming line | Nos. | RO
3.2 | 32 mm Dia incoming line | Nos. | 1 | 11200 | 11200 |  | 1 | 11200 | 11200
3.3 | 40 mm Dia incoming line | Nos. | 0
4 | Supply, installation,testing & commissioning of Storage Type Electric Hot Water Generator of mentioned capacity, suitable for 3 KG/cm2 pressure, Wall Mounted / Floor standing type, with Auto Shut-off Thermostat, along with isoltion Valves, Air Release valve, SS flexible connections andall other std accessories
4.1 | 5 L Capacity- | Nos. | RO
4.2 | 20 L Capacity | Nos. | 2 | 25000 | 50000 |  | 2 | 25000 | 50000
4.3 | 35 L Capacity- For shower | Nos. | RO
5 | Supply, installation,testing & commissioning of Stiebel Type Electric Hot Water Generator of mentioned capacity, suitable for 3 KG/cm2 pressure, Wall Mounted / Floor standing type, with Auto Shut-off Thermostat, along with isoltion Valves, Air Release valve, SS flexible connections andall other std accessories (Optional in pantry)
5.1 | 3.5kw in pantry- optional | Nos. | RO
5.2 | 8kw | Nos. | RO
5.3 | 13kw-3ph- Subject to load permits | Nos. | RO
6 | SITC of Eco smart RO-100 with all required accessories | Nos | 1 | 0 | 0 |  |  | 0 | 0
7 | SITC of ACO grease trap -model Lipumobil 0.8 -Capacity -48 lit ( 0.8 LPS) with all required accessories ( Order shall be placed as per space available below the counter) | Nos | 0
8 | SITC of ACO grease trap -model Lipumobil S -Capacity -32 lit ( 0.5 LPS) with all required accessories | Nos | 1 | 75800 | 75800 |  | 0 | 75800 | 0
A | SUB TOTAL OF A
B | DRAINAGE
1 | uPVC-SWR pipes conforming to IS 13592/92 including fittings conforming to IS-14935/99 and agri type pipes above 100 mm dia. conforming to IS: 4985, cutting the pipes to required lengths, laying in the position to required grade and level, jointing, supporting with PVC cleat,hot deep galvanised bracket supports,hot deep galvanised nut-bolts, anchor fastners, PVC coated U-clamp, testing and rectifying leakages for piping within vertical shafts / supported on wall / hung below slab etc. with all material & labor complete and as directed. [The Rate shall include supply and fixing of hotdip galvanised bracket nut bolts/ PVC Coated U-Clamp and screws] Vertical line bracket shall be fixed at every 0.8 mtr to 1.00 mtr.] (For Waste, Vent -Internal and vertical shaft ).
1.1 | 40mm Dia | R.mt | 10 | 350 | 3500 |  |  | 350 | 0
1.2 | 50mm Dia | R.mt | 5 | 500 | 2500 |  | 7.32 | 500 | 3660
1.3 | 65mm Dia | R.mt | 0
1.4 | 75mm Dia | R.mt | 20 | 800 | 16000 |  | 10.67 | 800 | 8536
1.5 | 100 mm Dia | R.mt | 40 | 1050 | 42000 |  | 29.73 | 1050 | 31216.5
1.6 | 150 mm Dia | R.mt | RO
2 | Supply, Install PVC Floor Trap for the following pipes including making all approved quality Solvent cement joints with material & labour etc. all complete as per direction of the engineer-in-charge. | Nos. | 4 | 750 | 3000 |  | 4 | 750 | 3000
3 | Supply, Install PVC Multi Floor Trap for the following pipes including making all approved quality Solvent cement joints with material & labour etc. all complete as per direction of the engineer-in-charge. | Nos. | 8 | 1200 | 9600 |  | 8 | 1200 | 9600
4 | Supply, Install PVC urinal Traps including fixing with necessary consumables with Circular SS Grating with anti cockroach jali Suitable for 75mm Dia outlet | Nos. | 0
5 | Supply, Install PVC P- Traps including fixing with necessary consumables with Circular SS Grating with anti cockroach jali Suitable for 75mm Dia outlet | Nos. | 0
SUB TOTAL OF B
C | SANITARY AND C. P. FITTINGS & FIXTURES
Only installation, testing and commissioning of sanitary and C.P. fittings
1.1 | EWC with seat cover | Nos | 0
1.2 | Concealed flush tank | Nos | 0
1.3 | Concealed flush valve | Nos | 0
1.4 | Health Faucet | Nos | 0
1.5 | 2 Way Bib-Cock with connection for Health Faucet | Nos | 0
1.6 | Bided | Nos | R.O.
1.7 | Under Counter Wash Basin including waste Coupling | Nos | 0
1.8 | Wash Basin Cock | Nos | 0
1.9 | shower and mixer | Nos | 0
1.1 | Jet Spray | Nos | 0
1.11 | Bath Tub including waste Coupling and nessessary connections | Nos | 0
1.12 | Under Counter Sink including waste Coupling | Nos | 8 | 1500 | 12000 |  |  | 1500 | 0
1.13 | Sink Pillar Cock | Nos | 8 | 250 | 2000 |  |  | 250 | 0
1.14 | Bottle Trap for WHB/ sink and urinal with all connecting pipes | Nos | 8 | 250 | 2000 |  |  | 250 | 0
1.15 | Angle Cock with PVC pipe connection upto WHB/sink/Geyser connection /Ro unit | Nos | 22 | 250 | 5500 |  |  | 250 | 0
1.16 | Urinal | Nos | 0
1.17 | Auto Flush Valve & Sensor with connecting piping & spreader for urinal(DC) | Nos | 0
SUB TOTAL -C-SANITARY AND C. P. FITTINGS & FIXTURES ( ONLY INSTALLATIONS)
D | S.S. GRATING
Only installations/ testing and commissioning of S.S.Gratings
1 | Making chamber in brick work including internal tiling etc for S.S Grating size, 2200mm x 200mm, in 16 swg 25mm x25mm Square Pipe around the Frame and 20mmX 20mm Square pipe in center of frame with SS perforated tray (304 SWR). Complete as per architectural detail drawing & Site Engineer's instruction. | Nos. | 1 | 49500 | 49500 |  | 1 | 49500 | 49500
2 | Making chamber in brick work including internal tiling etc for S.S Grating size, 1500mm x 200mm, in 16 swg 25mm x25mm Square Pipe around the Frame and 20mmX 20mm Square pipe in center of frame with SS perforated tray (304 SWR). Complete as per architectural detail drawing & Site Engineer's instruction. | Nos. | 1 | 35000 | 35000 |  | 1 | 35000 | 35000
4 | Making chamber in brick work including internal tiling etc for S.S Grating size, 300mm x 300mm, in 16 swg 25mm x25mm Square Pipe around the Frame and 20mmX 20mm Square pipe in center of frame with SS perforated tray (304 SWR). Complete as per architectural detail drawing & Site Engineer's instruction. | Nos. | 9 | 9500 | 85500 |  | 9 | 9500 | 85500
5 | Making chamber in brick work including internal tiling etc for S.S Grating size, 600mm x 300mm, in 16 swg 25mm x25mm Square Pipe around the Frame and 20mmX 20mm Square pipe in center of frame with SS perforated tray (304 SWR). Complete as per architectural detail drawing & Site Engineer's instruction. | Nos. | 2 | 18000 | 36000 |  | 2 | 18000 | 36000
SUB TOTAL -D-S.S. GRATING INSTALLATION ( ONLY INSTALLATIONS)
| GRAND - TOTAL A , B, C AND D |  |  |  | 498530 |  |  |  | 370101.5
NOTES :
1. Taxes and duties shall be Extra as actual
2. Supply and installation of Sanitary fixtures and fitting in th kitchen and toilets
3. Supply of S.S. gratings in kitchen

## Additional works
Sr no | Description | Unit | Quantity | Rate | Amount | Remarks
1 | Providing & Fixing of heavy Ball Valves
| 40mm | Nos | 8 | 1550 | 12400
2 | CPVC Pipes conforming to ASTM D-2846, SDR-11 grade - 40mm | Rft | 25 | 125 | 3125
3 | Installation of grease trap | Nos | 2 | 5500 | 11000
4 | Connection of dish washer,Ice cube & glass washer machine with required materials | Nos | 3 | 2500 | 7500
5 | Supply & installation of CP Fiitings
| Sink cock | Nos | 3 | 3050 | 9150
| Sink mixer | Nos | 4 | 4550 | 18200
| Angle cock | Nos | 22 | 1600 | 35200
| Rinse mixer | Nos | 2 | 30500 | 61000
6 | Supply & Installation of water tank with required pipe & fiitings | Ltr | 500 | 20 | 10000
7 | Supply & Installation of booster pump with required pipe & fittings ( including PRV ) | Job | 1 | 45000 | 45000
8 | Shifting of sink in kitchen & Bar area as per requirements | Nos | 2 | 3500 | 7000
9 | Dismantaling of chamber & Drain line in bar area | Job | 1 | 5000 | 5000
10 | Installation of RO Machine with required pipe & fittings | Job | 1 | 18500 | 18500
11 | Installation of water cooler with required pipe & Fittings | Job | 1 | 6500 | 6500
12 | Supply & Installation of nahani trap jali | Nos | 11 | 1350 | 14850
13 | Pump for glass washer & Ice cube machine | Nos | 2 | 13000 | 26000
14 | Supply & Installation SS Waste coupling for sink | Nos | 3 | 750 | 2250
15 | Drain work for cold room ( flexible pipe ) | Job | 1 | 3500 | 3500
0
| Total |  |  |  | 296175