## Summary
Summary of Fire Fighting System - Copper Chimney - Wakad - Pune
SL NO. | Description | Vart Infra | Target Amount | Vart Infra offer | As Per Measurment
1 | fire Fightinng Work | 340250 | 239150 | 250650 | 235759
2 | Extra Item BOQ | 0 | 0 |  | 497415

## FIRE- PRICED BOQ
COPPWER CHIMNEY -WAKAD
BOQ FOR FIRE FIGHTING SYSTEMS |  |  |  | Vart Infra |  | Target Amount |  | Vart Infra final
S/NO | DESCRIPTION | QUANTITY | UNIT | Rate | Amount | Rate | Amount | Rate | Amount | RA1 BILL
[10 empty] | RA1 QTY | UNIT | RA1 AMOUNT
1 | Providing, laying, jointing, testing and commissioning of G.I. `C' Class pipes (IS:1239 (Part-I)-1979) including cutting,threading welding etc providing all malleable galvanized iron fittings conforming to IS 1879, viz. Flanges, bends, tees, elbows,reducers, unions, supporting with G. I. clamps, hangers, M.S. brackets etc. including cutting holes and chases in brick or RCC wall / slabs and making good the same to the Approval of Architect / consultant,complete including painting with one coat of primer and two or more coats of synthetic enamel paint of approved make and shade. ( Note- Rigid/flexible pipe extension from existing line is considered)
i) | 25 mm dia. | 65 | RMT | 950 | 61750 | 750 | 48750 | 770 | 50050 | 64.7 |  | 49819
ii) | 32 mm dia. | 8 | RMT | 1050 | 8400 | 950 | 7600 | 850 | 6800 | 7.1 |  | 6035
iii) | 40 mm dia. | 5 | RMT | 1150 | 5750 | 1150 | 5750 | 950 | 4750 |  |  | 0
iv) | 50 mm dia. | 5 | RMT | 1500 | 7500 | 1450 | 7250 | 1250 | 6250 | 3.5 |  | 4375
v) | 65 mm dia. | 10 | RMT | 1850 | 18500 | 1650 | 16500 | 1550 | 15500 | 10.1 |  | 15655
vi) | 80 mm dia. | 15 | RMT | 2500 | 37500 | 2050 | 30750 | 1950 | 29250 | 15.9 |  | 31005
vii) | 100 mm dia. | 0 | RMT | 2800 |  |  |  | 2800 |  | 5.9 |  | 16520
2 | Providing , fixing testing and commissioning of pendant type sprinkler heads 68 deg. Temp.(Quick response type) | 0 | No. | 850 | [5 empty] | 9 |  | 0
3 | Providing , fixing testing and commissioning of concealed type sprinkler heads 68 deg. Temp.(Quick response type) | 21 | No. | 3050 | 64050 | 2050 | 43050 | 2300 | 48300 | 12 |  | 27600
4 | Providing , fixing testing and commissioning of upright type sprinkler heads 68 deg. temp(Quick response type)- Optional Subject to liasion team requirements | 0 | No. | 850 | [5 empty] | 25 |  | 0
5 | Providing , fixing testing and commissioning of upright type sprinkler heads 79 deg. Temp (Quick response type) | 12 | No. | 900 | 10800 | 900 | 10800 | 750 | 9000 |  |  | 0
6 | Providing & fixing testing and commissioning of braided UL Rated SS Flexible pipe
i) | 1 MT Long | 21 | No. | 3500 | 73500 | 1850 | 38850 | 2250 | 47250 | 21 |  | 47250
ii) | 1.6 MT Long | 12 | No. | 4000 | 48000 | 2250 | 27000 | 2500 | 30000 | 15 |  | 37500
7 | Gun metal chrome finished Ball valves (PN 16) with fittings of screwedend type.
I) | 40 mm dia. | R.O. | No. | 5000 | [7 empty] | 0
I) | 32 mm dia. (Sprinkler drain-OPTIONAL) | 1 | Nos. | 4500 | 4500 | 2850 | 2850 | 3500 | 3500 |  |  | 0
8 | Butterfly Valves (PN 16) with CI Body, Black Nitrile Body Liner and Nylon Coated SG Iron Disc with material and labour including hydraulic testing etc. complete as per drawing, specification & to the level of satisfaction of Site- Incharge.
I) | 150 mm dia. | R.O. | No. | 16000 | [7 empty] | 0
I) | 100 mm dia. (OPTIONAL) | R.O. | No. | 13500 | [7 empty] | 0
I) | 80 mm dia. | 0 | No. | 12000 | [7 empty] | 0
0
9 | 6kg capacity ABC type dry chemical powder fire Extinguishers with wall mounting brackets | 4 | Nos. | 3000 |  | 3000 |  | 3000 |  |  |  | 0
10 | 6kg capacity K type fire Extinguishers with wall mounting brackets | 2 | No. | 15500 |  | 12500 |  | 12500 |  |  |  | 0
11 | 5kg capacity CO2 type fire Extinguishers with wall mounting brackets | 1 | No. | 6500 |  | 4500 |  | 4500 |  |  |  | 0
12 | 9Lit AR-AFFF type fire Extinguishers with wall mounting brackets | R.O. | Nos. | 3500 | [7 empty] | 0
13 | Flow switch on sprinkler distribution header on each floor with 2 SPDT contacts suitably rated, capable of the high pressure system and connected to fire alarm panel through cable.
i) | 100 mm dia. | 0 | No. | 16500 | [7 empty] | 0
14 | Ceasefire 5 Kg Ceiling Mounted Fire Extinguisher Clean Agent FE-36, Zero ODP, Stored Pressure Type, Pressure Gauge, Gross Weight 7.7 Kg, empty Weight 2.7 Kg, Can Height 264MM, Diameter 240MM,Discharge Time less than 8 Secs, Auto discharge mechanism on temperature rise, applicable on Class A,B,C and electrically started Fire, Can Construction : Deep drawn & Co2 Mig welded, Valve Construction : Forging & Machining, Internal Coating of Can : Epoxy Powder coating, External Coating of Can : Epoxy Polyster Powder coating, Sheet metal thickness : 2.0MM, Helium Leak Detection Test, 5 Years Warranty-model no 1CH21CF | 0 | No. | 35000 | [7 empty] | 0
| SUB-TOTAL |  |  |  | 340250 |  | 239150 |  | 250650 |  |  | 235759
Note : | Taxes Extra as applicable.

## EXTRA ITEM BOQ
COPPWER CHIMNEY -WAKAD
BOQ FOR FIRE FIGHTING SYSTEMS
S/NO | DESCRIPTION | QUANTITY | UNIT | Rate | Amount
1 | Providing , fixing testing and commissioning of pendant type sprinkler heads 79 deg. Temp.(Quick response type) | 14 | No. | 750 | 10500
2 | Providing , fixing testing and commissioning of pendant type sprinkler heads 68 deg. Temp.(Quick response type) | 9 | No. | 710 | 6390
3 | Supply, Installation, Testing & Commisioning Of ABC Dry Powder MAP - 50% Moduler Type Fire Extinguishet (Ceiling Mounted) conforming to IS : 15683 : 2018 finish complete. (5KG) | 1 | No. | 5250 | 5250
4 | Supply, Installation, Testing & Commisioning Of 2KG Firessense Automatic Fire detection and fire fighting system consisting of | 1 | No. | 38900 | 38900
Cylinder filled with F-K-5-1-12 Clean Agent GAS (UL & FM Approved)
Fitted with Direct Low Pressure Volve
Pressure guage
End of Line Adaptor
Wall bracket
5 | Commisioning of Heat Detection tube (UL & FM Approved) | 50 | No. | 950 | 47500
6 | Supply, Installation, Testing & Commisioning Of Pressure Switch | 1 | No. | 13000 | 13000
7 | Supply, Installation, Testing & Commisioning Of Audio Visual Alaram System | 1 | No. | 11000 | 11000
8 | Supply, Installation, Testing & Commisioning Of Sprinkler, K-80 (5.6) QR, SC, 68 deg, 15mm bulb type, Chrome Finish, UL & FM Approved. | 15 | No. | 750 | 11250
9 | Supply, Installation, Testing & Commisioning Of Concealed Sprinkler, K-5.6 (80) QR, SC, 68 deg, Pendent Chrome Finish, 15mm with cover plate white finish UL & FM Approved. | 12 | No. | 2100 | 25200
10 | Supply of Smart GAS Detector System. | 6 | No. | 30400 | 182400
MODEL NO. GT-2511-FLP-ATEX
Smart Gas Detector 3 Wire
Make: AMBETRONICS ENGINEERS PVT LTD., INDIA
For GAS LEAKAGE IN AMBIENT MONITORING
Gas to be detected-PNG
Range-0-100% LEL
Sensor Principle:- Catalytic Bead
Standard Output1 : 4-20 mA Output with users settable range
Output 2: Three SDPT Relays of rating '2A'
Output 3: Isolated RS-485 Modbus Communication
4-20mA rated at 470 ohms load driving capacity
programming can be done remote via Fieldbus
Configurable STEL and TWA Set points for Toxic Gases
11 | Supply, Installation, Testing & Commisioning of Monitor Module | 6 | No. | 6850 | 41100
12 | Supply, Installation, Testing & Commisioning of Relay Module | 5 | No. | 5265 | 26325
13 | Testing & commissioning of Smart GAS Detector System. | 1 | No. | 36000 | 36000
14 | Rectification charges for per sprinkler points | 12 | No. | 1050 | 12600
15 | Form A Certification | 1 | Job | 30000 | 30000
| SUB-TOTAL |  |  |  | 497415
Note : | Taxes Extra as applicable.

## M SHEET
COPPWER CHIMNEY -WAKAD
BOQ FOR FIRE FIGHTING SYSTEMS
S/NO | DESCRIPTION | QUANTITY | UNIT
|  |  |  | LOCATION | FROM | TO | QTY | RUN | TOTAL QTY | UNIT | REMARK
1 | Providing, laying, jointing, testing and commissioning of G.I. `C' Class pipes (IS:1239 (Part-I)-1979) including cutting,threading welding etc providing all malleable galvanized iron fittings conforming to IS 1879, viz. Flanges, bends, tees, elbows,reducers, unions, supporting with G. I. clamps, hangers, M.S. brackets etc. including cutting holes and chases in brick or RCC wall / slabs and making good the same to the Approval of Architect / consultant,complete including painting with one coat of primer and two or more coats of synthetic enamel paint of approved make and shade. ( Note- Rigid/flexible pipe extension from existing line is considered)
i) | 25 mm dia. | 65 | RMT | FOH AREA | SPRINKLER | SPRINKLER | 30.9 | 1 | 30.9
[5 empty] | FOH AREA | BAR AREA & LIVE KITCHEN | 11.7 | 1 | 11.7
|  |  |  | KITCHEN AREA | SPRINKLER | SPRINKLER | 22.1 | 1 | 22.1
[7 empty] | TOTAL QTY |  | 64.7
ii) | 32 mm dia. | 8 | RMT | KITCHEN AREA | SPRINKLER | SPRINKLER | 7.1 | 1 | 7.1
[7 empty] | TOTAL QTY |  | 7.1
iii) | 40 mm dia. | 5 | RMT
iv) | 50 mm dia. | 5 | RMT | KITCHEN AREA | SPRINKLER | SPRINKLER | 3.5 | 1 | 3.5
[7 empty] | TOTAL QTY |  | 3.5
v) | 65 mm dia. | 10 | RMT | FOH AREA | SPRINKLER | SPRINKLER | 10.1 | 1 | 10.1
[7 empty] | TOTAL QTY |  | 10.1
vi) | 80 mm dia. | 15 | RMT | FOH AREA | SPRINKLER | SPRINKLER | 15.9 | 1 | 15.9
[7 empty] | TOTAL QTY |  | 15.9
vii) | 100 mm dia. | 0 | RMT | FOH AREA MAIN ENTRANCE |  |  | 5.9 | 1 | 5.9
[7 empty] | TOTAL QTY |  | 5.9
2 | Providing , fixing testing and commissioning of pendant type sprinkler heads 68 deg. Temp.(Quick response type) | 0 | No. | FOH AREA |  |  | 9 |  | 9
[7 empty] | TOTAL QTY |  | 9
3 | Providing , fixing testing and commissioning of concealed type sprinkler heads 68 deg. Temp.(Quick response type) | 21 | No. | DINING AREA |  |  | 11 |  | 11
|  |  |  | BAR |  |  | 1 |  | 1
[7 empty] | TOTAL QTY |  | 12
4 | Providing , fixing testing and commissioning of upright type sprinkler heads 68 deg. temp(Quick response type)- Optional Subject to liasion team requirements | 0 | No. | DINING AREA |  |  | 11 |  | 11
|  |  |  | BAR |  |  | 1 |  | 1
|  |  |  | TANDOOR AREA |  |  | 1 |  | 1
|  |  |  | DISH WASH AREA |  |  | 1 |  | 1
|  |  |  | KITCHEN AREA |  |  | 11 |  | 11
[7 empty] | TOTAL QTY |  | 25
5 | Providing , fixing testing and commissioning of upright type sprinkler heads 79 deg. Temp (Quick response type) | 12 | No.
6 | Providing & fixing testing and commissioning of braided UL Rated SS Flexible pipe
i) | 1 MT Long | 21 | No. | DINING & KITCHEN AREA |  |  | 21 |  | 21
[7 empty] | TOTAL QTY |  | 21
ii) | 1.6 MT Long | 12 | No. | DINING & KITCHEN AREA |  |  | 15 |  | 15
[7 empty] | TOTAL QTY |  | 15
7 | Gun metal chrome finished Ball valves (PN 16) with fittings of screwedend type.
I) | 40 mm dia. | R.O. | No.
I) | 32 mm dia. (Sprinkler drain-OPTIONAL) | 1 | Nos.
8 | Butterfly Valves (PN 16) with CI Body, Black Nitrile Body Liner and Nylon Coated SG Iron Disc with material and labour including hydraulic testing etc. complete as per drawing, specification & to the level of satisfaction of Site- Incharge.
I) | 150 mm dia. | R.O. | No.
I) | 100 mm dia. (OPTIONAL) | R.O. | No.
I) | 80 mm dia. | 0 | No.
9 | 6kg capacity ABC type dry chemical powder fire Extinguishers with wall mounting brackets | 4 | Nos.
10 | 6kg capacity K type fire Extinguishers with wall mounting brackets | 2 | No.
11 | 5kg capacity CO2 type fire Extinguishers with wall mounting brackets | 1 | No.
12 | 9Lit AR-AFFF type fire Extinguishers with wall mounting brackets | R.O. | Nos.
13 | Flow switch on sprinkler distribution header on each floor with 2 SPDT contacts suitably rated, capable of the high pressure system and connected to fire alarm panel through cable.
i) | 100 mm dia. | 0 | No.
14 | Ceasefire 5 Kg Ceiling Mounted Fire Extinguisher Clean Agent FE-36, Zero ODP, Stored Pressure Type, Pressure Gauge, Gross Weight 7.7 Kg, empty Weight 2.7 Kg, Can Height 264MM, Diameter 240MM,Discharge Time less than 8 Secs, Auto discharge mechanism on temperature rise, applicable on Class A,B,C and electrically started Fire, Can Construction : Deep drawn & Co2 Mig welded, Valve Construction : Forging & Machining, Internal Coating of Can : Epoxy Powder coating, External Coating of Can : Epoxy Polyster Powder coating, Sheet metal thickness : 2.0MM, Helium Leak Detection Test, 5 Years Warranty-model no 1CH21CF | 0 | No.
SUB-TOTAL
Note : | Taxes Extra as applicable.

## Extra Item M. Sheet
COPPWER CHIMNEY -WAKAD
BOQ FOR FIRE FIGHTING SYSTEMS
S/NO | DESCRIPTION | QUANTITY | UNIT
|  |  |  | LOCATION | FROM | TO | QTY | RUN | TOTAL QTY | UNIT | REMARK
1 | Providing , fixing testing and commissioning of pendant type sprinkler heads 68 deg. Temp.(Quick response type) | 0 | No. | KITCHEN AREA |  |  | 11 |  | 11
|  |  |  | DISH WASH |  |  | 2 |  | 2
|  |  |  | TANDOOR AREA |  |  | 1 |  | 1
[7 empty] | TOTAL QTY |  | 14
2 | Providing , fixing testing and commissioning of pendant type sprinkler heads 68 deg. Temp.(Quick response type) | 0 | No. | DINING AREA |  |  | 9 |  | 9
[7 empty] | TOTAL QTY |  | 9
3 | Supply, Installation, Testing & Commisioning Of ABC Dry Powder MAP - 50% Moduler Type Fire Extinguishet (Ceiling Mounted) conforming to IS : 15683 : 2018 finish complete. (5KG) | 0 | No. | BAR AREA |  |  | 1 |  | 1
[7 empty] | TOTAL QTY |  | 1
4 | Supply, Installation, Testing & Commisioning Of 2KG Firessense Automatic Fire detection and fire fighting system consisting of | 0 | No. | KITCHEN AREA |  |  | 1 |  | 1
| Cylinder filled with F-K-5-1-12 Clean Agent GAS (UL & FM Approved) | [5 empty] | TOTAL QTY |  | 1
Fitted with Direct Low Pressure Volve
Pressure guage
End of Line Adaptor
Wall bracket
5 | Commisioning of Heat Detection tube (UL & FM Approved) | 0 | No. | FOH & BOH AREA |  |  | 50 |  | 50
[7 empty] | TOTAL QTY |  | 50
8 | Supply, Installation, Testing & Commisioning Of Sprinkler, K-80 (5.6) QR, SC, 68 deg, 15mm bulb type, Chrome Finish, UL & FM Approved. | 0 | No. | FOH & BOH AREA |  |  | 15 |  | 15
[7 empty] | TOTAL QTY |  | 15
9 | Supply, Installation, Testing & Commisioning Of Concealed Sprinkler, K-5.6 (80) QR, SC, 68 deg, Pendent Chrome Finish, 15mm with cover plate white finish UL & FM Approved. | 0 | No. | FOH & BOH AREA |  |  | 12 |  | 12
[7 empty] | TOTAL QTY |  | 12
10 | Supply of Smart GAS Detector System. | 0 | No. | KITCHEN AREA |  |  | 6 |  | 6
| MODEL NO. GT-2511-FLP-ATEX | [5 empty] | TOTAL QTY |  | 6
Smart Gas Detector 3 Wire
Make: AMBETRONICS ENGINEERS PVT LTD., INDIA
For GAS LEAKAGE IN AMBIENT MONITORING
Gas to be detected-PNG
Range-0-100% LEL
Sensor Principle:- Catalytic Bead
Standard Output1 : 4-20 mA Output with users settable range
Output 2: Three SDPT Relays of rating '2A'
Output 3: Isolated RS-485 Modbus Communication
4-20mA rated at 470 ohms load driving capacity
programming can be done remote via Fieldbus
Configurable STEL and TWA Set points for Toxic Gases
11 | Supply, Installation, Testing & Commisioning of Monitor Module | 0 | No. | KITCHEN AREA |  |  | 6 |  | 6
[7 empty] | TOTAL QTY |  | 6
12 | Supply, Installation, Testing & Commisioning of Relay Module | 0 | No. | KITCHEN AREA |  |  | 5 |  | 5
[7 empty] | TOTAL QTY |  | 5
13 | Testing & commissioning of Smart GAS Detector System. | 0 | No. | KITCHEN AREA |  |  | 1 |  | 1
[7 empty] | TOTAL QTY |  | 1
14 | Rectification charges for per sprinkler points | 0 | No. | DINING AREA |  |  | 11 |  | 11
|  |  |  | BAR |  |  | 1 |  | 1
[7 empty] | TOTAL QTY |  | 12
SUB-TOTAL
Note : | Taxes Extra as applicable.